EDS \ RIT \ FARA Registry Project Navigator Process

Purpose

The purpose of this process is to define a detailed step by step approach to completing, monitoring and controlling all of the work required to deliver the FARA Registry project solution to the client's requirements.

Process Owner

EDS and RIT FARA Registry Project Team

Objectives

- Develop a process that defines who is responsible for completing deliverables

- Develop a process that pulls together best practices from proven software development methodologies

- Provide step by step instruction on how and when to complete project deliverables according to chosen methodologies

- Develop a process that will increase quality and productivity

- Enhance the accountability of team members toward successful completion of project deliverables

- Participants

- Sandra Morris – RIT Student

- Tracy Rericha – RIT Student

- Steve Coad – RIT Student

- Elaine Simone  - RIT Student

- Michelle Whalen – EDS PM Mentor\Coach

- John Manos – EDS Technical Mentor\Coach

- Table of Contents

Activity:  Project Management Startup and Planning	3

Activity:  Analyze Phase	4

Activity:  Define Phase	7

Activity:  Design Phase	12

Activity:  Produce Phase	18

Activity:  Optimize Phase	25

Activity:  Implement Phase	27

Modification Log	28

# Activity:  Project Management Startup and Planning

| Project Management Startup and Planning |  |  |  |
| --- | --- | --- | --- |
| - Who: | Step: | - Action: | - Templates\Tools\Locations: |
| - Project Team |  | Project Management Startup and Planning: A Project Plan will be established for the FARA Project. The following identifies the main project plan components that will be defined and completed: - Workbook Repository - Requirements Determination Process - Requirements Traceability - Review Process - Change Control Process - Estimate - Detailed Requirements - Prototype (Flowcharts) - Business and Technical Design - Test Plan and Cases (Unit, System, Regression and UAT) - Implementation Plan - Communication Management Plan - Status Reporting Process - Quality Management Plan - Risk Management Plan - Issues Management Plan - Scope Statement, Project Assumptions and Constraints - WBS (Work Breakdown Structure) - Project Schedule - Configuration Management Plan - Technical Launch - Coding Standards | - Various – too numerous to list here. |

# Activity:  Analyze Phase

| Analyze Phase |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| - Who: |  | Step: |  | - Action: |  | - Templates\Tools\Locations: |
| - Customer |  |  |  | Define High Level Requirements: Ultimately it is the customer’s responsibility to complete an initial draft of project High level requirements. |  | - High_level_requirements.doc |
| RIT Team Customer EDS Mentors |  |  |  | ###### High Level Requirements Review – Analyze Phase: This is a REQUIRED review. The objective of this review is to review and clarify all high level requirements so that they can be baselined and become input into determining detailed requirements. RIT Team will send out a conformance review meeting invitation using the outlook form template. - This formal review REQUIRES the following participants: - RIT Student Team - EDS PM Mentor - EDS Technical Mentor - Customer - This formal review should invite the following OPTIONAL participants: - Any other stakeholders identified by the customer - You must distribute ALL review materials to the attendees at least 24 hours in advance. - You must follow the Conformance Reviews Process using the rev_analyze mmddyy.doc conformance review report to facilitate and document the review. |  | ###### Process = p_review_process.doc Template = FARA Project Conformance Review Invitation Template.oft Template = rev_analyze mmddyy.doc |
| Assigned Team Members |  |  |  | - Resolve and Re-Review Review Issues: - Resolve all issues and actions that were found in the Analyze phase review and update the appropriate documents in the workbook. - Have a person from the review re-review the resolved issues and actions. - Depending on the results of the review, either conduct an informal or formal review of the resolved issues following the project Review process. - If re-review is INFORMAL ask one of the original reviews to validate that all issues have been resolved that are documented in the review report. They should add their initials to the check mark column. - If re-review is FORMAL send out another meeting invitation and conduct another review of the request. All issues captured should be added to the existing review report. |  | Template = rev_analyze mmddyy.doc |
| RIT Team |  |  |  | - Obtain Customer Signoff on High Level Requirements: - Before any detailed requirements gathering activities can commence approval from ALL authorized approvers must be received for the high level requirements. - The RIT Team will submit a request for approval using the standard High Level Requirements Approval e-mail template. Make sure to CC: ALL assigned team members for the tracker. - Save all reply’s in workbook |  | - Template = FYA FARA Registry Project High Level Requirements Approval Request.oft |
| - NOTE: Once the High Level Requirements are Signed Off\Approved by the Authorized Approvers it is considered BASELINED. If any changes must be made to the Requirement(s) after this point the project’s Change Control Process MUST BE EXECUTED. |  |  |  |  |  |  |
| RIT Team EDS Mentors Customer |  |  | - Requirements Change Control: - If new requirements or changes to existing requirements are introduced any time after requirements have been signed off, a change control process must be followed. - The team member must fill out the change control form “change control nnnn.doc” and submit it to the Project Manager. - The team member will evaluate the impact of the new or changed requirement(s) and work with the Project Manager to determine how to proceed with the change. - Obtain acceptance/denial/postpone of the change/impact via email from the requester. - If it is determined that the requirements will be updated to reflect the change, the team member must: - Communicate status to Project Manager. - Update all appropriate Requirements document(s). This insures that changes to the requirements are tracked. (Make sure to modify the mod log) - Make sure that all assigned persons for the requirements are aware of all changes - Modify scheduled release & Project Schedule, if necessary - Update Test Cases, if necessary - Update Technical Design, if necessary - Make the Change Control Change - Rerun the original test cases - Re-review change with developers from the initial review |  | Template = change control nnnn.doc |  |

# Activity:  Define Phase

| Define Phase |  |  |  |
| --- | --- | --- | --- |
| - Who: | Step: | - Action: | - Templates\Tools\Locations: |
| RIT Team |  | ###### Schedule JAD Sessions: RIT Team will schedule JAD (Joint Application Design) sessions with the customer. JAD is an extended workshop with end users that identifies detailed requirements and creates a preliminary design and\or prototype. The JAD sessions should be held face to face with the customer if possible. The length of the JAD sessions should allow for enough time to collaboratively define detailed requirements. |  |
| RIT Team |  | ###### Create Initial Context, System and Architecture Diagrams: The RIT Team will create initial context, system and architecture diagrams using the information from the High Level Requirements. |  |
| RIT Team |  | ###### Create a Solution Prototype: A prototype is used to obtain and validate requirements through demonstrations of a partially functional solution. The use of flow charts can be used to supplement and complete a prototype solution. |  |
| RIT Team |  | Conduct JAD Session to Determine Detailed Requirements: The JAD sessions need to be tightly facilitated\managed and all findings must be captured real time during the JAD session. The prototype solution will be used to facilitate the JAD session. |  |
| RIT Team |  | Document Detailed Requirements: As a result of reviewing High Level Requirements and conducting JAD sessions the RIT team will document detailed requirements for the project. All Detailed Requirements must be document in the project template FARA_Detailed_Requirements.doc. Reference the Requirements Determination Process Reference Sheets to assist in creating documenting detailed requirements. | Template = FARA_Detailed_Requirements.doc - Process = Requirements Determination Process Reference Sheets |
| RIT Team Customer EDS Mentors |  | ###### Detailed Requirements Review – Define Phase: This is a REQUIRED review. The objective of this review is to review and clarify all detailed requirements so that they can be baselined and become input into business designing. RIT Team will send out a conformance review meeting invitation using the outlook form template. - This formal review REQUIRES the following participants: - RIT Student Team - EDS PM Mentor - EDS Technical Mentor - Customer - This formal review should invite the following OPTIONAL participants: - Any other stakeholders identified by the customer - Steering Committee Members - You must distribute ALL review materials to the attendees at least 24 hours in advance. - You must follow the Conformance Reviews Process using the rev_define mmddyy.doc conformance review report to facilitate and document the review. | ###### Process = p_review_process.doc Template = FARA Project Conformance Review Invitation Template.oft Template = rev_define mmddyy.doc |
| Assigned Team Members |  | - Resolve and Re-Review Review Issues: - Resolve all issues and actions that were found in the define phase review and update the appropriate documents in the workbook. - Have a person from the review re-review the resolved issues and actions. - Depending on the results of the review, either conduct an informal or formal review of the resolved issues following the project Review process. - If re-review is INFORMAL ask one of the original reviews to validate that all issues have been resolved that are documented in the review report. They should add their initials to the check mark column. - If re-review is FORMAL send out another meeting invitation and conduct another review of the request. All issues captured should be added to the existing review report. | Template = rev_define mmddyy.doc |
| RIT Team |  | - Obtain Customer Signoff on Detailed Requirements: - Before any Design activities can commence for a tracker a formal approval from ALL authorized approvers must be received for the detailed requirements. - The RIT Team will submit the Detailed Requirement(s) to all authorized approvers using the standard Detailed Requirements Approval e-mail template. Make sure to CC: ALL team members. - Save all reply’s in workbook | - Template = FYA FARA Registry Project Detailed Requirements Approval Request.oft |
| - NOTE: Once the High Level Requirements are Signed Off\Approved by the Authorized Approvers it is considered BASELINED. If any changes must be made to the Requirement(s) after this point the project’s Change Control Process MUST BE EXECUTED. |  |  |  |
| Team |  | Validate Project Estimate: Now that the requirements have been defined re-validate the project estimate and schedule. Work with the project manager if the estimate or schedule needs to change. |  |

# Activity:  Design Phase

| Design Phase |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| - Who: | Step: |  | - Action: |  | - Templates\Tools\Locations: |  |
| RIT Team |  |  | Create Business Design: - If necessary hold designing meetings with appropriate customer\stakeholders and assigned resources to design business solutions for approved requirements. - Complete the BD (Business Design) using the Business Design Template. The BD must be completed using business language – no technical, pseudo code or code language can be used. The customer will be the recipient of the BD and the BD will be used as input into UAT test case creation and end user work instructions. - The business design document should be sectionized by requirement using the requirement number. It should easily trace back to the detailed requirement so that there is a clear traceability of requirements. - A single business design must incorporate all requirements for the project. |  | - Template = FARA Business Design.doc |  |
| RIT Team Customer EDS Mentors |  |  |  | ###### Business Design Review – Design Phase: This is a REQUIRED review. The objective of this review is to review the business design to become input into technical designing. RIT Team will send out a conformance review meeting invitation using the outlook form template. - This formal review REQUIRES the following participants: - RIT Student Team - EDS PM Mentor - EDS Technical Mentor - Customer - This formal review should invite the following OPTIONAL participants: - Any other stakeholders identified by the customer - Steering Committee Members - You must distribute ALL review materials to the attendees at least 24 hours in advance. - You must follow the Conformance Reviews Process using the rev_business_design mmddyy.doc conformance review report to facilitate and document the review. |  | ###### Process = p_review_process.doc Template = FARA Project Conformance Review Invitation Template.oft Template = rev_business_design mmddyy.doc |
| Assigned Team Members |  |  |  | - Resolve and Re-Review Review Issues: - Resolve all issues and actions that were found in the business design phase review and update the appropriate documents in the workbook. - Have a person from the review re-review the resolved issues and actions. - Depending on the results of the review, either conduct an informal or formal review of the resolved issues following the project Review process. - If re-review is INFORMAL ask one of the original reviews to validate that all issues have been resolved that are documented in the review report. They should add their initials to the check mark column. - If re-review is FORMAL send out another meeting invitation and conduct another review of the request. All issues captured should be added to the existing review report. |  | Template = rev_business_design mmddyy.doc |
| RIT TEAM |  |  |  | - Obtain Customer Signoff on Business Design: - Before any Design activities can commence for a tracker a formal approval from ALL authorized approvers must be received for the detailed requirements. - The RIT Team will submit the Detailed Requirement(s) to all authorized approvers using the standard Detailed Requirements Approval e-mail template. Make sure to CC: ALL team members. - Save all reply’s in workbook |  | - Template = FYA FARA Registry Project Business Design Approval Request.oft |
| - NOTE: Once the Business Design is Signed Off\Approved by the Authorized Approvers it is considered BASELINED. If any changes must be made to the Business Design after this point the project’s Change Control Process MUST BE EXECUTED. |  |  |  |  |  |  |
| RIT Team |  |  | - Document Technical Design: - Creating a technical design should be in conjunction with creating the business design BUT the technical design cannot be completed until the business design is completed. - Document what work products you plan to change and how you plan to change them in the technical design document. This can be accomplished using flowcharts, pseudo code. Avoid using actual code. - Complete the Technical Design using the Technical Design Template. - The technical design document should trace back to all of the requirements. - There should be ONE technical design for the project. A single technical design must incorporate all requirements. |  | - Template = FARA Technical Design.doc |  |
| RIT Team |  |  | - Create Unit Test Cases: - Using the test case form document test cases for each requirement. Test cases must be completed prior to starting changes so that the test cases reflect requirements gathered and designed, not changes made. |  | - Template = FARA unit test cases v x.x mmddyy.doc |  |
| RIT Team Customer EDS Mentors |  |  |  | ###### Technical Design Review – Design Phase: This is a REQUIRED review. The objective of this review is to review the technical design to become input into technical designing. RIT Team will send out a conformance review meeting invitation using the outlook form template. - This formal review REQUIRES the following participants: - RIT Student Team - EDS PM Mentor - EDS Technical Mentor - Customer - This formal review should invite the following OPTIONAL participants: - Any other stakeholders identified by the customer - Steering Committee Members - You must distribute ALL review materials to the attendees at least 24 hours in advance. - You must follow the Conformance Reviews Process using the rev_technical_design mmddyy.doc conformance review report to facilitate and document the review. |  | ###### Process = p_review_process.doc Template = FARA Project Conformance Review Invitation Template.oft Template = rev_technical_design mmddyy.doc |
| Assigned Team Member |  |  |  | - Resolve and Re-Review Review Issues: - Resolve all issues and actions that were found in the review and update the appropriate documents in the workbook. - Have a person from the review re-review the resolved issues and actions. - Depending on the results of the review, either conduct an informal or formal review of the resolved issues following the Conformance Review process. - If re-review is INFORMAL ask one of the original reviews to validate that all issues have been resolved that are documented in the review report. They should add their initials to the check mark column. - If re-review is FORMAL send out another meeting invitation and conduct another review of the request. All issues captured should be added to the existing review report. |  | - Template = rev_technical_design mmddyy.doc |
| RIT Team EDS Mentors |  |  | - Validate Estimate and Project Schedule: Now that the business and technical designs have been defined re-validate the project estimate and schedule. Work with the project manager if the estimate or schedule needs to change. |  |  |  |

# Activity:  Produce Phase

| Produce Phase |  |  |  |
| --- | --- | --- | --- |
| - Who: | Step: | - Action: | - Templates\Tools\Locations: |
| RIT Team |  | - Define and Document System Test and Regression Cases: - The RIT Team is responsible for completing all system test cases necessary for all requirements of the project. - Follow the project’s Testing Process and System Test Case Form to complete all system test cases. | - Template – TO BE DEFINED |
| Customer |  | - Create or Modify End User Procedures: - The customer is responsible for creating end user system procedures. - End user procedures are step instructions for end users to follow when using the solution to perform business functions. - Use the System Procedure Template to complete all system procedures. | - Template – TO BE DEFINED |
| Customer RIT Team |  | - Define and Document User Acceptance Test (UAT) Cases: - The customer with assistance from the RIT Team will define and document necessary User Acceptance Test Cases. - The project team’s Testing Process and User Acceptance Test Case Form will be used to complete all UAT test cases. | - Template – TO BE DEFINED |
| RIT Team EDS Mentors Customer |  | - Optimize Phase Planning Begins: - Define and document a system and regression testing plan. - Define and document a UAT testing plan. - Create System\Regression and UAT testing schedule. - Begins to communicate to UAT participants. | - Template – TO BE DEFINED |
| RIT Team |  | - Document Software Configuration Management (SCM) for Effected Products: To be defined | - Template – TO BE DEFINED |
| RIT Team |  | Coordinate Changes to Software Objects with Team Members: If another developer is working the same software object you must coordinate your changes appropriately and communicate the situation to the technical team leader. To be defined | - Template – TO BE DEFINED |
| RIT Team |  | Construct changes in Development Instance: To be defined - Use coding standards when applicable. | - Template – TO BE DEFINED |
| RIT Team |  | - Create Unit Testing Data: - As documented in the unit test case forms, create all data that needs to be created in non-production environments to facilitate unit testing. For example user id’s/profiles need to be created in order to test from a user perspective. - NOTE: YOU SHOULD NOT UNIT TEST USING AN ADMINISTRATIVE RIGHTS LOGIN. YOU SHOULD TEST USING LOGIN’S MODELING END USERS, UNLESS THE TEST REQUIRES ADMIN ACCESS. |  |
| RIT Team |  | - Execute Unit Test Cases in Development Environment: - Perform Unit Testing in development environment according to the test cases and document the actual results in the Unit Test case form. |  |
| RIT Team |  | - Perfect Unit Testing: - Continue Unit Testing until all of the actual results match the expected results for each Unit Test case and document the actual results in the Unit Test case form. |  |
| RIT Team |  | - If Applicable Update Business Designs and Get Re-Approval: - The RIT Team is responsible for communicating to the customer any changes introduced during produce that could impact the business design. - The RIT Team is responsible for updating all applicable business documentation (requirement, BD, system procedures, UAT test cases, solution documentation Library), and is also responsible for determining if the business design and\or requirement should be re-approved. |  |
| RIT Team |  | - Perform “Development” Produce Review: RIT Team will send out a conformance review meeting invitation using the outlook form template. - This formal review REQUIRES the following participants: - RIT Student Team - EDS PM Mentor - EDS Technical Mentor - You must distribute ALL review materials to the attendees at least 24 hours in advance. - You must follow the Conformance Reviews Process using the rev_produce mmddyy.doc conformance review report to facilitate and document the review. (Please note you should not invite the customer this is a technical review not a business review) | ###### Process = p_review_process.doc Template = FARA Project Conformance Review Invitation Template.oft - Template = rev_produce mmddyy.doc |
| RIT Team |  | - Resolve and Re-Review Review Issues: - Resolve all issues and actions that were found in the review and update the appropriate documents in the workbook. - Have a person from the review re-review the resolved issues and actions. - Depending on the results of the review, either conduct an informal or formal review of the resolved issues following the Conformance Review process. - If re-review is INFORMAL ask one of the original reviews to validate that all issues have been resolved that are documented in the review report. They should add their initials to the check mark column. - If re-review is FORMAL send out another meeting invitation and conduct another review of the request. All issues captured should be added to the existing review report. | - Template = rev_produce mmddyy.doc |
| RIT Team EDS Mentors Customer |  | - Perform “Testing” Produce Review: RIT Team will send out a conformance review meeting invitation using the outlook form template. - This formal review REQUIRES the following participants: - RIT Student Team - EDS PM Mentor - EDS Technical Mentor - Customer - You must distribute ALL review materials to the attendees at least 24 hours in advance. - You must follow the Conformance Reviews Process using the rev_testcases mmddyy.doc conformance review report to facilitate and document the review. | ###### Process = p_review_process.doc Template = FARA Project Conformance Review Invitation Template.oft - Template = rev_testcases mmddyy.doc |
| Assigned Team Member |  | - Resolve and Re-Review Review Issues: - Resolve all issues and actions that were found in the review and update the appropriate documents in the workbook. - Have a person from the review re-review the resolved issues and actions. - Depending on the results of the review, either conduct an informal or formal review of the resolved issues following the Conformance Review process. - If re-review is INFORMAL ask one of the original reviews to validate that all issues have been resolved that are documented in the review report. They should add their initials to the check mark column. - If re-review is FORMAL send out another meeting invitation and conduct another review of the request. All issues captured should be added to the existing review report. | - Template = rev_testcases mmddyy.doc |

# Activity:  Optimize Phase

| Optimize Phase |  |  |  |
| --- | --- | --- | --- |
| - Who: | Step: | - Action: | - Templates\Tools\Locations: |
|  |  | Create Release Deployment Plan: The Project Manager is responsible for ensuring that an overall Release Deployment Plan is created prior to the completion of the optimize Phase. This plan is not a technical implementation plan but may include steps to execute technical tasks. TO BE DEFINED. |  |
|  |  | Build Environment For System Testing: TO BE DEFINED. |  |
| All Team Members |  | System Test Plan is Executed: All team members will be participants in executing system testing activities. A system test coordinator is responsible for planning and managing system testing activities. |  |
| ALL Team Members |  | Resolve Defects Found During System Testing: Execute the team Defect Remediation Process to resolve all defects and issues found during system testing. All team members will be responsible for resolving defects found during system testing. | TO BE DEFINED. |
|  |  | Modify Release Package: Ensure that all necessary changes introduced during System Testing execution and Defect Remediation are reflected in the Release Master Package |  |
|  |  | Build Environment For UAT Testing: TO BE DEFINED. |  |
|  |  | UAT Plan is Executed: All team members will be participants in supporting UAT testing activities. A UAT coordinator is responsible for planning and managing UAT testing activities. |  |
| ALL Team Members |  | Resolve Defects Found During UAT Testing: Execute the team Defect Remediation Process to resolve all defects and issues found during UAT testing. All team members will be responsible for resolving defects found during UAT testing. | TO BE DEFINED. |
|  |  | Obtain UAT Customer Signoff: For all requirements that were selected for UAT testing. Approval is required from all authorized approvers of the tested tracker\requirement. Use the project template for UAT Signoff. | TO BE DEFINED. |
|  |  | Modify Release Package: Ensure that all necessary changes introduced during UAT Testing execution and Defect Remediation are reflected in the Release Master Package |  |

# Activity:  Implement Phase

| Implement Phase |  |  |  |
| --- | --- | --- | --- |
| - Who: | Step: | - Action: | - Templates\Tools\Locations: |
|  |  | Execute Release Deployment Plan: TO BE DEFINED. |  |

# Modification Log

| Date | Version | Author | Description |
| --- | --- | --- | --- |
| 12/2005 | 1.0 | Michelle Whalen | Initial Release |