## Instructions
Your Name: | Cailin Li
Instructions
Enter your name above.
At the end of each week:
Under "Accomplished this week"
Make sure planned tasks from last week copied correctly with estimated times
Fill in the actual amount of time spent on each task and indicate whether it is done.
Add any other tasks you worked on this week
Teams seem to relate better to times in hours down to the 1/4 hour, but feel free to use minutes if that has more meaning to you.
Under "Planned for next week"
Enter unfinished tasks from this week that you will continue next week
Enter other planned tasks for next week
Estimate the time you will spend on each task. Estimate your time in minutes or hours down to the 1/4 hour.
Tasks and estimates will copy to next week's accomplished section
Under "Issues"
Enter any unexpected problems you encountered
Enter any issues that require discussion with your team

## Example
First Term - Week 1
Accomplished this week
Done? | ACT | EST | Task
Y | 0.5 |  | Attended expectations talk
Y | 1 |  | Prepared for first meeting with sponsor
Y | 1.75 |  | Met with sponsor
Y | 5.25 |  | Researched webservices
Y | 2 |  | Team meeting to assign initial roles and responsibilities
| 10.5 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Regular team meeting
|  | 2 | Meeting with project sponsor
|  | 1 | Write draft synopsis with Kate
|  | 4 | Look for webservices tutorials and work through them
|  | 2.5 | Work with Adam to make list of requirements questions
|  | 11.5 | TOTAL TIME
Issues
Hard disk on my computer died, had to restore from backup
Team is having trouble finding time to meet together
May need help coding error-handling subsystem

## 1-Wk1
First Term - Week 1
Accomplished this week
Done? | ACT |  | Task
Y | 1 |  | Attended Expectations Meeting and Met with Faculty Coach
Y | 1 |  | Reviewed Project Descriptions to Come Up with Questions
Y | 1 |  | Met to Prepare for Sponsor Meeting
Y | 0.5 |  | Add Agenda for Kick-Off Meeting
Y | 1.15 |  | Met with Sponsor and Faculty Coach
Y | 0.15 |  | Set Up Slack / When2Meet
| 4.8 |  | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1 | Review Deliverables, Set Up Four-Up Chart, Time / Effort Tracking Spreadsheet
|  | 1.5 | Run Web App / Review Codebase
|  | 1.5 | Run iOS App / Review Codebase
|  | 1.15 | Meet with team to prep for next sponsor meeting
|  | 0.5 | Review Gimbal SDK
|  | 1.15 | Sponsor / Coach Meeting
|  | 6.8 | TOTAL TIME
Issues
Won't be able to borrow a Macbook until next Thursday, will have to go to the labs for now
Working with existing codebase may challenging

## 1-Wk2
First Term - Week 2
Accomplished this week
Done? | ACT | EST | Task
Y | 1.15 | 1 | Review Deliverables, Set Up Four-Up Chart, Time / Effort Tracking Spreadsheet
Y | 1.5 | 1.5 | Run Web App / Review Codebase
Y | 0.5 | 1.5 | Run iOS App / Review Codebase
Y | 1.5 | 1.15 | Meet with team to prep for next sponsor meeting
N | 0 | 0.5 | Review Gimbal SDK
Y | 1.15 | 1.15 | Sponsor / Coach Meeting
Y | 0.75 |  | Set Up Website
| 6.55 | 6.8 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1 | Meeting to work on Project Synopsis
|  | 1.15 | Meeting to work on Project Plan
|  | 1.5 | Meeting with Sponsor and Coach
|  | 3 | Login Flow Designs
|  | 3 | Learning / Development
|  | 9.65 | TOTAL TIME
Issues
Need to figure out how to host on AWS

## 1-Wk3
First Term - Week 3
Accomplished this week
Done? | ACT | EST | Task
Y | 1 | 1 | Meeting to work on Project Synopsis
Y | 1 | 1.15 | Meeting to work on Project Plan
Y | 1 | 1.5 | Meeting with Sponsor and Coach
Y | 4.5 | 3 | Login Flow Designs
Y | 1 | 3 | Learning / Development
Y | 2 |  | Investigate / Help Getting Remote Server and Database to work
Y | 0.3 |  | Fill out Project Plan (Measurements & Metrics)
| 10.8 | 9.65 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1 | Exploratory Testing Meeting
|  | 2 | Regular Meetings
|  | 5 | Master Detail Designs
|  | 1 | Investigate Jenkins
|  | 0.5 | Update Project Website
|  | 9.5 | TOTAL TIME
Issues
Taking time to pick up where the last team left off
Still figuring out process methodology

## 1-Wk4
First Term - Week 4
Accomplished this week
Done? | ACT | EST | Task
Y | 1 | 1 | Exploratory Testing Meeting
Y | 2 | 2 | Regular Meetings
Y | 5.5 | 5 | Master Detail Designs
N | 0 | 1 | Investigate Jenkins
Y | 1.5 | 0.5 | Update Project Website
Y | 1 |  | Investigate / Write Up Development Workflow Readme
Y | 1.5 |  | Improve Sign in Design
| 12.5 | 9.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 3 | Master Detail Designs, Map Details
|  | 3 | Tab Bar Designs
|  | 2 | Regular Meetings
|  | 0.5 | Update Project Website
|  | 1 | Investigate Jenkins
|  | 2.5 | Add Racer Flow Designs
|  | 12 | TOTAL TIME
Issues

## 1-Wk5
First Term - Week 5
Accomplished this week
Done? | ACT | EST | Task
Y | 5.5 | 3 | Master Detail Designs, Map Details
Y | 2 | 3 | Tab Bar Designs
Y | 2 | 2 | Regular Meetings
N | 0 | 0.5 | Update Project Website
N | 0 | 1 | Investigate Jenkins
Y | 6 | 3 | New Login Design Implementation
N | 0 | 2.5 | Add Racer Flow Designs
Y | 3.5 |  | Storyboard, StackView Tutorial
| 19 | 15 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Regular Meetings
|  | 0.15 | Update Website
|  | 1 | Admin Login Designs
|  | 3 | Edit Racer Designs
|  | 4 | Swift 3 Conversion Help
|  | 10.15 | TOTAL TIME
Issues

## 1-Wk6
First Term - Week 6
Accomplished this week
Done? | ACT | EST | Task
Y | 1 | 2 | Regular Meetings
N | 0 | 0.15 | Update Website
N | 0 | 1 | Admin Login Designs
Y | 3 | 3 | Edit Racer Designs
N | 0 | 4 | Swift 3 Conversion Help
Y | 1 |  | Swift Tutorial
| 5 | 10.15 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0.25 | Update Website
|  | 1.5 | Swift Tutorial (cont.)
|  | 0.5 | Device Name Default
|  | 1 | Update Stories with Designs
|  | 1 | Show only friendly name column
|  | 2 | Revise Edit Participant Designs
|  | 2 | Regular Meetings
|  | 2 | Admin Designs
|  | 10.25 | TOTAL TIME
Issues

## 1-Wk7
First Term - Week 7
Accomplished this week
Done? | ACT | EST | Task
Y | 0.25 | 0.25 | Update Website
Y | 1.5 | 1.5 | Swift Tutorial (cont.)
Y | 1 | 0.5 | Device Name Default
Y | 1 | 1 | Update Stories with Designs
Y | 2.5 | 1 | Show only friendly name column
Y | 2.5 | 2 | Revise Edit Participant Designs
Y | 1 | 2 | Regular Meetings
N | 0 | 2 | Admin Designs
| 9.75 | 10.25 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0.5 | Update Metrics
|  | 0 | Regular Meetings
|  | 0.5 | Admin Login
|  | 6 | Participant TableView
|  | 3 | Swipe to Edit / View on Map
|  | 10 | TOTAL TIME
Issues

## 1-Wk8
First Term - Week 8
Accomplished this week
Done? | ACT | EST | Task
Y | 0.5 | 0.5 | Update Metrics
Y | 1 | 0 | Regular Meetings
Y | 1 | 0.5 | Admin Login
N | 2 | 6 | Participant TableView
N | 0 | 3 | Swipe to Edit / View on Map
Y | 0.25 |  | Update Website
Y | 3 |  | Swift Tutorial
| 7.75 | 10 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | Regular Meetings
|  | 6 | Participants TableView
|  | 1 | Swift / iOS Videos
|  | 7 | TOTAL TIME
Issues

## 1-Wk9
First Term - Week 9
Accomplished this week
Done? | ACT | EST | Task
|  | 0 | Regular Meetings
N | 6.5 | 6 | Participants TableView
Y | 1 | 1 | Swift / iOS Videos
Y | 1 |  | Update Connections.js
| 8.5 | 7 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Regular Meetings
|  | 2 | Finish Participants TableView
|  | 3 | Swipe to Edit
|  | 3 | Refactoring
|  | 0.25 | Update Website
|  | 10.25 | TOTAL TIME
Issues

## 1-Wk10
First Term - Week 10
Accomplished this week
Done? | ACT | EST | Task
|  | 2 | Regular Meetings
|  | 2 | Finish Participants TableView
|  | 3 | Swipe to Edit
|  | 3 | Refactoring
|  | 0.25 | Update Website
| 0 | 10.25 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 1-Finals
First Term - Finals Week
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-Wk1
Second Term - Week 1
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-Wk2
Second Term - Week 2
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-Wk3
Second Term - Week 3
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-Wk4
Second Term - Week 4
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-Wk5
Second Term - Week 5
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-Wk6
Second Term - Week 6
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-Wk7
Second Term - Week 7
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-Wk8
Second Term - Week 8
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-Wk9
Second Term - Week 9
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-Wk10
Second Term - Week 10
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-Finals
Second Term - Finals Week
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Issues

## AllData
t1-1a | t1-2e | t1-2a | t1-3e | t1-3a | t1-4e | t1-4a | t1-5e | t1-5a | t1-6e | t1-6a | t1-7e | t1-7a | t1-8e | t1-8a | t1-9e | t1-9a | t1-10e | t1-10a | wt1-fe | t1-fa
4.8 | 6.8 | 6.55 | 9.65 | 10.8 | 9.5 | 12.5 | 15 | 19 | 10.15 | 5 | 10.25 | 9.75 | 10 | 7.75 | 7 | 8.5 | 10.25 | 0 | 0 | 0
t2-1e | t2-1a | t2-2e | t2-2a | t2-3e | t2-3a | t2-4e | t2-4a | t2-5e | t2-5a | t2-6e | t2-6a | t2-7e | t2-7a | t2-8e | t2-8a | t2-9e | t2-9a | t2-10e | t2-10a | t2-fe | t2-fa
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0