FARA Registry Modularity Document

There are ten modules that constitute a logical business representation for Release 1.0 of the FARA registry project.

Module 1: Database

Module 2: User authentication / login

Module 3: Data entry view

Module 4: Data Entry Logic

Module 5: Patient Update

Module 6: Coordinator – Patient Review

Module 7: Admin functionality

Module 8: Querying

Module 9: Registry Auto-maintenance

Module 10: Static Site Content

The purpose of this document is to modularize Release 1.0 for assignment and division of work among the RIT students as well as provide a framework for development progress tracking.

This document needs to be completed as follows:

- Assign each Release 1.0 “in scope” requirement into the module that is best associated to the requirement.  If a requirement associates to more than one module, add the requirements to all modules that apply (therefore the requirement could be listed twice).

- For each requirement added provide Requirement Number, Requirement Title, Technical Design Number(or reference), Developer Assigned, Target Date for completing the requirement, Status of working the requirement and indication of whether the requirement was completed and when.

- Per the defined development progress tracking process the RIT technical leader will provide a development status weekly at the module level.

- Per the defined development progress tracking process the RIT developers will provide a development status weekly for each assigned requirement.

- This document needs to be source controlled and will contain a running log of all entries.

The RIT Developers will develop these modules using the following approach:

- Requirements should be worked in order of their importance determined by the FARA customer.  High ranked requirements should be worked before Medium and Medium before Low.  There may be exceptions to this if working one requirement also completes other requirements.

- Module 1: Database needs to be started immediately.  One developer should be assigned to do this independently (Developer #1).

- As Developer #1 is working on Module 1, Developers #2, and #3 will be working on Module 9: Data Entry View and Module 8: Patient Update (respectively).

- As this is occurring, Developer #4 will be able to begin developing Module 7: Querying. Developer #4 will be working on this module throughout the produce phase. As parts of Modules 8 and 9 are developed, Developer #4 will also work on Module 10: Data Entry Logic (Developer #4).

- Once Developer #1 finishes Module 1: Database they will immediately start working on Module 3: User Authentication (Developer #1).

- Once Developer #1 finishes Module 3: User Authentication they will immediately start working on Module 4: Registry Auto-Maintenance (Developer #1).

- As Developers #2 and #3 finish their respective modules, Developer #2 will begin work on Module 2, while Developer #3 will work on Module 5: Registry Coordinator.

- Once Developer #1 finishes Module 3: User Authentication they will immediately start working on Module 6: Admin (Developer #1).

The following areas have been identified as high risk areas for development.  This means that they could be challenging to complete or will take a considerable amount of time.  To mitigate these risks the RIT students must address their development as soon as possible – before other lower risk requirements.

- Querying Flexibility (use of conditions)

- E-Mailing with .Net

- Business Rules – there are a lot of business rules of  this project and the Validator in .Net will be used to code these rules

- Documentation for Business Process Not delivered in Release 1.0 – Administrator Role, Ongoing Development Support etc.

Module 1 Database

Module 1 - Database - Development Status

03/20/2006 – The module is approximately 70% complete. The database and scripts are done, stored procedures are started. 03/23/2006 – The module is 100% complete.

| Req # | Req. Title | Tech Des # | Approver | Responsible Person | Participants in Task | Date and Progress Status |
| --- | --- | --- | --- | --- | --- | --- |
| F6.008.000 | All fields documented in FieldAttributes.xls |  | Tracy Rericha | Steven Coad | Steven Coad, Tracy Rericha | 003/20/06 – Estimated 70% complete. Created the database and populated it with some initial data. Created script to make tables and populate them. Started work on the stored procedures. 03/23/06 – 100% complete. |

Module 2 User Authentication / Login

Module 2 – User Authentication/Login - Development Status

03/20/2006 – This module is not scheduled to start until later this week, so no progress has been made on it. 03/23/2006 – This module will not be started until tomorrow. No progress has been made yet. 03/30/2006 – This module is 20% complete. Work has been deferred as database was higher priority. The completion date was (with EDS approval) pushed back a day so that there would be a Saturday available to complete work. This module will be on-time and ready for the review. 04/06/06 – This module is 60% complete. Tweaking and/or polishing needs to be done with the UI. Work will finish Saturday.

| Req # | Req. Title | Tech Des # | Approver | Responsible Person | Participants in Task | Date and Progress Status |
| --- | --- | --- | --- | --- | --- | --- |
| F11.026.000 | Password specifics |  | Elaine Simone | Steven Coad | Steven Coad, Elaine Simone | 03/30/06 – 100% complete. Passwords are validated based on rules in the fields doc/requirements/design. |
| F11.027.000 | Stronger password requirements for RC/Admin |  | Elaine Simone | Steven Coad | Steven Coad, Elaine Simone | 03/30/06 – 100% complete. Passwords are validated based on rules in the fields doc/requirements/design. |
| F11.028.000 | User lockout after attempting to login # of times |  | Elaine Simone | Steven Coad | Steven Coad, Elaine Simone | 03/30/06 – 0%, I need to research this tonight. 04/06/06 – 50% complete. Lockout function is in place. |
| F11.029.000 | Retrieving authentication information via email |  | Elaine Simone | Steven Coad | Steven Coad, Elaine Simone | 03/30/06 – 0%, I need to research this tonight. 04/06/06 – 50% complete. Password reset function is in place. |
| F11.031.000 | Administrator can reset passwords |  | Elaine Simone | Steven Coad | Steven Coad, Elaine Simone | 03/30/06 – 0%, I need to research this tonight. 04/06/06 – 50% complete. Password reset function is in place. |
| F17.045.000 | All Account Types Log In through the same interface |  | Elaine Simone | Steven Coad | Steven Coad, Elaine Simone | 03/30/06 - 100% complete. One login page for everyone. |
| F17.045.001 | Authentication Method Leads to correct screen based on Account Type |  | Elaine Simone | Steven Coad | Steven Coad, Elaine Simone | 03/30/06 - 75% complete, page redirects based on account level, need to connect to database for login. 04/06/06 – 100% complete. |

Module 3 data Entry View

Module 3 – Data Entry View - Development Status

03/17/2006 – Overall this module is 45%-50% complete. UI components have been made. Remaining work is dependent on the completion of module 1. 03/23/2006 – This module is about 70% complete. Now that the database is complete, the remaining work should be finishing on time. 03/30/2006 – This module is 97% complete. Remaining work just needs help plugging into database. This is on-time. 04/06/06 – This module is 100% complete.

| Req # | Req. Title | Tech Des # | Approver | Responsible Person | Participants in Task | Date and Progress Status |
| --- | --- | --- | --- | --- | --- | --- |
| F6.008.000 | All fields documented in FieldAttributes.xls |  | Steven Coad | Sandy Morris | Sandy Morris, Steven Coad | 03/17/06 – All pages were created with what is currently in this document. Document needs to be updated to reflect international fields. However, because I consider this to also include the functionality behind these fields I would estimate that I am 25% complete. 03/23/06 – I worked some more this week on updating some fields and mapping them back to database elements and creating session variables. The fields on the UI are all complete now. I would estimate that I am not about 50% complete. This week I also made sure the pages were all browser compatible and fixed the issues we were having with Firefox. 03/30/06 – I only need to hook in the data objects that Steve is working on. And I have one bug I need to fix before this is complete. I plan to ask Prof. Wu and possibly John for help on it. It seems that when new patients go back to review their information and make changes those changes are being lost somehow… I am about 95% complete. 04/06/06 – Finished 100% complete. |
| F6.009.000 | International Patients Accounted For |  | Steven Coad | Sandy Morris | Sandy Morris, Steven Coad | 03/23/06: All of the fields have been finalized and are finished. I only need to set up the fields so that they change the region label based on the country. And the underlying functionality needs to be implemented. Estimated 25% complete. 03/30/06: I have international patients accounted for and am pulling items from the database. 100% complete |
| F11.024.000 | Email address is the userid |  | Steven Coad | Sandy Morris | Sandy Morris, Steven Coad | 03/23/06: I am unsure of how to do this. 03/30/06: I have figured out how to do this and just have to plug it in. 99% complete. 04/06/06: 100% complete. |
| F14.036.000 | Each field shall have an instruction |  | Steven Coad | Sandy Morris | Sandy Morris, Steven Coad | 03/17/06 – All fields in the Field Attributes.xls file have instructions. I only need to add them for international patients. Finished 100% complete. 03/23/06 This is finished. 100% complete. |
| F14.038.000 | Context Help |  | Steven Coad | Sandy Morris | Sandy Morris, Steven Coad | 03/17/06 – The popup window is there. I just have to figure out how to reference tooltips in one page from another and if I can do that. Estimated 25% complete. 03/17/06 The Context Help has been created for all of the data entry view pages. I only need to add the logic so that for each page only the context help for that page shows up. I also need a few page descriptions for the other pages. Estimated 75% complete. 03/30/06: I have the page descriptions I only need to add the logic for the pages that are not data entry view pages (included in this module). So I’m 99% complete. 04/06/06: 100% complete. |
| F15.040.000 | Printable Confirmation Screen |  | Steven Coad | Sandy Morris | Sandy Morris, Steven Coad | 03/23/06: The confirmation screen is finished. It just needs the logic that will allow it to be dynamic. Then I just need to add the print button. Estimated: 75% complete. 03/30/06: I tested this today and it works. 100% complete. |
| D5.050.000 | Screens easy to read and uncluttered |  | Steven Coad | Sandy Morris | Sandy Morris, Steven Coad | 03/17/06: 100% complete. |
| D5.052.000 | Site has navigation/progress indicator |  | Steven Coad | Sandy Morris | Sandy Morris, Steven Coad | 03/17/06: I need to change the progress indicator based upon the suggestions given to me in the UI Review but it has been created. Estimated 50% complete. 03/23/06: This is finished. 100% complete. |
| D1.049.000 | Information entered in multiple screens |  | Steven Coad | Sandy Morris | Sandy Morris, Steven Coad | 03/17/06: I need to break up the clinical information into two screens otherwise this is finished. Estimated 85% complete. 03/17/06: This is finished. 100% complete. |
| F13.034.000 | Read Only Fields are Grayed-out |  | Steven Coad | Sandy Morris | Sandy Morris, Steven Coad | 03/30/06: I have implemented the graying out functionality for when the demographics screen when user decides that they have the same address as their guardian. The rest is really a patient review requirement. So for this module 100% complete. |
| D5.055.000 | Buttons on the page will have directional arrows |  | Steven Coad | Sandy Morris | Sandy Morris, Steven Coad | 03/23/06: This is finished: 100% complete. |

Module 4 data Entry Logic

Module 4 – Data Entry Logic - Development Status

03/17/2006 – This module is not scheduled to start until after the status reporting date. One requirement has been satisfied through the UI review. 03/23/2006 – This module is about 60% complete. Validators are mostly done. Remaining work is mostly dependent on database and session state information. This is progressing on-time. 03/30/2006 – This module is 100% complete.

| Req # | Req. Title | Tech Des # | Approver | Responsible Person | Participants in Task | Date and Progress Status |
| --- | --- | --- | --- | --- | --- | --- |
| F3.003.000 | HIPAA Acceptance a Must |  | Sandy Morris | Elaine Simone | Elaine Simone, Sandy Morris | 03/17/06 – per discussion during the User Interface review today: A Patient will accept by choosing the accept button and going to the next page, and decline by canceling all together or clicking back, which will end his or her progress. This changes the design of this requirement, making a validation on a users selection to determine the next webpage location not necessary. 03/30/06 - 100% Complete |
| F4.005.000 | Guardian Age Check |  | Sandy Morris | Elaine Simone | Elaine Simone, Sandy Morris | 03/23/06 – Intend to try using compareValidator. May need to create custom validator, because have to convert from date of birth to age, or compare date of birth date to current date minus 18 years. 10% Complete 03/30/06 – Created Function for this and test page. Function must be pasted in “code behind the page” though because cannot figure out how to import other classes. 100% Complete* |
| F6.010.000 | Validation Page-by-Page |  | Sandy Morris | Elaine Simone | Elaine Simone, Sandy Morris | 03/23/06 – Validators are in place, and mostly working (need to test regular expression based validators some more) Need to change screen layout to incorporate error summary. Would like to review visuals of validation. 85% Complete. 03/30/06 – Validators 100% complete |
| D5.053.000 | Cancelling will cause a loss of previously entered information |  | Sandy Morris | Elaine Simone | Elaine Simone, Sandy Morris | 03/23/06 – Need to double check how data is being saved for data entry view pages before completing this task. 0% 03/30/2006 – Wrote method that clears all session variables. Function must be pasted in “code behind the page” though because cannot figure out how to import other classes. 100% Complete* |
| F11.023.000 | Authentication Fields Entered Twice |  | Sandy Morris | Elaine Simone | Elaine Simone, Sandy Morris | 03/23/06 – Required field validator for each, and a Compare Validator used to make sure the values are equal. 100% Complete. |

Module 5 Patient Update

Module 5 – Patient Update - Development Status

03/17/2006 – This module is approximately 30% complete. 03/23/2006 – This module is approximately 30% complete. Most work is deferred until completion of module 3. 03/30/2006 – This module is approximately 60% complete. Remaining work is heavily database dependent. This is on-time. 04/06/06 – This module is approximately 97% complete. Work will finish on Saturday.

| Req # | Req. Title | Tech Des # | Approver | Responsible Person | Participants in Task | Date and Progress Status |
| --- | --- | --- | --- | --- | --- | --- |
| F9.018.000 | Patients Actively Confirm Information Up to Date |  | Sandy Morris | Tracy Rericha | Tracy Rericha, Sandy Morris | 3/17/06: Estimated 40% complete; confirmation screen has been created and linked to Registry Coordinator pages. 3/23/06: Estimated 40% complete; confirmation screen has been created and linked to Registry Coordinator pages. 3/30/06: Estimated 60% complete; still need to utilize database components which just became available. 4/6/06: 97% complete; still needs to be tested. Will be completed on-time for review. |
| F11.025.000 | Email address update can be changed to userid |  | Sandy Morris | Tracy Rericha | Tracy Rericha, Sandy Morris | 3/23/06: I’ve done some research on this, but am unsure of how to do this. 3/30/06: Estimated 60% complete. After getting some help from John on a different way to do this, the UI components are all completed and now I just need to interface with the database when those components are available. 4/6/06: Estimated 97% complete; still needs to be tested. Will be completed on-time for review. |
| Req TBD | User declines informed consent; alert pops up to inform them and their account is set to disabled |  | Sandy Morris | Tracy Rericha | Tracy Rericha, Sandy Morris | 4/6/06: New; estimated 97% completed; pending testing. Will be completed on-time for review. |

Module 6 Coordinator – Patient Review

Module 6 – Coordinator – Patient Review - Development Status

03/17/2006 – This module is approximately 40% complete. This is on time. 03/30/2006 – This module is approximately 60% complete. Remaining work is dependent on database. This module is on time. 04/06/06 – This module is approximately 88% complete.

| Req # | Req. Title | Tech Des # | Approver | Responsible Person | Participants in Task | Date and Progress Status |
| --- | --- | --- | --- | --- | --- | --- |
| F6.011.000 | Patient Pending List |  | Sandy Morris | Tracy Rericha | Tracy Rericha, Sandy Morris | 3/17/06: Estimated 60% complete; UI piece completed but need to integrate with database to populate list with data from the database. 3/23/06: Estimated 70% complete. 3/30/06: Estimated 70% complete; need database components. 4/6/06: Estimated 90% complete; needs testing. Will be completed on-time for review. |
| F6.011.001 | Message with Number of Pending Patients |  | Sandy Morris | Tracy Rericha | Tracy Rericha, Sandy Morris | 3/17/06: Estimated 90% complete; the only thing left to do is populate the actual number of patients pending in this text with the number in the database. 3/23/06: Estimated 90% complete. 3/30/06: Estimated 90% complete; need database components. 4/6/06: Estimated 98% complete; need testing. Will be completed on-time for review. |
| F5.006.000 | Change Log |  | Sandy Morris | Tracy Rericha | Tracy Rericha, Sandy Morris | 3/17/06: Estimated 5% complete; UI component realized. 3/23/06: Estimated 5% complete. 3/30/06: Estimated 5% complete; need database components. 4/6/06: Estimated 85% complete; needs testing. Will be completed on-time for review. |
| F5.007.000 | Communication Log |  | Sandy Morris | Tracy Rericha | Tracy Rericha, Sandy Morris | 3/23/06: Estimated 5% completed. 3/30/06: Estimated 5% completed; need database components. 4/6/06: Estimated 85% complete; needs testing. Will be completed on-time for review. |
| F6.012.000 | Registry Coordinator Approves New Patients |  | Sandy Morris | Tracy Rericha | Tracy Rericha, Sandy Morris | 3/23/06: Estimated 10% completed; UI component in place. 3/30/06: Estimated 10% completed; need database components. 4/6/06: Estimated 90% complete; needs testing and integration with new patient logic (Module 3). Will be completed on-time for review. |
| F7.013.000 | Registry Coordinators perform Patient Lookups |  | Sandy Morris | Tracy Rericha | Tracy Rericha, Sandy Morris | 3/17/06: Estimated 50% complete. UI approval screens created (Patient Lookup page), but need to interface with the database for actual values. 3/23/06: Estimated 50% complete. 3/30/06: Estimated 70% complete; session variables have been created to use for lookups as soon as I know how to use the database components with them. 4/6/06: Estimated 85% complete; needs testing and database integration, as well as validation (Module 4). Will be completed on-time for review. |
| F11.030.000 | Registry Coordinators can disable accounts |  | Sandy Morris | Tracy Rericha | Tracy Rericha, Sandy Morris | 3/17/06: Estimated 30% complete. UI components realized, but need to work on logistics of disable and database interaction. 3/23/06: Estimated 30% complete. 3/30/06: Estimated 30% complete; need database components. 4/6/06: Estimated 90% complete; needs testing. Will be completed on-time for review. |
| F13.035.000 | Registry Coordinators can edit any patient field |  | Sandy Morris | Tracy Rericha | Tracy Rericha, Sandy Morris | 3/17/06: Estimated 20% complete; UI components realized. 3/23/06: Estimated 25% complete. 3/30/06: Estimated 50% complete; RCs should be able to edit any patient field as soon as those patient fields are truly editable by using database components. 4/6/06: Estimated 95% complete; needs testing and integration with existing edit logic (Module 3). Will be completed on-time for review. |
| D5.054.000 | Mechanism for RC/Admin navigation of site |  | Sandy Morris | Tracy Rericha | Tracy Rericha, Sandy Morris | 3/17/06: Estimated 40% complete; created tabs for navigation of pages but need to look into setup of pages further. 3/23/06: Estimated 40% complete. 3/30/06: Estimated 60% complete. Tabs are now standard along with the rest of the pages, but templates for headers/footers need to be integrated. 4/6/06: Estimated 99% complete; only remaining task is to link to Query pages (Module 8) when the Query pages become available. Will be completed on-time for review. |
| Requirement TBD | Coordinator needs mechanism to delete non-approved patients from the pending list |  | Sandy Morris | Tracy Rericha | Tracy Rericha, Sandy Morris | 4/6/06: New; estimated 98% complete; needs to be tested. Will be completed on-time for review. |

Module 7 Admin Functionality

Module 7 – Admin Functionality - Development Status

03/17/2006 – This module is not scheduled to begin at the time of the status report so no progress has been made. 03/23/2006 – This module is not scheduled to begin at the time of the status report so no progress has been made. 03/30/2006 – This module is not scheduled to begin at the time of the status report so no progress has been made. 04/06/06 – This module is approximately 65% complete. This will be completed on Saturday.

| Req # | Req. Title | Tech Des # | Approver | Responsible Person | Participants in Task | Date and Progress Status |
| --- | --- | --- | --- | --- | --- | --- |
| F11.031.000 | Administrator can reset passwords |  | Tracy Rericha | Steven Coad | Steven Coad, Tracy Rericha | 04/06/06 – 50% complete. Under-the-hood functions are in place, UI needed. |
| F17.043.000 | Adminstrator Manages All Types of Accounts |  | Tracy Rericha | Steven Coad | Steven Coad, Tracy Rericha | 04/06/06 -100% complete. |

Module 8 Querying

Module 8 - Querying - Development Status

03/17/2006 – Approximately 35% complete. UI components have been made, back-end components need to be finished. This is on time. 03/17/2006 – Approximately 60% complete. Work needs to be made to integrate with database. This is on time. 03/30/2006 – Approximately 70% complete. This module is on-time.\ 04/06/06 – Approximately 85% complete.

| Req # | Req. Title | Tech Des # | Approver | Responsible Person | Participants in Task | Date and Progress Status |
| --- | --- | --- | --- | --- | --- | --- |
| F7.014.000 | Querying the Registry |  | Steven Coad | Elaine Simone | Elaine Simone, Steven Coad | 3/17/06 Completed Initial User Interface for the Querying Screen and the Results. Must incorporate results of the discussion 3/23/06 Incorporated UI Changes. UI 100% Complete for Querying. Validation Controls added and tested. Requirement 70% Complete 03/30/06 Completed Research on how to print query results. Need to implement and test. 75% Complete 04/06/06 Need to setup connection to database. Looking over Steve’s stored procedures to do this. Need to test possible printing solution. 80% Complete Remaining tasks Generate Country, Region and Referral List based on values in the database Query database Investigate scrollbar on data grid, if so then include all columns of results Print Results |
| F8.017.000 | Query Results can be Export to Excel |  | Steven Coad | Elaine Simone | Elaine Simone, Steven Coad | 3/17/06 during the User Interface discussion it was suggested to include what the query was into the results when exported if this is easily completed. 03/30/06 Completed Research on methods to Export query results to Excel. Need to implement and test. 25% Complete 04/06/06 Exporting to Excel is working in prototype. Need to implement with out database. Depends on the querying functionality setup. 90% Complete |

# Module 9 Registry Auto-maintenance

Module 9 – Registry Auto-maintenance - Development Status

03/17/2006 – This module is not scheduled to begin at the time of the status report so no progress has been made. 03/23/2006 – This module is not scheduled to begin at the time of the status report so no progress has been made. 03/30/2006 – This module is not scheduled to begin at the time of the status report so no progress has been made. 04/06/2006 – This module is not scheduled to begin at the time of the status report so no progress has been made.

| Req # | Req. Title | Tech Des # | Approver | Responsible Person | Participants in Task | Date and Progress Status |
| --- | --- | --- | --- | --- | --- | --- |
| F10.020.000 | Annual Email Reminder |  | Elaine Simone | Steven Coad | Steven Coad, Elaine Simone |  |
| F10.021.000 | 3 Consecutive Email Reminders |  | Elaine Simone | Steven Coad | Steven Coad, Elaine Simone |  |
| F10.022.000 | Automatic Account Disabling |  | Elaine Simone | Steven Coad | Steven Coad, Elaine Simone |  |

Module 10 Static Site Content

Module 10 – Static Site Content – Development Status

03/17/2006 – This is approximately 98% complete. This is ahead of schedule. 03/17/2006 – This is approximately 99% complete. This is ahead of schedule. 03/17/2006 – This module is 100% complete. This is ahead of schedule.

| Req # | Req. Title | Tech Des # | Approver | Responsible Person | Participants in Task | Date and Progress Status |
| --- | --- | --- | --- | --- | --- | --- |
| F2.002.000 | General Information about Registry on Site |  | Tracy Rericha | Sandy Morris | Sandy Morris, Tracy Rericha | 03/17/06: 100% complete. |
| F3.004.000 | Explanation Page for HIPAA Decline |  | Tracy Rericha | Sandy Morris | Sandy Morris, Tracy Rericha | 03/23/06: I just need to link in the page. Estimated: 75% complete. 03/30/06: Finished: 100% complete. |
| F4.005.001 | Error Page for Invalid Guardian Age |  | Tracy Rericha | Sandy Morris | Sandy Morris, Tracy Rericha | 03/23/06: I need to determine how the age is being computed based on the date of birth before I can link in this page. I also need to add the warning message. The page has been completed though. Estimated: 75% complete. 03/30/06: Finished: 100% complete. |
| F16.042.000 | Links/News/Educational Resources on Home Page |  | Tracy Rericha | Sandy Morris | Sandy Morris, Tracy Rericha | 03/17/06: I only need to finish the links popup for the footer. The links on the home page are finished. Estimated 75% complete. 03/23/06: Finished: 100% complete. |
| F9.019.000 | Home Page Reminders |  | Tracy Rericha | Sandy Morris | Sandy Morris, Tracy Rericha | 03/17/06: 100% complete. |
| D6.056.000 | Header/footer is similar to FARA site |  | Tracy Rericha | Sandy Morris | Sandy Morris, Tracy Rericha | 03/17/06: I need to finish the popup windows for the Help, Links, and Contact Us Links. Estimated 75% complete. 03/23/06: Again, the popup window for the help just needs the logic to make it page specific. Estimated: 95% complete. 03/30/06: Finished: 100% complete. |
| F14.037.000 | Email link |  | Tracy Rericha | Sandy Morris | Sandy Morris, Tracy Rericha | 03/17/06: Email links are present on all pages but the Informed Consent Error Screen which has yet to be implemented. Estimated 95% complete. 03/23/06: Finished: 100% complete. |