## Testing_Issues_Defects
Test Issues/Defects Log Version 1.1 (21 November, 2003)
Issues identified from testing must be evaluated to determine if the issue should be counted as a pre-release defect.
Testing "issues" are considered pre-release defects if they would cause the final system not to work as specified by the requirements.
A green shaded column header indicates there is a drop down box.
NOTE: Take care not to delete the drop down lists found at row 3000 column AA.
|  |  |  | Issue/Defect Identification | [6 empty] | Issue/Defect Evaluation and Assignment | [5 empty] | Enter this information when the issue/defect is resolved.
ID | Date Identified | Short Title | Description | Identified By | Release # /functional area/Application | Affected Work Product | Test Case ID | Defect Module | Severity | Priority | Assigned to | Date Assigned | Status | Status Date | Date Closed | Closure/Resolution | Closure/Resolution Type | Duplicate Defect (Y/N) | Defect Type | Process Introduced (Origin)
15 | 2006-04-30 | Tool Tips and Commit Collapse |  | Lei Wu | 1 |  | 3 |  | 2 - Major - No Work Around | Medium | Sandy Morris | 2006-05-01 | Retest | 2006-05-04 |  | Added missing tooltips, unable to reproduce system crashing | Not reproducible | N | 5 - Documentation Error
24 | 2006-05-01 | Context Help | Nothing on Pending Patient Home | Lei Wu | 1 | PendingPatientHome.aspx | 4 | 10 Static Site Content | 5 - Cosmetic | Low | Sandy Morris | 2006-05-02 | Closed | 2006-05-02 | 2006-05-04
2a | 2006-04-28 | Help Email doesn't arrive | Logged in the gmail.com as instructed and email was not there. I believe it went to 'jen.farmer@faresearchalliance.org' instead. | Darren Bielby | 1 | System Test Cases | 6 | 10 Static Site Content | 4 - Minor | Low | Sandy Morris | 2006-04-28 | Closed | 2006-04-28 | 2006-04-28 | Update System Test Cases | Functions as Designed | N | 4 - Testing Error
2c | 2006-04-28 | Additional pop up in test case | In this test case, there is a pop up window which displays after step 9 which isn't listed. I realize it's an actual expected result, but I thought I'd mention it. | Darren Bielby | 1 | System Test Cases | 6 | 10 Static Site Content | 5 - Cosmetic | Low | Sandy Morris | 2006-04-28 | Closed | 2006-04-28 | 2006-04-28 | Update System Test Cases | Functions as Designed | N | 4 - Testing Error
11 | 2006-04-30 | Validation on Clinical Age fields | Invalid characters accepted in the Age of Symptom OnsetAge of Diagnosis | Michelle Whalen | 1 | ClinicalInfo.aspx | 9 | 4 Validation | 1 - Catastrophic | Medium | Elaine Simone | 2006-05-01 | Closed | 2006-05-01 | 2006-05-01 | "duplicate" of defect 4. (Validation error is what caused the confirmation error | Fixed | Y | 3 - Coding Error
12 | 2006-04-30 | Validtion on Triplet Repeat Fields | Invalid characters accepted in the Triple Repeat 1Triple Repeat 2 | Michelle Whalen | 1 | ClinicalInfo.aspx | 9 | 4 Validation | 2 - Catastrophic | Medium | Elaine Simone | 2006-05-01 | Closed | 2006-05-01 | 2006-05-01 | Validation on Second Clinicial page was mistakingly off. Now turned on again. These missing fields had caused the error on confirmation | Fixed | Y | 3 - Coding Error
13 | 2006-04-30 | Validation on Clinical Age fields | Invalid characters accepted in the Age of Symptom OnsetAge of Diagnosis | Michelle Whalen | 1 | ClinicalInfo.aspx | 9 | 4 Validation | 1 - Catastrophic | Medium | Elaine Simone | 2006-05-01 | Closed | 2006-05-01 | 2006-05-01 | "duplicate" of defect 4. (Validation error is what caused the confirmation error | Fixed | Y | 3 - Coding Error
3 | 2006-04-28 | Validation on Email Error | Cannot register. Kept telling me that the email address already exists. See attached for error and javascript error message being generated. Tested in IE. | Darren Bielby | 1 | AccountInfo.aspx | 11 | 4 Validation | 2 - Major - No Work Around | High | Elaine Simone | 2006-04-28 | Closed | 2006-04-28 | 2006-04-28 | ClientValidatorFunction should be empty. This field names the script that is run for onpage client validation. The server side script is defined in the html representation. Select to view Source OnServerValidate="X_ServerValidate"¦ deployed immediately | Fixed | N | 3 - Coding Error
4 | 2006-04-28 | Error on Confirmation | Received the following error after pressing the Confirm Information button. I believe there is a known issue with the log file. Also attached is the confirmation information screen which may help with what data I was using when completing the registration. | Darren Bielby | 1 | Confirmation.aspx | 11 | 4 Validation | 2 - Major - No Work Around | High | Elaine Simone | 2006-04-28 | Closed | 2006-04-30 | 2006-05-01 | Validation on Clinicial page was mistakingly off. Now turned on again. These missing fields had caused the error on confirmation | Fixed | N | 3 - Coding Error
8 | 2006-04-29 | Issue with default value of patient free form region | I created a new user who was less than 18 yrs of age, entered demographic information for the guardian, went to the demographic information page for the minor, I checked the Same as Guardian Check box for demographic information and then unchecked it. I got the following error: 'PatRegionDD' has a SelectedValue which is invalid because it does not exist in the list of items.Parameter name: valueNote: this error will not prevent me from completing this test case | Julian Pisoni | 1 | DemInfo.aspx | 13 | 3 Patient data Entry | 3 - Major - Work Around | Medium | Sandy Morris | 2006-04-30 | Closed | 2006-04-30 | 2006-04-30 | The region was being set to an id that doesn't exist for international users. | Fixed | N | 3 - Coding Error
21 | 2006-05-01 | Received the following error after pressing the Confirm Information button time after time. | Received the following error after pressing the Confirm Information button time after time. | Darren Bielby | 1 | Confirmation.aspx | 16 |  | 2 - Major - No Work Around | High | Elaine Simone | 2006-05-02 | Closed | 2006-05-02 | 2006-05-04
26 | 2006-05-01 |  | Could not enter the account:Username: faraPatient@gmail.comPassword: faratest | Lei Wu | 1 | Login.aspx | 17 | 2 Login | 2 - Major - No Work Around | High | Steven Coad | 2006-05-02 | Closed | 2006-05-02 | 2006-05-04
16 | 2006-04-30 | Incorrect Password Logs in | On step 4: when the password is incorrect, it directs to page Informed Consent | Lei Wu | 1 | Login.aspx | 19 | 2 Login | 2 - Major - No Work Around | High | Steven Coad | 2006-05-01 | Closed | 2006-05-01 | 2006-05-04
27 | 2006-04-30 | Incorrect Password Logs in | On step 4: when the password is incorrect, it directs to page Informed Consent | Lei Wu | 1 | Login.aspx | 19 | 2 Login | 2 - Major - No Work Around | High | Steven Coad | 2006-05-01 | Closed | 2006-05-02 | 2006-05-04 |  | Issue, not a defect
17 | 2006-04-30 | No Security Question drop down and Email isn't sent | Step 3: Choose security question from a drop down listQuestion: There’s no drop down listFailed: after type correct answer “Squirt”, it shows the correct password has sent to gmail. But I couldn’t find any email in that gmail account after many hours.Meanwhile, if I type an incorrect answer, it still shows the correct password has sent to the gmail address. | Lei Wu | 1 | Login.aspx | 20 | 2 Login | 2 - Major - No Work Around | High | Steven Coad | 2006-05-01 | Retest | 2006-05-04
28 | 2006-05-01 | Forgotten Password page issues | Forgotten Password page issues | Lei Wu | 1 | System Test Cases | 20 | 2 Login | 2 - Major - No Work Around | Medium | Steven Coad | 2006-05-02 | Closed | 2006-05-02 | 2006-05-02 | Updated System Test Cases | Issue, not a defect | N | 5 - Documentation Error
30 | 2006-05-01 | system collapses |  | Lei Wu | 1 | Login.aspx | 22 | 2 Login | 2 - Major - No Work Around | High | Steven Coad | 2006-05-02 | Retest | 2006-05-03
9 | 2006-04-30 | dob required field Validator for returning patient is still triggering | Even though the DOB field is not editable, the field validator always triggers. Whether I try to edit the DOB or not, the field validator triggers and will not let me continue and therefore cannot edit any of the other fields on the page. | Julian Pisoni | 1 | InitialInfo.aspx | 25 | 4 Validation | 2 - Major - No Work Around | Medium | Elaine Simone | 2006-05-01 | Closed | 2006-05-01 | 2006-05-03 | disabled Validation on uneditable dob field for returning patients | Fixed | N | 3 - Coding Error
7 | 2006-04-29 | Cannot login with provide account info | I could not login with the information provided in the test case. faraPatient@gmail.com faratest | Julian Pisoni | 1 | Login.aspx | 27 | N/A | 2 - Major - No Work Around | ASAP - as soon as possible | Elaine Simone | 2006-04-30 | Closed | 2006-04-30 | 2006-04-20 | User accounts password had been changed in another test case (as directed). Updated system test cases and informed users that password may be etiher faratest or eternal | Issue, not a defect | N | 4 - Testing Error
5 | 2006-04-28 | Cannot find Genetic information, and Back Button Issues | Issues. Tried using the Back button on the screen and it took me through what seemed like the user registration process while I’m logged in as Jen.Farmer | Don Pecor | 1 | Data entry Screens | 31 | 6 | 4 - Minor | Medium | Sandy Morris | 2006-04-28 | Closed | 2006-04-30 | 2006-05-02 | Disabled the Back button for returning users. | Fixed | N | 2 - Design Error
6 | 2006-04-28 | Country needs to always be selected | Patient Lookup not working properlyDeveloper Follow up: (Abbreviated) Patty Pending was from Columbia, not United StatesTester Follow up: Seems like the default should be "Select Country" in the dropdown or this should not be a required field similar to the birthday fields. | Don Pecor | 1 | PendingPatientLookup.aspx | 31 | 6 | 4 - Minor | Medium | Tracy Rericha | 2006-04-28 | Cancelled | 2006-04-30 | 2006-05-01 | Although this is not a defect I have explored several solutions anyway to try and accommodate the need, but the solution requires major rework (if it is even possible) – because of the way the Country dropdown is populated (directly from the database) as opposed to the way the Last Name and Date of Birth fields are being populated (via session variables). As this issue has been discussed at one of our previous technical reviews, and the consensus was that it is okay for the user to always select a country, this issue is resolved. | Functions as Designed | N | 2 - Design Error
18 | 2006-05-01 | Patient Lookup not working properly | Enter Pending in Last Name field. Click Search and list return with Patty Pending in it. Try to Select Patty Pending and screen refreshes to show all patients. | Don Pecor | 1 | PatientPendingPatientLookup.aspx | 31 | 6 Patient-Coordinator Review | 4 - Minor | Medium | Tracy Rericha | 2006-05-01 | Closed | 2006-05-01 | 2006-05-01 | Placed GetAllActive function call inside the if !Page.IsPostBack block. | Fixed | N | 3 - Coding Error
31 | 2006-05-02 | Unhandled Login Error | UnhandledLogin Error occurred on mistyped username | Don Pecor | 1 | Login.aspx | 31 | 2 Login | 2 - Major - No Work Around | High | Steven Coad | 2006-05-02 | Closed | 2006-05-02 | 2006-05-04
32 | 2006-05-02 | Need two clicks | Entering clinical information part 2, triplet repeat info. Had to click Next twice for it to update.*Note: Firefox browser, cannot replicate in IE | Don Pecor | 1 | ClinicalInfo2.aspx | 31 | 2 Login | 4 - Minor | Low | Sandy Morris | 2006-05-02 | Cancelled | 2006-05-02 | 2006-05-03 | This is actually just a fluke that occurs because of the auto postback check on the triplet repeat fields (have to check to see if the optional point mutation field will be shown) and it only shows up in Firefox. To get around you have to tab through the window so the checks work themselves out. So for example, if you edit one triplet repeat field tab down and edit the next and then click the ‘Next’ button, the processing will have to finish so that is why the ‘Next’ button must be clicked twice. The first time you click it the auto postback for the second field runs and does the check. Then you must click it again to go to the next screen. | Issue, not a defect | N
19 | 2006-05-01 | Column Names on Reporting Screen | Functionality is fine, column names look like database names. | Don Pecor | 1 | Reporting.aspx | 32 | 6 Patient-Coordinator Review | 5 - Cosmetic | Low | Elaine Simone | 2006-05-01 | Closed | 2006-05-01 | 2006-05-02 | Changed Column Headers on Reporting Page | Fixed | N | 3 - Coding Error
20 | 2006-05-01 | Cannot access disabled patients | no patient listed for that combination (United States 2/10/1983) – went to Reporting and found 2 disabled patients (Summers and Drake) but could get them to be listed in the patient lookup tool. | Don Pecor | 1 | PatientPendingPatientLookup.aspx | 34 | 6 Patient-Coordinator Review | 2 - Major - No Work Around | High | Tracy Rericha | 2006-05-02 | Closed | 2006-05-02 | 2006-05-05
29 | 2006-05-01 | system collapses |  | Lei Wu | 1 | Login.aspx | 41 | 2 Login | 2 - Major - No Work Around | High | Steven Coad | 2006-05-02 | Closed | 2006-05-02 | 2006-05-02 | Updated System Test Cases | Issue, not a defect | N | 6 - Documentation Error
22 | 2006-05-01 | error after pressing the Reset Password button. |  | Darren Bielby | 1 | AdminPasswordReset.aspx | 43 | 7 Admin Functionality | 2 - Major - No Work Around | High | Steven Coad | 2006-05-02 | Closed | 2006-05-02 | 2006-05-04
23 | 2006-05-01 | Mouseover / tool tips | 1. on test step 1:when mouse is located on the link of “Help ¦ Links ¦ Contact Us”, the cursor doesn’t change to “hand”.2. on step 9: tool tips incorrect, see figure 3.1 | Lei Wu | 1 |  | 3 | 10 Static Site Content | 4 - Minor | Low | Sandy Morris | 2006-05-02 | Closed | 2006-05-02 | 2006-05-02 |  | Issue, not a defect
1 | 2006-04-28 | Cosmetic Issues on Login Page | Browser title Untitled. default button, tab index not intutive | Don Pecor | 1 | Login.aspx | 28 (Found in 30) | 2 Login | 5 - Cosmetic | Low | Steven Coad | 2006-04-28 | Closed | 2006-05-01 | 2006-05-01 | Follwed Recommendations | Fixed | N | 3 - Coding Error
10 | 2006-04-30 | Untitled Login | The Login Page has the title of “Untitled Page” on the IE title bar. | Julian Pisoni | 1 | Login.aspx |  | 2 Login | 5 - Cosmetic | Low | Steven Coad | 2006-04-28 | Closed | 2006-05-01 | 2006-05-01 | duplicate of defect 1 |  | Y | 3 - Coding Error
14 | 2006-04-30 | Forgot Password page does not redirect | Did not go back to home page | Michelle Whalen | 1 | ForgotPassword.aspx |  | 2 Login | 4 - Minor | Low | Steven Coad | 2006-05-01 | Closed | 2006-05-02 | 2006-05-04
25 | 2006-05-02 | Cancel button logs out coordinators | When a registry coordinator or Administrator is viewing a patient record, and hits cancel, instead of confirm this logs them out and returns them to the homepage | Elaine Simone | 1 | Confirmation.aspx |  | 6 Patient-Coordinator Review | 3 - Major - Work Around | Medium | Sandy Morris | 2006-05-02 | Closed | 2006-05-02 | 2006-05-04 | Now when you press the cancel button for a registry coordinator/administrator it clears all fo the patients information out of session so nothing is changed and the user is redirected to the Registry Coordinator/Admin Home Page, not logged out. | Fixed | N | 2 - Design Error
2b | 2006-04-28 | dob Validation error message | Also, on the registration screen, if you put in an invalid date like 03/42/2001, the error message doesn't say invalid date, but rather says something like 'contains invalid characters'. | Darren Bielby | 1 | InitialInfo.aspx GuardianInfo.aspx |  | 4 Validation | 5 - Cosmetic | Low | Elaine Simone | 2006-04-28 | Closed | 2006-04-30 | 2006-05-01 | Changed error message on dob regEx Validator | Fixed | N | 9 - Other Error
33 | 2006-05-05 | When a patient is set to inactive they are given the status of disable. | When a patient is set to inactive they are given the status of disable. | Elaine Simone | 1 | AccountInfo.aspx | 34 | 6 Patient-Coordinator Review | 5 - Cosmetic | Low | Sandy Morris | 2006-05-05 | Closed | 2006-05-05 | 2006-05-05 |  | Functions as Designed
34 | 2006-05-05 | Account Lockout never happens | Accounts that have been “locked out” never actually have their status changed.User is able to log in again immediatelyDoes not appear in registry database with status of locked out (3). | Elaine Simone | 1 | Login.aspx | 21, 29, 40 | 2 Login | 2 - Major - No Work Around | High | Steven Coad | 2006-05-05 | Open | 2006-05-05
35 | 2006-05-05 | Account disable field is always set to a status of active, even when a patient is not | Account disable field is always set to a status of active, even when a patient is not | Elaine Simone | 1 | AccountInfo.aspx | 35 | 6 Patient-Coordinator Review | 4 - Minor | Medium | Sandy Morris | 2006-05-05 | Open | 2006-05-05
36 | 2006-05-05 | Registry Automatienence does not appear to be working. | Registry Automatienence does not appear to be working.Waited half an hour.Patients did not receive emailsStatus did not changeNo updates in change logNo emails received. | Elaine Simone | 1 | Reporting.aspx | 38 | 9 Auto Maitenence | 1 - Catastrophic | High | Steven Coad | 2006-05-05 | Open | 2006-05-05
[21 empty] | System Testing | 1 - Catastrophic | ASAP - as soon as possible | Open | Fixed | Y | 1 - Requirements Error | Refine and Analyze Requirements
[21 empty] | User Acceptance Testing | 2 - Major - No Work Around | High | Retest | Functions as Designed | N | 2 - Design Error | Design application
[21 empty] | Unit Testing | 3 - Major - Work Around | Medium | Ready to Implement | Not reproducible |  | 3 - Coding Error | Produce Application
[22 empty] | 4 - Minor | Low | Cancelled | Change Request Created |  | 4 - Testing Error | Produce Application - Integration Testing
[22 empty] | 5 - Cosmetic |  | Closed | Issue, not a defect |  | 5 - Documentation Error | Release Application
[22 empty] | 6 - Internal |  | Ready to Implement |  |  | 6 - Process/Standards Error | Release Application - Formal Acceptance Testing
[27 empty] | 7 - Hardware/Systems Software Error | Implement Application
[27 empty] | 8 - Human Intervention Error | Implement Application - Post Implementation
9 - Other Error
10 - Project Management Error
11 - Third Party Error
Note on B7: Date when the issue/defect was identified.
Note on C7: A short name for issue/defect.
Note on D7: Give a description of the issue/defect.
Note on E7: Enter the person's name reporting the issue/defect.
Note on F7: Specify the release the item is in; the functional area responsible or application affected.
Note on G7: What Work Product was the issue/defect found in?
Note on H7: Enter the test case id where the issue/defect was discovered.
Note on J7: This is a measure of what the severity of the impact would be if the issue/defect was found in production.
Note on K7: Enter the priority for resolving or fixing this issue/defect.
Note on L7: Enter the name of the person who assigned to this issue/defect.
Note on M7: Enter the date this issue/defect was assigned.
Note on N7: Enter the current status of this item.
Note on O7: Enter the date when the issue/defect was closed.
Note on P7: Enter the date when the issue/defect was closed.
Note on Q7: Enter any text about the closure or resolution of this issue/defect.
Note on R7: Enter what action was taken to close the issue/defect.
Note on S7: This is to eliminate duplication of issue/defects reports that required only one fix and items that are not defects. A "Y" would not be counted for entry into PreSage.
Note on T7: This is the type of defect - or the underlying or fundamental cause of the problem.
Note on U7: What project common process/phase was the origin of the defect? That is, where did the original problem creep into the process?

## Field Descriptions
Test Issues/Defects Log Version 1.1 (21, November, 2003)
1. This log is intend to have recorded all issues, defects or incidents from testing. All fields may be modified except the ones designated with an asterisk *. This indicates they are required for enterprise reporting of valid, unique defects. 2. The data entry format for the date fields is MM/DD/YYYY and is displayed as DD/MMM/YYYY. This may be different depending on the local settings of the computers. You may want to modify the date formats based on local or project standards. Also note there is conditional formatting on the date fields so when the closed date is entered the date fields are shaded gray. 4. To update the drop down lists, go to row 3000 column AA on the "Testing_Issues_Defects" tab and update the dropdown list. Use the Data/Validation command options to increase the size of the list.
Field | Description
ID | A sequential unique number for the issue/defect.
Date Identified | The date the issues/defect was identified. This date provides the number of newly discovered issues/defects.
Short Title | A short name for issue/defect.
Description | Detailed description of the issue/defect.
Identified By | The person reporting the issue/defect.
Release # /functional area/Application | Specify the release the item is in; the functional area responsible or application affected. If all items are needed create additional columns.
Affected Work Product | The specific work product where the issue/defect is located.
Test Case ID | If applicable, the test case ID where the issue/defect was identified.
Defect Module | Which Module does the defect come from
1 - Database
2 – User authentication / login
3 – Patient data Entry
4 -Validation
5 – Returning Patient
6 – Coordinator – Patient Review
7 – Admin Functionality
8 – Querying
9 – Registry Auto-Maintenance
10 – Static Site Content
Process Detected * | The testing activity where the issue/defect was detected. Select from the following
Integration Testing
Formal Acceptance Testing
Unit Testing
Severity * | Severity of defect, choose from the following
1 - Catastrophic
2 - Major - No Work Around
3 - Major - Work Around
4 - Minor
5 - Cosmetic
6 - Internal
Priority | ASAP - as soon as possible
High
Medium
Low
Assigned to | This is the person who is assigned to evaluate and resolve the issue/defect.
Date Assigned | The date the issues/defect was assigned.
Status | Current issue/defect status, choose from the following:
Open
Retest
Hold
Cancelled
Closed
Status Date | The date of the most current status update.
Date Closed | The date the issues/defect was closed.
Resolution | Textual information on how the issue/defect was resolved.
Closure/Resolution Type | Final disposition of the issue/defect, choose from the following
Fixed
Functions as Designed
Not reproducible
Change Request Created
Issue, not a defect
Duplicate Defect (Y/N) * | If "N" then this item should be a valid, unique defect that would be counted for reporting to PreSage.
Defect Type * | Defect type based on underlying problem, choose from the following
1 - Requirements Error
2 - Design Error
3 - Coding Error
4 - Testing Error
5 - Documentation Error
6 - Process/Standards Error
7 - Hardware/Systems Software Error
8 - Human Intervention Error
9 - Other Error
10 - Project Management Error
11 - Third Party Error
Process Introduced (Origin) * | Common process/phase in which the defect was introduced, choose from the following common processes/phases:
| Application Waterfall | Work Management | Production Support | Object and Component Engineering | Process Management | Work Migration
| Refine and Analyze Requirements | Plan Project Work | Perform Minor Changes | Establish Arch. - Development View | Deploy Process | Assess Work Migration Alternatives
| Design application | Execute Project Plan | Perform Minor Changes - Analyze Request(s) | Establish Arch. - Logical View | Improve Processes | Prepare for Work Migration
| Produce Application | Manage Suppliers | Perform Minor Changes - Design Application Change(s) | Establish Arch. - Physical View | Analyze Process Effectiveness | Migrate Work
| Produce Application - Integration Testing |  | Perform Minor Changes - Revise/Create Component(s) | Establish Arch. - Process View | Evaluate New Approaches
| Release Application |  | Perform Minor Changes - Test Component(s) | Establish Arch. - Use Case View | Support Process Usage
| Release Application - Formal Acceptance Testing |  | Perform Minor Changes - Verify Documentation Package | Evolve Arch. - Development View | Administer and Provide Training
| Implement Application |  | Perform Minor Changes - Create Impl. Plan | Evolve Arch. - Logical View | Determine Training Requirements
|  |  | Monitor System Operations | Evolve. - Physical View
|  |  | Ongoing Support - Temporary Fix | Evolve Arch. - Process View
|  |  | Provide Client Support | Evolve Arch. - Use Case View
|  |  | Release Application | Evolve Arch - Integrate System Components
|  |  | Release Application - Formal Acceptance Testing | Evolve Arch - Int. System Comp. - Integration Test
|  |  | Implement Application | Conclude Iteration - General
Plan/Prepare for Iteration
Optimize Release - OCE
Optimize Release OCE - FAT
Implement Release - OCE

## Amendment_History
Copyright © 2002 Electronic Data Systems. All rights reserved | Test Issues/Defects Log Version 1.1 (21 November, 2003)
These commodities, technology, or software were exported from the United States in accordance with the Export Administration Regulatios. Diversion contrary to U.S. law is prohibited. Individuals and corporations are required to comply with ALL import and export regulations.
Version | Issue Date | Modified By | CR # | Section, Page(s) and Text Revised
1 | 2002-10-28 | P. Bimba-Hood | 1188 | initial release
1.1 | 2003-11-21 | Micki O'Leary | 1693 | The Test Defects Log (Test_Defects_Log.xls) was updated to reflect the changes in the defects operational definition (the changes to the Production Support work type defect discovery and origin process/phases).
1.1 | 2003-11-21 | P. Bimba-Hood | 1700 | Add the processes for the Work Migration work type.
1 | 2006-05-09 | Elaine Simone |  | Initial Revision for FARA Registry Project
Perform Minor Changes - Design Application Change(s)
Perform Minor Changes - Verify Documentation Package