## Sheet1
Create User Acceptance Test Cases | 2006-03-29
Review User Acceptance Test Cases | 2006-03-31
Update User Acceptance Test Cases (if necessary) | 2006-04-14
Create System Testing Plan | 2006-04-20
Create System Test Cases | 2006-04-20
Create User Acceptance Testing Plan | 2006-04-20
Review System Test Cases | 2006-04-22 | 10:00-11:00am
Update System Test Cases (if necessary) | 2006-04-26
Kick off for System Testing | 2006-04-26 | 4:30 - 6:00pm
Setup System Test Environment | 2006-04-27
Create System Test Data | 2006-04-27
Execute System Test Cases (first run through) | 04/28/06 - 05/02/06
Document/Track/Retest any defects/issues | 04/28/06 - 05/07/06
Testing defect fixes | 04/29/06 - 05/07/06
System Testing Status Meeting (phone) | 2006-05-01 | 5:30-6:30
System Testing Status Meeting (phone) | 5/4/2006 or 5/5/2006
Full regresson testing of defect fixes complete | 2006-05-06
System Testing Complete | 2006-05-07
System Testing SignOff | 2006-05-07
Kick off for User Acceptance Testing |  | 90 minutes
Create User Acceptance Test Data | 2006-05-07
Execute User Acceptance Test Cases | 05/08/06 - 05/15/06
Document/Track/Retest any defects/issues | 05/08/06 - 05/15/06
Initial Sessions | 5/08/2006 - 05/11/2006 | 60 minutes
Returning Sessions | 05/12/2006 - 05/15/2006 | 45 minutes
User Acceptance Testing Complete | 2006-05-16
User Acceptance Testing Sign Off | 2006-05-16