# Meeting Agenda and Minutes

| Meeting Date: | 01/26/06 | Time: | 4:00 PM Eastern – 6:00 PM Eastern |
| --- | --- | --- | --- |
| Host: | Tracy Rericha | Recorder: | Sandy Morris |
| Location: | Teleconference | Conference Call: | (866) 811-0794; Passcode: 902629# |

|  | Name | Role |
| --- | --- | --- |
|  | Steve Coad | RIT – Technical Leader / Developer |
|  | Sandra Morris | RIT – UI Coordinator / Developer |
|  | Tracy Rericha | RIT – Project Manager / Developer |
|  | Elaine Simone | RIT – Quality Assurance Manager / Developer |
|  | John Manos | EDS – Technical Leader SME and Mentor |
|  | Michelle Whalen | EDS – Project Manager SME and Mentor |

##### Agenda:

| Num | Topic | Responsible |
| --- | --- | --- |
|  | - 4:00 – 4:15pm - Schedule slippage – the issue at hand | - Tracy |
|  | - 4:15 – 4:40pm - Wrapping up the Define Phase | - Tracy |
|  | - 4:40 – 5:10pm - Moving ahead to the Design Phase | - Team |
|  | - 5:10 – 5:30pm - Stepping through the schedule | - Team |
|  | 5:30 – 5:45 Scoping Discussion | - Team |
|  | - 5:45 – 6:00pm - Round Table | - Team |

##### Discussion / Minutes:

| Topic 1. Schedule slippage – the issue at hand | Tracy |
| --- | --- |
| Document Detailed Requirements – slipping because original detailed requirements were not detailed enough and in the format expected by EDS - Baseline start was 1/12/06, Baseline finish was the same day; 1/12/06. - Actual start was 1/12/06; Actual Finish: 1/24/06 - This gave us enough time to complete second-round changes to detailed requirements based on discussions from the detailed requirements review Obtain Customer Signoff on Detailed Requirements – slipping because the detailed requirements were not completed on schedule, and we were not able to wrap up the define phase on schedule - Baseline start was 1/19/06, Baseline finish was the same day; 1/19/06 - Actual start was 1/24/06; Proposed Actual finish: 1/26/06 - Already sent out to Jen for approval with all changes from the review Requirements Traceability – need to update after detailed requirements are finalized - Send out for informal review 1/28/06 - Aim to get them signed off 1/31/06 |  |

| Topic 2. Wrapping up the Define Phase | Tracy |
| --- | --- |
| Define Phase Review \ Resolve Issues – slipping because the detailed requirements were not completed on schedule - Baseline start was 1/12/06, Baseline finish was 1/19/06 - Actual start was 1/12/06; Proposed Actual finish: 1/26/06 - Scope must be estimated in terms of effort; the prioritization is used to make a final decision based on that Define and Document User Acceptance Test (UAT) Cases - Start when detailed requirements are approved, proposed date: 1/26/06 General Schedule Changes/Information - Development Environment Done – Monday - Split Learning Environment into two tasks one for SourceSafe (so it can be sooner) and one for the overall environment - Jen will now own the UAT’s so Elaine & Sandy’s primary role will be to review them; Tracy needs to email Jen and give her the timeframe for this task; use the Unit template but add confusion-free instructions so she knows what to do - Add a separate task for the review of the UAT Test Cases - Project schedule is IMPORTANT - Validate estimate – next Thursday |  |

| Topic 3. Moving ahead to the Design Phase | Team |
| --- | --- |
| - Beginning 1/26/06 (or when Define Phase is complete) - Create Initial Context, System and Architecture Diagrams - Document Business/Technical Design - Business/Technical Design Phase Review/Resolve Issues - Obtain Customer Signoff on Business/Technical Design - Create data model design General Info/Schedule Changes - Design phase complete by February 14th - See schedule for further changes - Unit test cases are created alongside the design document - Review of Data Model added |  |

| Topic 4. Stepping through the schedule | Team |
| --- | --- |
| - This part of the agenda reserved to go through the schedule task by task and evaluate dates and resources Deliverables for the next two weeks - Jen is doing the UAT Test Cases - Tracy is going to be working on finalizing the Business/Tech Design Template - Elaine & Sandy working on Unit Test Cases - Steve is working on setting up our development environment - Then we’ll all be working on learning how to use it - Team - Steve will start working on implementing a vertical slice of our application - Data Model & Architecture Diagrams - Team - Scope Estimate Completed |  |

| Topic 5. Scoping Discussion | Team |
| --- | --- |
| - What is in scope? Out of scope? - What do we need to address? |  |

| Topic 6. Round Table | Team |
| --- | --- |