# Meeting Agenda and Minutes

| Meeting Date: | 01/26/06 | Time: | 4:00 PM Eastern – 6:00 PM Eastern |
| --- | --- | --- | --- |
| Host: | Tracy Rericha | Recorder: | Sandy Morris |
| Location: | Teleconference | Conference Call: | (866) 811-0794; Passcode: 902629# |

|  | Name | Role |
| --- | --- | --- |
|  | Steve Coad | RIT – Technical Leader / Developer |
|  | Sandra Morris | RIT – UI Coordinator / Developer |
|  | Tracy Rericha | RIT – Project Manager / Developer |
|  | Elaine Simone | RIT – Quality Assurance Manager / Developer |
|  | John Manos | EDS – Technical Leader SME and Mentor |
|  | Michelle Whalen | EDS – Project Manager SME and Mentor |

##### Agenda:

| Num | Topic | Responsible |
| --- | --- | --- |
|  | 4:00 – 4:15pm Schedule slippage – the issue at hand | Tracy |
|  | 4:15 – 4:40pm Wrapping up the Define Phase | Tracy |
|  | 4:40 – 5:10pm Moving ahead to the Design Phase | Team |
|  | 5:10 – 5:30pm Stepping through the schedule | Team |
|  | 5:30 – 5:45 Scoping Discussion | Team |
|  | 5:45 – 6:00pm Round Table | Team |

##### Discussion / Minutes:

| Topic 1. Schedule slippage – the issue at hand | Tracy |
| --- | --- |
| Document Detailed Requirements – slipping because original detailed requirements were not detailed enough and in the format expected by EDS Baseline start was 1/12/06, Baseline finish was the same day; 1/12/06. Actual start was 1/12/06; Actual Finish: 1/24/06 This gave us enough time to complete second-round changes to detailed requirements based on discussions from the detailed requirements review Obtain Customer Signoff on Detailed Requirements – slipping because the detailed requirements were not completed on schedule, and we were not able to wrap up the define phase on schedule Baseline start was 1/19/06, Baseline finish was the same day; 1/19/06 Actual start was 1/24/06; Proposed Actual finish: 1/26/06 Already sent out to Jen for approval with all changes from the review Requirements Traceability – need to update after detailed requirements are finalized Send out for informal review 1/28/06 Aim to get them signed off 1/31/06 |

| Topic 2. Wrapping up the Define Phase | Tracy |
| --- | --- |
| Define Phase Review \ Resolve Issues – slipping because the detailed requirements were not completed on schedule Baseline start was 1/12/06, Baseline finish was 1/19/06 Actual start was 1/12/06; Proposed Actual finish: 1/26/06 Scope must be estimated in terms of effort; the prioritization is used to make a final decision based on that Define and Document User Acceptance Test (UAT) Cases Start when detailed requirements are approved, proposed date: 1/26/06 General Schedule Changes/Information Development Environment Done – Monday Split Learning Environment into two tasks one for SourceSafe (so it can be sooner) and one for the overall environment Jen will now own the UAT’s so Elaine & Sandy’s primary role will be to review them; Tracy needs to email Jen and give her the timeframe for this task; use the Unit template but add confusion-free instructions so she knows what to do Add a separate task for the review of the UAT Test Cases Project schedule is IMPORTANT Validate estimate – next Thursday |

| Topic 3. Moving ahead to the Design Phase | Team |
| --- | --- |
| Beginning 1/26/06 (or when Define Phase is complete) Create Initial Context, System and Architecture Diagrams Document Business/Technical Design Business/Technical Design Phase Review/Resolve Issues Obtain Customer Signoff on Business/Technical Design Create data model design General Info/Schedule Changes Design phase complete by February 14th See schedule for further changes Unit test cases are created alongside the design document Review of Data Model added |

| Topic 4. Stepping through the schedule | Team |
| --- | --- |
| This part of the agenda reserved to go through the schedule task by task and evaluate dates and resources Deliverables for the next two weeks Jen is doing the UAT Test Cases Tracy is going to be working on finalizing the Business/Tech Design Template Elaine & Sandy working on Unit Test Cases Steve is working on setting up our development environment Then we’ll all be working on learning how to use it - Team Steve will start working on implementing a vertical slice of our application Data Model & Architecture Diagrams - Team Scope Estimate Completed |

| Topic 5. Scoping Discussion | Team |
| --- | --- |
| What is in scope? Out of scope? What do we need to address? |

| Topic 6. Round Table | Team |
| --- | --- |