# Meeting Agenda and Minutes

| Meeting Date: | 03/17/06 | Time: | 9:00 AM Eastern – 10:00 AM Eastern |
| --- | --- | --- | --- |
| Facilitator: | Tracy Rericha | Recorder: | Elaine Simone |
| Location: | Teleconference | Con Call: | (866) 811-0794 ; Passcode: 902629# |

|  | Name | Role |
| --- | --- | --- |
|  | Steve Coad | RIT – Technical Leader \ Developer |
|  | Sandra Morris | RIT – UI Coordinator \ Developer |
|  | Tracy Rericha | RIT – Project Manager \ Developer |
|  | Elaine Simone | RIT – Quality Assurance Manager \ Developer |
|  | Michelle Whalen | EDS – Project Manager SME and Mentor |
|  | John Manos | EDS – Technical Leader SME and Mentor |
|  | Jen Farmer | FARA – Customer |
|  | Steve Baiera | EDS |
|  | Bill Hartnett | EDS |
|  | Marty Ohman | EDS |
|  | Marianne Wilcox | EDS |
|  | Lei Wu | RIT – Faculty Advisor |

##### Agenda:

| Nbr | Topic | Responsible |
| --- | --- | --- |
|  | 9:00 – 9:05am Recent Review Participation | Tracy |
|  | 9:05 – 9:10am High Level Scope Review of Release 1.0 | Elaine |
|  | 9:10 - 9:15am Significant Changes in Requirements, Design, and Scope | Steve |
|  | 9:15 – 9:25am Review project milestones and project status | Tracy |
|  | 9:25 – 9:35am Review Schedule for Modules | Tracy |
|  | 9:35 – 9:45am Project Risks | Sandy |
|  | 9:45 – 9:50am Review Meeting Objective | Sandy |
|  | 9:50 – 9:55am EDS Steering Committee feedback | EDS Steering Committee |
|  | 9:55 – 10:00am Round Table | EDS/FARA/RIT Team |

##### Discussion / Minutes :

| Topic 1. Recent Review Participation | Tracy |
| --- | --- |
| Thank you for your participation, input, and ideas! Thanked EDS for help in reviewing and support |

| Topic 2. High Level Scope Review of Release 1.0 | Elaine |
| --- | --- |
| What is in and out of scope for the RIT team (Release 1.0) Reviewed Scope on a high level Must remember to point out each document that we’re going over (suggestion: put in document either document names and/or link to where they reside on the website) Scope was discussed at a more detailed level during the previous Steering Committee meeting |

| Topic 3. Significant Changes in Requirements, Design, and Scope | Steve |
| --- | --- |
| Any changes needed due to issues encountered during the creation and review of design, database, and unit test cases Web host has been determined Switched development to .net 2.0 technologies (Microsoft Visual Web developer 2005 Express, Microsoft SQL Server 2005 Express) Change in Registry Auto Maintenance, since there is no scheduler on the web host, this will be kicked off by manually by the Registry Coordinator role. Made changes to give Admin/Registry Coordinator ability to reset their own password, since the account information has been pushed off to future releases. |

| Topic 4. Review project milestones and project status | Tracy |
| --- | --- |
| Completed: Modularity Document signoff Design documented Database design documented Unit Test Cases documented Upcoming: End User Procedures System Test Cases User Acceptance Test Cases Module development Minor slippage trying to resolve some minor design issues, having to push back test case review, but still moving forward. Overlapping with development activities |

| Topic 5. Review Schedule for Modules | Tracy |
| --- | --- |
| Concerns / issues Agreement on this schedule Are these times good for reviewers? Marty will follow up with Tracy about timing Tracy will follow up with Steve Sullivan and Steve Baiera about timing Does this take into consideration new development environment/language? Scheduled Reviews are within time frame in baseline schedule Schedule is very tight, there is no room for slipping We are tightly monitoring progress to mitigate risk of unknown effort |

| Topic 6. Project Risks | Sandy |
| --- | --- |
| Risks encountered and how we are mitigating them Reviewed five highest risks, discussed mitigation strategies and contingency plans Inexperience with .Net tools Inadequate amount of time to complete the project Risk number wrong (multiplication error) John is concerned Should be conservative considering end of the quarter/graduation Contingency plan: work extra hours Should be moved to highest risk currently Development environment Issues with browser works in Internet Explorer, not as well in Firefox Progress tracking Scope Creep Michelle / Marianne like our template for Risk Management |

| Topic 7. Review Meeting Objective | Sandy |
| --- | --- |
| Give information on current status, and future direction, open for feedback Reviewed what we discussed today |

| Topic 8. EDS Steering Committee Feedback | EDS Steering Committee |
| --- | --- |
| Concerns / Feedback? Marianne: if we trigger contingency plans (reducing scope because of time) make sure to discuss with board before Jennifer. We all agree there is really little that can be removed to deliver a complete product. Marty: Which document for Review Schedule? Add version number in file name Next Steering Meeting: April 7, 2006 9:00-10:00 |

| Topic 9. Round Table | EDS/FARA/RIT Team |
| --- | --- |
| Michelle: regarding handoff of project, detailed what was needed to participate. Have found seven volunteers. Need to work with them to determine who will participate. Then team will have to schedule dates meeting with participants for a smooth hand off of project details. |