# Meeting Agenda and Minutes

| Meeting Date: | 01/24/06 | Time: | 4:30 PM Eastern – 5:30 PM Eastern |
| --- | --- | --- | --- |
| Host: | Tracy Rericha | Recorder: | Sandy Morris |
| Location: | Teleconference | Con Call: | (866) 811-0794 ; Passcode: 902629# |

|  | Name | Role |
| --- | --- | --- |
|  | Steve Coad | RIT – Technical Leader / Developer |
|  | Jen Farmer | FARA – Customer |
|  | John Manos | EDS – Technical Leader SME and Mentor |
|  | Sandra Morris | RIT – UI Coordinator / Developer |
|  | Tracy Rericha | RIT – Project Manager / Developer |
|  | Elaine Simone | RIT – Quality Assurance Manager / Developer |
|  | Michelle Whalen | EDS – Project Manager SME and Mentor |

##### Agenda:

| Nbr | Topic | Responsible |
| --- | --- | --- |
|  | - Review Action Items and Issues | - Tracy |
|  | - Review Project Risks | - Sandy |
|  | - Weekly Status | - Tracy |
|  | - Project Schedule / Upcoming Milestones | - Tracy |
|  | - Special Topics | - Team |
|  | - Round Table | - Team |

##### Discussion / Minutes:

| Topic 1. Review Action Items and Issues | Tracy |
| --- | --- |
| Action Items List Updates: Items due today: - Send John example of how we'll be representing the data model for Steering Committee to look at - Completed by Steve ASAP items: - Discuss with Michelle what strategies to take on schedule slippage due to detailed reqs - Michelle & John want to get together with Tracy to discuss the schedule slippage and reworking it to fit the current needs at some point this week Coming up: - Update Requirements Traceability doc – after detailed reqs complete - Moved to be sent out on Saturday the 28th after the detailed requirements are signed off on Thursday the 26th - Traceability Matrix is signed off on Tuesday the 31st and completed by Thursday the 2nd - Look into XML configuration files – Tech design - Eventually this will be back filled with the end date minus a few days for the Tech Design phase - John provide information answering Marianne's flow / capacity questions – Tech design - Michelle thinks John sent it out & she will check with him - Resources who will be taking over the system (turning over deliverables) – not until 2/7/06 - Not finished Note: - Still waiting on Jen to complete her action items - Provide the links to us by the date listed - ok - Homepage description - ok - Wording for HIPAA – she will need more time - Key search words for the search engines - ok - Research what Crystal Reports in .NET can do for reporting and exporting to PDF – has already begun - Sandy has begun doing research into it and it can be done we are just unsure on the effort it will take - This item is closed since the research has been done as the action item stated |  |

| Topic 2. Review Project Risks | Sandy |
| --- | --- |
| Project Risks |  |

| Topic 3. Weekly Status | Tracy |
| --- | --- |
| Team Issues/Concerns |  |

| Topic 4. Project Schedule \ Upcoming Milestones | Tracy |
| --- | --- |
| Project Schedule: - Completed detailed reqs – due today, 1/24/06 - Sent out today on schedule - Completed define phase review – 1/24/06 - Scope must be estimated at a high level in terms of effort - The prioritization is used to make a final decision based on that - So for example ‘How many hours would it take for one person to complete this requirement to measure effort?’ - Then add in the variable of 4 people….500 hours/4 people = duration - If we have a question about the rating ask Jen about it - The rest of the discussion on these project schedule \ upcoming milestones will be addressed in the schedule meeting with Tracy & Michelle & John - Signed off/approved detailed reqs – Thursday 1/27/06 - Begin documenting UAT cases – Thursday 1/27/06 - Begin creating Initial Context, System and Architecture Diagrams – Thursday 1/27/06 - Begin documenting Technical Design – Thursday 1/27/06 - Set up/learn/teach development environment – continue as we are - Getting a repository up for documents this week is important |  |

| Topic 5. Special Topics | Team |
| --- | --- |
| Review of Docs: A. Project Schedule - Risk Management Plan Development Environment Status from Steve – he is still working on it. |  |

| Topic 6. Round Table | Team |
| --- | --- |