# Meeting Agenda and Minutes

| Meeting Date: | 02/20/06 | Time: | 4:30 PM Eastern – 5:30 PM Eastern |
| --- | --- | --- | --- |
| Host: | Tracy Rericha | Recorder: | Sandy Morris |
| Location: | Teleconference | Con Call: | (866) 811-0794 ; Passcode: 902629# |

|  | Name | Role |
| --- | --- | --- |
|  | Jen Farmer | FARA – Customer |
|  | John Manos | EDS – Technical Leader SME and Mentor |
|  | Michelle Whalen | EDS – Project Manager SME and Mentor |
|  | Sandra Morris | RIT – UI Coordinator / Developer |
|  | Tracy Rericha | RIT – Project Manager / Developer |
|  | Steve Coad | RIT – Technical Leader / Developer |
|  | Elaine Simone | RIT – Quality Assurance Manager / Developer |
|  | Lei Wu | RIT – Faculty Advisor |

##### Agenda:

| Nbr | Topic | Responsible |
| --- | --- | --- |
|  | - Review Action Items and Issues | - Tracy |
|  | - Weekly Status | - RIT Team |
|  | - Project Schedule / Upcoming Milestones | - Tracy |
|  | - Roles and Responsibilities Review | - Michelle |
|  | - Workload Review | - Michelle |
|  | - Special Topics | - Team |
|  | - Round Table | - Team |

##### Discussion / Minutes:

| Topic 1. Review Action Items and Issues | Tracy |
| --- | --- |
| Action Items List Updates: Open: - Provide language for the HIPAA statement – by 2/10/06; Jen - Resources who will be taking over the system (turning over deliverables) – by 2/28/06; Michelle These are still open items and Michelle & Jen are still working on them. John still needs to meet tomorrow with the people at EDS to get a decision on the ready hosting so the date will be moved from today to two weeks from today. |  |

| Topic 2. Weekly Status | RIT Team |
| --- | --- |
| Team Issues/Concerns Let’s break up the overall reviewing of documents so its not just delegated to one person. |  |

| Topic 3. Project Schedule \ Upcoming Milestones | Tracy |
| --- | --- |
| Project Schedule: - Learn development environment Learn development environment refers to ready host decision and the date has changed to 2 weeks from today. This task will also be moved to the ‘Design’ Phase instead of being listed under the ‘Define’ Phase. - Unit Test Case Review Unit Test Case Review is looking like it will be late Friday evening. Mandatory participants are Jen, Elaine, Sandy, Professor Wu, and one of the EDS mentors (either Michelle or John). - Re-review of Design and Unit Test Case documents; signoff Send out the new version incorporating the feedback from the review via email on Wednesday. - Design Phase Review The two reviews of Unit Test Case & Design Doc will make up the Design Phase Review. - Interim evaluations - Due this week by Friday the 24th to Professor Wu Professor Wu needs them still from Jen & Michelle. - Interim presentation for RIT - When: Thursday, February 23rd; 6:25pm - Where: GCCIS (Building 70) Auditorium - Who: RIT Team. Sponsors are encouraged to attend, but not required. Michelle & John & some of the steering committee members will be in attendance. Split up the sign off for Design & Unit Test Cases on the project schedule. Professor Wu will require a physical signature on the documents to have them considered officially approved. We will be asking Jen about what her expectations are for End User Procedures, which is currently an item on the schedule. We want the expectations from the perspective of the registry coordinator and the administrator possibly in scenario or procedure format. The RIT team should start producing the modules they are responsible for as soon as possible. |  |

| Topic 4. Roles and Responsibilities Review | Michelle |
| --- | --- |
| - Roles and Responsibilities document Technical Lead Role Comments - We need to make sure that everyone has a development environment that they can use whether that be a remote one on a personal desk top or a personal development environment on a laptop - We need to make sure we follow coding standards - We need to put together an implementation plan at the close of this phase Quality Assurance Manager Role Comments - We need to make sure that this is done in any downtime that is not taken up by development activities |  |

| Topic 5. Workload Review | Michelle |
| --- | --- |
| - Modularity document - Schedule Developers and Modules Assigned - Developer 1 – Steve (Modules 1, 3, 6) - Developer 2 – Sandy (Modules 2, 9) - Developer 3 – Tracy (Modules 5, 8) - Developer 4 – Elaine (Modules 7, 10) The latest Modularity document will be updated on the website later today. The modules will be added into the schedule so we can track it along with everything else. We need to add the target dates to the Modularity Document as soon as possible. We have 6 weeks after we come back from break to complete the Produce Phase (not just code). We also need to finalize a date for the UI Review with Jen. We need to think about how to have multiple reviews for the produce phase. - Review each module as it is completed. - Adding 1 or 2 additional reviews. |  |

| Topic 6. Special Topics | Team |
| --- | --- |
| - .NET Training – first week back at classes; discuss meeting during business hours or after work during weekdays We will need to talk to John about this in the future. |  |

| Topic 7. Round Table | Team |
| --- | --- |
| Add review of risks to list for the next status meeting. |  |