# Meeting Agenda and Minutes

| Meeting Date: | 03/20/06 | Time: | 4:30 PM Eastern – 5:30 PM Eastern |
| --- | --- | --- | --- |
| Host: | Tracy Rericha | Recorder: | Elaine Simone |
| Location: | Teleconference | Con Call: | (866) 811-0794 ; Passcode: 902629# |

|  | Name | Role |
| --- | --- | --- |
|  | Jen Farmer | FARA – Customer |
|  | John Manos | EDS – Technical Leader SME and Mentor |
|  | Michelle Whalen | EDS – Project Manager SME and Mentor |
|  | Sandra Morris | RIT – UI Coordinator / Developer |
|  | Tracy Rericha | RIT – Project Manager / Developer |
|  | Steve Coad | RIT – Technical Leader / Developer |
|  | Elaine Simone | RIT – Quality Assurance Manager / Developer |
|  | Lei Wu | RIT – Faculty Advisor |

##### Agenda:

| Nbr | Topic | Responsible |
| --- | --- | --- |
|  | Module Discussion | Steve |
|  | Weekly Status | Tracy |
|  | Action Items / Upcoming Project Schedule Items | Tracy |
|  | Project Risks Review | Sandy |
|  | Round Table | Team |

##### Discussion / Minutes:

| Topic 1. Module Discussion | Steve |
| --- | --- |
| Modularity Document Database Has some data Scripts made Working on lookup tables Working on stored procedures As of 3/17 (50%) now (70%) tonight 100%? Data Entry View 60% UI Pages 25% Help Requirements 90% Concerned about effort for the code behind the pages. Will verify progress for Thursday report and discuss at meeting Monday next week. Just starting this part of the component now. Data Entry Logic Just notes on changes to how the approval will work with the new scheme for Informed Consent Acceptance Needs to coordinate a good time with Module 3 developer to proceed with adding validators Patient Update Front end of pages created / complete 40% Rest of the work centers around pulling information from the database Patient Review (45-50%) Front end of pages created / complete Again, rest of the work centers around pulling information from the database Admin Functionality Has not been scheduled to start yet Querying Pages complete Steve will help with providing what is needed from the database module as we move forward Registry Auto-Maitanence Has not been scheduled to start yet Static Site Content Nearly 100% complete, because of the User Interface demo Notes on document Status should be put into the Module headings to summarize (Steve) what is in the individual requirements (Team) Adopt Sandy’s Style of update, Percent Complete then high level of accomplishment. Also include high level percent complete in module update Send out with version appended into filename (date) |

| Topic 2. Weekly Status | Tracy |
| --- | --- |
| Team Issues/Concerns Requirements Traceability document Is there value in continuing this considering our document / development strategy? Show how it traces to each module Then show how requirements those are not in design (scope document?) Consolidate Reporting to cut down overhead Michelle still needs to read through email and will get back to Tracy Design question for Jen Should the Admin password reset be a free text box, or a drop down (this is preffered because there is a better control of data. Jen has no preference. |

| Topic 3. Action Items / Upcoming Project Schedule Items | Tracy |
| --- | --- |
| Action Items: Language for HIPAA statement – Jen, ASAP Copy Paste, can wait until the 30th, but should have sooner Resources for delivering system – Michelle, 3/31/06 10 volunteers, (thought 2 developers, .25 dba). Will go with 4 developers. Perhaps a rotation basis. Once people are decided Michelle will talk with Tracy about setting up meetings for handoff in May. May invite them to listen in to reviews clinical.disability field that states what this range will be – Jen, ASAP We think we have this. Closed How to proceed with HIPAA - present screen each time user logs in, and update that timestamp in the database – RIT Team, end of Produce (4/28/06) Address during the produce phase in the appropriate modules Tool tips are blinking in some people's browsers and not in others - need to fix this issue during development of tool tips/help – RIT Team, end of Produce (4/28/06) Address during the produce phase in the appropriate modules The wrapping text issue that Michelle experienced / sent out an email about also Project Schedule: Design – have we signed off? John gives overall approval. Silence from other reviewers considered approval Professor Wu has received the sign off for design (minus Michelle, looking for Fax machine) Needs to be sent to Jen now that approval has been received from EdS Unit Test Cases signoff – by today Today received input from Jen Still need to receive review from Michelle (Tonight / Tomorrow Morning) End User Procedures System Test Cases Denial of Service Attacks, Security Concerns UAT Cases Need to start thinking of identifying additional testers (patients, future RCs) Module development |

| Topic 4. Project Risks Review | Sandy |
| --- | --- |
| Project Risks Incorporated feedback from the Steering meeting Moved up Morale Moved down Inclement Weather Will be on the website this evening? / Tomorrow |

| Topic 5. Round Table | Team |
| --- | --- |
| End Users Procedures Elaine will set up a meeting with Michelle to discuss procedures Then Elaine will meet with Jen to discuss how to proceed / work together / put forth a time frame. Remember to update Unit Test Cases as test cases are being performed April 10th Status Meeting: meeting at EdS to Meet the girls during that meeting Michelle will be out next week (not in any meetings) Need to set time for the database review meeting? Need to set time for the webhosting setup meeting? When do we want additional information from Jen (information from User Interface meeting) Would like this as soon as possible. Shooting for the 27th or sooner. Need to put issues from UI review into phase review document to track fixing effort. |