# Meeting Agenda and Minutes

| Meeting Date: | 04/03/06 | Time: | 12:00 PM Eastern – 1:00 PM Eastern |
| --- | --- | --- | --- |
| Host: | Tracy Rericha | Recorder: | Elaine Simone |
| Location: | Teleconference | Con Call: | (866) 811-0794 ; Passcode: 902629# |

|  | Name | Role |
| --- | --- | --- |
|  | Jen Farmer | FARA – Customer |
|  | John Manos | EDS – Technical Leader SME and Mentor |
|  | Michelle Whalen | EDS – Project Manager SME and Mentor |
|  | Sandra Morris | RIT – UI Coordinator / Developer |
|  | Tracy Rericha | RIT – Project Manager / Developer |
|  | Steve Coad | RIT – Technical Leader / Developer |
|  | Elaine Simone | RIT – Quality Assurance Manager / Developer |
|  | Lei Wu | RIT – Faculty Advisor |

##### Agenda:

| Nbr | Topic | Responsible |
| --- | --- | --- |
|  | - Module Discussion | - Tracy |
|  | - Weekly Status | - Tracy |
|  | - Action Items / Upcoming Project Schedule Items | - Tracy |
|  | - Round Table | - Team |

##### Discussion / Minutes:

| Topic 1. Module Discussion | Tracy |
| --- | --- |
| - Modularity Document - Module 1: database - Implemented in Model Office - Updates during development - Altered two Stored Procedures - Made more stored procedures - Can use something to drop tables - Steve will double check this - Module 2: authentication - As of Thursday, not started - Can merge work with admin functionality - Need to update new finish date - This is ok because of reviews being pushed back - Module 3: data entry view - Now 95% complete. - Single bug: Issue with data time object in Consent Error - Module 4: data entry logic - Same thing as module 3 - Module 5: patient update - Overlap with module 3, and database stuff - Aiming for completion for the end of the week - Need to later integrate the new requirements from User Acceptance Test Review - Discuss with Michelle Process - Discuss amendment to Tech design - Make change in requirements and module document? - Module 6: patient review - 75% Complete - Need database components - Module 7: Admin Functionality - Work has not yet been scheduled to start - Combination of work effort with Module 2 Login - 25% Complete - Module 8: Querying - Exporting now working in prototype - Transitioning to our database - Exploring other options for printing - Hitting print button will create new page with only - All records - Query Criteria - Module 9: Registry Auto maintenance - Not yet scheduled to start - Research on Sending emails in C# - Some stored procedures - Module 10: Static Site Content - 100% - Ahead of Schedule |  |

| Topic 2. Weekly Status | Tracy |
| --- | --- |
| Team Issues/Concerns Steve: doing all the database work / stored procedures is taking more effort then estimated, concerned that other work is not getting time to be addressed. There were some snags in the database Supporting other team members has been good Some slippage, but justified Review of Module 2 has been pushed back also helps Steve thinks module 2 and 7 will be complete by this weekend Elaine: Working with Steve to learn stored procedures so can work on specific stuff for querying Will look at examples, then arrange time to discuss with Steve any further questions Tracy: Concern about delay in patient update module, because waiting for Module 3’s material, which was waiting for Module 1’s material. Because of Aggressive Schedule, expected slippage, we’re still doing good General: Need to schedule a better time for holding status meetings (12-1 time slot does not work for all RIT group members who need to attend). Revert back to 4:30 schedule But what about module review? RIT events (April 5th (wed), not April 24th(mon)) Status Meeting next week April 10 4:00-4:30 Module 2/3/4 review Monday April 10 4:30-7:30 Steering Committee Meeting April 19 4:30-5:30 |  |

| Topic 3. Action Items / Upcoming Project Schedule Items | Tracy |
| --- | --- |
| - Action Item List Wording for Informed Consent Received no changes from one lawyer Will consider “done” Will make sure Sandy has the updated copy Project Schedule: - Unit Test Cases - have we signed off? - Baselined - End User Procedures - Elaine will email Michelle about available times in the next two days - UAT Cases - Review went well - Jen has sent response - Need to review - System Test Cases - Ongoing Module development |  |

| Topic 4. Round Table | Team |
| --- | --- |
| Jen is concerned that discussion of new requirements from the Review Meeting Issues were captured in an email and will be integrated into documents Face to Face for Steering Meeting so we can meet our inspiration Perform pre-integration testing on the system as modules begin to be completed. |  |