## Sheet1
Task name | Iteration | Priority | Description
Cart Display | R2 | 0 | Moving cart to the fly-out, and display of all items in the cart
Cart Add/Remove/Edit | R2 | 0 | Removal of an item, Editing an existing item, Adding an item
R1 Reworks | R2 | 0 | Remaking Order page variants for usability testing, + adding missed items
Cancel Order | R2 | 0 | Cancelling a session
Send and Receive Response | R2 | 0 | Sending a request from the kiosk to the server and receive a response
Create system admin UI | R2 | 1 | Create an initial mockup of the system administration interface (for viewing reports, changing item prices, etc.)
Parse JSON from server into objects | R2 | 0 | Take the JSON strings returned from requests sent to the server and parse them into objects of the appropriate type
Implement Splash Screen | R2 | 1 | Load splash screen data from the server and display a splash screen after a given period of inactivity
Item Catalog Search | R2 | 1 | Allow customers to search through the current item catalog
Admin Login | R2 | 1 | Implement the functionality to allow and administrative user to log into the system
Unit test kiosk code base | R2 | 1 | Create unit tests for all classes
R1 Testing Re-works | R2 | 1 | Implement the testing framework for RESTFULL Services and create unit tests for deli heiarchy and printing subystem. Not started yet but good idea what to do
Format Printer Order | R2 | 0 | Create and flesh out printing subsystem to allow for modular creation of different ZPL commands. Create structure that makes it easy to add and remove new commands, but enforce good practices and standards
Configure Printer | R2 | 0 | On the server, user will be able to add new printers to the system so that printing orders will be handled
R2 Bug Fixes | R2 | 0 | Fix the JSON response type of the REST service to remove extra quotes and return a valid json object that can be correctly read and manipulated with the browser, and not just the program
Testing communication with the client | R2 | 0 | To ensure that communication is working correctly, we have set aside time to test and debug this setup.
Setup Communication to Client | R2 | 0 | The server must have REST web services setup that the client can access. This basic layout or flow of execution will be used for all of the web services on the server side.
Handle Load Item Catalog Request | R2 | 0 | On the server, the customer kiosk will send a request when ever a new order is started in order to check if the item catalog has been modified. If it has been modified, then the server will respond with the new item catalog.
Complete Order | R2 | 0 | On the server, we must handle a complete order server request. This will consist of the server receiving a web service request, extracting the parameters, and servicing the request of processing an order and saving the details in the database.
View Order Detals | R2 | 1 | On the server. A deli kiosk can send a request to view a detailed view of an order. This will happen via a web service request that is recieved on the server side and the appropriate data will be retrieved from the database and sent back to the client.
View Order | R2 | 1 | On the server. A deli kiosk will be constantly sending requests to view the most up to date orders. This will funtion as a web service request, where the server will retrieve all relevant data from the database and send it back to the client.
Order Logging | R2 | 0 | On the server, this ties into the complete order web service. When an order is completed, the information must be sent to the deli kiosk, so that the deli workers know that there is a new order and additionally, the server will print the initial receipt.
Usability Testing | R2 | 1 | For this iteration, we want to begin performing usability tests for the customer kiosk. If time permits, we would also like to begin testing the employee and manager interfaces. This will require us to create usability test scripts and to set aside time to meet with test subjects to perform these tests.
Browse Promotions (Kiosk) | R3 | 2 | The ability to browse promotions from the deli kiosk
Manager Authentication | R3 | 1 | Authenticating manager credentials on the server from a currently unknown (probably mocked) source
Manager Browse Items | R3 | 1 | Browse items as a manager with elevated rights
Manager Search for Items | R3 | 1 | Search items as a manager with elevated rights
Manual Receipt Printing | R3 | 1 | Manually print a receipt for an order from behind deli
Edit Splash Screens (Manager UI) | R3 | 3 | Manager manually editing splash screens
Manager Change Price (Server) | R3 | 1 | Ability to change a product's price on the server
Manager Mark Product In/Out Stock (Server) | R3 | 0 | Ability to mark a product in/out of stock on the server
Manager Mark Product In/Out Stock (Kiosk) | R4 | 0 | Manager marking products in/out of stock at the Kiosk
Splash Screen Sequencing On Server | R3 | 3 | Change splash screen sequencing on server
Update Item Catalog on Kiosk | R3 | 0 | Update the item catalog on the kiosk (includes out of stock, etc)
View System Report(Server) | R4 | 1 | View the system report (TBD)
View Kiosk Report(Server) | R4 | 1 | View the Kiosk report (sales etc)
View Daily Report(Server) | R4 | 1 | View the Daily report (daily kiosk report)
Employee Tracking on Server | R4 | 2 | Implement anonymous order tracking on server
Employee Tracking on Kiosk | R4 | 2 | Implement anonymous order trackong on Kiosk
Manger change price (Kiosk) | R4 | 2 | Manager change price of items from kiosk
View System Report(Kiosk) | R4 | 3 | Viewing system report from the kiosk
View Kiosk Report(Kiosk) | R4 | 2 | Viewing kiosk report(s) from the kiosk
View Daily Report(Kiosk) | R4 | 2 | Viewing daily report from the kiosk
Send Reports (Server) | R4 | 1 | Send reports to outside location from server
Add/Remove/Update Product Promotion (Server) | R4 | 2 | Add/Remove/Update the list of promoted products on the server.
Barcode Employee Order Tracking | STRETCH
Employee ID Order Tracking | STRETCH
Shoppers Club Collecting ID of User | STRETCH
Shoppers Club Reccomendations | STRETCH
Fancier Splash Screens | STRETCH
Text Notification when order finished (Req. Employee Tracking) | STRETCH
Email Notification when order finished (Req. Employee Tracking) | STRETCH
Order time estimation (Req. Employee Tracking) | STRETCH
QR Codes on Printer | STRETCH
Adds on printer | STRETCH