## Team
Fall Semester
| Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Total
Jared | 4.5 | 12.5 | 11 | 10 | 9.5 | 12 | 10 | 8.25 | 11.25 | 9 | 5 | 11.5 | 11.25 | 7.25 | 9.5 | 10 | 152.5
Dan | 5.5 | 3.5 | 8 | 7.5 | 11 | 9.5 | 6 | 6.5 | 10.5 | 13.5 | 12.5 | 10.5 | 8.5 | 11 | 12.5 | 0 | 136.5
Tim | 4 | 5 | 4 | 7 | 10.25 | 6.25 | 8.5 | 0.75 | 8.3 | 10.25 | 4.95 | 12.6 | 9.25 | 4.25 | 11.2 | 0 | 106.55
Warren | 2 | 6.5 | 4.1 | 8.5 | 8 | 5.5 | 7 | 10 | 13.5 | 8.5 | 10 | 10.5 | 20 | 0 | 16 | 7.5 | 137.6
Fall Team Total | 16 | 27.5 | 27.1 | 33 | 38.75 | 33.25 | 31.5 | 25.5 | 43.55 | 41.25 | 32.45 | 45.1 | 49 | 22.5 | 49.2 | 17.5 | 533.15
Spring Semester
| Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Break Week | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Total
Jared | 13.5 | 13.5 | 11 | 10.5 | 9 | 5.75 | 8.25 | 9 | 26.5 | 16 | 12.25 | 14.75 | 21.5 | 13 | 8 | 0 | 192.5
Dan | 12 | 10 | 11.5 | 13.5 | 7 | 21 | 15.5 | 12.5 | 0 | 14 | 28.5 | 17 | 17.5 | 15 | 0 | 0 | 195
Tim | 3.5 | 8.5 | 4.65 | 2.75 | 12 | 10.5 | 4.5 | 4.25 | 2.75 | 7 | 3 | 7.25 | 2 | 4 | 4.25 | 0 | 80.9
Warren | 14.5 | 14.5 | 3 | 15 | 3.5 | 6.5 | 21 | 4 | 4 | 14.5 | 5.5 | 8.5 | 17.5 | 27.5 | 0 | 0 | 159.5
Spring Team Total | 43.5 | 46.5 | 30.15 | 41.75 | 31.5 | 43.75 | 49.25 | 29.75 | 33.25 | 51.5 | 49.25 | 47.5 | 58.5 | 59.5 | 12.25 | 0 | 627.9

## Jared 1st Term
Week 1 | [5 empty] | Week 2 | [5 empty] | Week 3 |  |  |  |  | Week 4 |  |  |  | Week 5 |  |  |  | Week 6 |  |  |  | Week 7 |  |  |  | Week 8 |  |  |  | Week 9 |  |  |  | Week 10 |  |  |  | Week 11 |  |  |  | Week 12 |  |  |  | Week 13 |  |  |  | Week 14 |  |  |  | Week 15 |  |  |  | Week 16
Finished ? | Estimate | Hours Logged | Activity |  |  | Finished ? | Estimate | Hours Logged | Activity |  |  | Finished ? | Estimate | Hours Logged | Activity |  | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity
Y |  | 2.5 | Attended Team Meetings |  |  | Y | 5 | 5 | Create Project Website |  |  | Y | 2 | 2 | Work through initial plans for project |  | Y | 1.5 | 1.5 | Finalize Process Methodology | Y | 1 | 1 | Update Time Tracker and Project Website | Y | 1 | 1 | Update Time Tracker and Project Website | Y | 1.5 | 1 | Update Time Tracker, Project Website, and Project Metrics | Y | 1.5 | 1 | Update Time Tracker, Project Website, and Project Metrics | Y | 1.25 | 1.25 | Team Meeting | Y | 2.5 | 2.5 | Team Meetings | Y | 2.5 | 2.5 | Team Meetings | Y | 2.5 | 2.5 | Team Meetings | Y | 1.25 | 2.5 | Team Meetings | Y | 1.25 | 1.25 | Team Meeting | Y | 2.5 | 2.5 | Team Meetings | Y | 2.5 | 2.5 | Team Meetings
Y |  | 2 | Worked on initial questions for initial sponsor meeting. |  |  | Y | 1.25 | 1.25 | Attend Team Meetings |  |  | Y | 1 | 1 | Refine results from sponsor meeting |  | N | 1.5 | 0 | Finalize Project Plan | Y | 2.5 | 2.5 | Team Meetings | Y | 2.5 | 2.5 | Team Meetings | Y | 2.5 | 2.5 | Team Meetings | Y | 2.5 | 1.25 | Team Meetings | Y | 1 | 1 | Update Time Tracker, Project Website, and Project Metrics | Y | 1.5 | 1.5 | Architectural Review | Y | 1 | 1 | Update Time Tracking, Metrics, and Team Website | Y | 1 | 0.5 | Update Time Tracking, Metrics, and Team Website | Y | 1 | 1 | Update Time Tracking, Metrics, and Team Website | Y | 0.5 | 1 | Update Time Tracking, Metrics, and Team Website | Y | 1 | 0.5 | Update Time Tracking, Metrics, and Team Website | N | 0.5 | 0 | Update Time Tracking, Metrics, and Team Website
[6 empty] | Y | 1.25 | 1.25 | Attend Sponsor Meeting |  |  | Y | 0.5 | 0.5 | Finish Agenda for sponsor meeting |  | Y | 2.5 | 2.5 | Team Meetings | Y | 1.5 | 0 | Finalize Project Plan | N | 4 | 1 | Work on Functional Requirements | Y | 2 | 2 | Refine Functional Requirements | N | 8 | 6 | Work on Architectural Design | N | 4 | 6 | Work on Subsystem Design | Y | 4 | 2 | Finish Subsystem Design | Y | 3 | 0 | Finish additional sequence diagrams | Y | 2.5 | 1.5 | Get Server Environment setup on local machine | N | 3 | 2 | Finish setting up Restful Services | N | 8 | 5 | Continue Working on Server System | N | 8 | 4 | Continue Working on Server System | Y | 4 | 5 | Complete remaining work for 1st iteration
[6 empty] | N | 1 | 0 | Refine Results from Sponsor Meeting |  |  | Y | 1.5 | 1.5 | Team Meetings |  | Y | 1 | 0.5 | Update Time Tracker and Project Website | Y | 2 | 3 | Refine Functional Requirements from customer | N | 1.5 | 0 | Refine Customer Requirements | N | 4 | 2 | Work on System and Application Architecture |  |  |  |  | Y | 2 | 2 | Work on System Overview Design | N | 2 | 2 | Create additional sequence diagrams | N | 2 | 1.5 | Get Server environment setup on local machine | N | 5 | 7 | Begin working on server system | Y | 3 | 2.5 | Finish setting up NHibernate |  |  |  |  | Y | 2 | 1 | Work on Interim Presentation | Y | 1 | 0.5 | Complete Peer Evals
[6 empty] | N | 1 | 0 | Work Through initial plans for project |  |  | Y | 1 | 1 | Update Time Tracker and Project Website |  | Y | 1 | 0.5 | Specify Project, Process, and Individual Metrics to track | Y | 2 | 2 | Learn new technologies for application (iOS) | Y | 2 | 2 | Work on Admin Use Cases and Wireframes | Y | 2.5 | 2.5 | Learn iOS |  |  |  |  | Y | 1.5 | 1 | Work on Deployment Diagram | Y | 1.5 | 1 | Finish Architectural Presentation and practice | N | 3 | 0 | Skeleton server and client system |  |  |  |  | N | 3 | 5 | Continue work on server system |  |  |  |  | N | 3 | 1.5 | Work on Interim Evaluation | Y | 2 | 2 | Finish Interim Evaluation
[6 empty] | Y | 1.5 | 1.5 | Work on adding Time Tracker to Google Docs |  |  | Y | 1.5 | 1 | Complete Project Synopsis and Survey |  | N | 2 | 0.5 | Setup VM with necessary applications | N | 1.5 | 0 | Setup VM with necessary applications | N | 2 | 3 | Work on Use-Case Document
[6 empty] | Y | 0.5 | 0.5 | Update individual Time Tracker |  |  | Y | 3 | 2 | Complete First Draft of Process Methodology and Project Plan |  | Y | 2 | 2 | Learn new technologies for application (iOS) | N | 2 | 1 | Work on Functional Requirements for administration section of application | Y | 1 | 1 | Work on Team Metrics
[6 empty] | Y | 2 | 2 | Research process methodologies for project |  |  | Y | 1 | 1 | Finalize Technology choices for project |  | Y | 1.5 | 1.5 | Setup Metrics spreadsheet |  |  |  |  | Y | 1 | 1.5 | Refine Project Plan
[6 empty] | Y | 1 | 1 | Research technologies for project |  |  | N | 3 | 0 | Proof of concept of Technology choice. |  | Y | 1 | 1 | Work on Customer Questions for Functional Requirements Discussion
Totals |  | 4.5 |  |  |  | Totals | 14.5 | 12.5 |  |  |  | Totals | 14.5 | 10 |  |  | Totals | 14 | 10 |  | Totals | 12.5 | 9.5 |  | Totals | 15 | 12 |  | Totals | 12.5 | 10 |  | Totals | 12 | 8.25 |  | Totals | 9.75 | 11.25 |  | Totals | 11.5 | 9 |  | Totals | 11.5 | 5 |  | Totals | 11 | 11.5 |  | Totals | 11.25 | 13 |  | Totals | 9.75 | 7.25 |  | Totals | 16.5 | 9.5 |  | Totals | 10 | 10
Week 2 Estimates | [5 empty] | Week 3 Estimates | [5 empty] | Week 4 Estimates |  |  |  |  | Week 5 Estimates |  |  |  | Week 6 Estimates |  |  |  | Week 7 Estimates |  |  |  | Week 8 Estimates |  |  |  | Week 9 Estimates |  |  |  | Week 10 Estimates |  |  |  | Week 11 Estimates |  |  |  | Week 12 Estimates |  |  |  | Week 13 Estimates |  |  |  | Week 14 Estimates |  |  |  | Week 15 Estimates |  |  |  | Week 16 Estimates
Estimated Time |  | Activity |  |  |  | Estimated Time |  | Activity |  |  |  | Estimated Time |  | Activity |  |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity
5 |  | Create Project Website |  |  |  | 2 |  | Work through initial plans for project |  |  |  | 1.5 |  | Finalize Process Methodology |  |  | 1 |  | Update Time Tracker and Project Website |  | 1 |  | Update Time Tracker and Project Website |  | 1.5 |  | Update Time Tracker, Project Website, and Project Metrics |  | 1.5 |  | Update Time Tracker, Project Website, and Project Metrics |  | 1.25 |  | Team Meeting |  | 2.5 |  | Team Meetings |  | 2.5 |  | Team Meetings |  | 2.5 |  | Team Meetings |  | 2.5 |  | Team Meetings |  | 1.25 |  | Team Meeting |  | 2.5 |  | Team Meetings |  | 2.5 |  | Team Meetings
1.25 |  | Attend Team Meetings |  |  |  | 1 |  | Refine results from sponsor meeting |  |  |  | 1.5 |  | Finalize Project Plan |  |  | 2.5 |  | Team Meetings |  | 2.5 |  | Team Meetings |  | 2.5 |  | Team Meetings |  | 2.5 |  | Team Meetings |  | 1 |  | Update Time Tracker, Project Website, and Project Metrics |  | 1.5 |  | Architectural Review |  | 1 |  | Update Time Tracking, Metrics, and Team Website |  | 1 |  | Update Time Tracking, Metrics, and Team Website |  | 1 |  | Update Time Tracking, Metrics, and Team Website |  | 0.5 |  | Update Time Tracking, Metrics, and Team Website |  | 1 |  | Update Time Tracking, Metrics, and Team Website |  | 0.5 |  | Update Time Tracking, Metrics, and Team Website
1.25 |  | Attend Sponsor Meeting |  |  |  | 0.5 |  | Finish Agenda for Sponsor Meeting |  |  |  | 2.5 |  | Team Meetings |  |  | 1.5 |  | Finalize Project Plan |  | 4 |  | Work on Functional Requirements |  | 2 |  | Refine Functional Requirements |  | 8 |  | Work on Architectural Design |  | 4 |  | Work on Subsystem Design |  | 4 |  | Finish Subsystem Design |  | 3 |  | Finish additional sequence diagrams |  | 2.5 |  | Get Server Environment setup on local machine |  | 2 |  | Finish setting up Restful Services |  | 8 |  | Continue Working on Server System |  | 8 |  | Continue Working on Server System |  | 4 |  | Complete remaining work for 1st iteration
1 |  | Refine Results from Sponsor Meeting |  |  |  | 1.5 |  | Team Meetings |  |  |  | 1 |  | Update Time Tracker and Project Website |  |  | 2 |  | Refine Functional Requirements from customer |  | 1.5 |  | Refine Customer Requirements |  | 4 |  | Work on System and Application Architecture | [5 empty] | 2 |  | Work on System Overview Design |  | 2 |  | Create additional sequence diagrams |  | 2 |  | Get Server environment setup on local machine |  | 5 |  | Begin working on server system |  | 2.5 |  | Finish setting up NHibernate | [5 empty] | 2 |  | Work on Interim Presentation |  | 2 |  | Finish Interim Evaluation
1 |  | Work Through initial plans for project |  |  |  | 1 |  | Update Time Tracker and Project Website. |  |  |  | 1 |  | Specify Project, Process, and Individual Metrics to track |  |  | 2 |  | Learn new technologies for application (iOS) | [13 empty] | 1.5 |  | Work on Deployment Diagram |  | 1.5 |  | Finish Architectural Presentation and practice |  | 3 |  | Skeleton server and client system | [5 empty] | 5 |  | Continue work on server system | [9 empty] | 1 |  | Complete Peer Evals
1.5 |  | Work on adding Time Tracker to Google Docs |  |  |  | 1.5 |  | Complete Project Synopsis and Survey |  |  |  | 2 |  | Setup VM with necessary applications |  |  | 1.5 |  | Setup VM with necessary applications
0.5 |  | Update individual Time Tracker |  |  |  | 3 |  | Complete First Draft of Process Methodology and Project Plan |  |  |  | 2 |  | Learn new technologies for application (iOS)
[6 empty] | 1 |  | Finalize Technology choices for Project
[6 empty] | 3 |  | Proof of concept of Technology choice
Total | 11.5 |  |  |  |  | Total | 14.5 |  |  |  |  | Total | 11.5 |  |  |  | Total | 10.5 |  |  | Total | 9 |  |  | Total | 10 |  |  | Total | 12 |  |  | Total | 9.75 |  |  | Total | 11.5 |  |  | Total | 11.5 |  |  | Total | 11 |  |  | Total | 13 |  |  | Total | 9.75 |  |  | Total | 13.5 |  |  | Total | 10
Weekly Totals
| Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16
Estimated Time | 0 | 11.5 | 14.5 | 11.5 | 10.5 | 9 | 10 | 12 | 9.75 | 11.5 | 11.5 | 11 | 13 | 9.75 | 13.5 | 10
Actual Time | 4.5 | 12.5 | 10 | 10 | 9.5 | 12 | 10 | 8.25 | 11.25 | 9 | 5 | 11.5 | 13 | 7.25 | 9.5 | 10

## Jared 2nd Term
Week 1 | [5 empty] | Week 2 | [5 empty] | Week 3 |  |  |  |  | Week 4 |  |  |  | Week 5 |  |  |  | Week 6 |  |  |  | Week 7 |  |  |  | Week 8 |  |  |  | Week 9 |  |  |  | Week 10 |  |  |  | Week 11 |  |  |  | Week 12 |  |  |  | Week 13 |  |  |  | Week 14 |  |  |  | Week 15 |  |  |  | Week 16
Finished ? | Estimate | Hours Logged | Activity |  |  | Finished ? | Estimate | Hours Logged | Activity |  |  | Finished ? | Estimate | Hours Logged | Activity |  | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity
Y | 2.5 | 2.5 | Team Meetings |  |  | N | 1 | 1 | Updated Team Website, Time Tracking, and Metrics |  |  | Y | 2.5 | 2.5 | Team Meetings |  | Y | 2.5 | 2.5 | Team Meetings | Y | 2.5 | 2.5 | Team Meetings | Y | 1.25 | 1.25 | Team Meetings | Y | 1.25 | 1.25 | Team Meetings | Y | 2.5 | 2.5 | Team Meetings | Y | 0.5 | 0.5 | update team website, time tracking, and metrics | N | 0.5 | 0 | update team website, time tracking, and metrics | Y | 0.5 | 0.25 | Update team website, time tracking, and metrics | Y | 0.5 | 0.25 | Update team website, time tracking, and metrics | Y | 0.5 | 0.5 | Update team website, time tracking, and metrics |  | 0.5 | 0.5 | Update team website, time tracking, and metrics | N | 0.5 | 0.5 | Final Presentation |  | 1 |  | Give presentation at wegmans
Y | 1 | 1 | Updating Team Website, Time Tracking, and Metrics |  |  | Y | 2.5 | 1.5 | Team Meetings |  |  | Y | 1 | 0.5 | Updated Team Website, Time Tracking, and Metrics |  | Y | 1 | 0.5 | Updated Team Website, Time Tracking, and Metrics | Y | 0.5 | 0.5 | Update Team Website, Time Tracking, and Metrics | N | 0.5 | 0 | Update Team Website, Time Tracking, and Metrics | Y | 1 | 1 | Finish determining tasks for iteration 3 | Y | 0.5 | 0.5 | update team website, time tracking, and metrics | Y | 2 | 2 | setup admin application | N | 2 | 2 | update admin page for coupons after discussion with team | Y | 2 | 2 | finish the admin page for coupons. | Y | 2 | 2 | finish any remaining bugs for existing web services | Y | 2 | 1 | Determine tasks for 4th iteration |  | 2.5 | 2.5 | team meetings | Y | 5 | 2 | finish setting up local server to work with kiosks. |  | 1.5 |  | go to wegmans to test local setup
Y | 1 | 1 | Research usability testing possibilities |  |  | Y | 1 | 1.5 | Coding : setup remaining web service methods |  |  | Y | 1 | 0.5 | Update Web Service Documentation |  | Y | 1 | 0.5 | Update Web Service Documentation | Y | 0.5 | 0.5 | Update Web Service Documentation | Y | 2.5 | 2.5 | Work on remaining client/server issues and ensuring that everything is working for the demo | Y | 0.5 | 0.5 | update website, time tracking, and metrics | N | 2 | 0 | setup repeatable process for setting up SQL Server | Y | 2 | 3 | setup nhibernate for admin application | N | 4 | 2 | update admin page for splash screens after discussion with team and finish its implementation | N | 4 | 6 | finish the admin page for splash screen | Y | 4 | 6 | finish the admin page for splash screens | Y | 2.5 | 2.5 | team meetings |  | 6 | 3 | write documentation for setting up server | N | 1.5 | 0.5 | comment code |  | 0.5 |  | update team website, time tracking, and metrics
Y | 7 | 7 | Coding - researched how to send complex json via .NET webservice - implemented what I researched - debugged issues with web service on server |  |  |  | 1.5 | 1.5 | Update Web Service Documentation |  |  | N | 3 | 0 | Work on Usability Test Documents |  | N | 4 | 0 | Work on Usability Tests for Customer | N | 4 | 0 | Work on Usability Testing for Customers | N | 1.5 | 0 | Work on Usability Testing for Customers | Y | 1 | 1 | coding: change ProcessOrder to return the new order id | N | 4 | 0 | setup repeatable process for setting up server | Y | 2 | 3 | create admin page for managing manager logins | N | 6 | 0 | begin working on updating items on server to use custom attributes | Y | 4 | 3 | fix bugs discovered in web services | Y | 2 | 2 | fix any remaining bugs for existing kiosk admin application | Y | 4 | 13 | Begin working on reporting in kiosk admin web application : determine which reports to do and setup the page to display them |  | 3 | 1.5 | use documentation to setup server on local machine for demo. | N | 5 | 0 | update documentation |  | 5 |  | update documentation
Y | 2 | 2 | Documented Web Services |  |  | N | 2 | 1 | Work on Usability Testing Documents |  |  | Y | 3 | 4 | Coding: Debug the process order web service |  | Y | 2.5 | 6 | Coding: Finish debugging processOrder web service. | N | 3 | 1 | Coding: Test Communication and services between kiosk and server | Y | 2 | 2 | Work on determining tasks for the next iteration | Y | 1 | 2 | coding: change database to have real order number and dispay order number | Y | 1.5 | 3 | coding: create web service for updating items. | Y | 2 | 4 | create admin page for managing printers | Y | 1.5 | 1.5 | begin fixing server webservice methods | N | 3 | 1 | add ability to configure printer to kiosk association from the admin web application | Y | 2 | 2 | finish ability to configure printer to kiosk association from the admin web application. | Y | 2 | 1.5 | Setup web services for retrieving and generating the information for the reports. |  | 0 | 1.5 | Adding AccentColor to kiosk and kiosk management | Y | 0.5 | 0.5 | update team website, time tracking, and metrics |  | 1.5 |  | comment code
[6 empty] | N | 3 | 2 | Coding : work on complete order web service |  |  | Y | 2 | 1 | Coding: Test communication between kiosk and server, with getCatalog |  | N | 3 | 1 | Codeing: Test communication and services between kiosk and server | Y | 1.5 | 1.5 | Comment and Document all new code |  |  |  |  | Y | 1.5 | 2 | coding: finish implementation of manager login webservice | N | 4 | 0 | coding: setup admin web site. | Y | 2 | 1.5 | create admin page for managing splash screens | Y | 0.5 | 0.5 | update web service documentation |  |  |  |  | Y | 0 | 2.5 | team meetings | N | 3 | 0 | Begin writing documentation for setting up the server. |  | 0 | 4 | Work on making KioskAdmin app work on multiple server environments, without having to modify the code. | Y | 0 | 3.5 | test local setup for presentation next week
[6 empty] | Y | 2 | 2 | Coding : work on view order details web service |  |  | Y | 1.5 | 1.5 | Coding: Finish web service for GetNewOrders | [5 empty] | Y | 1.5 | 0.5 | Coding: Setup Order and OrderItem validation on server side |  |  |  |  | Y | 1.5 | 0.5 | coding: finish implementation of manager logout webservice | N | 2 | 0 | setup repeatable process for setting up IIS | Y | 2 | 1.5 | create admin page for managing kiosk themes | Y | 0 | 7 | Work on fixing issues with the admin web application | [8 empty] | Y | 2 | 2 | Finish Implementation of getting splash screens from the server. |  |  |  |  | Y | 0 | 1 | Debug some issues found during testing of local setup
[6 empty] | Y | 2 | 3 | Coding : re-work json format for loadCatalog web service |  |  | Y | 1 | 1 | Coding: Add saving of items to database when kiosk requests catalog. | [5 empty] | Y | 2.5 | 2.5 | Coding: Add web service for Downloading an item image |  |  |  |  | N | 2 | 0 | Setup repatable process for setting up IIS | Y | 2 | 2 | coding: create web service for checking updates to product catalog | Y | 2 | 2 | create admin page for managing coupons | Y | 0 | 3 | Work on fixing issues with the web services. | [10 empty] | 1 | Bug Fix
[33 empty] | Y | 1 | 1 | coding: update load catalog webservice | Y | 3 | 6 | debug admin application issues
[37 empty] | Y | 3 | 3 | add admin application to source control and handle issues
Totals | 13.5 | 13.5 |  |  |  | Totals | 15 | 13.5 |  |  |  | Totals | 15 | 11 |  |  | Totals | 14 | 10.5 |  | Totals | 16 | 9 |  | Totals | 7.75 | 5.75 |  | Totals | 9.75 | 8.25 |  | Totals | 19.5 | 9 |  | Totals | 20.5 | 26.5 |  | Totals | 14.5 | 16 |  | Totals | 13.5 | 12.25 |  | Totals | 10.5 | 14.75 |  | Totals | 16 | 21.5 |  | Totals | 12 | 13 |  | Totals | 12.5 | 8 |  | Totals | 9.5 | 0
Week 2 Estimates | [5 empty] | Week 3 Estimates | [5 empty] | Week 4 Estimates |  |  |  |  | Week 5 Estimates |  |  |  | Week 6 Estimates |  |  |  | Week 7 Estimates |  |  |  | Week 8 Estimates |  |  |  | Week 9 Estimates |  |  |  | Week 10 Estimates |  |  |  | Week 11 Estimates |  |  |  | Week 12 Estimates |  |  |  | Week 13 Estimates |  |  |  | Week 14 Estimates |  |  |  | Week 15 Estimates |  |  |  | Week 16 Estimates
Estimated Time |  | Activity |  |  |  | Estimated Time |  | Activity |  |  |  | Estimated Time |  | Activity |  |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity
1 |  | Updated Team Website, Time Tracking, and Metrics |  |  |  | 2.5 |  | Team Meetings |  |  |  | 2.5 |  | Team Meetings |  |  | 2.5 |  | Team Meetings |  | 1.25 |  | Team Meetings |  | 1.25 |  | Team Meetings |  | 2.5 |  | Team Meetings |  | 0.5 |  | update team website, time tracking, and metrics |  | 0.5 |  | update team website, time tracking, and metrics |  | 0.5 |  | Update team website, time tracking, and metrics |  | 0.5 |  | Update team metrics website, time tracking and metrics |  | 0.5 |  | Update team website, time tracking, and metrics |  | 0.5 |  | Update team website, time tracking, and metrics |  | 0.5 |  | Final Presentation |  | 1 |  | Give presentation at wegmans
2.5 |  | Team Meetings |  |  |  | 1 |  | Updated Team Website, Time Tracking, and Metrics |  |  |  | 1 |  | Updated Team Website, Time Tracking, and Metrics |  |  | 0.5 |  | Update Team Website, Time Tracking, and Metrics |  | 0.5 |  | Update Team Website, Time Tracking, and Metrics |  | 1 |  | Finish Determining Tasks for Iteration 3 |  | 0.5 |  | update team website, time tracking, and metrics |  | 2 |  | setup admin application |  | 2 |  | update admin page for coupons after discussion with team |  | 2 |  | finish the admin page for coupons |  | 4 |  | finish the admin page for splash screens |  | 2 |  | Determine tasks for 4th iteration |  | 2.5 |  | team meetings |  | 5 |  | Finish setting up local server to work with kiosks. |  | 1.5 |  | Go to wegmans to test local setup
1 |  | Coding : setup remaining web service methods |  |  |  | 1 |  | Update Web Service Documentation |  |  |  | 1 |  | Update Web Service Documentation |  |  | 0.5 |  | Update Web Service Documentation |  | 2.5 |  | Work on remaining client/server issues, and ensuring that everything is working for the demo |  | 0.5 |  | Update Website, Time Tracking, and Metrics |  | 2 |  | setup repeatable process for setting up SQL Server |  | 2 |  | setup nhibernate for admin application |  | 4 |  | update admin page for splash screens after discussion with team and finish its implementation |  | 4 |  | finish the admin page for splash screens |  | 2 |  | fix any remaining bugs for existing web services |  | 2.5 |  | Team meetings |  | 6 |  | Write documentation for setting up server |  | 1.5 |  | Comment Code |  | 0.5 |  | update team website, time tracking, and metrics
1.5 |  | Update Web Service Documentation |  |  |  | 3 |  | Work on Usability Testing Documents |  |  |  | 4 |  | Work on Usability Tests for Customer |  |  | 4 |  | Work on Usability Testing for Customers |  | 1.5 |  | Work on Usability Testing for Customers |  | 1 |  | Coding: change ProcessOrder to return the new order id |  | 4 |  | setup repeatable process for setting up server |  | 2 |  | create admin page for managing manager logins |  | 6 |  | begin working on updating items on server to use custom attributes |  | 4 |  | fix bugs discovered in web services |  | 2 |  | fix any remaining bugs for existing kiosk admin application |  | 4 |  | Begin working on reporting in kiosk admin web application : determine which reports to do and setup the page to display them |  | 3 |  | Use documentation to setup server on local machine for demo. |  | 5 |  | Update Documentation |  | 5 |  | update documentation
2 |  | Work on Usability Testing Documents |  |  |  | 3 |  | Coding: Debug the process order web service |  |  |  | 2.5 |  | Coding: finish debugging processOrder web service. |  |  | 3 |  | Coding: Test Communication and services between kiosk and server. |  | 2 |  | Work on determining tasks for the next iteration |  | 1 |  | Coding: Change database to have real order number and display order number. |  | 1.5 |  | coding: create web service for updating items. |  | 2 |  | create admin page for managing printers |  | 1.5 |  | begin fixing server webservice methods |  | 3 |  | add ability to configure printer to kiosk association from the admin web application |  | 2 |  | finish ability to configure printer to kiosk association from the admin web application |  | 2 |  | Setup web services for retrieving and generating the information for the reports. | [5 empty] | 0.5 |  | Update team website, time tracking, and metrics |  | 1.5 |  | comment code
3 |  | Coding : work on complete order web service |  |  |  | 2 |  | Coding: Test communication between kiosk and server |  |  |  | 3 |  | Coding: Test communication and services between kiosk and server. |  |  | 1.5 |  | Comment and Document all new code | [5 empty] | 1.5 |  | Coding: Finish implementation of Manager Login Webservice |  | 4 |  | coding: setup admin web site |  | 2 |  | create admin page for managing splash screens | [13 empty] | 3 |  | Begin writing documentation for setting up the server.
2 |  | Coding : work on view order details web service |  |  |  | 1.5 |  | Coding: Finish web service for GetNewOrders | [8 empty] | 1.5 |  | Coding: Setup Order and OrderItem validation on server side | [5 empty] | 1.5 |  | Coding: Finish implementation of Manager Logout Webservice |  | 2 |  | setup repeatable process for setting up IIS |  | 2 |  | create admin page for managing kiosk themes
2 |  | Coding : re-work json format for loadCatalog web service | [22 empty] | 2 |  | Setup Repeatable Process for setting up IIS | [5 empty] | 2 |  | create admin page for managing coupons
Total | 15 |  |  |  |  | Total | 14 |  |  |  |  | Total | 14 |  |  |  | Total | 13.5 |  |  | Total | 7.75 |  |  | Total | 9.75 |  |  | Total | 16.5 |  |  | Total | 14.5 |  |  | Total | 14 |  |  | Total | 13.5 |  |  | Total | 10.5 |  |  | Total | 14 |  |  | Total | 12 |  |  | Total | 12.5 |  |  | Total | 9.5
Weekly Totals
| Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16
Estimated Time | 0 | 15 | 14 | 14 | 13.5 | 7.75 | 9.75 | 16.5 | 14.5 | 14 | 13.5 | 10.5 | 14 | 12 | 12.5 | 9.5
Actual Time | 13.5 | 13.5 | 11 | 10.5 | 9 | 5.75 | 8.25 | 9 | 26.5 | 16 | 12.25 | 14.75 | 21.5 | 13 | 8 | 0

## Dan 1st Term
Week 1 | [5 empty] | Week 2 | [5 empty] | Week 3 |  |  |  |  | Week 4 |  |  |  | Week 5 |  |  |  | Week 6 |  |  |  | Week 7 |  |  |  | Week 8 |  |  |  | Week 9 |  |  |  | Week 10 |  |  |  | Week 11 |  |  |  | Week 12 |  |  |  | Week 13 |  |  |  | Week 14 |  |  |  | Week 15 |  |  |  | Week 16
Finished ? | Estimate | Hours Logged | Activity |  |  | Finished ? | Estimate | Hours Logged | Activity |  |  | Finished ? | Estimate | Hours Logged | Activity |  | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity
Y |  | 2.5 | Attended Team Meetings |  |  |  |  | 2.5 | Attended Team Meetings |  |  | Y | 1 | 2 | Organize Meeting Notes |  | Y | 2.5 | 2.5 | Attend Team Meetings | Y | 2.5 | 2.5 | Team Meetings | Y | 3 | 1 | Additional Sharepoint config |  |  | 1 | Finished making requirements |  |  | 2 | Finished configuring users for sharepoint |  | 2.5 | 3.5 | Team Meetings |  | 3 | 3 | Powerpoint | Y | 3 | 3 | TFS Iteration/Priority Planning |  | 2.5 | 3.5 | Team Meetings |  | 8 | 6 | Development |  | 12 | 9 | Developemt of Browse & Home |  | 14 | 9 | Development
Y |  | 1 | Drafted Welcome Email |  |  |  |  | 1 | Refined Questions |  |  | Y | 1 | 1 | Timeline |  | Y | 2 | 2.5 | Finalize Project Plan | Y | 2.5 | 3 | User Stories | Y | 4 | 3 | Requirements Work |  |  | 3 | Technology analyzation |  |  | 1.5 | Team Meeting |  | 0 | 2 | Set up TFS |  | 2 | 2 | Class diagram designs | Y | 2.5 | 2.5 | Team Meetings |  | 8 | 7 | Development (Kiosk Menu & Cart) |  | 1 | 0.5 | UI Research |  | 0 | 2 | VM Config for SQL and uninstalling SP |  | 3 | 3.5 | Team Meetings
Y |  | 2 | Worked on initial questions for initial sponsor meeting. | [8 empty] | Y | 2.5 | 2.5 | Team Meeting |  | Y | - | 1 | Re-set Timeline | Y | 1 | 0.5 | Project Plan Touch Ups. |  | 3 | 3 | User Stories updating to use cases |  |  | 2 | Sharepoint User config |  |  | 1 | Architecture Design Doc |  | 1.5 | 1 | Architectural Class diagrams |  | 2.5 | 2.5 | Team Meetings | Y | 5 | 4 | Stubbing Classes | [5 empty] | 2.5 | 1.5 | Team Meetings | [5 empty] | 2 |  | Presentation
[12 empty] | Y | 1 | 2 | Process Description |  |  |  | 1.5 | Wednesday question meeting | Y | 1 | 1 | Timeline Touchups | Y | 2.5 | 2.5 | Team Meeting | [6 empty] | 2 | Server and Kiosk Designs |  | 1.5 | 2 | Architectural Subsystem Diagrams |  | 1 | 1 | Presentation |  | 0 | 2 | Technology Research | [5 empty] | 0 | 0.5 | Progress Spreadsheet
[14 empty] | 0.5 | Change Project Synopsis | [5 empty] | Y | 0 | 4 | VM Sharepoint/Project setup | Y | [12 empty] | 0 | 1 | Set up Project Code |  | 0 | 2 | Sequence Diagrams |  | 0 | 1 | Sponsor Iteration Planning Doc
[38 empty] | 0 | 1 | Timeline Update |  | 0 | 3 | TFS Work Item Setup
Totals |  | 5.5 |  |  |  | Totals | 0 | 3.5 |  |  |  | Totals | 5.5 | 8 |  |  | Totals | 4.5 | 7.5 |  | Totals | 7 | 11 |  | Totals | 12.5 | 9.5 |  | Totals | 0 | 6 |  | Totals | 0 | 6.5 |  | Totals | 5.5 | 10.5 |  | Totals | 8.5 | 13.5 |  | Totals | 10.5 | 12.5 |  | Totals | 10.5 | 10.5 |  | Totals | 11.5 | 8.5 |  | Totals | 12 | 11 |  | Totals | 19 | 12.5 |  | Totals | 0 | 0
Week 2 Estimates | [5 empty] | Week 3 Estimates | [5 empty] | Week 4 Estimates |  |  |  |  | Week 5 Estimates |  |  |  | Week 6 Estimates |  |  |  | Week 7 Estimates |  |  |  | Week 8 Estimates |  |  |  | Week 9 Estimates |  |  |  | Week 10 Estimates |  |  |  | Week 11 Estimates |  |  |  | Week 12 Estimates |  |  |  | Week 13 Estimates |  |  |  | Week 14 Estimates |  |  |  | Week 15 Estimates |  |  |  | Week 16 Estimates
Estimated Time |  | Activity |  |  |  | Estimated Time |  | Activity |  |  |  | Estimated Time |  | Activity |  |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity
[6 empty] | 2.5 |  | Attend Team Meetings |  |  |  | 2.5 |  | Attend Team Meetings |  |  | 2.5 |  | Attend Team Meetings |  | 3 |  | Sharepoint/Project or other tracking tool finalization |  | 3 |  | Finishing requirements |  | 4 |  | Architecture Analysis |  | 2.5 |  | Team Meetings |  | 3 |  | Powerpoint for presentation |  | 3 |  | TFS Iteration Planning / Priority Planning |  | 2.5 |  | Team Meetings |  | 8 |  | More development on Browse funcitonality |  | 12 |  | Continuing Development (Browse, Item Details) |  | 14 |  | More development |  | 8 |  | Finishing development
[6 empty] | 1 |  | Meeting Notes |  |  |  | 2 |  | Finalize Project Plan |  |  | 2.5 |  | Create User Stories for Requirements discussion |  | 4 |  | Requirements Generation |  | 3 |  | Technology analyzation |  | 2 |  | Finish up sharepoint config |  | 3 |  | Architecture Design |  | 2 |  | Class Design |  | 2.5 |  | Team Meetings |  | 8 |  | Development |  | 1 |  | UI Look and Feel research | [5 empty] | 3 |  | Team Meetings |  | 5 |  | Work on documentation, testing and finalizing artifacts
[6 empty] | 2 |  | Process Work | [8 empty] | 2 |  | High Level Requirements |  | 3 |  | User Stories changing | [13 empty] | 2.5 |  | Team Meetings |  | 5 |  | Stubbing Classes | [5 empty] | 2.5 |  | Team Meetings
[17 empty] | 1 |  | Project Plan touch ups |  | 2.5 |  | Team Meeting | [13 empty] | 1 |  | Presentation
[17 empty] | 1 |  | Timeline Touchups
Total | 0 |  |  |  |  | Total | 5.5 |  |  |  |  | Total | 4.5 |  |  |  | Total | 9 |  |  | Total | 12.5 |  |  | Total | 6 |  |  | Total | 6 |  |  | Total | 5.5 |  |  | Total | 8.5 |  |  | Total | 10.5 |  |  | Total | 10.5 |  |  | Total | 11.5 |  |  | Total | 12 |  |  | Total | 17 |  |  | Total | 13
Weekly Totals
| Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16
Estimated Time | 0 | 0 | 5.5 | 4.5 | 9 | 12.5 | 6 | 6 | 5.5 | 8.5 | 10.5 | 10.5 | 11.5 | 12 | 17 | 13
Actual Time | 5.5 | 3.5 | 8 | 7.5 | 11 | 9.5 | 6 | 6.5 | 10.5 | 13.5 | 12.5 | 10.5 | 8.5 | 11 | 12.5 | 0

## Dan 2nd Term
Week 1 | [5 empty] | Week 2 | [5 empty] | Week 3 |  |  |  |  | Week 4 |  |  |  | Week 5 |  |  |  | Week 6 |  |  |  | Week 7 |  |  |  | Week 8 |  |  |  | BREAK | Week 9 |  |  |  | Week 10 |  |  |  | Week 11 |  |  |  | Week 12 |  |  |  | Week 13 |  |  |  | Week 14 |  |  |  | Week 15 |  |  |  | Week 16
Finished ? | Estimate | Hours Logged | Activity |  |  | Finished ? | Estimate | Hours Logged | Activity |  |  | Finished ? | Estimate | Hours Logged | Activity |  | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | BREAK | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity
Y | 2.5 | 2.5 | Team Meetings |  |  | Y | 2.5 | 0 | Team Meetings |  |  | Y | 2.5 | 2.5 | Team Meetings |  | Y | 6 | 6 | Second Item Page |  | 3 | 2 | Cart Changes |  |  | 2 | Searching |  | 3 | 3 | Finish Prototype projects |  |  | 3 | Kiosk Initiation |  |  |  | 5 | Kiosk Init finished | Y | 6 | 6 | Poster Work | Y | 5 | 4 | Out of stock images | Y | 3 | 2 | Iteration Setup | N | 5 | 4 | Bug fixes
Y | 1.5 | 2 | Organized R2 Features into document with priorities for sponsor meeting |  |  | N | 2 | 2 | Cart SLide out |  |  | N | 8 | 3 | Item Detail Page CHanges |  | Y | 2.5 | 2.5 | Team Meetings |  | 5 | 2 | Editing |  |  | 10 | Changes to Cart, Cart Button, UI |  | 3 | 2 | Plan work items |  |  | 2.5 | Team Meetings |  |  |  | 6 | Changing APIs to work with new REST calls | Y | 4 | 5 | Item Editing Gateway Calls | Y | 3 | 3 | Individual item page changes | Y | 3 | 3 | Fix N/A Bug | Y | 0 | 5 | Presentation making
Y | 1.5 | 1.5 | Timeline Work |  |  | Y | 0 | 2 | Completed prioritized feature list |  |  | N | 0 | 6 | Item Detail page research |  | N | 0 | 5 | Cart Changes |  | 2.5 | 3 | Team Meetings |  |  | 4 | Team Meetings |  | 2.5 | 2.5 | Team Meetings |  |  | 7 | Finished Browse Page |  |  |  | 3 | Item Updating | Y | 2 | 1 | Updating some rest docs | Y | 2 | 2 | Splash Screen enhancements | Y | 3 | 3 | Locked printer types during init to respective modes | Y | 0 | 6 | Implemented custom attributes
Y | 2 | 4 | Cart UI research |  |  | Y | 0 | 1 | Status Update | [17 empty] | 2 | Image Loading |  | 5 | 8 | Browse redesign | [9 empty] | Y | 5 | 5 | Managerial page | Y | 4 | 5 | Order Updating | Y | 2 | 2 | Demo Prep
N | 2 | 2 | Started Cart Coding |  |  |  | 2 | 2 | Cart Data Object | [17 empty] | 1 | Random Bug fixing | [14 empty] | 0 | 6 | Log in Log out | Y | 2.5 | 3 | Team Meeting | Y | 2.5 | 2.5 | Team Meetings
[7 empty] | 0 | 1 | Cart Update Price | [17 empty] | 2 | Multiple Projects | [14 empty] | 0 | 3 | Fixed processing and retriving orders | [5 empty] | 0 | 4 | Meeting with Warren
[7 empty] | 2 | 2 | Item Definition Changes for cart | [33 empty] | 2.5 | 2.5 | Team meetings | [5 empty] | 0 | 1 | Timeline
Totals | 9.5 | 12 |  |  |  | Totals | 8.5 | 10 |  |  |  | Totals | 10.5 | 11.5 |  |  | Totals | 8.5 | 13.5 |  | Totals | 10.5 | 7 |  | Totals | 0 | 21 |  | Totals | 13.5 | 15.5 |  | Totals | 0 | 12.5 |  |  | Totals | 0 | 14 |  | Totals | 19.5 | 28.5 |  | Totals | 16.5 | 17 |  | Totals | 13.5 | 17.5 |  | Totals | 5 | 15 |  | Totals | 0 | 0 |  | Totals | 0 | 0 |  | Totals | 0 | 0
Week 2 Estimates | [5 empty] | Week 3 Estimates | [5 empty] | Week 4 Estimates |  |  |  |  | Week 5 Estimates |  |  |  | Week 6 Estimates |  |  |  | Week 7 Estimates |  |  |  | Week 8 Estimates |  |  |  | Week 9 Estimates |  |  |  |  | Week 10 Estimates |  |  |  | Week 11 Estimates |  |  |  | Week 12 Estimates |  |  |  | Week 13 Estimates |  |  |  | Week 14 Estimates |  |  |  | Week 15 Estimates |  |  |  | Week 16 Estimates
Estimated Time |  | Activity |  |  |  | Estimated Time |  | Activity |  |  |  | Estimated Time |  | Activity |  |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity |  |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity
4 |  | Continue Cart Coding (for making individual Item templates) |  |  |  | 8 |  | Item Detail Page |  |  |  | 6 |  | Item Detail second page (alternate input) |  |  | 3 |  | More Cart Changes |  | 4 |  | Underlying Item System |  | 3 |  | Add more project types for usability testing |  | 6 |  | Kiosk Initiation |  | 5 |  | More initialization |  |  | 2 |  | Update some documentation for rest calls |  | 4 |  | Order Updating |  | 3 |  | Set items up for next iteration |  | 5 |  | Assorted bug fixes (see status sheet) |  | 2 |  | Demo Work
4 |  | Cart Data object coding (behind the scenes representation) |  |  |  | 2.5 |  | Team Meetings |  |  |  | 2.5 |  | Team Meetings |  |  | 5 |  | Editing Item Changes |  | 5 |  | Search |  | 3 |  | Planning work items |  | 2.5 |  | Team Meetings |  | 3 |  | Gateway commands for initialization and catalog updating |  |  | 6 |  | Poster work |  | 2 |  | Splash Screen enhancements |  | 3 |  | Fix N/A bug |  | 4 |  | Ability to remove from current orders. Also add daily restriction (NOTE: MOVED TO TIM) |  | 5 |  | More bug fixes
2.5 |  | Team Meetings | [9 empty] | 6 |  | More research |  |  | 2.5 |  | Team Meetings |  | 8 |  | Other Usability Changes (Grids, Cart etc) |  | 2.5 |  | Team Meetings |  | 5 |  | Continue with browse page | [6 empty] | 4 |  | Item Editing calls in gateway |  | 3 |  | Individual item page changes |  | 2.5 |  | Team Meetings | [5 empty] | 1 |  | Implementing new order call with dates
[21 empty] | 3 |  | Team Meetings |  | 5 |  | Begin working on whatever Items | [10 empty] | 5 |  | Possible manager page work |  | 5 |  | Out of stock images | [9 empty] | 8 |  | Presentation, Team meetings, senior project presentations
[42 empty] | 2.5 |  | Team Meeting
Total | 10.5 |  |  |  |  | Total | 10.5 |  |  |  |  | Total | 14.5 |  |  |  | Total | 10.5 |  |  | Total | 20 |  |  | Total | 13.5 |  |  | Total | 13.5 |  |  | Total | 8 |  |  |  | Total | 17 |  |  | Total | 16.5 |  |  | Total | 8.5 |  |  | Total | 9 |  |  | Total | 16 |  |  | Total | 0 |  |  | Total | 0
Weekly Totals
| Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16
Estimated Time | 9.5 | 10.5 | 10.5 | 14.5 | 10.5 | 20 | 13.5 | 13.5 | 8 | 17 | 16.5 | 8.5 | 9 | 16 | 0 | 0
Actual Time | 12 | 10 | 11.5 | 13.5 | 7 | 21 | 15.5 | 12.5 | 14 | 28.5 | 17 | 17.5 | 15 | 0 | 0 | 0

## Tim 1st Term
Week 1 | [5 empty] | Week 2 | [5 empty] | Week 3 |  |  |  |  | Week 4 |  |  |  | Week 5 |  |  |  | Week 6 |  |  |  | Week 7 |  |  |  | Week 8 |  |  |  | Week 9 |  |  |  | Week 10 |  |  |  | Week 11 |  |  |  | Week 12 |  |  |  | Week 13 |  |  |  | Week 14 |  |  |  | Week 15 |  |  |  | Week 16
Finished ? | Estimate | Hours Logged | Activity |  |  | Finished ? | Estimate | Hours Logged | Activity |  |  | Finished ? | Estimate | Hours Logged | Activity |  | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity
Y |  | 4 | Team Meetings |  |  | Y | 4 | 5 | Team meetings |  |  | Y | 4 | 4 | Team meetings |  | Y | 4 | 5 | Team meetings | Y | 5 | 5.5 | Team meetings | Y | 2.5 | 3 | Team meetings | Y | 3 | 3 | Team meetings | Y | 3 | 0 | Team meetings | Y | 3 | 4 | Team Meetings | Y | 5 | 6.5 | Team meetings | Y | 4 | 2.5 | Team meetings | Y | 3 | 2 | Team meetings | Y | 2 | 1.5 | Team meetings | Y | 8 | 4 | Development Tasks | Y | 8 | 5 | Development Tasks | N | 5 | 2.5 | Development Tasks
[17 empty] | Y | 2.5 | 2 | iOS education | Y | 2.5 | 2.5 | iOS education | Y | 2.5 | 1.25 | iOS education | Y | 2.5 | 2.5 | iOS education | N | 2.5 | 0 | iOS education | N | 2.5 | 1.25 | Technology Research | Y | 3 | 2.25 | Architecture Work | Y | 3 | 1 | Finalizing Architecture document and diagrams | Y | 4 | 10 | Development Tasks | Y | 8 | 7.5 | Development Tasks | Y | 0.25 | 0.25 | Sponsor communication | Y | 0.25 | 0.2 | Sponsor communication | N | 0.5 | 0.3 | Sponsor communication
[21 empty] | Y | 0.5 | 0.75 | Sponsor communication | Y | 2 | 1.25 | Update wireframes | Y | 3 | 1.5 | Sponsor meeting prep | N | 2 | 0 | Updating wireframes | Y | 0 | 2.5 | Work on Architecture Diagram | Y | 0.5 | 1 | Sponsor communication | Y | 0.5 | 0.45 | Sponsor communication | Y | 0.5 | 0.6 | Sponsor communication | Y | 0.5 | 0.25 | Sponsor communication |  |  |  |  | Y | 2 | 4 | Team Meetings | N | 3 | 3.75 | Team Meetings
[21 empty] | Y | 0 | 1.5 | Wireframe creation | Y | 0.5 | 0.75 | Sponsor communication | Y | 0.5 | 1.5 | Sponsor communication | Y | 0.5 | 0.75 | Sponsor communication | Y | 0.5 | 0.55 | Sponsor communication | N | 1 | 0 | Technology Research | Y | 2 | 1 | Technology Research | [12 empty] | Y | 2 | 2 | Project Presentations
[41 empty] | Y | 0.75 | 0.5 | Presentation preparation
Totals |  | 4 |  |  |  | Totals | 4 | 5 |  |  |  | Totals | 4 | 4 |  |  | Totals | 6.5 | 7 |  | Totals | 8 | 10.25 |  | Totals | 7.5 | 6.25 |  | Totals | 9 | 8.5 |  | Totals | 8 | 0.75 |  | Totals | 6 | 8.3 |  | Totals | 10.25 | 10.25 |  | Totals | 9.5 | 4.95 |  | Totals | 7.5 | 12.6 |  | Totals | 10.5 | 9.25 |  | Totals | 8.25 | 4.25 |  | Totals | 12.25 | 11.2 |  | Totals | 8.5 | 6.55
Week 2 Estimates | [5 empty] | Week 3 Estimates | [5 empty] | Week 4 Estimates |  |  |  |  | Week 5 Estimates |  |  |  | Week 6 Estimates |  |  |  | Week 7 Estimates |  |  |  | Week 8 Estimates |  |  |  | Week 9 Estimates |  |  |  | Week 10 Estimates |  |  |  | Week 11 Estimates |  |  |  | Week 12 Estimates |  |  |  | Week 13 Estimates |  |  |  | Week 14 Estimates |  |  |  | Week 15 Estimates |  |  |  | Week 16 Estimates
Estimated Time |  | Activity |  |  |  | Estimated Time |  | Activity |  |  |  | Estimated Time |  | Activity |  |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity
4 |  | Team meetings |  |  |  | 4 |  | Team meetings |  |  |  | 4 |  | Team meetings |  |  | 5 |  | Team meetings |  | 2.5 |  | Team meetings |  | 3 |  | Team meetings |  | 3 |  | Team meetings |  | 3 |  | Team meetings |  | 5 |  | Team meetings |  | 4 |  | Team meetings |  | 3 |  | Team meetings |  | 2 |  | Team meetings |  | 8 |  | Development Tasks |  | 8 |  | Development Tasks |  | 5 |  | Development Tasks
[12 empty] | 2.5 |  | iOS education |  |  | 2.5 |  | iOS education |  | 2.5 |  | iOS education |  | 2.5 |  | iOS education |  | 2.5 |  | iOS education |  | 2.5 |  | Technology Research |  | 3 |  | Architecture Work |  | 3 |  | Finalizing Architecture document and diagrams |  | 4 |  | Development Tasks |  | 8 |  | Development Tasks |  | 0.25 |  | Sponsor communication |  | 0.25 |  | Sponsor communication |  | 0.5 |  | Sponsor communication
[17 empty] | 0.5 |  | Sponsor communication |  | 2 |  | Update wireframes |  | 3 |  | Sponsor meeting prep |  | 2 |  | Updating wireframes |  | 0.5 |  | Sponsor communication |  | 0.5 |  | Sponsor communication |  | 0.5 |  | Sponsor communication |  | 0.5 |  | Sponsor communication |  | 0.5 |  | Sponsor communication | [5 empty] | 2 |  | Team meetings |  | 3 |  | Team meetings
[21 empty] | 0.5 |  | Sponsor communication |  | 0.5 |  | Sponsor communication |  | 0.5 |  | Sponsor communication | [5 empty] | 1 |  | Technology Research |  | 2 |  | Technology Research | [13 empty] | 2 |  | Project Presentations
[37 empty] | 0.75 |  | Presentation preparation
Total | 4 |  |  |  |  | Total | 4 |  |  |  |  | Total | 6.5 |  |  |  | Total | 8 |  |  | Total | 7.5 |  |  | Total | 9 |  |  | Total | 8 |  |  | Total | 6 |  |  | Total | 10.25 |  |  | Total | 9.5 |  |  | Total | 7.5 |  |  | Total | 10.5 |  |  | Total | 8.25 |  |  | Total | 12.25 |  |  | Total | 8.5
Weekly Totals
| Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16
Estimated Time | 0 | 4 | 4 | 6.5 | 8 | 7.5 | 9 | 8 | 6 | 10.25 | 9.5 | 7.5 | 10.5 | 8.25 | 12.25 | 8.5
Actual Time | 4 | 5 | 4 | 7 | 10.25 | 6.25 | 8.5 | 0.75 | 8.3 | 10.25 | 4.95 | 12.6 | 9.25 | 4.25 | 11.2 | 6.55

## Tim 2nd Term
Week 1 | [5 empty] | Week 2 | [5 empty] | Week 3 |  |  |  |  | Week 4 |  |  |  | Week 5 |  |  |  | Week 6 |  |  |  | Week 7 |  |  |  | Week 8 |  |  |  | Break Week |  |  |  | Week 9 |  |  |  | Week 10 |  |  |  | Week 11 |  |  |  | Week 12 |  |  |  | Week 13 |  |  |  | Week 14 |  |  |  | Week 15 |  |  |  | Week 16
Finished ? | Estimate | Hours Logged | Activity |  |  | Finished ? | Estimate | Hours Logged | Activity |  |  | Finished ? | Estimate | Hours Logged | Activity |  | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity
Y | 2.25 | 2.5 | Team Meetings |  |  | Y | 2.5 | 1.25 | Team Meetings |  |  | Y | 2 | 2.5 | Team Meetings |  | Y | 2.25 | 1 | Team Meetings | Y | 2.25 | 2.5 | Team Meetings | Y | 4 | 2.75 | Team Meetings | Y | 2.5 | 2.75 | Team Meetings | Y | 2.5 | 1.5 | Team Meetings | N | 2 | 1.5 | Continue implementing and testing the server communication interface for the kiosk | N | 5 | 4 | Finish implementing and testing the server communication interface for the kiosk | N | 3 | 1.5 | Fix the current issues with the communicaiton between the kiosk and the server | Y | 3 | 0 | Finish fixing the current issues with the communicaiton between the kiosk and the server | Y | 2.5 | 2 | Team meetings | Y | 2.5 | 1.5 | Team meetings | Y | 2 | 2 | Team meetings | N | 3 | 0 | Team meetings
Y | 0.5 | 1 | Sponsor communication |  |  | Y | 4 | 4.5 | Work on assigned development tasks |  |  | Y | 6 | 1.5 | Work on assigned development tasks |  | N | 10 | 1.5 | Work on assigned development tasks | N | 5 | 5.25 | Finish implementing the server communication interface for the kiosk | Y | 4 | 0.5 | Finish implemention and testing of the server communication interface for the kiosk | N | 4 | 0.5 | Continue implementing and testing the server communication interface for the kiosk | N | 5 | 2 | Continue implementing and testing the server communication interface for the kiosk | N | 2 | 0.75 | Fix the functionality for associating ordered items with deli item objects stored in the kiosk catalog | N | 3 | 0 | Implement admin login | N | 1 | 0 | Get the "view order details" functionality working | Y | 1 | 0 | Get the "view order details" functionality working (this was fixed by a refactoring of the order retrieval functionality by Dan) | N | 3 | 0 | Work on UI enhancements | N | 3 | 0 | Work on UI enhancements | Y | 3 | 1 | Work on UI enhancements | N | 3 | 0 | Team presentation preparation
[6 empty] | Y | 0.5 | 0.25 | Sponsor communication |  |  | Y | 0.25 | 0.15 | Sponsor communication |  | Y | 0.25 | 0.25 | Sponsor communication | N | 2 | 2.5 | Setup automated JSON serialization/deserialization between C# data representation objects and JSON strings which are properly formatted for consumption by the server | Y | 2.5 | 2 | Finish setting up automated JSON serialization/deserialization between C# data representation objects and JSON strings which are properly formatted for consumption by the server | N | 2 | 0.75 | Continue working on fixing the deserialization of orders retreived from the server as JSON | Y | 1.5 | 0.75 | Continue working on fixing the deserialization of orders retreived from the server as JSON. I fixed some issues last week, but an exception is still being thrown every time that I try to test it. | Y | 1 | 0.5 | Fix issues with unit tests (the retrieve item catalog test is currently failing and I'm not sure why) | Y | 2.5 | 3 | Team meetings | Y | 1.5 | 1.5 | Team meetings | Y | 2 | 0 | Implement manager login functionality (this task was taken over by Dan) | N | 2 | 0 | Improve unit tests | N | 2 | 0 | Improve unit tests | N | 4 | 0.5 | Improve unit tests and clean up the client side code in preparation for final delivery | N | 4 | 0 | Improve unit tests and clean up the client side code in preparation for final delivery
[6 empty] | Y | 2 | 2.5 | Technical research |  |  | Y | 1 | 0.5 | Technical research | [5 empty] | N | 3 | 1.75 | Create and run unit tests for new functionalities | Y | 4 | 5.25 | Implement a simple splashscreen | Y | 2 | 0.5 | Iteration planning (task creation and organization, etc.) | [16 empty] | Y | 3 | 3 | Team meetings |  |  |  |  | Y | 2 | 2.5 | Pull and display splashscreen images from the server | Y | 0 | 0.75 | Individaul preparation for team presentation | N | 2 | 0 | Prepare documentation and all other project artifacts for final delivery
[49 empty] | Y | 0 | 3.5 | Implement splashscreen transitions/animations
[49 empty] | Y | 0 | 0.75 | Add chime which will be played to indicate new orders have arrived
[12 empty] | Open Issues: | Need to test URL parameter passing and seriailization and deserialization of data objects sent to and received from the server respectively and figure out exactly how this is going to work | [7 empty] | Open Issues: |  |  |  | Open Issues: | [7 empty] | Open Issues: | There is currently an issue with associating ordered-items which are received from the server as part of an order (when getting the order history) with the corresponding item in the catalog; the cause is currently unknown, but I do not expect it to be too difficult to fix. |  |  | Open Issues: | Need to talk with Jared about how item details for orders will be loaded and then finish intigrating that informaiton into the app |  |  | Open Issues: | Having some trouble getting the app to talk to the server after we changed some of the methods to PUTs instead of GET (in one case) or POSTs. We changed the methods back to POSTs, so everything should work fine, except I am still having trouble with initializing the kiosk, which used to be a GET but is now a POST (because it got changed to a PUT and then a POST). There are also some issues with retrieving the items which were in an order using the order-item ID's retrieved from the server to display in the admin/deli worker UI, but I think that I have that mostly figured out. |  |  | Open Issues: | Still having a problem with loading images for the item catalog using the asynchronous gateway functions and I have not made any progress on displaying order details due to focusing on the other issues with the gateway which popped up over the past week. |  |  | Open Issues: | We still need to figure out recipt re-printing for order tickets from the admin/employee interface |  |  | Open Issues: | No current issues. Will continue to work on uncompleted items from this week during week 13. |  |  | Open Issues: | Waiting on the receipt reprint functionality to be completed on the server side so that it can be integrated into the deli worker interface functionalities. No other issues at this point. |  |  | Open Issues: | No current issues at this time. All functional items assigned to me have been completed. |  |  | Open Issues:
Totals |  | 3.5 |  |  |  | Totals | 9 | 8.5 |  |  |  | Totals | 9.25 | 4.65 |  |  | Totals | 12.5 | 2.75 |  | Totals | 12.25 | 12 |  | Totals | 14.5 | 10.5 |  | Totals | 10.5 | 4.5 |  | Totals | 9 | 4.25 |  | Totals | 5 | 2.75 |  | Totals | 10.5 | 7 |  | Totals | 5.5 | 3 |  | Totals | 9 | 7.25 |  | Totals | 7.5 | 2 |  | Totals | 9.5 | 4 |  | Totals | 9 | 4.25 |  | Totals | 12 | 0 |  | Totals | 0 | 0
Week 2 Estimates | [5 empty] | Week 3 Estimates | [5 empty] | Week 4 Estimates |  |  |  |  | Week 5 Estimates |  |  |  | Week 6 Estimates |  |  |  | Week 7 Estimates |  |  |  | Week 8 Estimates |  |  |  | Break Week Estimates |  |  |  | Week 9 Estimates |  |  |  | Week 10 Estimates |  |  |  | Week 11 Estimates |  |  |  | Week 12 Estimates |  |  |  | Week 13 Estimates |  |  |  | Week 14 Estimates |  |  |  | Week 15 Estimates |  |  |  | Week 16 Estimates
Estimated Time |  | Activity |  |  |  | Estimated Time |  | Activity |  |  |  | Estimated Time |  | Activity |  |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity
2.5 |  | Team Meetings |  |  |  | 2 |  | Team Meetings |  |  |  | 2.25 |  | Team Meetings |  |  | 2.25 |  | Team Meetings |  | 4 |  | Team Meetings |  | 2.5 |  | Team Meetings |  | 2.5 |  | Team Meetings |  | 2 |  | Continue implementing and testing the server communication interface for the kiosk |  | 5 |  | Finish implementing and testing the server communication interface for the kiosk |  | 3 |  | Fix the current issues with the communicaiton between the kiosk and the server |  | 3 |  | Finish fixing the current issues with the communicaiton between the kiosk and the server |  | 2.5 |  | Team Meetings |  | 2.5 |  | Team Meetings |  | 2 |  | Team Meetings |  | 3 |  | Team Meetings
4 |  | Work on assigned development tasks |  |  |  | 6 |  | Work on assigned development tasks |  |  |  | 10 |  | Work on assigned development tasks |  |  | 5 |  | Finish implementing the server communication interface for the kiosk |  | 4 |  | Finish implemention and testing of the server communication interface for the kiosk |  | 4 |  | Continue implementing and testing the server communication interface for the kiosk |  | 5 |  | Continue implementing and testing the server communication interface for the kiosk |  | 2 |  | Fix the functionality for associating ordered items with deli item objects stored in the kiosk catalog |  | 3 |  | Implement admin login |  | 1 |  | Get the "view order details" functionality working |  | 1 |  | Get the "view order details" functionality working |  | 3 |  | Work on UI enhancements |  | 3 |  | Work on UI enhancements |  | 3 |  | Work on UI enhancements |  | 3 |  | Team presentation preparation
0.5 |  | Sponsor communication |  |  |  | 0.25 |  | Sponsor communication |  |  |  | 0.25 |  | Sponsor communication |  |  | 2 |  | Setup automated JSON serialization/deserialization between C# data representation objects and JSON strings which are properly formatted for consumption by the server |  | 2.5 |  | Finish setting up automated JSON serialization/deserialization between C# data representation objects and JSON strings which are properly formatted for consumption by the server |  | 2 |  | Continue working on fixing the deserialization of orders retreived from the server as JSON |  | 1.5 |  | Continue working on fixing the deserialization of orders retreived from the server as JSON |  | 1 |  | Fix issues with unit tests (the retrieve item catalog test is currently failing and I'm not sure why) |  | 2.5 |  | Team Meetings |  | 1.5 |  | Team Meetings |  | 2 |  | Implement manager login functionality |  | 2 |  | Improve unit tests |  | 2 |  | Improve unit tests |  | 4 |  | Improve unit tests and clean up the client side code in preparation for final delivery |  | 4 |  | Improve unit tests and clean up the client side code in preparation for final delivery
2 |  | Technical research |  |  |  | 1 |  | Technical research | [8 empty] | 3 |  | Create and run unit tests for new functionalities |  | 4 |  | Implement a simple splashscreen |  | 2 |  | Iteration planning (task creation and organization, etc.) | [17 empty] | 3 |  | Team Meetings | [5 empty] | 2 |  | Pull and display splashscreen images from the server | [5 empty] | 2 |  | Prepare documentation and all other project artifacts for final delivery
Total | 9 |  |  |  |  | Total | 9.25 |  |  |  |  | Total | 12.5 |  |  |  | Total | 12.25 |  |  | Total | 14.5 |  |  | Total | 10.5 |  |  | Total | 9 |  |  | Total | 5 |  |  | Total | 10.5 |  |  | Total | 5.5 |  |  | Total | 9 |  |  | Total | 7.5 |  |  | Total | 9.5 |  |  | Total | 9 |  |  | Total | 12 |  |  | Total | 0
Weekly Totals
| Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Break Week | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15
Estimated Time | 0 | 9 | 9.25 | 12.5 | 12.25 | 14.5 | 10.5 | 9 | 5 | 10.5 | 5.5 | 9 | 7.5 | 9.5 | 9 | 12
Actual Time | 3.5 | 8.5 | 4.65 | 2.75 | 12 | 10.5 | 4.5 | 4.25 | 2.75 | 7 | 3 | 7.25 | 2 | 4 | 4.25 | 0

## Warren 2nd Term
Week 1 | [5 empty] | Week 2 | [5 empty] | Week 3 |  |  |  |  | Week 4 |  |  |  | Week 5 |  |  |  | Week 6 |  |  |  | Week 7 |  |  |  | Week 8 |  |  |  | Week 9 |  |  |  | Week 10 |  |  |  | Week 11 |  |  |  | Week 12 |  |  |  | Week 13 |  |  |  | Week 14 |  |  |  | Week 15 |  |  |  | Week 16
Finished ? | Estimate | Hours Logged | Activity |  |  | Finished ? | Estimate | Hours Logged | Activity |  |  | Finished ? | Estimate | Hours Logged | Activity |  | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity
| 2.5 | 2.5 | Team Meetings |  |  |  | 2.5 | 1.5 | Team Meetings |  |  |  | 3 | 0 | refine receipt design based on feedback |  | 6 |  |  | refine receipt design based on feedback | 3 |  | 0 | refine receipt design based on feedback | 4 |  | 1 | Implement some basic testing for server |  |  | 1 | Formatting Wegmans Logo into a PNG of reasonable size, finding out transparency doesnt work as well | [5 empty] | 4 | 0 | Implement more testing for server |  | 2.5 | 2.5 | Team meetings |  | 2.5 | 2.5 | Team meetings |  | 2.5 | 2.5 | Team Meetings |  | 2.5 | 2.5 | Team Meetings
| 1 | 3 | Research different testing methodologies for WCF services including SoapUI RestEasy and built in vs |  |  |  | 6 | 8 | Getting indepth with ZPL. figuring out the structure of message you have to send to the printer. figuring out what modes need to be flipped on, what configuration modes need to happen, how spacing out the text works, drawing lines |  |  |  | 2 | 0 | finish implementing classes and commenting/ polish |  | 4 |  |  | finish implementing classes and commenting/ polish | 4 |  | 1 | move some logic into constructor of ZPL command classes to reduce number of lines and repititous code | 4 |  | 3 | move some logic into constructor of ZPL command classes to reduce number of lines and repititous code |  |  | 8 | Looking on internet for answers to why PNGs wont print on zebra printers and finding out others have the same problem but no one can solve it | [5 empty] | 4 | 4 | move some logic into constructor of ZPL command classes to reduce number of lines and repititous code |  | 3 | 0 | Testing for server | n |  | 3 | Fixed slice type, fixed printer to stay on forever and not shut off. | y | 0 | 5 | Get 2 printers to work with same ZPL code. Different printer sizes had different internal paper widths- had to figure out how to get both to print the same with a special ^PW zpl command |  | 3 | 0 | Write more server unit tests
| 1 | 1 | Research usability testing possibilities |  |  |  |  | 2 | Debugging Zebra printer why it was randomlly turning off, discovering it isnt right printer to automically cut off the paper |  |  |  | 2.5 | 2.5 | team meetings |  | 2.5 |  | 1.5 | team meetings | 2.5 |  | 2.5 | team meetings | 2.5 |  | 2.5 | team meetings |  |  | 3 | Tried stripping PNG header from PNG file and converting it to Base64 and hexidecimal seperately to try to get file to send. | [5 empty] | 2.5 | 2.5 | team meetings |  | 5 | 3 | Fix bugs with receipt formating | y |  | 2 | fixed formatting of barcode text by fixing bugs with text wrapping function. | y | 0 | 2 | Fix receipt spacing on some of the lines and to adjust margin padding in the code to 0 once ^PW was discovered |  | 2 | 0 | Write configuration methods for pre-loading logo onto printer instead of sending it every time
| 0 | 4 | Debug why project wouldnt launch WCF Test client(on a new OS without existing code environment) |  |  |  | 2 | 3 | fleshing out all of the ZPL interfaces and classes to be able to handle linking together the different codes, providing default values/ boundary checking the values in |  |  |  |  | 0.5 | Fixed heiarchy to include type for catagory and department |  |  |  | 8 | Restructuring subystem to handle checking for invalid values for zpl command and throwing exceptions. Create all necessary ZPL classes and corresponding commands to be able to create entire receipt | 5 |  | 0 | Create Behind the deli customer receipt | 5 |  | 0 | Create Behind the deli customer receipt |  |  | 3 | Gave up trying to send PNG, found out It should hopefulyl work by sending .GRF version of PNG. Spent time trying to see how to convert PNG to .GRF. Found answers that point to old software that i accessed after making a new zebra account only to find out it wont run on my OS. Found another answer that points to a single java jar that can convert the images for you. Went ahead and did that and now a .GRF version of PNG |  |  | 4 | Get wegmans logo onto receipt |  | 5 | 3 | Create Behind the deli customer receipt |  |  |  |  | y |  | 1 | added exceptions to catch and gracefully handle when no valid printers are configured | y | 0 | 2 | Demo Prep |  | 5 | 13 | Fix Custom Attribute problems that arise
| 0 | 1 | Install Visual Studio and Windows Features needed to make IIS work | [11 empty] | *Was sick entire weekend, didnt get any work done* |  |  |  | 4 | Figure out how to do inverted text and the drawing of lines and boxes and cleaning up some complexity for some of the commands(no longer include default values due to the complicated interdependence among some zpl commands) | [10 empty] | 3 | Found out reason why PNGs most likely dont work because of an older ZPL manual(different than modern one im using) that shows the format of packets expected by the printer of base64 encoded images(runs CRC check so i have to manually create CRC codes for each packet) | [5 empty] | 10 | 1 | Get Wegmans Logo onto receipt | [8 empty] | n | 0 | 6 | Custom attribute - added sql data bas calls. added checking for Custom Attributes and Custom values in the system controller top level class. Filled in various missing methods |  |  | 3 | Create all the DAO classes for custom attributes and attribute values and mapping files
| 2 | 2 | Update Printing Subystem UML diagram to make it easier and cleaner to create ZPL commands with a good structure | [15 empty] | 0.5 | Briefly looked into how to handle custom fonts, decided it as a stretch goal or ask for existing zpl code to save time | [10 empty] | 2 | Started looking into how difficult it would be to Convert from printing from a TCP stream and move to PrintQueues. Still torn if i want to start down that route | [6 empty] | 4 | Print UPC-A barcode and cupon text on receipt | [14 empty] | 3 | Fix receipt formatting with barcode text and placement. add more exception handling with printing
|  | 1 | Create the classes and interfaces that will be used for implementing the printing subsystem | [15 empty] | 1 | Moved all of the logic out of the systemcontroller class into the printing subsystem | [10 empty] | 1 | Could get wegmans png logo printed on printer using Zebra software | [22 empty] | 2 | Inserted Custom attribute and values into item order DAO and performed checks on them when building catelog. insert ids into the catelog and savining.
[55 empty] | 4 | Changed way CA and VA stored in database - instead of creating new ones every load - keep CA and va unique and just do lookups
Totals |  | 14.5 |  |  |  | Totals | 10.5 | 14.5 |  |  |  | Totals | 7.5 | 3 |  |  | Totals | 0 | 15 |  | Totals | 0 | 3.5 |  | Totals | 0 | 6.5 |  | Totals | 0 | 21 |  | Totals | 0 | 4 |  | Totals | 25.5 | 14.5 |  | Totals | 10.5 | 5.5 |  | Totals | 2.5 | 8.5 |  | Totals | 2.5 | 17.5 |  | Totals | 12.5 | 27.5 |  | Totals | 0 | 0 |  | Totals | 0 | 0 |  | Totals | 0 | 0
Week 2 Estimates | [5 empty] | Week 3 Estimates | [5 empty] | Week 4 Estimates |  |  |  |  | Week 5 Estimates |  |  |  | Week 6 Estimates |  |  |  | Week 7 Estimates |  |  |  | Week 8 Estimates |  |  |  | Week 9 Estimates |  |  |  | Week 10 Estimates |  |  |  | Week 11 Estimates |  |  |  | Week 12 Estimates |  |  |  | Week 13 Estimates |  |  |  | Week 14 Estimates |  |  |  | Week 15 Estimates |  |  |  | Week 16 Estimates
Estimated Time |  | Activity |  |  |  | Estimated Time |  | Activity |  |  |  | Estimated Time |  | Activity |  |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity
2.5 |  | Team meetings |  |  |  | 3 |  | refine receipt design based on feedback |  |  |  | 6 |  | refine receipt design based on feedback |  |  | 3 |  | refine receipt design based on feedback |  | 4 |  | Implement some basic testing for server |  | 4 |  | Implement more testing for server |  | 4 |  | Implement more testing for server | [5 empty] | 2.5 |  | Team meetings |  | 2.5 |  | Team meetings |  | 2.5 |  | Team Meetings |  | 2.5 |  | Team Meetings |  | 2.5 |  | Team Meetings
6 |  | Continue working on getting zebra printer to print out a good receipt |  |  |  | 2 |  | finish implementing classes and commenting/ polish |  |  |  | 4 |  | finish implementing classes and commenting/ polish |  |  | 4 |  | move some logic into constructor of ZPL command classes to reduce number of lines and repititous code |  | 4 |  | move some logic into constructor of ZPL command classes to reduce number of lines and repititous code |  | 4 |  | move some logic into constructor of ZPL command classes to reduce number of lines and repititous code |  | 4 |  | move some logic into constructor of ZPL command classes to reduce number of lines and repititous code | [5 empty] | 3 |  | Testing for server |  | 3 |  | Testing for server |  | 3 |  | Write more server unit tests |  | 3 |  | Write more server unit tests |  | 3 |  | Write more server unit tests
2 |  | flesh out the rest of the ZPL classes |  |  |  | 2.5 |  | team meetings |  |  |  | 2.5 |  | team meetings |  |  | 2.5 |  | team meetings |  | 2.5 |  | team meetings |  | 2.5 |  | team meetings |  | 2.5 |  | team meetings | [5 empty] | 5 |  | Fix bugs with receipt formating |  | 5 |  | Fix bugs with receipt formating |  | 2 |  | Write configuration methods for pre-loading logo onto printer instead of sending it every time |  | 2 |  | Write configuration methods for pre-loading logo onto printer instead of sending it every time |  | 2 |  | Write configuration methods for pre-loading logo onto printer instead of sending it every time
[17 empty] | 5 |  | Create Behind the deli customer receipt |  | 5 |  | Create Behind the deli customer receipt |  | 5 |  | Create Behind the deli customer receipt |  | 5 |  | Create Behind the deli customer receipt | [17 empty] | 5 |  | Fix Custom Attribute problems that arise |  | 4 |  | Look into using dns lookup/ find printer by IP
[25 empty] | 10 |  | Get Wegmans Logo onto receipt |  | 10 |  | Get Wegmans Logo onto receipt
Total | 10.5 |  |  |  |  | Total | 7.5 |  |  |  |  | Total | 12.5 |  |  |  | Total | 14.5 |  |  | Total | 15.5 |  |  | Total | 25.5 |  |  | Total | 25.5 |  |  | Total | 0 |  |  | Total | 10.5 |  |  | Total | 10.5 |  |  | Total | 7.5 |  |  | Total | 12.5 |  |  | Total | 11.5 |  |  | Total | 0 |  |  | Total | 0
Weekly Totals
| Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16
Estimated Time | 0 | 10.5 | 7.5 | 12.5 | 14.5 | 15.5 | 25.5 | 25.5 | 0 | 10.5 | 10.5 | 7.5 | 12.5 | 11.5 | 0 | 0
Actual Time | 14.5 | 14.5 | 3 | 15 | 3.5 | 6.5 | 21 | 4 | 14.5 | 5.5 | 8.5 | 17.5 | 27.5 | 0 | 0 | 0

## Warren 1st Term
Week 1 | [5 empty] | Week 2 | [5 empty] | Week 3 |  |  |  |  | Week 4 |  |  |  | Week 5 |  |  |  | Week 6 |  |  |  | Week 7 |  |  |  | Week 8 |  |  |  | Week 9 |  |  |  | Week 10 |  |  |  | Week 11 |  |  |  | Week 12 |  |  |  | Week 13 |  |  |  | Week 14 |  |  |  | Week 15 |  |  |  | Week 16
Finished ? | Estimate | Hours Logged | Activity |  |  | Finished ? | Estimate | Hours Logged | Activity |  |  | Finished ? | Estimate | Hours Logged | Activity |  | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity | Finished ? | Estimate | Hours Logged | Activity
Y |  | 2.5 | Attended Team Meetings |  |  | Y | 1 | 2 | Take Meeting notes and organize and summary them |  |  |  | 1 | 0 | Refine results from sponsor meeting |  |  | 1 | 1 | Refine results from sponsor meeting |  | 1 | 1 | Refine results from sponsor meeting |  | 1 |  | Refine results from sponsor meeting |  | 1 | 1 | Refine results from sponsor meeting |  | 1 | 0 | Refine results from sponsor meeting |  | 1 | 0 | Refine results from sponsor meeting |  | 1 |  | Refine results from sponsor meeting |  | 1 |  | Refine results from sponsor meeting |  | 1 | 0 | Refine results from sponsor meeting |  | 10.5 | 1.5 | Team Meetings/Get hello world ZPL printer example working |  | 0 | 0 | Refine results from sponsor meeting |  |  | 0.5 | Fixed some previous build issues with method visibility in the Reporting package |  |  |  | Refine results from sponsor meeting
Y |  | 1 | Worked on initial questions for initial sponsor meeting. |  |  | Y | 1.25 | 1.25 | Attend Team Meetings |  |  |  | 0.5 | 0.5 | Finish Agenda for Sponsor Meeting |  |  | 0.5 | 0.5 | Finish agenda for sponsor meeting |  | 0.5 | 0.5 | Finish agenda for sponsor meeting |  | 0.5 |  | Finish agenda for sponsor meeting |  | 0.5 | 0.5 | Finish agenda for sponsor meeting |  | 0.5 | 0 | Finish agenda for sponsor meeting |  | 0.5 | 0 | Finish agenda for sponsor meeting |  | 0.5 | 0.5 | Finish agenda for sponsor meeting |  | 0.5 | 0 | Finish agenda for sponsor meeting |  | 0.5 | 0 | Finish agenda for sponsor meeting |  |  | 1 | Installing WIndows 8.1 and visual studio on surface |  | 0 | 0 | Finish agenda for sponsor meeting |  |  | 2 | Implemented the FileLoader class to take all csv files located in this case my absolute directory(we will decide on standard later) and concats them together into a single source inserting newlines and tabs where appropriate. then returns a memory stream to be used later on |  |  |  | Finish agenda for sponsor meeting
[6 empty] | Y | 1.25 | 1.25 | Attend Sponsor Meeting |  |  |  | 3 | 0 | Complete First Draft of Process Methodology and Project Plan |  |  | 3 | 3 | create a initial draft of all Project risks |  | 1.5 | 1.5 | Further refine Project Risks |  | 2.5 | 2.5 | Team Meetings |  | 2.5 | 2.5 | Team meetings |  | 2.5 | 2.5 | Team meetings |  | 2.5 | 3.5 | Team Meetings |  | 2.5 | 6.5 | Team Meetings |  | 2.5 | 1.5 | Team Meetings |  | 2.5 | 2.5 | Team Meetings |  |  | 1 | Look into how Windows apps handle printing(very few win32 apis are supported. WPF not included) |  | 1.5 | 0 | Team Meetings |  | 1.5 | 2.5 | Team Meetings |  | 1.5 | 2.5 | Team Meetings
[6 empty] | Y | 1 | 1 | Update individual Time Tracker |  |  |  | 1 | 0 | Finalize Technology choices for Project |  |  | 1 | 0.5 | Create a hello world GUI iOS app with a few different buttons and textfields |  | 2.5 | 3.5 | Team Meetings |  |  | 3 | Write down steps, exceptions, and alternative path flows for all administrative user stories |  | 0 | 1 | Prepare agenda for meeting |  |  | 1 | Downloading and installing Jenkins and GIT on Windows VM |  | 2 | 2 | Finish Integrating Jenkins with Github |  |  | 1 | Give Wegmans presentation |  |  | 3 | Read ZPL Programming manual and looked at different features it can do(barcodes, qr codes, tcp/udp server/client, bluetooth, and AES + WPA2 |  | 5 |  | Get hello world example program to work with Printer using ZPL |  |  | 4 | Find helloWorld example and modify to open handle to Zebra printer(wired) and have it print my name |  | 1 | 0 | Create CSV text file of information |  | 1 | 0.5 | Created CSV text files from excel spreadsheets |  | 1 | 2 | Practice Demo
[6 empty] | Y | 1 | 1 | Research technologies for project |  |  |  | 3 | 0 | Proof of concept of Technology choice |  |  |  | 0.5 | Look over Methodology to be prepared for meeting |  |  | 1.5 | Write up Administrative User Stories | [5 empty] | 0 | 1 | Look over Windows Sideloading licensing |  | 3 | 0 | Integrate Jenkins + Github and build a simple project |  |  | 3 | Design out initially Data Kiosk Management subsystem to handle Dynamic workflow and generic containers to handle different kind of items like Sub items, Deli Items, Pizza items etc.. - Class Diagram |  |  | 0.5 | Fix the kiosk data mangement subsystem class diagram to move item loading down into data access subsystem |  |  | 1 | Created skeleton files for all Kiosk Data management subsytem |  |  | 1 | fixed build issues with interface visibility for interfaces in data kiosk subsystem |  |  | 3 | Research a way to figure out how to progomatically invoke printing without going through the windows printer charm(finding out it's impossible) |  | 9 | 0 | Create code to recursively construct item heiarchy |  |  | 1 | Added csproj to include the JSON nuget package we need. added gitignore file to ignore all of the JSON binaries(dont want to push that) Modified BasicItem and Custom Attribute class to handle decimals instead of doubles(Decimals should be used exclusively for money) |  |  | 2 | Debug trying to establish an tcp connection to the printer via IP address
[13 empty] | 2 | 0 | Choose a methodology to present to sponsers |  |  |  | 0.5 | Look over Meeting questions and re-organize/prioritize to make it easier to follow when leading meeting | [9 empty] | 0 | 1 | Look over Apples Enterprise licensing |  |  | 1 | Finding the right GitHub and MSBuild Jenkins plugin to download and install |  |  | 4 | Refine The Data Kiosk Management subsystem to be able to create custom logic for each different workflow and to handle any number of custom attributes to items(Ie. Ham item can have a cut of thin or thick slice) - Class Diagram | [6 empty] | 4 | Created basic logic in all files in kiosk data management system except for complicated item heiarchy files |  |  | 1 | Printed configuration specs of the printer from computer using printer management(windows solution) |  |  | 3 | Try to create a helloworld example to open a connection with Zebra printer using new USB Api introduced in 8.1. Had to look in registry to find PID and VID of Zebra printer in order to find it with DeviceManager. | [5 empty] | 9 | 7 | Created Deli workflow which takes a stream of byes, and goes through and determines all of the links between the items, creates all of the necessary basic items and item containers and custom attributes, and then links all of the items together based on what was provided in the csv file. |  |  | 1 | TIdy up and change status of tfs tasks
[13 empty] | 1 | 0.5 | Finialize Project Synopsis |  |  | 2.5 | 2.5 | Team Meetings | [9 empty] | 1 |  | Prepare agenda for meeting |  |  | 3 | Troubleshooting why Jenkins cant connect with Github |  |  | 1 | Design out the Client side of Deli Item Subsystem to be able to take in JSON object representation of the item heirarchy and display it dnyamically - Class Diagram | [6 empty] | 0.5 | Figured out how to push code after getting authentication errors to our tfs server |  |  | 5 | Printed a barcode and my name on printer using USB Wired connection and Win32 api for a console c# application |  |  | 1 | Find out that the USB API doesn't support printer classes. Couldnt open a connection with the printer(Would just time out) | [6 empty] | 1 | Work on Interm Presentation
[13 empty] | 0.5 | 0.1 | Complete Project Survey | [19 empty] | 1 | Researching SSH vs HTTPS connecting with Jenkins | [14 empty] | 1 | Researched and found hopeful library which will let me connect and print to printers in a windows 8.1 app |  |  | 2 | Abandon wired printer and research how the Zebra printer handles wireless connections(found and downloaded Zebra Network Utility tool) | [6 empty] | 1.5 | Added sample code to kick off the workflow and returns the root IItemType and also created a string representation of the tree so you can see how the relationships are. need to add Windows Forms and uncomment the comments to see it run
[13 empty] | 2 | 1 | Research Different Methodologies | [19 empty] | 1 | Looking into creating new ssh keys to be used with our private Repository | [18 empty] | 1.5 | Got Printer to connect to my home network, and sent a ZPL hello world example using a TCP connection after progomatically enabling tcp on printer
[13 empty] | 1 | 2 | Setup an Environment for developing iOS | [19 empty] | 0.5 | Setup a new GitHub private repository, and shared it with all team members | [18 empty] | 2 | Got Printer to print out my name on RIT'S WPA/WPA2 encrypted Network from my surface
Totals |  | 3.5 |  |  |  | Totals | 5.5 | 6.5 |  |  |  | Totals | 15 | 4.1 |  |  | Totals | 8 | 8.5 |  | Totals | 5.5 | 8 |  | Totals | 4 | 5.5 |  | Totals | 5 | 7 |  | Totals | 7 | 10 |  | Totals | 6 | 13.5 |  | Totals | 4 | 8.5 |  | Totals | 4 | 10 |  | Totals | 9 | 10.5 |  | Totals | 10.5 | 20 |  | Totals | 11.5 | 0 |  | Totals | 11.5 | 16 |  | Totals | 2.5 | 7.5
Week 2 Estimates | [5 empty] | Week 3 Estimates | [5 empty] | Week 4 Estimates |  |  |  |  | Week 5 Estimates |  |  |  | Week 6 Estimates |  |  |  | Week 7 Estimates |  |  |  | Week 8 Estimates |  |  |  | Week 9 Estimates |  |  |  | Week 10 Estimates |  |  |  | Week 11 Estimates |  |  |  | Week 12 Estimates |  |  |  | Week 13 Estimates |  |  |  | Week 14 Estimates |  |  |  | Week 15 Estimates |  |  |  | Week 16 Estimates
Estimated Time |  | Activity |  |  |  | Estimated Time |  | Activity |  |  |  | Estimated Time |  | Activity |  |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity |  | Estimated Time |  | Activity
1.25 |  | Attend Team Meetings |  |  |  | 1 |  | Refine results from sponsor meeting |  |  |  | 1 |  | Refine results from sponsor meeting |  |  | 1 |  | Refine results from sponsor meeting |  | 1 |  | Refine results from sponsor meeting |  | 1 |  | Refine results from sponsor meeting |  | 1 |  | Refine results from sponsor meeting |  | 1 |  | Refine results from sponsor meeting |  | 1 |  | Refine results from sponsor meeting |  | 1 |  | Refine results from sponsor meeting |  | 1 |  | Refine results from sponsor meeting |  | 1 |  | Refine results from sponsor meeting |  | 0 |  | Refine results from sponsor meeting |  | 0 |  | Refine results from sponsor meeting |  | 0 |  | Refine results from sponsor meeting
1.25 |  | Attend Sponsor Meeting |  |  |  | 0.5 |  | Finish Agenda for Sponsor Meeting |  |  |  | 0.5 |  | Finish Agenda for Sponsor Meeting |  |  | 0.5 |  | Finish agenda for sponsor meeting |  | 0.5 |  | Finish agenda for sponsor meeting |  | 0.5 |  | Finish agenda for sponsor meeting |  | 0.5 |  | Finish agenda for sponsor meeting |  | 0.5 |  | Finish agenda for sponsor meeting |  | 0.5 |  | Finish agenda for sponsor meeting |  | 0.5 |  | Finish agenda for sponsor meeting |  | 0.5 |  | Finish agenda for sponsor meeting |  | 0.5 |  | Finish agenda for sponsor meeting |  | 0 |  | Finish agenda for sponsor meeting |  | 0 |  | Finish agenda for sponsor meeting |  | 0 |  | Finish agenda for sponsor meeting
0.5 |  | Update individual Time Tracker |  |  |  | 3 |  | Complete First Draft of Process Methodology and Project Plan |  |  |  | 3 |  | Create a initial draft of all Project risks |  |  | 1.5 |  | Further refine Project Risks | [13 empty] | 2.5 |  | Team Meetings |  | 2.5 |  | Team Meetings |  | 2.5 |  | Team Meetings |  | 2.5 |  | Team Meetings |  | 2.5 |  | Team Meetings |  | 1.5 |  | Team Meetings |  | 1.5 |  | Team Meetings |  | 1.5 |  | Team Meetings
[6 empty] | 1 |  | Finalize Technology choices for Project |  |  |  | 1 |  | Create a hello world GUI iOS app with a few different buttons and textfields |  |  | 2.5 |  | Team Meetings |  | 2.5 |  | Team Meetings |  | 2.5 |  | Team Meetings |  | 2.5 |  | Team Meetings |  | 2 |  | Finish Integrating Jenkins with Github | [9 empty] | 5 |  | Get hello world example program to work with Printer using ZPL |  | 8 |  | Get hello world example program to work with Printer using ZPL |  | 1 |  | Create CSV text file of information |  | 1 |  | Create CSV text file of information |  | 1 |  | Practice Demo
[6 empty] | 3 |  | Proof of concept of Technology choice |  |  |  | 2.5 |  | Team Meetings | [10 empty] | 1 |  | Prepare to lead the meeting |  | 1 |  | Prepare to lead the meeting | [21 empty] | 9 |  | Create code to recursively construct item heiarchy |  | 9 |  | Create code to recursively construct item heiarchy
[6 empty] | 2 |  | Choose a methodology to present to sponsers | [20 empty] | 0.5 |  | Create a private github project and share to group members
[6 empty] | 1 |  | Finialize Project Synopsis | [20 empty] | 3 |  | Integrate Jenkins + Github and build a simple project
[6 empty] | 0.5 |  | Complete Project Survey
[6 empty] | 2 |  | Research Different Methodologies
Total | 3 |  |  |  |  | Total | 14 |  |  |  |  | Total | 8 |  |  |  | Total | 5.5 |  |  | Total | 4 |  |  | Total | 5 |  |  | Total | 8.5 |  |  | Total | 6 |  |  | Total | 4 |  |  | Total | 4 |  |  | Total | 9 |  |  | Total | 12 |  |  | Total | 11.5 |  |  | Total | 11.5 |  |  | Total | 2.5
Weekly Totals
| Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16
Estimated Time | 0 | 3 | 14 | 8 | 5.5 | 4 | 5 | 8.5 | 6 | 4 | 4 | 9 | 12 | 11.5 | 11.5 | 2.5
Actual Time | 3.5 | 6.5 | 4.1 | 8.5 | 8 | 5.5 | 7 | 10 | 13.5 | 8.5 | 10 | 10.5 | 20 | 0 | 16 | 7.5