## Instructions
Your Name: | James Flanagan
Instructions
Fill in your name above.
At the end of each week:
Under "Accomplished this week"
Make sure planned tasks from last week copied correctly with estimated times
Fill in the actual amount of time spent on each task and indicate whether it is done
Add any other tasks you worked on this week
Under "Planned for next week"
Enter unfinished tasks from this week that you will continue next week
Enter other planned tasks for next week
Estimate how many minutes you will spend on each task
Tasks and estimates will copy to next week's accomplished section
Under "Issues"
Enter any unexpected problems you encountered
Enter any issues that require discussion with your team

## W-Wk1
Winter - Week 1
Accomplished this week
Done? | ACT |  | Task
| 1 |  | Project Familiarization
| 4 |  | Class Time
| 5 |  | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1 | Project Synopsis
|  | 4 | Class Time
|  | 5 | TOTAL TIME
Issues

## W-Wk2
Winter - Week 2
Accomplished this week
Done? | ACT | EST | Task
| 2 | 1 | Project Synopsis
| 4 | 4 | Class Time
| 6 | 5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 5 | First Draft Process Plan
|  | 4 | Class Time
|  | 9 | TOTAL TIME
Issues

## W-Wk3
Winter - Week 3
Accomplished this week
Done? | ACT | EST | Task
| 3 | 5 | First Draft Process Plan
| 4 | 4 | Class Time
| 7 | 9 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 3 | Process Plan Updates
|  | 4 | Class Time
|  | 7 | TOTAL TIME
Issues

## W-Wk4
Winter - Week 4
Accomplished this week
Done? | ACT | EST | Task
| 2 | 3 | Process Plan Updates
|  | 4 | Class Time
| 2 | 7 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 4 | Class Time
|  | 3 | Process Plan Updates
|  | 7 | TOTAL TIME
Issues
|  | 3 | Risk Document
|  | 4 | Class Time

## W-Wk5
Winter - Week 5
Accomplished this week
Done? | ACT | EST | Task
No | 2 | 3 | Risk Document
| 2 | 3 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Finish Rick Document
|  | 4 | Class Time
|  | 3 | Set up internet access to source control
|  | 9 | TOTAL TIME
Issues

## W-Wk6
Winter - Week 6
Accomplished this week
Done? | ACT | EST | Task
| 2 | 2 | Finish Rick Document
| 4 | 4 | Class Time
| 4 | 3 | Set up internet access to source control
| 10 | 9 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 4 | Class time
|  | 2 | Continue work on source control
|  | 5 | Use cases
|  | 11 | TOTAL TIME
Issues

## W-Wk7
Winter - Week 7
Accomplished this week
Done? | ACT | EST | Task
| 4 | 4 | Class time
| 1 | 2 | Continue work on source control
| 3 | 5 | Use cases
| 8 | 11 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 4 | Class time
|  | 2 | Document upkeep
|  | 3 | Use Cases
|  | 9 | TOTAL TIME
Issues

## W-Wk8
Winter - Week 8
Accomplished this week
Done? | ACT | EST | Task
| 4 | 4 | Class time
| 1 | 2 | Document upkeep
| 2 | 3 | Use Cases
| 7 | 9 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 4 | Class time
|  | 0.5 | Document Revisions
|  | 4 | Presentation Practice
|  | 8.5 | TOTAL TIME
Issues

## W-Wk9
Winter - Week 9
Accomplished this week
Done? | ACT | EST | Task
| 4 | 4 | Class time
| 0 | 0.5 | Document Revisions
| 3 | 4 | Presentation Practice
| 7 | 8.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 4 | Class Time
|  | 4 | TOTAL TIME
Issues

## W-Wk10
Winter - Week 10
Accomplished this week
Done? | ACT | EST | Task
| 4 | 4 | Class Time
| 4 | 4 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | End of Term Review
|  | 2 | TOTAL TIME
Issues

## W-Finals
Winter - Finals Week
Accomplished this week
Done? | ACT | EST | Task
| 2 | 2 | End of Term Review
| 2 | 2 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 4 | Class Time
|  | 2 | Test Plan
|  | 6 | TOTAL TIME
Issues

## S-Wk1
Spring - Week 1
Accomplished this week
Done? | ACT | EST | Task
| 4 | 4 | Class Time
| 2 | 2 | Test Plan
| 6 | 6 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 4 | Class Time
|  | 1 | Test Plan
|  | 5 | TOTAL TIME
Issues

## S-Wk2
Spring - Week 2
Accomplished this week
Done? | ACT | EST | Task
| 4 | 4 | Class Time
| 1 | 1 | Test Plan
| 5 | 5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## S-Wk3
Spring - Week 3
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 4 | Class Time
|  | 2 | Design Patterns Research
|  | 6 | TOTAL TIME
Issues

## S-Wk4
Spring - Week 4
Accomplished this week
Done? | ACT | EST | Task
| 4 | 4 | Class Time
| 3 | 2 | Design Patterns Research
| 7 | 6 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 4 | Class Time
|  | 2 | Testing Framework Creation
|  | 2 | User Testing
|  | 8 | TOTAL TIME
Issues

## S-Wk5
Spring - Week 5
Accomplished this week
Done? | ACT | EST | Task
| 4 | 4 | Class Time
| 3 | 2 | Testing Framework Creation
| 1 | 2 | User Testing
| 8 | 8 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 4 | Class Time
|  | 2 | User Testing
|  | 2 | Course and Lesson Testing
|  | 1 | Testing Framework Updating and Expansion
|  | 9 | TOTAL TIME
Issues

## S-Wk6
Spring - Week 6
Accomplished this week
Done? | ACT | EST | Task
| 4 | 4 | Class Time
| 3 | 2 | User Testing
| 2 | 2 | Course and Lesson Testing
| 1 | 1 | Testing Framework Updating and Expansion
| 10 | 9 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 4 | Class Time
|  | 1 | Document Upkeep
|  | 1 | Retest Course and Lesson
|  | 2 | IAB Presentations
|  | 6 | Imagine RIT Presentations
|  | 14 | TOTAL TIME
Issues

## S-Wk7
Spring - Week 7
Accomplished this week
Done? | ACT | EST | Task
| 4 | 4 | Class Time
| 1 | 1 | Document Upkeep
| 2 | 1 | Retest Course and Lesson
| 2 | 2 | IAB Presentations
| 6 | 6 | Imagine RIT Presentations
| 15 | 14 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 4 | Class Time
|  | 2 | User Management System Testing
|  | 2 | Course and Lesson System Testing
|  | 8 | TOTAL TIME
Issues

## S-Wk8
Spring - Week 8
Accomplished this week
Done? | ACT | EST | Task
| 4 | 4 | Class Time
| 1 | 2 | User Management System Testing
| 3 | 2 | Course and Lesson System Testing
| 8 | 8 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 4 | Class Time
|  | 2 | Presentation Preparation
|  | 3 | System Testing
|  | 9 | TOTAL TIME
Issues

## S-Wk9
Spring - Week 9
Accomplished this week
Done? | ACT | EST | Task
| 4 | 4 | Class Time
| 2 | 2 | Presentation Preparation
| 2 | 3 | System Testing
| 8 | 9 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 4 | Class Time
|  | 1 | Technical Document
|  | 5 | TOTAL TIME
Issues

## S-Wk10
Spring - Week 10
Accomplished this week
Done? | ACT | EST | Task
| 4 | 4 | Class Time
| 1 | 1 | Technical Document
| 5 | 5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Document Upkeep
|  | 1 | Technical Document
|  | 3 | TOTAL TIME
Issues

## S-Finals
Spring - Finals Week
Accomplished this week
Done? | ACT | EST | Task
| 1 | 2 | Document Upkeep
| 1 | 1 | Technical Document
| 2 | 3 | TOTAL TIME
Issues

## Example
Winter - Week 1
Accomplished this week
Done? | ACT | EST | Task
Y | 20 | 30 | Read textbook about version control
Y | 45 | 30 | Set up subversion on my computer
N | 30 | 60 | Design error-handling subsystem
Y | 15 |  | Read good introduction to subversion on web
| 110 | 120 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 30 | Design error-handling subsystem
|  | 120 | Code error-handling subsystem
|  | 150 | TOTAL TIME
Issues
Hard disk on my computer died, had to restore from backup
Team is having trouble finding time to meet together
May need help coding error-handling subsystem