## Instructions
Your Name: | Josh Kierpiec
Instructions
Fill in your name above.
At the end of each week:
Under "Accomplished this week"
Make sure planned tasks from last week copied correctly with estimated times
Fill in the actual amount of time spent on each task and indicate whether it is done
Add any other tasks you worked on this week
Under "Planned for next week"
Enter unfinished tasks from this week that you will continue next week
Enter other planned tasks for next week
Estimate how many minutes you will spend on each task
Tasks and estimates will copy to next week's accomplished section
Under "Issues"
Enter any unexpected problems you encountered
Enter any issues that require discussion with your team

## W-Wk1
Winter - Week 1
Accomplished this week
Done? | ACT |  | Task
Y | 0.25 |  | Contact Kurt for Team Project Webspace and Accounts
Y | 0.25 |  | Contact team and gather contact information
Y | 0.25 |  | Compile contact information into spreadsheet to be posted on team webspace
Y | 2 |  | Review project definition to gather understanding
Y | 1 |  | Meet with customer to clarify initial project questions
Y | 2 |  | Create the project synopsis and clarify its validity with customer
| 5.75 |  | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Take notes on project definition
|  | 1 | Prepare questions for second meeting with customer
|  | 0.25 | Prepare team roles for project
|  | 1 | Prepare vision document template
|  | 1 | Prepare SRS document template
|  | 2 | Meet with customer on site
|  | 1 | Meet with team to organize project plan for the first quarter
|  | 8.25 | TOTAL TIME
Issues
None so far.

## W-Wk2
Winter - Week 2
Accomplished this week
Done? | ACT | EST | Task
Y | 3 | 2 | Take notes on project definition
Y | 0.75 | 1 | Prepare questions for second meeting with customer
Y | 0.5 | 0.25 | Prepare team roles for project
Y | 1 | 1 | Prepare vision document template
N | 0 | 1 | Prepare SRS document template
Y | 2 | 2 | Meet with customer on site
Y | 1 | 1 | Meet with team to organize project plan for the first quarter
| 8.25 | 8.25 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1 | Finish SRS document template
|  | 3 | Complete initial version of vision document
|  | 1 | Create questions for customer meeting on Thursday
|  | 2 | Meet with customer to go over vision document and answer initial questions
|  | 0.5 | Coordinate the creation of the team website
|  | 0.25 | Ensure that the inidividual reports are being done on a weekly basis
|  | 8 | Create more in-depth question and document the initial needs of the system
|  | 15.75 | TOTAL TIME
Issues
Kurt never responded about project website. Will need to on our own to him and gather the required materials to get this off the ground.

## W-Wk3
Winter - Week 3
Accomplished this week
Done? | ACT | EST | Task
| 2 | 1 | Finish SRS document template
| 2 | 3 | Complete initial version of vision document
| 1 | 1 | Create questions for customer meeting on Thursday
| 2 | 2 | Meet with customer to go over vision document and answer initial questions
| 0.5 | 0.5 | Coordinate the creation of the team website
| 0.25 | 0.25 | Ensure that the inidividual reports are being done on a weekly basis
| 8 | 8 | Create more in-depth question and document the initial needs of the system
| 15.75 | 15.75 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0.25 | Send out the .xls sheets for each of us to Professor Hawker
|  | 0.25 | Prepare list of hardware requirements for Professor Hawker
|  | 2 | Prepare initial list of risks for the project
|  | 1 | Create list of questions for Sean and email out
|  | 5 | Prepare working environment at home
|  | 0.25 | Put together the list of roles for everyone to be integrated into the website
|  | 8.75 | TOTAL TIME
Issues

## W-Wk4
Winter - Week 4
Accomplished this week
Done? | ACT | EST | Task
| 0.25 | 0.25 | Send out the .xls sheets for each of us to Professor Hawker
| 0.25 | 0.25 | Prepare list of hardware requirements for Professor Hawker
| 1.5 | 2 | Prepare initial list of risks for the project
| 1.5 | 1 | Create list of questions for Sean and email out
| 3 | 5 | Prepare working environment at home
| 0.25 | 0.25 | Put together the list of roles for everyone to be integrated into the website
| 6.75 | 8.75 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Hold requirements elicitation meetings
|  | 3 | Analyze needs of system for bubble diagram
|  | 2 | Finish Vision and Scope Document
|  | 0.25 | Update weekly time sheet
|  | 0.5 | Coordinate tasks for following week
|  | 7.75 | TOTAL TIME
Issues

## W-Wk5
Winter - Week 5
Accomplished this week
Done? | ACT | EST | Task
| 2 | 2 | Hold requirements elicitation meetings
| 3 | 3 | Analyze needs of system for bubble diagram
| 2 | 2 | Finish Vision and Scope Document
| 0.25 | 0.25 | Update weekly time sheet
| 0.5 | 0.5 | Coordinate tasks for following week
| 7.75 | 7.75 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1.5 | Finish up elicitation during class time
|  | 0.5 | Walk through prototype that was prepared by Scott/Jim
|  | 0.5 | Walk through the risk document with Sean
|  | 0.25 | Gather sign-offs for documents if possible
|  | 2 | Go through bubble diagram if completed
|  | 4 | Continue working on bubble diagram
|  | 3 | Prepare initial revision of requirements (page one)
|  | 2 | Gather prototype feedback and integrate
|  | 13.75 | TOTAL TIME
Issues

## W-Wk6
Winter - Week 6
Accomplished this week
Done? | ACT | EST | Task
|  | 1.5 | Finish up elicitation during class time
|  | 0.5 | Walk through prototype that was prepared by Scott/Jim
|  | 0.5 | Walk through the risk document with Sean
|  | 0.25 | Gather sign-offs for documents if possible
|  | 2 | Go through bubble diagram if completed
|  | 4 | Continue working on bubble diagram
|  | 3 | Prepare initial revision of requirements (page one)
|  | 2 | Gather prototype feedback and integrate
| 0 | 13.75 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0.25 | Ensure sign offs on final versions of Process, Vision and Scope, and Risk documents
|  | 2 | Finish working on documents if needed. Must be completed this week.
|  | 2 | Prepare updated version of requirements based on prototype feedback.
|  | 3 | Finish setting up both school and home workstation systems for development.
|  | 0.5 | Coordinate work to be completed in the following week.
|  | 7.75 | TOTAL TIME
Issues

## W-Wk7
Winter - Week 7
Accomplished this week
Done? | ACT | EST | Task
| 0.4 | 0.25 | Ensure sign offs on final versions of Process, Vision and Scope, and Risk documents
| 2 | 2 | Finish working on documents if needed. Must be completed this week.
| 2.25 | 2 | Prepare updated version of requirements based on prototype feedback.
| 3 | 3 | Finish setting up both school and home workstation systems for development.
| 0.5 | 0.5 | Coordinate work to be completed in the following week.
| 8.15 | 7.75 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1 | Prepare for mid-project presentation.
|  | 2 | Complete SRS final sections.
|  | 1 | Coordinate planning for design document and sections needed.
|  | 1 | Prepare research materials for learning what is needed for VB.net
|  | 0.5 | Coordinate work to be completed in the following week.
|  | 5.5 | TOTAL TIME
Issues

## W-Wk8
Winter - Week 8
Accomplished this week
Done? | ACT | EST | Task
| 1 | 1 | Prepare for mid-project presentation.
| 2 | 2 | Complete SRS final sections.
| 1 | 1 | Coordinate planning for design document and sections needed.
| 1.5 | 1 | Prepare research materials for learning what is needed for VB.net
| 0.5 | 0.5 | Coordinate work to be completed in the following week.
| 6 | 5.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 4 | Finish project presentations.
|  | 0.5 | Perform project presentations.
|  | 3.5 | Watch other presentations.
|  | 0.5 | Coordinate activities for project.
|  | 8.5 | TOTAL TIME
Issues

## W-Wk9
Winter - Week 9
Accomplished this week
Done? | ACT | EST | Task
| 4 | 4 | Finish project presentations.
| 0.5 | 0.5 | Perform project presentations.
| 3.5 | 3.5 | Watch other presentations.
| 0.5 | 0.5 | Coordinate activities for project.
| 8.5 | 8.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0.5 | Coordinate design document creation
|  | 0.5 | Peer and presentation evaluations
|  | 1 | Team and project evaluations
|  | 10 | Final exam preparation for other classes
|  | 12 | TOTAL TIME
Issues

## W-Wk10
Winter - Week 10
Accomplished this week
Done? | ACT | EST | Task
| 0.5 | 0.5 | Coordinate design document creation
| 0.5 | 0.5 | Peer and presentation evaluations
| 1 | 1 | Team and project evaluations
| 10 | 10 | Final exam preparation for other classes
| 12 | 12 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 5 | Finals for all other classes.
|  | 1 | Close off any outstanding issues with first quarter of project.
|  | 6 | TOTAL TIME
Issues

## W-Finals
Winter - Finals Week
Accomplished this week
Done? | ACT | EST | Task
| 5 | 5 | Finals for all other classes.
| 1 | 1 | Close off any outstanding issues with first quarter of project.
| 6 | 6 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1 | Work on design document diagrams
|  | 0.5 | Coordinate group activities.
|  | 2 | Meet with group to resync after break and coordinate break activities.
|  | 1 | Coordinate milestone creation.
|  | 1 | Coordinate test document creations.
|  | 5.5 | TOTAL TIME
Issues

## S-Wk1
Spring - Week 1
Accomplished this week
Done? | ACT | EST | Task
| 1 | 1 | Work on design document diagrams
| 0.5 | 0.5 | Coordinate group activities.
| 2 | 2 | Meet with group to resync after break and coordinate break activities.
| 1 | 1 | Coordinate milestone creation.
| 1 | 1 | Coordinate test document creations.
| 5.5 | 5.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Meet with Sean to go over design document
|  | 3 | Ensure design document meets expectations and required section criteria.
|  | 5 | Begin implementation on particular milestones.
|  | 0.5 | Coordinate project activities
|  | 2 | Research more VB.net materials.
|  | 12.5 | TOTAL TIME
Issues

## S-Wk2
Spring - Week 2
Accomplished this week
Done? | ACT | EST | Task
| 2 | 2 | Meet with Sean to go over design document
| 3 | 3 | Ensure design document meets expectations and required section criteria.
| 4 | 5 | Begin implementation on particular milestones.
| 0.5 | 0.5 | Coordinate project activities
| 2 | 2 | Research more VB.net materials.
| 11.5 | 12.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 4 | Work on assigned implementation tasks
|  | 0.5 | Manage design document work efforts
|  | 6 | Build diagrams/etc for potential designs, work on designs
|  | 10.5 | TOTAL TIME
Issues

## S-Wk3
Spring - Week 3
Accomplished this week
Done? | ACT | EST | Task
| 4 | 4 | Work on assigned implementation tasks
| 0.5 | 0.5 | Manage design document work efforts
| 6 | 6 | Build diagrams/etc for potential designs, work on designs
| 10.5 | 10.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 3 | Re-work design efforts, finalize design
|  | 6 | Help with testing tasks
|  | 9 | TOTAL TIME
Issues

## S-Wk4
Spring - Week 4
Accomplished this week
Done? | ACT | EST | Task
| 3 | 3 | Re-work design efforts, finalize design
| 6 | 6 | Help with testing tasks
| 9 | 9 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Finish up design documentation
|  | 2 | Begin a management cycle on current documentation
|  | 4 | Help with implementation tasks
|  | 4 | Help with testing tasks
|  | 12 | TOTAL TIME
Issues

## S-Wk5
Spring - Week 5
Accomplished this week
Done? | ACT | EST | Task
| 2 | 2 | Finish up design documentation
| 2 | 2 | Begin a management cycle on current documentation
| 3.5 | 4 | Help with implementation tasks
| 4 | 4 | Help with testing tasks
| 11.5 | 12 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 3 | Work on Technical Document Draft 1
|  | 12 | Unit/QA Test Available source files
|  | 3 | Manage Documents
|  | 18 | TOTAL TIME
Issues

## S-Wk6
Spring - Week 6
Accomplished this week
Done? | ACT | EST | Task
| 3 | 3 | Work on Technical Document Draft 1
| 10 | 12 | Unit/QA Test Available source files
| 3 | 3 | Manage Documents
| 16 | 18 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 3 | Work on Technical Document Draft 2
|  | 3 | Work on Project Poster
|  | 5 | Continue with Testing
|  | 11 | TOTAL TIME
Issues

## S-Wk7
Spring - Week 7
Accomplished this week
Done? | ACT | EST | Task
| 3 | 3 | Work on Technical Document Draft 2
| 4 | 3 | Work on Project Poster
| 4 | 5 | Continue with Testing
| 11 | 11 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 3 | Finish project poster
|  | 3 | More work on technical document
|  | 1 | Create final implementation schedule
|  | 7 | TOTAL TIME
Issues

## S-Wk8
Spring - Week 8
Accomplished this week
Done? | ACT | EST | Task
| 8 | 3 | Finish project poster
| 2 | 3 | More work on technical document
| 1 | 1 | Create final implementation schedule
| 11 | 7 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Present for IAB
|  | 6 | Present for ImagineRIT
|  | 2 | Update documentation
|  | 2 | Continue with technical document
|  | 12 | TOTAL TIME
Issues

## S-Wk9
Spring - Week 9
Accomplished this week
Done? | ACT | EST | Task
| 2 | 2 | Present for IAB
| 6 | 6 | Present for ImagineRIT
| 2 | 2 | Update documentation
| 0 | 2 | Continue with technical document
| 10 | 12 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 5 | Catchup with technical document work
|  | 2 | Prepare final presentation
|  | 2 | Prepare for UI meeting with Sean
|  | 3 | Finish updating documents and making proper templates
|  | 0.5 | Give final presentation
|  | 12.5 | TOTAL TIME
Issues

## S-Wk10
Spring - Week 10
Accomplished this week
Done? | ACT | EST | Task
| 3 | 5 | Catchup with technical document work
| 2 | 2 | Prepare final presentation
| 2 | 2 | Prepare for UI meeting with Sean
| 2 | 3 | Finish updating documents and making proper templates
| 0.5 | 0.5 | Give final presentation
| 9.5 | 12.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 4 | Finish technical document
|  | 4 | Take exams
|  | 2 | Finish putting together document templates
|  | 2 | Organize collection for final submission
|  | 12 | Graduation activities
|  | 24 | TOTAL TIME
Issues

## S-Finals
Spring - Finals Week
Accomplished this week
Done? | ACT | EST | Task
| 8 | 4 | Finish technical document
| 4 | 4 | Take exams
| 2 | 2 | Finish putting together document templates
| 2 | 2 | Organize collection for final submission
|  | 12 | Graduation activities
| 16 | 24 | TOTAL TIME
Issues

## Example
Winter - Week 1
Accomplished this week
Done? | ACT | EST | Task
Y | 20 | 30 | Read textbook about version control
Y | 45 | 30 | Set up subversion on my computer
N | 30 | 60 | Design error-handling subsystem
Y | 15 |  | Read good introduction to subversion on web
| 110 | 120 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 30 | Design error-handling subsystem
|  | 120 | Code error-handling subsystem
|  | 150 | TOTAL TIME
Issues
Hard disk on my computer died, had to restore from backup
Team is having trouble finding time to meet together
May need help coding error-handling subsystem