## Instructions
Your Name: | Jim Spicknall
Instructions
Fill in your name above.
At the end of each week:
Under "Accomplished this week"
Make sure planned tasks from last week copied correctly with estimated times
Fill in the actual amount of time spent on each task and indicate whether it is done
Add any other tasks you worked on this week
Under "Planned for next week"
Enter unfinished tasks from this week that you will continue next week
Enter other planned tasks for next week
Estimate how many minutes you will spend on each task
Tasks and estimates will copy to next week's accomplished section
Under "Issues"
Enter any unexpected problems you encountered
Enter any issues that require discussion with your team

## W-Wk1
Winter - Week 1
Accomplished this week
Done? | ACT |  | Task
| 4 |  | Attend Senior Project Class Periods
yes | 0.15 |  | Select team roles.
| 4.15 |  | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 4 | Attend Senior Project Class Periods
|  | 4 | TOTAL TIME
Issues

## W-Wk2
Winter - Week 2
Accomplished this week
Done? | ACT | EST | Task
| 2 | 4 | Attend Senior Project Class Periods
| 2 | 4 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 4 | Attend Senior Project Class Periods
|  | 4 | TOTAL TIME
Issues

## W-Wk3
Winter - Week 3
Accomplished this week
Done? | ACT | EST | Task
| 4 | 4 | Attend Senior Project Class Periods
| 0.25 |  | fill out individual effor spreadsheet and send to Josh
| 4.25 | 4 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 4 | Attend Senior Project Class Periods
|  | 0.25 | fill out individual effor spreadsheet and send to Josh
|  | 4.25 | TOTAL TIME
Issues

## W-Wk4
Winter - Week 4
Accomplished this week
Done? | ACT | EST | Task
| 4 | 4 | Attend Senior Project Class Periods
| 0 | 0.25 | fill out individual effor spreadsheet and send to Josh
| 4 | 4.25 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 4 | Attend Senior Project Class Periods
|  | 0.25 | Fill out individual effort spreadsheet and send to Josh
|  | 4.25 | TOTAL TIME
Issues

## W-Wk5
Winter - Week 5
Accomplished this week
Done? | ACT | EST | Task
| 4 | 4 | Attend Senior Project Class Periods
| 0.25 | 0.25 | Fill out individual effort spreadsheet and send to Josh
| 0.25 |  | create list of possible risks
| 0.25 |  | create list of possiblle business objectives
| 26 |  | prepare new pc at home for development of project. (~$2500)
| 30.75 | 4.25 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 4 | attend senior project class periods
|  | 0.25 | fill out individual effort spreadsheet and send to scott
|  | 2 | produce prototype interfaces for major sections of project
|  | 6.25 | TOTAL TIME
Issues

## W-Wk6
Winter - Week 6
Accomplished this week
Done? | ACT | EST | Task
| 4 | 4 | attend senior project class periods
| 0.25 | 0.25 | fill out individual effort spreadsheet and send to scott
| 4 | 2 | produce prototype interfaces for major sections of project
| 4 |  | attempt to prepare team server for development next week.
| 12.25 | 6.25 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 4 | attend senior project class periods
|  | 0.25 | fill out individual effort spreadsheet and send to scott
|  | 6 | re-attempt to setup team server for development
|  | 10.25 | TOTAL TIME
Issues

## W-Wk7
Winter - Week 7
Accomplished this week
Done? | ACT | EST | Task
| 4 | 4 | attend senior project class periods
| 0.25 | 0.25 | fill out individual effort spreadsheet and send to scott
| 6 | 6 | re-attempt to setup team server for development
| 4 |  | Create prototype database
| 14.25 | 10.25 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 4 | attend senior project class periods
|  | 0.25 | fill out individual effort spreadsheet and send to scott
|  | 12 | begin development of project
|  | 2 | participate in preparation of presentation
|  | 18.25 | TOTAL TIME
Issues

## W-Wk8
Winter - Week 8
Accomplished this week
Done? | ACT | EST | Task
| 4 | 4 | attend senior project class periods
| 0.25 | 0.25 | fill out individual effort spreadsheet and send to scott
| 12 | 12 | begin development of project
| 2.5 | 2 | participate in preparation of presentation
| 18.75 | 18.25 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 4 | attend senior project class periods
|  | 0.25 | fill out individual effort spreadsheet and send to scott
|  | 12 | more development
|  | 6 | begin design doc
|  | 22.25 | TOTAL TIME
Issues

## W-Wk9
Winter - Week 9
Accomplished this week
Done? | ACT | EST | Task
| 4 | 4 | attend senior project class periods
| 0 | 0.25 | fill out individual effort spreadsheet and send to scott
| 4 | 12 | more development
| 8 | 6 | begin design doc
| 16 | 22.25 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 4 | Attend Senior Project Class Periods
|  | 0.25 | Fill out inidvidual effors spreadsheet and send to scott
|  | 12 | more development
|  | 16.25 | TOTAL TIME
Issues

## W-Wk10
Winter - Week 10
Accomplished this week
Done? | ACT | EST | Task
| 4 | 4 | Attend Senior Project Class Periods
| 0.5 | 0.25 | Fill out inidvidual effors spreadsheet and send to scott
| 12 | 12 | more development
| 16.5 | 16.25 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 12 | development
|  | 0.25 | fill out individual effort spreadsheet and send to scott
|  | 12.25 | TOTAL TIME
Issues

## W-Finals
Winter - Finals Week
Accomplished this week
Done? | ACT | EST | Task
| 12 | 12 | development
| 0 | 0.25 | fill out individual effort spreadsheet and send to scott
| 12 | 12.25 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0.25 | fill out individual effort spreadsheet and send to scott
|  | 6 | development (break week)
|  | 6 | development (week 1)
|  | 3 | design doc
|  | 15.25 | TOTAL TIME
Issues

## S-Wk1
Spring - Week 1
Accomplished this week
Done? | ACT | EST | Task
| 0.5 | 0.25 | fill out individual effort spreadsheet and send to scott
| 6 | 6 | development (break week)
| 0 | 6 | development (week 1)
| 4 | 3 | design doc
| 2 |  | extra meeting to discuss design and prepare for sponsor contact
| 4 |  | attend class periods
| 16.5 | 15.25 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0.25 | fill out individual effort spreadsheet and send to scott
|  | 8 | development
|  | 4 | attend class periods
|  | 12.25 | TOTAL TIME
Issues

## S-Wk2
Spring - Week 2
Accomplished this week
Done? | ACT | EST | Task
| 0.25 | #REF! | fill out individual effort spreadsheet and send to scott
| 14 | #REF! | development
| 4 | #REF! | attend class periods
| 18.25 | #REF! | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0.25 | fill out individual effort spreadsheet and send to scott
|  | 10 | development
|  | 4 | attend class periods
|  | 14.25 | TOTAL TIME
Issues

## S-Wk3
Spring - Week 3
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0.25 | fill out individual effort spreadsheet and send to scott
| 0 | 10 | development
| 4 | 4 | attend class periods
| 6 |  | discuss design with josh over aim Friday night
| 8 |  | discuss design with josh over aim Saturday
| 3 |  | discuss design with josh over aim Sunday
| 21 | 14.25 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 4 | continue failing to reason with irrational SE thumpers at meeting Monday
|  | 4 | attend class periods
|  | 0 | development
|  | 10 | futher failures to reason
|  | 0.25 | fill out individual effort timesheet and send to scott
|  | 18.25 | TOTAL TIME
Issues

## S-Wk4
Spring - Week 4
Accomplished this week
Done? | ACT | EST | Task
| 0 | 4 | continue failing to reason with irrational SE thumpers at meeting Monday
| 4 | 4 | attend class periods
| 0 | 0 | development
| 0 | 10 | futher failures to reason
| 0.25 | 0.25 | fill out individual effort timesheet and send to scott
| 2 |  | maintainence of design document
| 6.25 | 18.25 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 8 | development
|  | 4 | attend class periods
|  | 0.25 | fill out individual effort time sheet and send to scott
|  | 12.25 | TOTAL TIME
Issues

## S-Wk5
Spring - Week 5
Accomplished this week
Done? | ACT | EST | Task
| 14 | 8 | development
| 4 | 4 | attend class periods
| 0.25 | 0.25 | fill out individual effort time sheet and send to scott
| 18.25 | 12.25 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 12 | development
|  | 4 | attend class periods
|  | 0.25 | fill out individual effort time sheet and send to scott
|  | 16.25 | TOTAL TIME
Issues

## S-Wk6
Spring - Week 6
Accomplished this week
Done? | ACT | EST | Task
| 4 | 12 | development
| 4 | 4 | attend class periods
| 0 | 0.25 | fill out individual effort time sheet and send to scott
| 8 | 16.25 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 6 | development
|  | 4 | attend class periods
|  | 0.25 | fill out individual effort time sheet and send to scott
|  | 10.25 | TOTAL TIME
Issues

## S-Wk7
Spring - Week 7
Accomplished this week
Done? | ACT | EST | Task
| 6 | 6 | development
| 4 | 4 | attend class periods
| 0.5 | 0.25 | fill out individual effort time sheet and send to scott
| 10.5 | 10.25 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 12 | development
|  | 4 | attend class periods
|  | 0.25 | fill out individual time sheets and send to scott
|  | 16.25 | TOTAL TIME
Issues

## S-Wk8
Spring - Week 8
Accomplished this week
Done? | ACT | EST | Task
| 24 | 12 | development
| 4 | 4 | attend class periods
| 0.25 | 0.25 | fill out individual time sheets and send to scott
| 28.25 | 16.25 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 16 | development
|  | 4 | attend class periods
|  | 0.25 | fill out timesheet and send to James
|  | 20.25 | TOTAL TIME
Issues

## S-Wk9
Spring - Week 9
Accomplished this week
Done? | ACT | EST | Task
| 32 | 16 | development
| 4 | 4 | attend class periods
| 0.25 | 0.25 | fill out timesheet and send to James
| 36.25 | 20.25 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 32 | development
|  | 4 | addend class periods
|  | 0.25 | fill out timesheet and send to James
|  | 36.25 | TOTAL TIME
Issues

## S-Wk10
Spring - Week 10
Accomplished this week
Done? | ACT | EST | Task
| 20 | 32 | development
| 5 | 4 | addend class periods
| 0.25 | 0.25 | fill out timesheet and send to James
| 25.25 | 36.25 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | who knows…
|  | 0 | TOTAL TIME
Issues

## S-Finals
Spring - Finals Week
Accomplished this week
Done? | ACT | EST | Task
|  | 0 | who knows…
| 4 |  | final meetings and project wrapup
| 4 | 0 | TOTAL TIME
Issues

## Example
Winter - Week 1
Accomplished this week
Done? | ACT | EST | Task
Y | 20 | 30 | Read textbook about version control
Y | 45 | 30 | Set up subversion on my computer
N | 30 | 60 | Design error-handling subsystem
Y | 15 |  | Read good introduction to subversion on web
| 110 | 120 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 30 | Design error-handling subsystem
|  | 120 | Code error-handling subsystem
|  | 150 | TOTAL TIME
Issues
Hard disk on my computer died, had to restore from backup
Team is having trouble finding time to meet together
May need help coding error-handling subsystem