## Instructions
Your Name: | Scott Smith
Instructions
Fill in your name above.
At the end of each week:
Under "Accomplished this week"
Make sure planned tasks from last week copied correctly with estimated times
Fill in the actual amount of time spent on each task and indicate whether it is done
Add any other tasks you worked on this week
Under "Planned for next week"
Enter unfinished tasks from this week that you will continue next week
Enter other planned tasks for next week
Estimate how many minutes you will spend on each task
Tasks and estimates will copy to next week's accomplished section
Under "Issues"
Enter any unexpected problems you encountered
Enter any issues that require discussion with your team

## W-Wk1
Winter - Week 1
Accomplished this week
Done? | ACT |  | Task
X | 3 | 4 | Senior Project meetings
| 3 |  | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 6 | Development Estimates/Explaination
|  | 2 | Get Webserver information
|  | 8 | TOTAL TIME
Issues
Kurt not responding to Josh's emails

## W-Wk2
Winter - Week 2
Accomplished this week
Done? | ACT | EST | Task
yes | 6 | 6 | Development Estimates/Explaination
No | 2 | 2 | Get Webserver information
Yes | 2 | 4 | Senior Project Meetings
| 10 | 12 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Get Webserver information and files placed
|  | 2 | TOTAL TIME
Issues
Kurt still not responding to Josh's emails, going in person next week

## W-Wk3
Winter - Week 3
Accomplished this week
Done? | ACT | EST | Task
No | 3 | 2 | Get Webserver information and files placed
Yes | 2 | 4 | Senior Project Meetings
| 5 | 6 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 4 | Develop chart of individual estimates for Josh
|  | 1 | Place files as they come in
|  | 5 | TOTAL TIME
Issues
Finally got password, now going to attempt to use it from home.

## W-Wk4
Winter - Week 4
Accomplished this week
Done? | ACT | EST | Task
Yes | 2 | 4 | Develop chart of individual estimates for Josh
Yes | 2 | 1 | Place files as they come in
Yes | 2 | 4 | Senior Project Meetings
| 6 | 9 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 4 | Develop an actual main page for the site
|  | 4 | TOTAL TIME
Issues
Home use seems to be a complete failure, reset password and doing work from lab for now.

## W-Wk5
Winter - Week 5
Accomplished this week
Done? | ACT | EST | Task
Yes | 3 | 4 | Develop an actual main page for the site
Yes | 3 | 4 | Attend Senior Project Meetings
Yse | 1 | 1 | Maintain website
| 1 | 2 | Work on prototype
| 8 | 11 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 3 | Complete Prototype pathing and place within UI
|  | 3 | TOTAL TIME
Issues

## W-Wk6
Winter - Week 6
Accomplished this week
Done? | ACT | EST | Task
| 2 | 3 | Complete Prototype pathing and place within UI
| 2 | 2 | Work on Database design
| 3 | 4 | Attend meetings
| 7 | 9 | TOTAL TIME
Planned for next week
|  | EST | Task
Finalize DataBase design
Start On Object design
|  | 0 | TOTAL TIME
Issues

## W-Wk7
Winter - Week 7
Accomplished this week
Done? | ACT | EST | Task
| 3 | 3 | Finalize DataBase design
| 2 | 2 | Start On Object design
| 6 | 6 | Attend Meetings
| 11 | 11 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## W-Wk8
Winter - Week 8
Accomplished this week
Done? | ACT | EST | Task
| 6 | 6 | Attend Meetings
| 6 | 6 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## W-Wk9
Winter - Week 9
Accomplished this week
Done? | ACT | EST | Task
| 4 | 4 | Meetings
| 1 | 1 | Design Doc Discussion with jim
| 2 | 1 | Design Doc Review
| 7 | 6 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 4 | Meetings
|  | 4 | TOTAL TIME
Issues

## W-Wk10
Winter - Week 10
Accomplished this week
Done? | ACT | EST | Task
| 4 | 4 | Meetings
| 2 | 2 | Continued Design doc review with jim
| 6 | 6 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 4 | Meetings
|  | 2 | Continued Design doc review with jim
|  | 6 | TOTAL TIME
Issues

## W-Finals
Winter - Finals Week
Accomplished this week
Done? | ACT | EST | Task
| 0 | 4 | Meetings
| 0 | 2 | Continued Design doc review with jim
| 0 | 6 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 4 | Meetings
|  | 2 | Continued Design doc review with jim
|  | 6 | TOTAL TIME
Issues

## S-Wk1
Spring - Week 1
Accomplished this week
Done? | ACT | EST | Task
X | 6 | 4 | Meetings
| 3 | 2 | Continued Design doc review with jim
| 4(and a dead server) | 2 | Install VS 05 service pack on team server
X | 2 |  | Communications Corrections
| 2 | 4 | Auth design
| 13 | 12 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 3 | Finalize design
|  | 4 | Implement User, Users and User Proxy
|  | 4 | Meetings
|  | 4 | Finalize auth design
|  | 15 | TOTAL TIME
Issues
Apparently over the weekend our team server exploded, which is leaving me quite flustered. Thankfully we have backups
Communications issues left our sponsor hanging and us with a opening which the group should not have left open for him.

## S-Wk2
Spring - Week 2
Accomplished this week
Done? | ACT | EST | Task
| 2 | 3 | Finalize design
2 for3 | 4 | 4 | Implement User, Users and User Proxy
X | 3 | 4 | Meetings
|  | 4 | Finalize auth design
| 2 |  | Fix DataUtilities
| 4 | 4 | Fix Database access
| 15 | 19 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Reimplement User and User Proxy
|  | NA | Start on… what ever needs to be done for lesson/courses
|  | 2 | correct design doc
|  | 4 | Meetings
|  | 8 | TOTAL TIME
Issues
Database access through DataUtilities was not actually working
Needed to fix datautilities enumerations
Needed to correct datasource in datautilities connection string
Doesn't sound like much, but when you have no clue what the problem is it takes longer than it should

## S-Wk3
Spring - Week 3
Accomplished this week
Done? | ACT | EST | Task
| 2 | 2 | Reimplement User and User Proxy
|  | NA | Start on… what ever needs to be done for lesson/courses
| 0 | 2 | correct design doc
| 2 | 4 | Meetings
| 4 | 8 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 4 | Reimplement Lesson and course
|  | 3 | work through UI layout
|  | 4 | Meetings
|  | 11 | TOTAL TIME
Issues
Only half the team on Tuesday

## S-Wk4
Spring - Week 4
Accomplished this week
Done? | ACT | EST | Task
| 3 | 4 | Reimplement Lesson and course
| 3 | 3 | work through UI layout
| 2.5 | 4 | Meetings
| 8.5 | 11 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 4 | Make placeholder pages in UI layout
Fix any errors found in user, course or lesson
|  | 4 | Meetings
|  | 8 | TOTAL TIME
Issues

## S-Wk5
Spring - Week 5
Accomplished this week
Done? | ACT | EST | Task
| 2 | 4 | Make placeholder pages in UI layout
| 1 | 2 | Fix any errors found in user, course or lesson
| 4 | 4 | Meetings
| 3 |  | Add Role meaning to Master page
| 10 | 10 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 4 | Create Presentation for Sean
|  | 1 | Present to Sean
|  | 1 | Complete a task listing
|  | 6 | TOTAL TIME
Issues

## S-Wk6
Spring - Week 6
Accomplished this week
Done? | ACT | EST | Task
| 9 | 4 | Create Presentation for Sean
| 1 | 1 | Present to Sean
| 1 | 1 | Complete a task listing
| 11 | 6 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | User WebControl
|  | 2 | Course WebControl
|  | 1 | Quiz Datapage
|  | 2 | Enrollment Page
|  | 1 | Enrolled in Page
|  | 4 | Kick the design document around
|  | 4 | Meetings
|  | 16 | TOTAL TIME
Issues
I was driving myself nuts trying to get our datautilities to work on another system and I had no luck, but in the end I fixed an error with our webconfig that allows for remote access to our website. So we can now roll out any interface improvements to Sean in real time more or less

## S-Wk7
Spring - Week 7
Accomplished this week
Done? | ACT | EST | Task
|  | 2 | User WebControl
|  | 2 | Course WebControl
|  | 1 | Quiz Datapage
|  | 2 | Enrollment Page
|  | 1 | Enrolled in Page
|  | 4 | Kick the design document around
|  | 4 | Meetings
| 0 | 16 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## S-Wk8
Spring - Week 8
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## S-Wk9
Spring - Week 9
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## S-Wk10
Spring - Week 10
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## S-Finals
Spring - Finals Week
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Issues

## Example
Winter - Week 1
Accomplished this week
Done? | ACT | EST | Task
Y | 20 | 30 | Read textbook about version control
Y | 45 | 30 | Set up subversion on my computer
N | 30 | 60 | Design error-handling subsystem
Y | 15 |  | Read good introduction to subversion on web
| 110 | 120 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 30 | Design error-handling subsystem
|  | 120 | Code error-handling subsystem
|  | 150 | TOTAL TIME
Issues
Hard disk on my computer died, had to restore from backup
Team is having trouble finding time to meet together
May need help coding error-handling subsystem