## Gimball3000 Risks
Risk ID | Risk | Description of Risk | Probability (0 - 1) | Impact (low, med, high) | Exposure | Classification | Owner | Mitigation Plan | Management Plan | Status
3 | Inadequate bluetooth experience | None of the team members have an expertise in BLE beacon development, which may take time. | 1 | high | 10 | personnel | Anshul | Developing early prototypes will provide us with areas to learn more on (basically get a head start on beacon development). | Contact the beacon vendor if necessary for addressing specific issues (poor API, etc.). | mitigated
2 | No experience with iOS or Objective-C/Swift for Mobile application | Team members have very limited experience with iOS development | 0.8 | high | 8 | personnel | Tyler | The team members will do individual initial prototyping/testing with iOS development tools and practices, in attempt to get up to speed. | If there is a member that is not as good at iOS developement as required for the project, the team may meet to reorganize and reassign team member roles, to ensure the most knowledgeable team members are doing iOS development | inactive
4 | Difficulty connecting components | Connecting components representind various features may be difficult | 0.65 | high | 6.5 | design & implementation | Anshul | Our team will prototype each individual component and then additionally prototype meaningful pairings/integrations of various components | If the components end up having problems being integrated during the prototype stage, the team member who wrote the component may need to revise their prototype to adjust for the integration. This will provide useful experience for the actual application. If integration issues occur in the official application, the team will first refer to the prototypes, then research the issue and get assistance from other team members or external students/personel if necessary | mitigated
5 | Manufacturing defects in bluetooth beacon | There may be certain issues with the hardware that the team is currently unaware of. | 0.6 | high | 6 | technology | Anshul | Initial prototypes will reveal the strength of thebeacons, and show any defects if any. | Research multiple devices early on (all within the given budget), so that a switch can be made. | mitigated
6 | Choosing inappropriate/inadequate tech stack | The team doesn't have strong experience in mobile development, due to which we may choose an inefficient tech stack. | 0.5 | high | 5 | technology | Anshul | Early research and prototyping will help us better decide ont the technologies. Wisely consulting our coach's expertise will be helpful as well. | Seek advice from someone with expertise in iOS & real-time applications development to realize what went wrong, and how to fix it. | inactive
7 | Swift/Objective-C/iOS dev difficult to pick up | Related to risk 8 (No experience with iOS or Objective-C/Swift for Mobile application). Having no experience my make the development tools/language difficult to pick up | 0.5 | high | 5 | personnel | Tyler | As part of the spiral model, team members will spend time investigating, doing tutorials, and making prototypes with Swift, which will get us acclimated to iOS development. | The team will have the most knowledgeable members do the iOS development | inactive
7 | Difficulty integrating websocket support and backend | Synching up the backend to communicate through websockets to the front end and vice versa may be challenging | 0.5 | high | 5 | design & implementation | Randy | The team will first prototype integrating websockets into the backend to ensure there are as few issues as possible. | If issues occur with websocket integration, the team will refer to the prototype, do research online, and get help from other members or external sources. As a last resort, the team may consider using a method other than websockets for the component. | inactive
8 | Using Objective-C with bluetooth functionality may pose issues with using Swift | Since the bluetooth code is written in Objective-C and the rest of the iOS application is in Swift, there may be some difficulty integrating the two. | 0.5 | high | 5 | design & implementation | Anshul | The team will research how Objective-C and Swift are normally integrated and prototype this integration. | If there are problems, team members handling the integration may call in other team members for aid. If this fails, the team will reach out to SE students who have worked with iOS apps involving both Swift and Objective-C. | inactive
9 | Map tool not precise enough | The mapping tool our team has chosen may not have enough precision to compete and compare with the high level of accuracy tools like map my ride do. | 0.5 | high | 5 | technology | Anshul |  |  | mitigated
10 | No experience/knowledge for storing race map data | No team members have experience with manipulating map data, so this may take extra time. | 0.9 | medium | 4.5 | personnel | Randy | Early research into storing various file types into SQL database. | If map file type cannot be sotred, look into converting map into another file type that can be stored. | inactive
11 | Performance issues with VM | The Virtual Machine we were given may not be able to support the needs of our project in terms of size, load, etc. | 0.4 | high | 4 | technology | Randy | The team cannot do much to mitigate this, since the VM is handed to us by the SE department. | The team will bring up the issue with Kurt to see about any fixes and workarounds that are possible. The team will also let the sponsor and project faculty advisor know of the issue and find any potential fixes through those routes. | active
12 | Too much time documenting work. | The team is required to keep a lot of documentation and time keeping as part of this project, in addition to the tools our team has chosen. Since there is so much, it will take up increasingly more time unless it is managed. | 0.8 | medium | 4 | schedule | Danielle | Our team will attempt to maintain only the minimum reasonable amount of documentation for the project. Team members will also investigate tools and integrations that cross boundaries between tools that reduce the amount of manual work needed to keep documentation up to date. | The team will assess the amount of documentation work periodically. If a team member feels documentation is becoming too excessive or burdensome, the team will try to consolidate documentation and work efforts. | mitigated
13 | Documentation becoming out of sync | Related to the risk above, there is risk that due to having to do so much documentation that it may become out of sync. | 0.8 | medium | 4 | process | Danielle | Related to the mitigation plan for the above risk. The team will investigate tools that integrate documentation across areas like github, google docs, and project managment, in order to ensure everything is up to date and minimize the amount of manual work, thereby minimizing the chance of error and not having time to update docs. | The team will check different areas of the documentation at different times and notice any differences across documentation platforms. If discrepencies keep appearing, the team will re-assess the documentation process. | mitigated
14 | Team members have progressively less time to devote to the project | As the semester progresses, team members may become busy with other classes, meetings, or priorities, leaving less time to work on the project | 0.7 | medium | 3.5 | schedule | Danielle | Team members will attempt to individually manage their time and allocate the SE department suggested amount of 8-12 hours on senior project per week | If a team member begins to have less and less time available for the project, the PM will discuss the issue with them and attempt to resolve their time issues. As a last resort, other team members may temporarily take up some of the work of the preoccupied team member, but this fix should not be permanent. The other team member will be expected to pick back up their work as soon as possible. If a single team member continues to under-perform, they may be rated poorly by their fellow members in reviews and the members may discuss the problem with the faculty advisor. | mitigated
15 | Documentation creep | There is a certain amount of required documentation and other documentation that is required by the spiral methodology. This risk captures the possbility that the team keeps writing more and more documentation in order to capture the project, and that takes away from time to work and increases changes of documenation becoming stale | 0.7 | medium | 3.5 | process | Danielle | The team will attempt to keep documentation down to a minimum in order to reduce time spent on documentation and chance that it will become irrelevant. Documentation will only be done if the team feels it will be beneficial. | If documentation continues increasing, the team will meet and evaluate the documenation to determine which pieces are really necessary/beneficial, and will trim down documentation based on those qualities. The team will then update remaining documentation and come up with a revised management plan | mitigated
16 | Inadequately capturing requirements | Team members may have different understanding of the requirements which will have dominoe affects. | 0.2 | high | 2 | requirements | Danielle | Constant communication with the sponsor in regards to requirements is needed (flush out the initial details as much as possible). | Focus on the software desing to see if it adapts to the new requirements. Else, make appropriate modifications and test the product. | mitigated
17 | Inability to meet deadlines | Our team may be unable to meet deadlines due to poor schedule management or other unpredicated or unmanaged occurences | 0.2 | high | 2 | schedule | Danielle | The team will follow the planned schedule and check progress against the schedule on a weekly basis. | The team will meet to negotiate new deadlines with the sponsor. | mitigated
18 | Too much time spent reviewing one anothers' code | In trying to ensure code quality, our team may end up spending too much time reviewing one others code, which reduces amount of time available to do new feature development and bug fixes | 0.4 | medium | 2 | schedule | Randy | The team has specified and documented a code review process that they will follow. | As a team member starts to feel they are spending too much time reviewing code, they will bring up the issue with the rest of the team, who will meet to discuss this. The team will review the documented code review process and make any modifications as necessary to ensure the process is workable. | mitigated
26 | Spiral iterations don't have enough content | As iterations progress, team members who complete work more quickly or did not take on features of enough complexity/quantity may run out of work to do during the current iteration | 0.4 | medium | 2 | process | Danielle | For items in the requirements document, the team will attempt to divide a given feature into manageable chunks with minimal dependencies in a given iteration. |  | inactive
20 | Project scheduling and risk tracking is too minimal | As the term goes on, the team focuses heavily on development instead of maintaining a schedule and risks. | 0.3 | medium | 1.5 | process | Danielle | Members in charge of documentation will be in contact with the developers. Meetings will be held to review any missing items. | Call a team meeting to include/remove any missing topics. | mitigated
21 | Taking too long to decide on PM tools, technology, and methodology | The team may spend too much time trying to decide on PM tools, methodologies, etc, which will delay project start | 0.3 | medium | 1.5 | schedule | Danielle | Consider using tools the team/PM is familiar with. Limit research to a brief period and then proceed to choose tools/methodologies based on best judgement at the time | If choosing PM tools/methodology for the project start to take more than a week and a half, the team should meet as a unit to decide during a single meeting on tools. | inactive
22 | Scope creep | As there are alot of cool features that can be added, the scope will have to be strictly controlled. Ex - gather various statistics about the biker's trip. | 0.3 | medium | 1.5 | requirements | Randy | The team will avoid asking the project sponsor questions in the form of 'do you want x?', as it will usually lead to the sponsor saying 'yes of course, if you can, that'd be great!'. The team will also manage the requirements document and keep careful track of prioritized requirements. | If scope creep does occur (for example, a new requirement added), the team will discuss the necessity of the new requirement with the sponsor. If the new requirement is desired, requirement priority will be discussed. If it is a new, additional requirement, priority will likely be low (P3). | inactive
23 | Database scalability | The selected database might have issues with scalability | 0.3 | medium | 1.5 | technology | Randy | The selected database for the project will try to be chosen with scalability in mind. | If the database is not scalable enough for the customer, the team will meet with the sponsor to discuss their exact problems and try to find work arounds for the issue. If absolutely necessary, the team may consider changing database systems. | active
24 | Poor estimations (Parkinsons law) | The estimations for our project in general may be off. This includes any priority estimations, and probability and impact estimations | 0.3 | medium | 1.5 | schedule | Danielle | The team will attempt to use best judgement during estimations. Estimations will be reviewed with the rest of the team overall so may eyes can see the current estimations and provide feedback or suggest changes. | If an estimation turns out to be off, the team will discuss why the estimation was off/what occurred. If the problem was an estimation issue, the team may retroactively go back and review other estimations. | inactive
1 | Inadequate domain knowledge | Few of our members have raced in large-scale events similar to the AIDS Red Ribbon Ride this project is aimed at. For this reason, we may not fully understand how SAG vehicles and other operations work. | 0.9 | low | 0.9 | requirements | Anshul | Shadow a similar event if possible. Clarify all arcronyms ahead of time. | Contact the sponsor immediately if a requirement isn't clear. | mitigated | Status values explanation: * active - the risk is a risk that we still need to be aware of and look out for; the mitigation strategy is being followed * inactive - the risk is no longer an issue * mitigated - the risk has an increased chance of occuring and the mitigation plan is being followed * managed - the risk occurred/is occuring and is being actively managed
26 | Poor code documentation | Developers may not document the code effectively which will be a issue when the product is handed over to the sponsor. | 0.4 | low | 0.4 | process | Tyler | The team will create and follow a documented code documentation process. | If there is inadequate documentation, the team will determine if this issue occurs in a single person's commits or over the entire team. If it is a single person, the team will discuss the importance of documentation with them. If it is accross the team, the team will meet to reorganize and document the code, then go over the code documentation process again as a reminder and make any modifications necessary to ensure the process will be followed. | active
27 | Memory issues with iOS application | The iOS application may have issues trying to detect many bluetooth devices passing at once. Particularly surrounding threading and data temporarily local due to loss of network connection | 0.5 | high | 5 | design & implementation | Tyler | The team will test and try our best to optimize any threading and local data necessary. | If memory issues persist, the team will investigate an application modular redesign if that would help with memory issues. The team may also consider doing batch operations or, as a last resort, setting and documenting known application limits | mitigated |  | Impact | Weight
28 | Limited knowledge of UI development in iOS | Developing UIs in iOS can be difficult, particularly since the team has lack of iOS experience and this is a relatively complext application | 0.8 | medium | 4 | personnel | Anshul | The team will do prototypes and read up on tutorials for how to best develop iOS UIs, including best practices and recommendations | The team will consult with colleagues who have more experience in iOS application development if necessary | inactive |  |  | 0
29 | iOS storyboard merge issues | The iOS UI Storyboards may have merge issues if more than one person edits it at a time. As of now, developers find it difficult to resolve these conflicts without needing to start from scratch again. | 0.7 | medium | 3.5 | technology | Anshul | The team will attempt to keep iOS storyboard components as modular as possbile, in order to reduce coupling and resultant merge conflicts | The team may consult with iOS application experts at RIT if conflicts continue to arise, or alternatively may attempt to divide and schedule work so no two people will push changes to the story board at once. | mitigated |  | low | 1
30 |  |  |  |  | 0 | [6 empty] | medium | 5
31 |  |  |  |  | 0 | [6 empty] | high | 10
32 |  |  |  |  | 0
33 |  |  |  |  | 0
34 |  |  |  |  | 0
35 |  |  |  |  | 0
36 |  |  |  |  | 0
37 |  |  |  |  | 0
38 |  |  |  |  | 0
39 |  |  |  |  | 0
40 |  |  |  |  | 0
41 |  |  |  |  | 0
42 |  |  |  |  | 0
43 |  |  |  |  | 0
44 |  |  |  |  | 0
45 |  |  |  |  | 0
46 |  |  |  |  | 0
47 |  |  |  |  | 0
48
49