## Sheet1
Milestones | Estimated Completetion Date | 2006-12-22 | 2007-01-18 | 2007-01-25 | 2007-02-01 | 2007-02-08 | 2007-02-15 | 2007-02-22 | 2007-03-01 | 2007-03-08 | 2007-03-15 | 2007-03-22 | 2007-03-29 | 2007-04-05 | 2007-04-12 | 2007-04-19 | 2007-04-26 | 2007-05-03 | 2007-05-10 | 2007-05-17 | 2007-05-24 | Actual Compleation Date
Project Planning Milestone | 2006-12-22 | 2006-12-22: 2006-12-22; 2007-01-18: 2006-12-22; 2007-01-25: 2006-12-22 | 2006-12-22
Requirments Sign Off Milestone | 2007-01-18 | 2007-01-18 | 2007-01-18 | 2007-01-25 | 2007-01-25 | 2007-01-25 | 2007-01-25 | 2007-01-25 | 2007-01-25 | 2007-01-25 | 2007-01-25 | 2007-01-25 | 2007-01-25 | 2007-01-25 | 2007-01-25 | 2007-01-25 | 2007-01-25 | 2007-01-25 | 2007-01-25 | 2007-01-25 | 2007-01-25
Design Milestone | 2007-02-01 | 2007-02-01 | 2007-02-01 | 2007-02-12 | 2007-02-12 | 2007-02-12 | 2007-02-12 | 2007-02-12 | 2007-02-12 | 2007-02-12 | 2007-02-12 | 2007-02-12 | 2007-02-12 | 2007-02-12 | 2007-02-12 | 2007-02-12 | 2007-02-12 | 2007-02-12 | 2007-02-12 | 2007-02-12 | 2007-02-12
Acc. Testing Sign Off Milestone | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-15 | 2007-02-15 | 2007-02-15 | 2007-02-15 | 2007-02-15 | 2007-02-15 | 2007-02-15 | 2007-02-15 | 2007-02-15 | 2007-02-15 | 2007-02-15 | 2007-02-15 | 2007-02-15 | 2007-02-15 | 2007-02-15 | 2007-02-15 | 2007-02-15 | 2007-02-15
Implementation Inc. #1 Milstone | 2007-02-22 | 2007-02-22 | 2007-02-22 | 2007-03-01 | 2007-03-01 | 2007-03-01 | 2007-03-01 | 2007-03-01 | 2007-03-01 | 2007-03-01 | 2007-03-01 | 2007-03-01 | 2007-03-01 | 2007-03-01 | 2007-03-01 | 2007-03-01 | 2007-03-01 | 2007-03-01 | 2007-03-01 | 2007-03-01 | 2007-03-01
Implementation Inc. #2 Milstone | 2007-03-22 | 2007-03-22 | 2007-03-22 | 2007-03-29 | 2007-03-29 | 2007-03-29 | 2007-03-29 | 2007-03-29 | 2007-03-29 | 2007-03-29 | 2007-03-29 | 2007-03-29 | 2007-03-29 | 2007-03-29 | 2007-03-29 | 2007-03-29 | 2007-03-29 | 2007-03-29 | 2007-03-29 | 2007-03-29 | 2007-03-29
Implementation Inc. #3 Milstone | 2007-04-05 | 2007-04-05 | 2007-04-05 | 2007-04-12 | 2007-04-12 | 2007-04-12 | 2007-04-12 | 2007-04-12 | 2007-04-12 | 2007-04-12 | 2007-04-12 | 2007-04-12 | 2007-04-12 | 2007-04-12 | 2007-04-12 | 2007-04-12 | 2007-04-12 | 2007-04-12 | 2007-04-12 | 2007-04-12 | 2007-04-12
Verification Milestone | 2007-04-26 | 2007-04-26 | 2007-04-26 | 2007-05-03 | 2007-05-03 | 2007-05-03 | 2007-05-03 | 2007-05-03 | 2007-05-03 | 2007-05-03 | 2007-05-03 | 2007-05-03 | 2007-05-03 | 2007-05-03 | 2007-05-03 | 2007-05-03 | 2007-05-03 | 2007-05-03 | 2007-05-03 | 2007-05-03 | 2007-05-03
Acceptance Testing Milestone | 2007-05-10 | 2007-05-10 | 2007-05-10 | 2007-05-17 | 2007-05-17 | 2007-05-17 | 2007-05-17 | 2007-05-17 | 2007-05-17 | 2007-05-17 | 2007-05-17 | 2007-05-17 | 2007-05-17 | 2007-05-17 | 2007-05-17 | 2007-05-17 | 2007-05-17 | 2007-05-17 | 2007-05-17 | 2007-05-17 | 2007-05-17

## Sheet2
Project Planning Milestone
Plan and design the initial release of the following documents: Feature List, GUI Storyboard, Team Website
Risk Management Plan, Project Schedule, Project Plan. Also establish meeting times for both the team and the sponsor.
Requirments Sign Off Milestone
Create the baseline version of the System Requirements document and acquire the sponsor’s sign off on that document.
Design Milestone
Develop and design the baseline version of the System Architecture. This is to include, but is not limited
to: A Class Diagram of the entire system including all interactions between each class, a sequence diagram for all
identified risk areas, and a mapping of requirements to each object(s) that will be used to implement them.
Acc. Testing Sign Off Milestone
Create the baseline version of the Acceptance Test document and acquire the sponsor’s sign off on that document. Also create
a unit and integration test plan for the implementation portion of the project.
Implementation Inc. #1 Milstone
All of the code will be generated, tested, and functional to implement the following requirements:
1.1, 1.1.1, 1.1.2, 1.1.2.1, 1.1.2.2, 1.1.2.3, 1.1.3, 1.1.4, 1.1.4.1, 1.2, 1.2.1, 2.1, 2.1.1, 2.1.4, 2.3, 2.4, 3.1, 3.1.1, 3.1.2, 3.1.3, 3.2,
3.2.2, 3.2.3, 3.4, 3.4.3, 4.1, 4.1.1, 4.1.3, 4.4.5, 4.5, 4.5.1, 5.1, 5.1.1, 5.1.2, 5.2, 5.2.1
Implementation Inc. #2 Milstone
All of the code will be generated, tested, and functional to implement the following requirements:
1.2.1.1, 1.2.2, 2.1.2, 2.1.3, 2.1.3.1, 2.1.5, 2.1.5.1, 2.1.5.2, 3.2.1, 3.3, 3.4.1, 3.4.2, 3.6, 3.6.1, 3.7, 3.7.1, 3.7.2, 3.9, 3.9.1, 3.9.1.1,
4.1.2, 4.1.2.1, 4.1.2.2, 4.2, 4.2.1, 4.4, 4.4.1, 4.4.2, 4.5.2, 4.5.3, 5.3, 5.3.1, 5.3.2, 7.1, 7.1.1, 7.1.2, 7.1.3, 7.1.4, 7.1.4.1, 7.2,
7.2.1, 7.3, 7.3.1
Implementation Inc. #3 Milstone
All of the code will be generated, tested, and functional to implement the following requirements:
2.2, 2.2.1, 2.2.2, 2.2.2.1, 2.2.2.2, 2.2.2.3, 2.2.2.4, 3.5, 3.5.1, 3.5.2, 3.5.3, 3.7.3, 3.7.4, 3.8, 3.8.1, 3.8.2, 3.8.3, 3.8.3.1, 3.8.4,
3.8.4.1, 3.8.5, 3.8.5.1, 3.8.6, 3.8.7, 3.8.8, 3.8.8.1, 3.8.9, 4.3, 4.3.1, 4.3.2, 4.3.3, 4.4.3, 4.4.4, 4.4.6, 4.4.6.1, 4.4.6.2, 6.1, 6.2, 6.3,
6.4, 6.4.1, 6.4.2, 6.4.3, 6.4.3.1, 6.5, 6.5.1, 6.5.2, 6.6, 6.6.1, 6.7, 6.7.1, 6.7.2, 6.8, 6.8.1, 6.8.2, 6.9, 6.9.1, 6.9.2, 8.1,
8.1.1, 8.1.1.1, 8.1.2, 8.2, 8.3, 8.4, 8.5
Verification Milestone
All bugs will be worked out and the system will pass 100% of the acceptance tests that where signed-off by the sponsor, with
the exception of any acceptance tests that where agreed to be dropped by the sponsor. Also any and all training documents
are completed.
Acceptance Testing Milestone
The sponsor completes acceptance testing and passes 100% of the acceptance tests, except for any that where previously agreed
to not be tested, and signs off on the finalized system.