## Sheet1
Slippage |  | Earned Value |  |  |  | Estimation
Planned Completion (#Sprint) | Completed Sprint | Week Completed | # of Points | Item | Sum of Points | Estimated Team (hours) | Actual Team (hours) | Accuracy | Type of Activiity | Notes
0 | 0 | 1 | 2 | Week 1 Meeting (customer) | 2 | 2 | 2 | 1 | Customer Interaction
0 | 0 | 2 | 2 | Initial Website | 4 | 1 | 1 | 1 | Documentation
0 | 0 | 2 | 2 | Week 2 Meeting (customer) | 6 | 2 | 2 | 1 | Customer Interaction
0 | 0 | 3 | 5 | Project Plan (draft) | 11 | 2 | 3 | 1.5 | Documentation
0 | 0 | 3 | 2 | Week 3 Meeting (customer) | 13 | 2 | 2 | 1 | Customer Interaction
1 | 1 | 4 | 5 | Diagram of Services (draft) | 18 | 1.5 | 2 | 1.3333 | Documentation
1 | 1 | 4 | 5 | Project Plan (finished) | 23 | 2 | 4 | 2 | Documentation
1 | 1 | 4 | 2 | Week 4 Meeting (customer) | 25 | 2 | 2 | 1 | Customer Interaction
1 | 1 | 5 | 5 | Use case document (draft) | 30 | 4 | 6 | 1.5 | Documentation
1 | 1 | 5 | 2 | Week 5 Meeting (customer) | 32 | 2 | 2 | 1 | Customer Interaction | Originally conceived as towards the end but happened as a result of Thursdays meeting
n/a | 1 | 5 | 3 | User Interview | 35 | 2 | 2 | 1 | Customer Interaction | Moved back the Sprint Due Date By 2 Days to go until Sunday
1 | 2 | 6 | 5 | SCRUM document | 40 | 2 | 2 | 1 | Design | Worked on the archtecture before completing the SRS
2 | 2 | 6 | 2 | Week 6 Meeting (customer) | 42 | 2 | 2 | 1 | Customer Interaction
3 | 2 | 6 | 5 | Architecture Document (draft) | 47 | 3 | 3 | 1 | Design | Was concidered to be done, but made a point to get it done correctly.
2 | 2 | 7 | 5 | Diagram of Services (finished) | 52 | 2 | 2 | 1 | Design
2 | 2 | 7 | 2 | Week 7 Meeting (customer) | 54 | 2 | 2 | 1 | Customer Interaction
3 | 2 | 7 | 5 | Architecture Document (finished) | 59 | 3 | 4 | 1.3333 | Design
2 | 3 | 8 | 5 | Requirements Document (draft) | 64 | 3 | 3 | 1 | Requirements
3 | 3 | 8 | 2 | Week 8 Meeting (customer) | 66 | 2 | 2 | 1 | Customer Interaction
2 | 3 | 9 | 5 | Requirements Document (finished) | 71 | 3 | 6 | 2 | Requirements
3 | 3 | 9 | 5 | First Quarter Presentation Documents | 76 | 3 | 5 | 1.6667 | Documentation
3 | 3 | 9 | 5 | First Quarter Presentation | 81 | 4 | 6 | 1.5 | Documentation
3 | 3 | 10 | 2 | Week 10 Meeting (customer) | 83 | 2 | 2 | 1 | Customer Interaction
2 |  |  | 5 | Use case document (finished) | 88 | 2 | 3 | 1.5 | Documentation
4 |  |  | 2 | Week 11 Meeting (customer) / Dan P. | 90 | 1 |  | 0 | Customer Interaction
5 |  |  | 15 | Primary Query Services Setup | 105 | 3 | 4 | 1.3333 | Implementation
5 |  |  | 1 | Week 12 Meeting (customer) | 106 | 2 |  | 0 | Customer Interaction
5 |  |  | 1 | Week 13 Meeting (customer) | 107 | 2 |  | 0 | Customer Interaction
5 |  |  | 1 | Week 14 Meeting (customer) | 108 | 2 |  | 0 | Customer Interaction
5 |  |  | 1 | REQ-1.1: verify and validate and identify client | 109
5 |  |  | 1 | REQ-1.2: get all majors | 110
5 |  |  | 1 | REQ-1.3: get all colleges | 111
5 |  |  | 1 | REQ-1.4: get all job types | 112
5 |  |  | 1 | REQ-1.6: get all locations (state/regions) | 113
5 |  |  | 1 | REQ-1.7: get all OCECS regions (from regions table) | 114
5 |  |  | 1 | REQ-1.8: get quarters | 115
5 |  |  | 1 | REQ-1.9: get month/quarter mapping | 116
5 |  |  | 1 | REQ-2.1: filter student records by a start and end quarters (inclusive start and end). | 117
5 |  |  | 1 | REQ-2.2: filter by job types | 118
5 |  |  | 1 | REQ-2.3: filter students by gender | 119
5 |  |  | 1 | REQ-2.4: filter by major(s) - can select multiple majors to query | 120
5 |  |  | 1 | REQ-2.5: filter by only NTID students | 121
5 |  |  | 1 | REQ-2.6: filter by only International students | 122
5 |  |  | 1 | ERQ-2.7: filter by students search status | 123
5 |  |  | 1 | REQ-2.8: return report of only placed students | 124
5 |  |  | 1 | REQ-2.9: return report of active, but not placed students | 125
5 |  |  | 1 | REQ-2.10: return report of all students matching criteria | 126
5 |  |  | 1 | REQ-2.11: search for single student by first name | 127
5 |  |  | 1 | REQ-2.12: search for single student by last name | 128
6 |  |  | 15 | Prototype of New Front End | 143 |  |  | #DIV/0! | Implementation
6 |  |  | 1 | Week 15 Meeting (customer) | 144 | 2 |  | 0 | Customer Interaction
6 |  |  | 1 | Week 16 Meeting (customer) | 145 | 2 |  | 0 | Customer Interaction
6 |  |  | 1 | Week 17 Meeting (customer) | 146 | 2 |  | 0 | Customer Interaction
6 |  |  | 1 | REQ-2.13: search for single student by UID | 147
6 |  |  | 1 | REQ-2.14: get a student’s registration history | 148
6 |  |  | 1 | REQ-2.15: provide all reports in simple XML format | 149
6 |  |  | 1 | REQ-3.1: get all companies | 150
6 |  |  | 1 | REQ-3.2: get all account managers | 151
6 |  |  | 1 | REQ-3.3: filter current employers with postings by start and end quarters | 152
6 |  |  | 1 | REQ-3.4: filter by employers outside of the U.S | 153
6 |  |  | 1 | REQ-3.5: filter employers with job postings by job types | 154
6 |  |  | 1 | REQ-3.6: filter employers with job postings by location(state) | 155
6 |  |  | 1 | REQ-3.7: filter employer by account manager | 156
6 |  |  | 1 | REQ-3.8: filter employers with postings by major(s) | 157
6 |  |  | 1 | REQ-3.9: filter employers with postings by college(s) | 158
6 |  |  | 1 | REQ-3.10: return report of employers with postings (show info including contact) | 159
6 |  |  | 1 | REQ-3.11: get postings of a employer | 160
6 |  |  | 1 | REQ-3.12: get referrals for specific posting | 161
6 |  |  | 1 | REQ-3.13: search for employer by name | 162
6 |  |  | 1 | REQ-3.14: search for employer by account manager | 163
6 |  |  | 1 | REQ-3.15: search for employer by contact | 164
6 |  |  | 1 | REQ-3.15: filter employer by region | 165
6 |  |  | 1 | REQ-3.16: filter employer by city/state | 166
6 |  |  | 1 | REQ-3.17: filter employer by zip code | 167
6 |  |  | 1 | REQ-3.18: provide all reports in simple XML format | 168
6 |  |  | 1 | REQ-4.1: filter placements by start and end quarters | 169
6 |  |  | 1 | REQ-4.2: filter by international placements | 170
6 |  |  | 1 | REQ-4.3: filter placements with international students | 171
6 |  |  | 1 | REQ-4.4: filter placements with international students working in home country | 172
6 |  |  | 1 | REQ-4.5: filter placements with NTID students | 173
6 |  |  | 1 | REQ-4.6: filter placements by location (state/region) | 174
6 |  |  | 1 | REQ-4.7: filter placements by job type | 175
6 |  |  | 1 | REQ-4.8: filter placements by major(s) | 176
6 |  |  | 1 | REQ-4.9: filter placements by college(s) | 177
6 |  |  | 1 | REQ-4.10: return report of placements from employer perspective | 178
6 |  |  | 1 | REQ-4.11: return report of placements from student perspective(show SIS status) | 179
6 |  |  | 1 | REQ-4.12: provide all reports in simple XML format | 180
6 |  |  | 1 | REQ-5.1: get all possible activity types | 181
6 |  |  | 1 | REQ-5.2: filter activity records by start and end quarters | 182
6 |  |  | 1 | REQ-5.3: filter activity records by single activity | 183
6 |  |  | 1 | REQ-5.4: filter activity records by major(s) | 184
6 |  |  | 1 | REQ-5.5: return report of student’s activity by UID | 185
6 |  |  | 1 | REQ-5.6: return report of activity records grouped by activity type | 186
6 |  |  | 1 | REQ-5.7: return report of activity records grouped by college | 187
6 |  |  | 1 | REQ-5.8: return report of activity records grouped by major | 188
6 |  |  | 1 | REQ-5.9: return report of activity records grouped by quarter | 189
6 |  |  | 1 | REQ-5.10: return report of activity records grouped by month | 190
6 |  |  | 1 | REQ-5.11: return report of activity records grouped by office visit reason | 191
6 |  |  | 1 | REQ-5.12: return report of activity records grouped by student name | 192
6 |  |  | 1 | REQ-5.13: return report of activity records grouped by company | 193
6 |  |  | 1 | REQ-5.14: return report of student job activities | 194
6 |  |  | 1 | REQ-5.15: return report of all matching activity records | 195
7 |  |  | 5 | Second Quarter Presentation | 200 |  |  | #DIV/0! | Documentation
7 |  |  | 5 | Second Quarter Presentation Documents | 205 |  |  | #DIV/0! | Documentation
7 |  |  | 10 | Testing Stage: Testing of All Services | 215 |  |  | #DIV/0! | Testing
7 |  |  | 2 | Week 18 Meeting (customer) | 217 | 2 |  | 0 | Customer Interaction
7 |  |  | 2 | Week 20 Meeting (customer) / Dan P. | 219 | 2 |  | 0 | Customer Interaction
1.2778