## Release Plan
Sprint Plan
Sprint | Start | Days | End | Size | Status | Release Date | Goal | Increment
1 | 2011-12-05 | 18 | 2011-12-22 | 1 | Released |  | Planning
2 | 2012-01-07 | 13 | 2012-01-19 | 16 | Released |  | High level design and document drafts | 1
3 | 2012-01-20 | 16 | 2012-02-04 | 11 | Released |  | In depth documentation and design | 1
4 | 2012-02-05 | 21 | 2012-02-25 | 13 | Planned |  | Design, documentation and interim presentation | 1
5 | 2012-02-26 | 14 | 2012-03-10 | 0 | Planned |  | Implementation and testing | 2
6 | 2012-03-11 | 21 | 2012-03-31 | 38 | Planned |  | Implementation, testing and documentation | 2
7 | 2012-04-01 | 21 | 2012-04-21 | 38 | Planned |  | Release | 2
|  |  | Unallocated stories | 5
Formulas:
End = IF(AND([Start]<>"",[Days]<>""),[Start]+[Days]-1,"")
Start = IF(AND([Start, row above]<>"",[Days, row above]<>"",[Days]<>""),[Start, row above]+[Days, row above],"")

## Product Backlog
Product Backlog
Story ID | Story name | Status | Size | Sprint | Priority | Comments
1 | Architecture document | Done | 3 | 2
2 | Use cases / stories | Ongoing | 5 | 2
3 | Metrics | Ongoing | 3 | 2
4 | Layer interface | Ongoing | 8 | 3 |  | e.g. XML structure, security contract, etc
5 | Class design | Ongoing | 5 | 3
6 | Research | Done | 10 | 1
7 | SE tasks | Ongoing | 10 | 1
8 | Testing | Ongoing | 5
9 | REQ-1.1: verify and validate and identify client | Planned | 2 | 5
10 | REQ-1.2: get all majors | Planned | 2 | 5
11 | REQ-1.3: get all colleges | Planned | 2 | 5
12 | REQ-1.4: get all job types | Planned | 2 | 5
13 | REQ-1.6: get all locations (state/regions) | Planned | 2 | 5
14 | REQ-1.7: get all OCECS regions (from regions table) | Planned | 2 | 5
15 | REQ-1.8: get quarters | Planned | 2 | 5
16 | REQ-1.9: get month/quarter mapping | Planned | 2 | 5
17 | REQ-2.1: filter student records by a start and end quarters (inclusive start and end). | Planned | 2 | 5
18 | REQ-2.2: filter by job types | Planned | 2 | 5
19 | REQ-2.3: filter students by gender | Planned | 2 | 5
20 | REQ-2.4: filter by major(s) - can select multiple majors to query | Planned | 2 | 5
21 | REQ-2.5: filter by only NTID students | Planned | 2 | 5
22 | REQ-2.6: filter by only International students | Planned | 2 | 5
23 | ERQ-2.7: filter by students search status | Planned | 2 | 5
24 | REQ-2.8: return report of only placed students | Planned | 2 | 5
25 | REQ-2.9: return report of active, but not placed students | Planned | 2 | 5
26 | REQ-2.10: return report of all students matching criteria | Planned | 2 | 5
27 | REQ-2.11: search for single student by first name | Planned | 2 | 5
28 | REQ-2.12: search for single student by last name | Planned | 2 | 6
29 | REQ-2.13: search for single student by UID | Planned | 2 | 6
30 | REQ-2.14: get a student’s registration history | Planned | 2 | 6
31 | REQ-2.15: provide all reports in simple XML format | Planned | 2 | 6
32 | REQ-3.1: get all companies | Planned | 2 | 6
33 | REQ-3.2: get all account managers | Planned | 2 | 6
34 | REQ-3.3: filter current employers with postings by start and end quarters | Planned | 2 | 6
35 | REQ-3.4: filter by employers outside of the U.S | Planned | 2 | 6
36 | REQ-3.5: filter employers with job postings by job types | Planned | 2 | 6
37 | REQ-3.6: filter employers with job postings by location(state) | Planned | 2 | 6
38 | REQ-3.7: filter employer by account manager | Planned | 2 | 6
39 | REQ-3.8: filter employers with postings by major(s) | Planned | 2 | 6
40 | REQ-3.9: filter employers with postings by college(s) | Planned | 2 | 6
41 | REQ-3.10: return report of employers with postings (show info including contact) | Planned | 2 | 6
42 | REQ-3.11: get postings of a employer | Planned | 2 | 6
43 | REQ-3.12: get referrals for specific posting | Planned | 2 | 6
44 | REQ-3.13: search for employer by name | Planned | 2 | 6
45 | REQ-3.14: search for employer by account manager | Planned | 2 | 6
46 | REQ-3.15: search for employer by contact | Planned | 2 | 6
47 | REQ-3.15: filter employer by region | Planned | 2 | 6
48 | REQ-3.16: filter employer by city/state | Planned | 2 | 6
49 | REQ-3.17: filter employer by zip code | Planned | 2 | 6
50 | REQ-3.18: provide all reports in simple XML format | Planned | 2 | 6
51 | REQ-4.1: filter placements by start and end quarters | Planned | 2 | 6
52 | REQ-4.2: filter by international placements | Planned | 2 | 6
53 | REQ-4.3: filter placements with international students | Planned | 2 | 6
54 | REQ-4.4: filter placements with international students working in home country | Planned | 2 | 6
55 | REQ-4.5: filter placements with NTID students | Planned | 2 | 6
56 | REQ-4.6: filter placements by location (state/region) | Planned | 2 | 6
57 | REQ-4.7: filter placements by job type | Planned | 2 | 6
58 | REQ-4.8: filter placements by major(s) | Planned | 2 | 6
59 | REQ-4.9: filter placements by college(s) | Planned | 2 | 6
60 | REQ-4.10: return report of placements from employer perspective | Planned | 2 | 6
61 | REQ-4.11: return report of placements from student perspective(show SIS status) | Planned | 2 | 6
62 | REQ-4.12: provide all reports in simple XML format | Planned | 2 | 6
63 | REQ-5.1: get all possible activity types | Planned | 2 | 6
64 | REQ-5.2: filter activity records by start and end quarters | Planned | 2 | 6
65 | REQ-5.3: filter activity records by single activity | Planned | 2 | 6
66 | REQ-5.4: filter activity records by major(s) | Planned | 2 | 6
67 | REQ-5.5: return report of student’s activity by UID | Planned | 2 | 6
68 | REQ-5.6: return report of activity records grouped by activity type | Planned | 2 | 6
69 | REQ-5.7: return report of activity records grouped by college | Planned | 2 | 6
70 | REQ-5.8: return report of activity records grouped by major | Planned | 2 | 6
71 | REQ-5.9: return report of activity records grouped by quarter | Planned | 2 | 6
72 | REQ-5.10: return report of activity records grouped by month | Planned | 2 | 6
73 | REQ-5.11: return report of activity records grouped by office visit reason | Planned | 2 | 6
74 | REQ-5.12: return report of activity records grouped by student name | Planned | 2 | 6
75 | REQ-5.13: return report of activity records grouped by company | Planned | 2 | 6
76 | REQ-5.14: return report of student job activities | Planned | 2 | 6
77 | REQ-5.15: return report of all matching activity records | Planned | 2 | 6
Note on D4: Story Points or Ideal Days
Note on A4: Once a Story ID is given to a story, do not change that number or reuse it even if you delete the story.
Note on C4: Use the following statuses: Planned (or empty) Ongoing Done Removed The sheet uses the above statuses in the formatting and calculation formulas.
Note on E4: Create a release plan by assigning stories to planned sprints. If there are more stories in the backlog than in the plan, leave the remaining stories unassigned to sprints.
Note on F4: You may assign priorities to the stories, but keep in mind that priority does not always equal implementation order.

## PB Burndown
Product Backlog Burndown Chart
Original planned size |  |  | 137 |  | Sprint count | 5
Count trend from last |  |  | 3 | sprints | Trend sprint count | 3
[5 empty] | Trend offset | 0 | [9 empty] | Note:
Velocity (points per sprint) |  |  |  |  | Sprints in Trend | 3 | [9 empty] | In this chart, the tops of the bars show the amount of actual
Original estimate |  |  | 30 | [12 empty] | (or planned) implemented functionality at the beginning of each sprint.
3 |  |  | 25 | [12 empty] | The bottoms of the bars show the changes in project scope
Realized total average |  |  | 25 |  | Trend count | 7 | [9 empty] | (i.e. if the amount of story points
Average last 8 |  |  | 25 | [12 empty] | in the project increases, the bottoms move lower). The length
Avg. worst 3 in last 8 |  |  | 25 | [12 empty] | of the bars indicate the estimated size of the project at the
Trend |  |  | 25 | [12 empty] | beginning of each sprint.
[5 empty] | These hidden cells are used to draw the graph on this page. DO NOT DELETE! | [10 empty] | The red line indicates the current planned scope.
Predictions - Completion at the end of sprint…
Original estimate - Min |  |  | 3
Original estimate - Avg |  |  | 5
Original estimate - Max |  |  | 8 |  | Standard Dev. | 2.8284
3 |  |  | 6
Realized average |  |  | 6 |  | LastPlanned | 28
Average last 8 |  |  | 6 |  | LastRealized | 0
Avg. worst 3 in last 8 |  |  | 6
Trend |  |  | 6
Realized + St. Dev |  |  | 6
Realized - St. Dev |  |  | 6
[5 empty] | Trend | [7 empty] | Average Speeds
Sprint | Remain.Work | Planned Work | Realized Work | Current Total Size | Col top | Do not delete… |  | Col bottom | Trend Help | Raw Trend | Real Trend | Current Bottom | Realized | Last 8 | Worst 3 in Last 8
1 | 137 | 23 | 23 | 137 | 137 | 137 | 0 | 0 | 137 | 137.6667 | 137.6667 | 0 | 25 | 25 | 25
2 | 114 | 29 | 27 | 137 | 114 | 114 | 0 | 0 | 114 | 112.6667 | 112.6667 | 0 | 25 | 25 | 25
3 | 87 | 31 |  | 137 | 87 | 87 | 0 | 0 | 87 | 87.6667 | 87.6667 | 0 | 25 | 25 | 25
4 | 56 | 28 |  | 137 | 0 | 0 | 56 | 56 | 56 | 62.6667 | 62.6667 | 0 | 25 | 25 | 25
5 | 28 | 28 |  | 137 | 0 | 0 | 28 | 28 | 28 | 37.6667 | 37.6667 | 0 | 25 | 25 | 25
6 | [9 empty] | 12.6667 | 12.6667 | 0 | 25 | 25 | 25
7 | [9 empty] | 0 | 0 | 0 | 25 | 25 | 25
[10 empty] | #VALUE! | #VALUE! | 0 | 25 | 25 | 25
[10 empty] | #VALUE! | #VALUE! | 0 | 25 | 25 | 25
[10 empty] | #VALUE! | #VALUE! | 0 | 25 | 25 | 25
[10 empty] | #VALUE! | #VALUE! | 0 | 25 | 25 | 25
[10 empty] | #VALUE! | #VALUE! | 0 | 25 | 25 | 25
[10 empty] | #VALUE! | #VALUE! | 0 | 25 | 25 | 25
[10 empty] | #VALUE! | #VALUE! | 0 | 25 | 25 | 25
[10 empty] | #VALUE! | #VALUE! | 0 | 25 | 25 | 25
[10 empty] | #VALUE! | #VALUE! | 0 | 25 | 25 | 25
[10 empty] | #VALUE! | #VALUE! | 0 | 25 | 25 | 25
[10 empty] | #VALUE! | #VALUE! | 0 | 25 | 25 | 25
[10 empty] | #VALUE! | #VALUE! | 0 | 25 | 25 | 25
[10 empty] | #VALUE! | #VALUE! | 0 | 25 | 25 | 25
[10 empty] | #VALUE! | #VALUE! | 0 | 25 | 25 | 25
[10 empty] | #VALUE! | #VALUE! | 0 | 25 | 25 | 25
[10 empty] | #VALUE! | #VALUE! | 0 | 25 | 25 | 25
[10 empty] | #VALUE! | #VALUE! | 0 | 25 | 25 | 25
Note on B17: Average estimate * 1,6
Note on B15: Average estimate * 0,6
Note on B19: As of latest Product Backlog estimate

## Sp1
1
Sprint implementation days | 5 |  |  | Effort | Remaining on implementation day…
Trend calculated based on last | 5 | Days | Totals | 5 | 5 | 2
Task rows | 1 | Done days | 2 |  | 5 | 4 | 3 | 2 | 1
Warning! These are necessary |  | Trend |  |  | 5 | 2
template rows |  | Trend Days | 2 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Task name | Story ID | Responsible | Status | Est. | 5 1: 1; 2 2: 2; 2 3: 3; 2 4: 4; 2 5: 5
Study and comprehend system and technologies needed | 6 | Team | Done | 5 | 5 1: 5; 2 2: 2; 2 3: 0
Note on A9: Count only active working and implementation days. Do not include Planning Day or Sprint Review. E.g. a 4-week Sprint would most likely have 18 implementation days.

## Sp2
2
Sprint implementation days | 13 |  |  | Effort | Remaining on implementation day…
Trend calculated based on last | 5 | Days | Totals | 12 | 12 | 9 | 2 | 2
Task rows | 2 | Done days | 4 |  | 12 | 11.0769 | 10.1538 | 9.2308 | 8.3077 | 7.3846 | 6.4615 | 5.5385 | 4.6154 | 3.6923 | 2.7692 | 1.8462 | 0.92308
Warning! These are necessary |  | Trend |  |  | 11.8 | 8.1 | 4.4 | 0.7
template rows |  | Trend Days | 4 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Task name | Story ID | Responsible | Status | Est. | 11.8 1: 1; 8.1 2: 2; 4.4 3: 3; 0.7 4: 4; 0.7 5: 5; 0.7 6: 6; 0.7 7: 7; 0.7 8: 8; 0.7 9: 9; 0.7 10: 10; 0.7 11: 11; 0.7 12: 12; 0.7 13: 13
Create draft high level architecture | 2 | Mike | Done | 5 | 11.8 1: 5; 8.1 2: 2; 4.4 3: 0
Write primary flow/activity diagrams | 2 | Team | Done | 7 | 11.8 1: 7; 8.1 2: 7; 4.4 3: 2; 0.7 4: 2
Note on A9: Count only active working and implementation days. Do not include Planning Day or Sprint Review. E.g. a 4-week Sprint would most likely have 18 implementation days.

## Sp3
3
Sprint implementation in weeks | 2 |  |  | Effort | Remaining on implementation day…
Trend calculated based on last | 5 | Days | Totals | 20 | 20 | 8
Task rows | 8 | Done days | 2 |  | 20 | 10
Warning! These are necessary |  | Trend |  |  | 20 | 8
template rows |  | Trend Days | 2 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Task name | Story ID | Responsible | Status | Est. | 20 1: 1; 8 2: 2
Architecture document | 1 | Mike | Done | 5 | 20 1: 5; 8 2: 2; 8 3: 0
Class diagram | 5 | Chris | Ongoing | 5 | 20 1: 5; 8 2: 2; 8 3: 0
Metrics document | 3 | Dan | Ongoing | 5 | 20 1: 5; 8 2: 2; 8 3: 0
Use case document | 2 | Juan | Ongoing | 5 | 20 1: 5; 8 2: 2; 8 3: 0
Presentation | 7 | Mike | Done
Presentation | 7 | Dan | Done
Presentation | 7 | Chris | Done
Presentation | 7 | Juan | Done
Note on A9: Count only active working and implementation days. Do not include Planning Day or Sprint Review. E.g. a 4-week Sprint would most likely have 18 implementation days.

## Sp4
1
Sprint implementation days | 5 |  |  | Effort | Remaining on implementation day…
Trend calculated based on last | 5 | Days | Totals | 0 | 0
Task rows | 4 | Done days | 1 |  | 0 | 0 | 0 | 0 | 0
Warning! These are necessary |  | Trend |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
template rows |  | Trend Days | 1 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Task name | Story ID | Responsible | Status | Est. | 1: 1; 2: 2; 3: 3; 4: 4; 5: 5
Use cases | 2 | Team | Ongoing
Testing document | 8 | Chris | Ongoing
Metrics | 3 | Dan | Ongoing
Update website | 7 | Mike | Ongoing
Note on A9: Count only active working and implementation days. Do not include Planning Day or Sprint Review. E.g. a 4-week Sprint would most likely have 18 implementation days.

## Sp5
1
Sprint implementation weeks | 3 |  |  | Effort | Remaining on implementation week…
Trend calculated based on last | 5 | Days | Totals | 0 | 0
Task rows | 19 | Done days | 1 |  | 0 | 0 | 0
Warning! These are necessary |  | Trend |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
template rows |  | Trend Days | 1 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Task name | Story ID | Responsible | Status | Est. | 1: 1; 2: 2; 3: 3
REQ-1.1: verify and validate and identify client | 9 |  | Planned
REQ-1.2: get all majors | 10 |  | Planned
REQ-1.3: get all colleges | 11 |  | Planned
REQ-1.4: get all job types | 12 |  | Planned
REQ-1.6: get all locations (state/regions) | 13 |  | Planned
REQ-1.7: get all OCECS regions (from regions table) | 14 |  | Planned
REQ-1.8: get quarters | 15 |  | Planned
REQ-1.9: get month/quarter mapping | 16 |  | Planned
REQ-2.1: filter student records by a start and end quarters (inclusive start and end). | 17 |  | Planned
REQ-2.2: filter by job types | 18 |  | Planned
REQ-2.3: filter students by gender | 19 |  | Planned
REQ-2.4: filter by major(s) - can select multiple majors to query | 20 |  | Planned
REQ-2.5: filter by only NTID students | 21 |  | Planned
REQ-2.6: filter by only International students | 22 |  | Planned
ERQ-2.7: filter by students search status | 23 |  | Planned
REQ-2.8: return report of only placed students | 24 |  | Planned
REQ-2.9: return report of active, but not placed students | 25 |  | Planned
REQ-2.10: return report of all students matching criteria | 26 |  | Planned
REQ-2.11: search for single student by first name | 27 |  | Planned
Note on A9: Count only active working and implementation days. Do not include Planning Day or Sprint Review. E.g. a 4-week Sprint would most likely have 18 implementation days.

## Sp6
1
Sprint implementation weeks | 3 |  |  | Effort | Remaining on implementation week…
Trend calculated based on last | 5 | Days | Totals | 0 | 0
Task rows | 50 | Done days | 1 |  | 0 | 0 | 0
Warning! These are necessary |  | Trend |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
template rows |  | Trend Days | 1 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Task name | Story ID | Responsible | Status | Est. | 1: 1; 2: 2; 3: 3
REQ-2.12: search for single student by last name | 28 |  | Planned
REQ-2.13: search for single student by UID | 29 |  | Planned
REQ-2.14: get a student’s registration history | 30 |  | Planned
REQ-2.15: provide all reports in simple XML format | 31 |  | Planned
REQ-3.1: get all companies | 32 |  | Planned
REQ-3.2: get all account managers | 33 |  | Planned
REQ-3.3: filter current employers with postings by start and end quarters | 34 |  | Planned
REQ-3.4: filter by employers outside of the U.S | 35 |  | Planned
REQ-3.5: filter employers with job postings by job types | 36 |  | Planned
REQ-3.6: filter employers with job postings by location(state) | 37 |  | Planned
REQ-3.7: filter employer by account manager | 38 |  | Planned
REQ-3.8: filter employers with postings by major(s) | 39 |  | Planned
REQ-3.9: filter employers with postings by college(s) | 40 |  | Planned
REQ-3.10: return report of employers with postings (show info including contact) | 41 |  | Planned
REQ-3.11: get postings of a employer | 42 |  | Planned
REQ-3.12: get referrals for specific posting | 43 |  | Planned
REQ-3.13: search for employer by name | 44 |  | Planned
REQ-3.14: search for employer by account manager | 45 |  | Planned
REQ-3.15: search for employer by contact | 46 |  | Planned
REQ-3.15: filter employer by region | 47 |  | Planned
REQ-3.16: filter employer by city/state | 48 |  | Planned
REQ-3.17: filter employer by zip code | 49 |  | Planned
REQ-3.18: provide all reports in simple XML format | 50 |  | Planned
REQ-4.1: filter placements by start and end quarters | 51 |  | Planned
REQ-4.2: filter by international placements | 52 |  | Planned
REQ-4.3: filter placements with international students | 53 |  | Planned
REQ-4.4: filter placements with international students working in home country | 54 |  | Planned
REQ-4.5: filter placements with NTID students | 55 |  | Planned
REQ-4.6: filter placements by location (state/region) | 56 |  | Planned
REQ-4.7: filter placements by job type | 57 |  | Planned
REQ-4.8: filter placements by major(s) | 58 |  | Planned
REQ-4.9: filter placements by college(s) | 59 |  | Planned
REQ-4.10: return report of placements from employer perspective | 60 |  | Planned
REQ-4.11: return report of placements from student perspective(show SIS status) | 61 |  | Planned
REQ-4.12: provide all reports in simple XML format | 62 |  | Planned
REQ-5.1: get all possible activity types | 63 |  | Planned
REQ-5.2: filter activity records by start and end quarters | 64 |  | Planned
REQ-5.3: filter activity records by single activity | 65 |  | Planned
REQ-5.4: filter activity records by major(s) | 66 |  | Planned
REQ-5.5: return report of student’s activity by UID | 67 |  | Planned
REQ-5.6: return report of activity records grouped by activity type | 68 |  | Planned
REQ-5.7: return report of activity records grouped by college | 69 |  | Planned
REQ-5.8: return report of activity records grouped by major | 70 |  | Planned
REQ-5.9: return report of activity records grouped by quarter | 71 |  | Planned
REQ-5.10: return report of activity records grouped by month | 72 |  | Planned
REQ-5.11: return report of activity records grouped by office visit reason | 73
REQ-5.12: return report of activity records grouped by student name | 74
REQ-5.13: return report of activity records grouped by company | 75
REQ-5.14: return report of student job activities | 76
REQ-5.15: return report of all matching activity records | 77 |  | Planned
Note on A9: Count only active working and implementation days. Do not include Planning Day or Sprint Review. E.g. a 4-week Sprint would most likely have 18 implementation days.

## Sp7
1
Sprint implementation weeks | 2 |  |  | Effort | Remaining on implementation week…
Trend calculated based on last | 5 | Days | Totals | 0 | 0
Task rows | 1 | Done days | 1 |  | 0 | 0
Warning! These are necessary |  | Trend |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
template rows |  | Trend Days | 1 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Task name | Story ID | Responsible | Status | Est. | 1: 1; 2: 2
Note on A9: Count only active working and implementation days. Do not include Planning Day or Sprint Review. E.g. a 4-week Sprint would most likely have 18 implementation days.

## Sprint Sheet Template
1
Sprint implementation weeks | 2 |  |  | Effort | Remaining on implementation week…
Trend calculated based on last | 5 | Days | Totals | 0 | 0
Task rows | 1 | Done days | 1 |  | 0 | 0
Warning! These are necessary |  | Trend |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
template rows |  | Trend Days | 1 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Task name | Story ID | Responsible | Status | Est. | 1: 1; 2: 2
Note on A9: Count only active working and implementation days. Do not include Planning Day or Sprint Review. E.g. a 4-week Sprint would most likely have 18 implementation days.

## Task Slips
Story ID: | 1 | Story: | This is a sample story
Task: | Example task
Responsible Person: Team
Initial Estimate | 5 | Work Done |  | Work Left
Story ID: | 1 | Story: | This is a sample story
Task: | Example task 2
Responsible Person:
Initial Estimate | 7 | Work Done |  | Work Left
Story ID: | 2 | Story: | This is another sample story
Task: | Example task 3
Responsible Person:
Initial Estimate | 12 | Work Done |  | Work Left
Story ID: | 2 | Story: | This is another sample story
Task: | <Delete these example lines>
Responsible Person:
Initial Estimate | 9 | Work Done |  | Work Left