## Instructions
Your Name: | J. Daniel Behun
Instructions
Fill in your name above.
At the end of each week:
Under "Accomplished this week"
Make sure planned tasks from last week copied correctly with estimated times
Fill in the actual amount of time spent on each task and indicate whether it is done
Add any other tasks you worked on this week
Under "Planned for next week"
Enter unfinished tasks from this week that you will continue next week
Enter other planned tasks for next week
Estimate how many minutes you will spend on each task
Tasks and estimates will copy to next week's accomplished section
Under "Issues"
Enter any unexpected problems you encountered
Enter any issues that require discussion with your team

## W-Wk1
Winter - Week 1
Accomplished this week
Done? | ACT |  | Task
Y | 2 |  | Tuesday Meeting
Y | 2 |  | Thursday Meeting (meet with sponser)
| 4 |  | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Tuesday Meeting
|  | 2 | Thursday Meeting (meet with sponser)
|  | 4 | TOTAL TIME
Issues

## W-Wk2
Winter - Week 2
Accomplished this week
Done? | ACT | EST | Task
Y | 2 | 2 | Tuesday Meeting
Y | 2 | 2 | Thursday Meeting (meet with sponser)
| 4 | 4 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Tuesday Meeting
|  | 2 | Thursday Meeting (meet with sponser)
|  | 2 | Project Plan Document
|  | 6 | TOTAL TIME
Issues

## W-Wk3
Winter - Week 3
Accomplished this week
Done? | ACT | EST | Task
Y | 2 | 2 | Tuesday Meeting
Y | 2 | 2 | Thursday Meeting (meet with sponser)
Y | 2 | 2 | Project Plan Document
| 6 | 6 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Tuesday Meeting
|  | 2 | Thursday Meeting (meet with sponser)
|  | 2 | Update Project Plan Document
|  | 6 | TOTAL TIME
Issues

## W-Wk4
Winter - Week 4
Accomplished this week
Done? | ACT | EST | Task
Y | 2 | 2 | Tuesday Meeting
Y | 2 | 2 | Thursday Meeting (meet with sponser)
Y | 2 | 2 | Update Project Plan Document
| 6 | 6 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Sunday Meeting
|  | 2 | Tuesday Meeting
|  | 2 | Thursday Meeting (meet with sponser)
|  | 6 | TOTAL TIME
Issues
Throughout Saturday and Tuesday we worked on user case diagrams, three tier structure, and the server itself.

## W-Wk5
Winter - Week 5
Accomplished this week
Done? | ACT | EST | Task
Y | 2 | 2 | Sunday Meeting
Y | 2 | 2 | Tuesday Meeting
Y | 2 | 2 | Thursday Meeting (meet with sponser)
Y | 2 | 2 | Interview with Jill and meetings before and after to figure out more use cases
| 8 | 8 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Sunday Meeting / More Use Case Diagrams
|  | 2 | Tuesday Meeting / Meeting with group, finish up documents
|  | 2 | Thursday Meeting (meet with sponser)
|  | 6 | TOTAL TIME
Issues

## W-Wk6
Winter - Week 6
Accomplished this week
Done? | ACT | EST | Task
Y | 2 | 2 | Sunday Meeting / More Use Case Diagrams
Y | 2 | 2 | Tuesday Meeting / Meeting with group, finish up documents
Y | 2 | 2 | Thursday Meeting (meet with sponser)
Y | 1 |  | Outside Meetings / Looked at XML and web service ideas
| 7 | 6 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Sunday Meeting / Documents
|  | 2 | Tuesday Meeting
|  | 2 | Thursday Meeting
|  | 1 | Tuesday Meeting with Coops
|  | 7 | TOTAL TIME
Issues

## W-Wk7
Winter - Week 7
Accomplished this week
Done? | ACT | EST | Task
Y | 2 | 2 | Sunday Meeting / Documents
Y | 2 | 2 | Tuesday Meeting
Y | 2 | 2 | Thursday Meeting
Y | 0.5 | 1 | Tuesday Meeting with Coops
Y | 1 |  | Outside of meetings / Use Cases for Tuesday
Y | 1.5 |  | Looking over database
Y | 1.5 |  | Friday Meeting
| 10.5 | 7 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 3 | Metric Documents
|  | 0.5 | Tuesday Meeting with Coops
|  | 2 | Tuesday Meeting
|  | 2 | Thursday Meeting
|  | 7.5 | TOTAL TIME
Issues

## W-Wk8
Winter - Week 8
Accomplished this week
Done? | ACT | EST | Task
Y | 3 | 3 | Metric Documents
Y | 0.5 | 0.5 | Tuesday Meeting with Coops
Y | 2 | 2 | Tuesday Meeting
Y | 2 | 2 | Thursday Meeting
Y | 7.5 | 7.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | sunday meeting
|  | 2 | tuesday meeting (presentations)
|  | 2 | thursday meeting
|  | 3 | finish presentation (work in progress, 2 on monday)
|  | 9 | TOTAL TIME
Issues

## W-Wk9
Winter - Week 9
Accomplished this week
Done? | ACT | EST | Task
Y | 4 | 2 | sunday meeting
Y | 2 | 2 | tuesday meeting (presentations)
Y | 2 | 2 | thursday meeting
Y | 2 | 3 | finish presentation (work in progress, 2 on monday)
Y | 2 |  | presentation meeting & talk with dan after se presentations
Y | 2 |  | team meeting after presentations
Y | 3.5 |  | team presentation wrapup
| 17.5 | 9 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Sunday Meeting
|  | 2 | Tuesday Meeting
|  | 2 | Thursday Meeting
|  | 6 | TOTAL TIME
Issues

## W-Wk10
Winter - Week 10
Accomplished this week
Done? | ACT | EST | Task
Y | 2 | 2 | Sunday Meeting
Y | 2 | 2 | Tuesday Meeting
Y | 1 | 2 | Thursday Meeting
Y | 1 |  | Outside Meeting Work / Looked over, prepared for meetings, small tasks
| 6 | 6 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 4 | Sunday Meeting
|  | 0.5 | Meeting with Dan P.
|  | 4.5 | TOTAL TIME
Issues
Less work this week for most deadlines were last week. Also, I had many finals and projects do which caused a decrease in work for week 10.

## W-Finals
Winter - Finals Week
Accomplished this week
Done? | ACT | EST | Task
Y | 4 | 4 | Sunday Meeting
Y | 0.5 | 0.5 | Meeting with Dan P.
Y | 2.5 |  | Working on the server
| 7 | 4.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## S-Wk1
Spring - Week 1
Accomplished this week
Done? | ACT | EST | Task
Y | 1.5 | 2 | Tuesday Meeting
Y | 2 | 2 | Thursday Meeting
N | 1.5 |  | Performance Metrics
Y | 2 | 2 | Sunday Meeting
| 7 | 6 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Sunday Meeting
|  | 2 | Tuesday Meeting
|  | 2 | Thursday Meeting
|  | 6 | TOTAL TIME
Issues
Performance metrics were not able to be fully completed because we were unable to do it with indexing on.

## S-Wk2
Spring - Week 2
Accomplished this week
Done? | ACT | EST | Task
Y | 1 | 2 | Sunday Meeting
Y | 2 | 2 | Tuesday Meeting
Y | 2 | 2 | Thursday Meeting
N | 2.5 |  | Trying to understand what active is by tracing it.
| 7.5 | 6 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Saturday Meeting
|  | 4 | Tuesday Meeting with Coops
|  | 2 | Thursday Meeting
Updating Metric Documents
|  | 8 | TOTAL TIME
Issues
I was unable to go through and figure it out. I traced it through a series of pages, stored procedure, views, and looking through the tables.
Sunday Meeting was with Mike.

## S-Wk3
Spring - Week 3
Accomplished this week
Done? | ACT | EST | Task
y | 2 | 2 | Saturday Meeting
y | 4 | 4 | Tuesday Meeting with Coops
y | 2 | 2 | Thursday Meeting
Updating Metric Documents
| 8 | 8 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Sunday Meeting
|  | 2 | Tuesday Meeting
|  | 2 | Thursday Meeting
|  | 6 | TOTAL TIME
Issues
The Saturday Meeting is listed this week because it was originally a Sunday Meeting.

## S-Wk4
Spring - Week 4
Accomplished this week
Done? | ACT | EST | Task
y | 2 | 2 | Sunday Meeting
y | 2 | 2 | Tuesday Meeting
y | 2 | 2 | Thursday Meeting
y | 1 | 1 | stubed out the activity service
| 2 |  | started coding the actitivity service
| 9 | 7 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Sunday Meeting
|  | 2 | Tuesday Meeting
|  | 2 | Thursday Meeting
|  | 3 | Code more of the activity service
|  | 9 | TOTAL TIME
Issues

## S-Wk5
Spring - Week 5
Accomplished this week
Done? | ACT | EST | Task
y | 2 | 2 | Sunday Meeting
y | 2 | 2 | Tuesday Meeting
y | 2 | 2 | Thursday Meeting
| 3 | 2 | Code more of the activity service
| 1 |  | Meeting after Thursday with coops
| 10 | 8 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Sunday Meeting
|  | 2 | Tuesday Meeting
|  | 2 | Thursday Meeting
|  | 6 | TOTAL TIME
Issues

## S-Wk6
Spring - Week 6
Accomplished this week
Done? | ACT | EST | Task
y | 2 | 2 | Sunday Meeting
y | 2 | 2 | Tuesday Meeting
y | 2 | 2 | Thursday Meeting
| 1.5 | 1 | activity service
| 2.5 |  | logger class
| 1.5 |  | major update of metrics
| 11.5 | 7 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Sunday Meeting
|  | 2 | Tuesday Meeting
|  | 2 | Thursday Meeting
|  | 6 | TOTAL TIME
Issues

## S-Wk7
Spring - Week 7
Accomplished this week
Done? | ACT | EST | Task
y | 2 | 2 | Sunday Meeting
|  | 2 | Tuesday Meeting
|  | 2 | Thursday Meeting
| 2 |  | Coding the Activity Service and Logger
| 4 | 6 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## S-Wk8
Spring - Week 8
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## S-Wk9
Spring - Week 9
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## S-Wk10
Spring - Week 10
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## S-Finals
Spring - Finals Week
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Issues

## Example
Winter - Week 1
Accomplished this week
Done? | ACT | EST | Task
Y | 20 | 30 | Read textbook about version control
Y | 45 | 30 | Set up subversion on my computer
N | 30 | 60 | Design error-handling subsystem
Y | 15 |  | Read good introduction to subversion on web
| 110 | 120 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 30 | Design error-handling subsystem
|  | 120 | Code error-handling subsystem
|  | 150 | TOTAL TIME
Issues
Hard disk on my computer died, had to restore from backup
Team is having trouble finding time to meet together
May need help coding error-handling subsystem