# Weekly status report 03/24/05

## Status of Activities up to week ended on 02/22/05

| Task | Team Member(s) | Hours | Completed | Known Issues | Remarks |
| --- | --- | --- | --- | --- | --- |
| Acceptance Test Cases for Profiles | ALL |  | 03/15/05 |  | Need to do some program state testing to make sure protocol is being implemented properly. |
| RFCOMM layer implementation | Kyle and Lorien |  | 03/15/05 |  |  |
| SDP Implementation | Ray |  | 03/23/05 |  | Advertises services (BPP, OPP, FTP) on specific channels |
| OBEX layer implementation | Kyle and Lorien |  | continuing |  | Are now successfully transferring files, code is experimental so this week we are creating our objects and separating concerns between profile and OBEX |

## Milestones/Activities missed this week and the reasons for them

| Task | Team Member(s) | Reasons |
| --- | --- | --- |

## Milestones/Activities that at risk of missing deadlines

| Task | Team Member(s) | Due date | Known Issues | Remarks |
| --- | --- | --- | --- | --- |

## Activities planned in next week

| Task | Team Member(s) | Due Date |
| --- | --- | --- |
| Complete OBEX layer implementation | Kyle, Lorien | 03/28/05 |
| Implement profile super class (will contain default implementation for OBEX operations connect, put, fput, get, abort, disconnect) | Kyle and Lorien | 03/28/05 |
| Perform integration testing between profile super class and OBEX | Kyle and Lorien | 03/28/05 |
| Create state diagrams to model OBEX operation behavior from which to make acceptance test cases | Lorien | 03/28/05 |
| Research and begin Implementation of Soap message parses subsystem for BPP | Paul | 03/28/05 |
| Research BPP’s send document command inline image implementation | Ray | 03/28/05 |
| Begin implementation of SDP client negotiation | Ray | 03/28/05 |

## Completed Activities

| Activity/Milestone | Planned start | Planned complete | Actual start | Actual complete | Remarks |
| --- | --- | --- | --- | --- | --- |
| Draft 1 SRS | 1/6/05 | 1/27/05 | 1/6/05 | 1/27/05 |  |
| Feasibility assessment | 12/1/04 | 12/18/04 | 12/2/04 | 12/18/04 |  |
| Architecture Doc | 02/1/05 | 02/08/05 | 02/1/05 | 02/15/05 |  |
| Draft 2 SRS | 02/1/05 | 02/15/05 | 02/1/05 | 02/22/05 | Final SRS |

## Issues

We need a device to test FTP by the middle of April to test it effectively.

We believe that inline XHTML print will be very complex and time consuming and we are currently doing research to learn more and make an assessment of the time required for this task.

## Major Changes in Plan

## Other

# Weekly status report 02/22/05

## Status of Activities up to week ended on 02/22/05

| Task | Team Member(s) | Hours | Completed | Known Issues | Remarks |
| --- | --- | --- | --- | --- | --- |
| Draft 2 SRS | ALL |  | 02/22/05 |  |  |
| Draft 1 Class diagram | ALL |  | 02/22/05 | Some questions relating to the API not resolved | We have many API questions that will be documented and sent to customer on Thursday |

## Milestones/Activities missed this week and the reasons for them

| Task | Team Member(s) | Reasons |
| --- | --- | --- |

## Milestones/Activities that at risk of missing deadlines

| Task | Team Member(s) | Due date | Known Issues | Remarks |
| --- | --- | --- | --- | --- |

## Activities planned in next week

| Task | Team Member(s) | Due Date |
| --- | --- | --- |
| Task breakdown and time estimates | ALL (for individual profile) | 02/24/05 |
| Implementation and test schedule | ALL | 02/24/05 |
| Commented API (to be sent to customer) | ALL | 02/24/05 |
| Complete sequence diagrams of OBEX/BPP interaction | Paul, Ray | 02/24/05 |
| Start RFCOMM implementation | Kyle and Lorien | 02/24/05 |
| SDP implementation of OPP and FTP | Ray | 02/24/05 |
| Start configuration document | Ray | 02/24/05 |

## Completed Activities

| Activity/Milestone | Planned start | Planned complete | Actual start | Actual complete | Remarks |
| --- | --- | --- | --- | --- | --- |
| Draft 1 SRS | 1/6/05 | 1/27/05 | 1/6/05 | 1/27/05 |  |
| Feasibility assessment | 12/1/04 | 12/18/04 | 12/2/04 | 12/18/04 |  |
| Architecture Doc | 02/1/05 | 02/08/05 | 02/1/05 | 02/15/05 |  |
| Draft 2 SRS | 02/1/05 | 02/15/05 | 02/1/05 | 02/22/05 | Final SRS |

## Issues

## Major Changes in Plan

## Other

# Weekly status report 02/15/05

## Status of Activities up to week ended on 02/15/05

| Task | Team Member(s) | Hours | Completed | Known Issues | Remarks |
| --- | --- | --- | --- | --- | --- |
| Completed Architecture | All | 13 | 02/13/05 |  |  |
| Presentation | All | 8 | 02/15/05 |  |  |
| Updated SRS | All | 3 | 02/15/05 |  |  |

## Milestones/Activities missed this week and the reasons for them

| Task | Team Member(s) | Reasons |
| --- | --- | --- |
| Subsystem diagrams | All | We ran out of time. |
| Draft 2 of SRS | All | We need to reschedule this activity |

## Milestones/Activities that at risk of missing deadlines

| Task | Team Member(s) | Due date | Known Issues | Remarks |
| --- | --- | --- | --- | --- |

## Activities planned in next week

| Task | Team Member(s) | Due Date |
| --- | --- | --- |
| Fine grained task breakdown and time estimates | All for individual profiles | 02/24/05 |
| Individual updates to SRS | All for individual profiles | 02/22/05 |
| Subsystem design | All for individual profiles | 02/24/05 |
| Write up plan for delivering all elements identified by customer to be discussed on Wednesday’s status update. | Lorien | 02/22/05 |

## Completed Activities

| Activity/Milestone | Planned start | Planned complete | Actual start | Actual complete | Remarks |
| --- | --- | --- | --- | --- | --- |
| Draft 1 SRS | 1/6/05 | 1/27/05 | 1/6/05 | 1/27/05 |  |
| Feasibility assessment | 12/1/04 | 12/18/04 | 12/2/04 | 12/18/04 |  |
| Architecture Doc | 02/1/05 | 02/08/05 | 02/1/05 | 02/15/05 |  |

## Issues

## Major Changes in Plan

## Other

# Weekly status report 02/08/05

## Status of Activities up to week ended on 02/08/05

| Task | Team Member(s) | Hours | Completed | Known Issues | Remarks |
| --- | --- | --- | --- | --- | --- |
| Initial SDP class design | Ray | 3 |  | None | Everything has been done with OPP records, FTP and BPP still need to be considered |
| API review | Lorien, Paul | 1 | 02/04/05 | We are confused about some of the interactions with the profiles. | Jack is checking on one of these – that the kiosk needs to have the option to accept or reject file upload requests in the OPP server. |
| SRS review | Team and Jack | 2 | 02/04/05 |  | There were some questions that we need Jack to answer. |
| Architectural diagrams – Component structure, sequence diagrams showing interactions | Team | 3 | 02/05/05 | We are not in agreement as to how this should be implemented. | We see two ways of structuring the architecture – top down and bottom up. These will both be documented evaluated based on their pros and cons. We will make a final decision on Thursday. |

## Milestones/Activities missed this week and the reasons for them

| Task | Team Member(s) | Reasons |
| --- | --- | --- |
| Architecture definition | Lorien | The team has proposed two architectural solutions and has not yet decided between the two. |
| OBEX Interface | Kyle and Ray | This task was contingent on our original “top-down” architecture. We may be changing our architecture so that OBEX requires an interface to the profile and not the other way around. This will be re-addressed after we decide on an architecture. |

## Milestones/Activities that at risk of missing deadlines

| Task | Team Member(s) | Due date | Known Issues | Remarks |
| --- | --- | --- | --- | --- |
| Draft 2 of SRS | All | 02/10/05 | Waiting for answers from Kodak |  |

## Activities planned in next week

| Task | Team Member(s) | Due Date |
| --- | --- | --- |
| Create interim presentation | All | 02/13/05 |
| Write up pros and cons for “top-down” architecture. | Ray | 02/10/05 |
| Create sequence diagrams for “top-down” architecture. | Ray | 02/10/05 |
| Write up cons for “bottom-up” architecture. | Lorien | 02/10/05 |
| Write up pros for “bottom-up” architecture. | Kyle | 02/10/05 |
| Create class interaction diagrams for OBEX | Kyle | 02/15/05 |
| Create class interaction diagrams for SDP | Ray | 02/15/05 |
| Create class interaction diagrams for OPP | Lorien | 02/15/05 |
| Create class interaction diagrams for BPP | Paul | 02/15/05 |
| Create class interaction diagrams for FTP | Alonso | 02/15/05 |
| Make updates to SRS as per comments from meeting with Jack | All | 02/15/05 |
| Make updates to SRS when we get required information from Jack | All | undefined |

## Completed Activities

| Activity/Milestone | Planned start | Planned complete | Actual start | Actual complete | Remarks |
| --- | --- | --- | --- | --- | --- |
| Draft 1 SRS | 1/6/05 | 1/27/05 | 1/6/05 | 1/27/05 |  |
| Feasibility assessment | 12/1/04 | 12/18/04 | 12/2/04 | 12/18/04 |  |

## Issues

Our main issue this week has been choosing an architecture. Two architectural schemes have been proposed and one has not yet been agreed upon. The team is dealing with this by identifying the pros and cons of each design. A final decision will be made on Thursday based on this analysis and the design will be documented in our Architecture document. This document will include a Component Interaction diagram, Sequence diagrams showing key aspects of flow, and a Thread diagram to show the threads the system will contain. Our strategy for dealing with the milestone slippage is to work harder between 02/08/05 and 02/10/05 to identify the best Architecture.

## Major Changes in Plan

## Other

# Weekly status report 02/01/05

## Completed and Ongoing Task Progress for this week

| Task | Team Member(s) | Hours | Completed/Due date |
| --- | --- | --- | --- |
| OBEX SRS Draft 1 | Kyle | 2 | 01/27/05 |
| SRS Integration Draft 1 | Kyle, Lorien, Paul | 3 | 01/28/05 |
| Define deliverable due dates | Kyle, Lorien, Paul | 1 | 01/28/05 |
| Create automated Gantt Chart | Kyle | 2 | 01/29/05 |
| Updated Website | Lorien | 3 | 01/28/05 |
| Finalize OPP SRS draft 1 | Lorien | 1 | 01/27/05 |
| Update PM Documents | Lorien | 1 | 01/28/05 |
| Setting up CVS server and client | Paul | 1 | 02/01/05 |
| Update BPP SRS draft 1 | Paul | 2 | 01/27/05 |
| Integration SRS draft 1 | Ray | 3 | 01/27/05 |
| Microsoft Support Call | Ray | 1 | 01/26/05 |
| Update FTP SRS draft 1 | Alonso | 1 | 01/27/05 |
| Meeting Minutes | Alonso | 1 | 02/02/05 |

## Task Assignment for this week

| Task | Team Member(s) | Due Date |
| --- | --- | --- |
| Architecture Document | All | 02/08/05 |
| Find template for presentations | Lorien | 02/03/05 |
| Prepare for walkthrough | All | 02/03/05 |
| BPP Use Cases | Paul | 02/04/05 |
| FTP Use Cases | Alonso | 02/04/05 |
| OPP Use Cases | Lorien | 02/04/05 |
| Kiosk/Server Integration Use Cases | Kyle and Ray | 02/04/05 |

# Weekly status report 01/25/05

## Completed and Ongoing Task Progress for this week

| Task | Team Member(s) | Hours | Completed/Due date |
| --- | --- | --- | --- |
| BPP SRS first draft | Paul Caponetti | 6 | 01/27/05 |
| OPP SRS first draft | Lorien Henry-Wilkins | 2 | 01/27/05 |
| FTP SRS first draft | Alonso Villanueva | 2 | 01/27/05 |
| OBEX SRS first draft | Kyle Scholz | 2 | 01/27/05 |
| Gantt Chart | Kyle and Lorien | 1 | ongoing |
| SDP Research | Ray | 3 | undefined |
| Microsoft Call | Ray | 1 | Response on 01/27/05 |
| SDP Research | Kyle | 1 | undefined |
| Requirements Review | All | 4 | 01/25/05 |

## Task Assignment for this week

| Task | Team Member(s) | Due Date |
| --- | --- | --- |
| OPP SRS Scope, check API for additional requirements | Lorien Henry-Wilkins | 01/27/05 |
| Integrate review comments into BPP SRS, make a flow chart to describe Job Based Mechanism | Paul | 01/27/05 |
| Follow up on Microsoft Call | Ray | 01/26/05 |
| “Bluetooth Protocol Stack” SRS | Ray | 01/27/05 |
| SRS updates for OBEX | Kyle | 01/27/05 |
| Use Cases for OBEX SRS | Kyle | 02/01/05 |
| Schedule interim presentation with Kodak | Kyle | 01/26/05 |
| Updates and scope for FTP SRS | Alonso | 01/27/05 |

“Bluetooth Protocol Stack” is our working name for what we are building.

## Outstanding Issues

We still cannot properly advertise a service using SDP. A support call has been put in to Microsoft to help us resolve this issue and we are awaiting their reply.