Emergency Services Directory

Project Plan 2.1

5/20/08

Team Rain Delay

Mark Gehan

Kevin Tarchenski

Orlando Medina

TJ Wasik

Revision History

| Name | Revision | Date | Version |
| --- | --- | --- | --- |
| Team Rain Delay | Initial document revision | 12/13/08 | 1.0 |
| Kevin Tarchenski | Fixed date in overview, added dates to project plan | 1/10/08 | 1.1 |
| Orlando Medina | Added Time/Effort charts | 1/15/08 | 1.2 |
| Kevin Tarchenski | Fixed font issues, added additional required deliverables | 1/17/08 | 1.3 |
| Orlando Medina | Added Project Plan table, Added Test Plan, Fixed Risk table | 1/22/08 | 1.4 |
| Orlando Medina | Modified right margin, moved page numbers closer to the center (whole document) | 1/22/08 | 1.5 |
| Orlando Medina | -Updated Estimated Schedule: Dates for all sprints and the interim presentation (Page 8) -Added table with Sprint 1 tasks (Page 9) | 2/06/08 | 1.6 |
| Orlando Medina | -Updated Time and Effort Tracking charts (Page 10) -Added Requirements Volatility table (Page 11) | 2/07/08 | 1.7 |
| Orlando Medina | -Updated Sprint tables, Sprint 2 has been added (Page 10) -Updated Estimated Schedule: Sponsor Evaluation on 2/26 (Page 8) -Added Earned value column to sprint task tables (Page 9-10) | 2/19/08 | 1.8 |
| Orlando Medina | -Updated Estimated Schedule. Sprint 3 and 4 now last 3 weeks. Sprint 6 has been removed (Page 8). -Added Sprint 3 tasks (Page 9-10) -Updated Requirements Volatility for Sprint 2 (Page 12) | 3/13/08 | 1.9 |
| Orlando Medina | -Sprint 5 tasks to be added (Page 10) -Added Appendix with tasks from previous sprints (Pages 13-15) | 4/21/08 | 2.0 |
| Orlando Medina | -Updated all sprint tasks (Page 10, 15-19) -Updated Metrics section(Pages 12-14) | 5/20/08 | 2.1 |

Contents

- Overview

- Goals and Scope

  - Improvements

  - New Features

  - Dreams

  - Out of Scope

- Deliverables

  - Internal

  - External

- Risks

- Estimated Schedule

- Project Metrics

- Process Details

  - Scrum

  - Test Plan

Meeting schedule

- Overview

Our team has been assigned the function of taking a previous project, the EMS Online Directory, to the next level.  We have decided that project tasks will fall under one of two categories – site improvements, including changes for usability and superior engineering, and feature additions, which are all-new touches that will allow the directory to be used in new and exciting ways.  Our preliminary development plan is to focus on improvements first, as these will be immediately valuable to users, while simultaneously giving us a means to get acquainted with the project environment.  We will then gradually transition to prioritized feature development.   By weighting feature development toward the second half of the project, we will have more time to propose and design the features.  This also reduces the impact of schedule slippages, since cutting the lowest-priority add-ons will have a much lighter impact than cutting essential improvements.

Meetings will be held weekly with our sponsors on Tuesdays at 4:15 pm, while team meetings will be held Thursdays at 4 pm, and additionally as needed.  Responsibilities have been divided in the following team roles:  Kevin Tarchenski will serve as Team Lead, responsible for project planning, scheduling meetings, and communicating with project sponsors; TJ Wasik will serve as Development Lead, spearheading implementation and coding efforts; Orlando Medina will serve as Test Lead, coordinating and organizing testing efforts; and Mark Gehan will serve as Documentation Lead and Webmaster, keeping track of deliverables and running the team website.

- Goals and Scope

We have decided to break the requested features and improvements into four categories, Improvements, New Features, Dreams, and Out of scope. The features sorted into categories as well as descriptions of each category follow:

- Improvements

These features are improvements to the existing features of the site.

  - Implement name change from “EMS Directory” to “Emergency Services Directory”

  - Content Improvements, such as re-write directions for organization registration

  - List city where the hospital is located

  - Allow for searching/browsing by alphabet

  - Fix the page numbers on the search results

  - Allow searching for organizations in multiple counties

  - Allow searching for organizations in multiple states

  - Allow searching for physician

  - Make registration confirmation page more indicative of registration success

  - Make organization registration easier

    - move the enter password fields to the first page of registration and improve the look of the preview information page

    - make the list to check for your organization appear only once

    - Allow an organization to register as multiple types (such as a fire company and an ambulance company)

  - enabling searching by using a format such as EmergencyServicesDirectory.org/state/county

- New Features

These are New features which will be added to the website.

  - Change the output for the printed version of the Directory to output the pdf format

  - Add a links page that has categorized links including but not limited to:

- National gov links, national non-gov links (NFP and commercial)

- State gov and non-gov (NFP and commercial)

- County gov and non-gov links which would lead to: Ambulance, Fire, Police, Hospital

  - Create a password protected secure zone containing limited access information

  - Implement a method to do mass mailings to organizations in the directory (limited access)

  - Add information about schools and colleges

  - Add information about places of refuge

  - Allow browsing by clicking through a map

- Create a map of NYS (and all counties) with a way of showing how many organizations are registered in a county (approximation)

  - Add international resources using the two letter country codes

  - Add a category for international gov and non-gov organizations

  - Add a category for pharmacies that are open 24/7

  - Implement a method of providing a spreadsheet that could be used for printing mailing lables (limited access)

- Dreams
These are Features which are quite large and after completing the above features we will most likely not have time to complete, but which the sponsor wishes to have. If there is sufficient time remaining after the above features have been completed these features will be reconsidered

  - Provide software to access the database from portable devices, including but not limited to:

    - PDA

    - Blackberry

    - iPod

  - Automated datamining system to find organizations on the internet and add their information to the database

- Out of Scope
These features were decided to be out of the scope of our project.

  - Power failure backup for the dedicated server

  - Develop a common Ambulance Patient Information Report Form (pre-hospital)

  - Develop a common Hospital Emergency Department Patient Information Form

  - offer on-demand printing by Xerox

  - List current inventory of disaster supplies at retail stores

  - offer incentives for registration such as raffles

- Deliverables

  - Internal

    - Individual and Team Work Reports

    - Team Time Tracking

    - Team Peer Evaluations

  - External

    - Finalized Directory Website

    - Interim and Final Presentations

    - Project Poster

    - Team Website

    - SRS Document

    - Meeting Minutes

    - Meeting Agendas

    - Technical Report

Reflection Report

- Risks

- Estimated Schedule

|  | Week (Dates) | Tasks |
| --- | --- | --- |
| Winter | Week 1 (12/02 – 12/08) | 12/08: Team Name |
|  |  | 12/08: Project Synopsis |
|  | Week 2 (12/09 – 12/15) | 12/11: Team website |
|  |  | 12/11: Clearly define project scope |
|  | Week 3 (12/16 – 12/22) | 12/22: Project Plan |
|  | Week 4 (1/06 – 1/12) |  |
|  | Week 5 (1/13 – 1/19) | 1/15: Requirements Document |
|  | Week 6 (1/20 – 1/26) | 1/22: Begin Sprint 1 |
|  |  | 1/24: Schedule Interim Project Progress Presentation |
|  | Week 7 (1/27 – 2/02) |  |
|  | Week 8 (2/03 –2/09) | 2/05: Wrap up Sprint 1 |
|  |  | 2/05: Begin Sprint 2 |
|  | Week 9 (2/10 – 2/16) | 2/12: Interim Project Progress Presentation @ 5:00pm |
|  | Week 10 (2/17 – 2/23) | 2/19: Wrap up Sprint 2, begin transitioning to Feature development |
|  |  | Team Peer Evaluations |
|  | Week 11 (2/24 – 3/01) | 2/26: Sponsor Evaluations |
| Spring | Week 1 (3/09 – 3/15) | 3/11: Begin Sprint 3 |
|  | Week 2 (3/16 – 3/22) |  |
|  | Week 3 (3/23 – 3/29) | 3/25: Poster rough draft |
|  | Week 4 (3/30 – 4/05) | 4/01: Wrap up Sprint 3 |
|  |  | 4/01: Begin Sprint 4 |
|  | Week 5 (4/06 – 4/12) | (Week 5-6) Poster finalized for shop printing |
|  | Week 6 (4/13 – 4/19) |  |
|  | Week 7 (4/20 – 4/26) | 4/22: Wrap up Sprint 4, finalize transition to Feature development |
|  |  | 4/22: Begin Sprint 5 |
|  |  | 4/24: Write technical & reflection reports |
|  | Week 8 (4/27 –5/03) |  |
|  | Week 9 (5/04 – 5/10) | 5/06: Wrap up Sprint 5 and all feature development/testing |
|  | Week 10 (5/11 – 5/17) | Poster Day |
|  |  | Final Project Presentation |
|  |  | Reflection Meeting |
|  |  | Team Peer Evaluations |
|  |  | Sponsor Final Evaluations |

  - Sprint 5 Tasks

| Task | Classification | Task Description | Sprint | Assigned Priority | Effort Points | Earned Value | Status |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Content improvements | Improvement | Enlarge banner at the top of the main page | 5 | 6 | 2 | 5.33 | Complete |
| Create Spreadsheets from Database Information | Feature | Add extra column to Account table for exporting permissions | 5 | 12 | 1 | 1.33 | Complete |
| Create Spreadsheets from Database Information | Feature | Create an excel file from the specified data | 5 | 12 | 4 | 5.33 | Complete |
| Editors can change the representative of an organization | Feature | In AddOrganization add a field with the organization's representative to allow it to be changed | 5 | 5 | 2 | 6.40 | Complete |
| Emergency Shelter | Feature | Modify the database to add the new organization type | 5 | 16 | 4 | 4.00 | Complete |
| Emergency Shelter | Feature | Add the specific fields to the registration page | 5 | 16 | 2 | 2.00 | Complete |
| Emergency Shelter | Feature | Create function for loading Emergency Shelter information from database | 5 | 16 | 2 | 2.00 | Complete |
| Emergency Shelter | Feature | Create specific view in View Organization page for Emergency Shelter | 5 | 16 | 2 | 2.00 | Complete |
| Emergency Shelter | Feature | Create view for Emergency Shelter | 5 | 16 | 2 | 2.00 | Complete |
| Emergency Shelter | Feature | Create Stored Procedure for adding a Emergency Shelter to the database | 5 | 16 | 2 | 2.00 | Complete |
| Emergency Shelter | Feature | Add a new view to the Search page | 5 | 16 | 2 | 2.00 | Complete |
| Google Maps on Organization Information Page | Feature | Make stuff look good | 5 | 11 | 2 | 2.91 | Complete |
| International Organizations | Feature | Tag an entry as an international organization | 5 | 19 | 8 | 0.00 | Not Started |
| International Organizations | Feature | Include country code | 5 | 19 | 2 | 0.00 | Not Started |
| International Organizations | Feature | Gather required information for registering an international organization | 5 | 19 | 1 | 0.00 | Not Started |
| Mass Mailing System | Feature | Modify search results to allow creating a mailing list | 5 | 14 | 1 | 0.00 | Not Started |
| Mass Mailing System | Feature | Add a Send Email button and a new page if necessary | 5 | 14 | 2 | 0.00 | Not Started |
| Modify searching | Feature | Add search box to all pages | 5 | 8 | 4 | 8.00 | Complete |
| Modify searching | Feature | Implement new search algorithm for regular search | 5 | 8 | 4 | 8.00 | Complete |
| Modify searching | Feature | Modify advanced search to include multiple counties or states | 5 | 8 | 4 | 0.00 | Not Started |
| Organization registration | Improvement | Add a success page after a registration is successful | 5 | 9 | 1 | 0.00 | Not Started |
| Organization registration | Improvement | Change pages to support multiple organization type unique fields | 5 | 9 | 4 | 0.00 | Not Started |
| Organization registration | Improvement | Add a feature to registration to allow an organization to be filed as multiple types | 5 | 9 | 2 | 0.00 | Not Started |
| Organization registration | Improvement | Modify all pages that access the database to accommodate the new organization type table | 5 | 9 | 2 | 0.00 | Not Started |
| Secure Data Zone | Feature | develop and implement password rules | 5 | 10 | 1 | 1.60 | Complete |

- Project Metrics

  - Time and Effort Tracking 

Our team will be tracking the time and effort required to complete tasks for each week, both on an individual basis as well as on a group basis. This will be used to keep track of all team members, and ensure that the assigned work is being completed on time. This will also give the team a measure of how they are doing and help identify if a member is running into issues with their tasks.

|  | Project | Winter | Spring |
| --- | --- | --- | --- |
| Mark Gehan | 197.5 | 75 | 122.5 |
| Kevin Tarchenski | 228.25 | 34 | 194.3 |
| TJ Wasik | 258.75 | 82 | 176.8 |
| Orlando Medina | 161 | 58 | 103 |
| Team totals | 845.5 | 249 | 596.5 |

| Winter Quarter | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Mark Gehan | 2 | 6.5 | 3 | 2.5 | 6 | 9 | 11.75 | 9.75 | 16.5 | 8 |
| Kevin Tarchenski | 2.25 | 2.5 | 0.25 | 0.5 | 1.25 | 6 | 4.5 | 5.25 | 6.5 | 5 |
| TJ Wasik | 4.25 | 9 | 4 | 4 | 5.5 | 4 | 9.5 | 8.5 | 17.75 | 15.5 |
| Orlando Medina | 3 | 0.5 | 1.5 | 1 | 4.75 | 8.5 | 8.75 | 11.5 | 10.25 | 8.25 |
| Team totals | 11.5 | 18.5 | 8.75 | 8 | 17.5 | 27.5 | 34.5 | 35 | 51 | 36.75 |

| Spring Quarter | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Mark Gehan | 6 | 8 | 11 | 11.5 | 10.5 | 9.5 | 14 | 16 | 16 | 20 |
| Kevin Tarchenski | 9 | 8 | 14 | 22 | 25.25 | 25.25 | 25.25 | 28 | 24 | 13.5 |
| TJ Wasik | 15.5 | 19.25 | 17.5 | 10.5 | 17.5 | 17.5 | 38 | 14 | 20 | 7 |
| Orlando Medina | 8 | 11 | 12.5 | 8.5 | 8 | 11 | 8 | 11.5 | 17 | 7.5 |
| Team totals | 38.5 | 46.25 | 55 | 52.5 | 61.25 | 63.25 | 85.25 | 69.5 | 77 | 48 |

  - Earned Value Chart 

To supplement the time and effort tracking being done, the team will also maintain a chart that associates the activities being worked on with points. Each completed activity will earn a certain number of points based on complexity. Since not all activities are created equal - meaning that some are more complex than others, assigning different point values to each activity will more accurately show the progress being made for each sprint. This also gives us the ability to accurately assign activities for each week, reducing the possibility of falling behind in a sprint. To measure the earned value, we will track the number of points earned over time.

  - Requirements Volatility 

To help ensure that our work stays on track, we will be measuring the percentage of requirements that change during each sprint. Understanding that requirements may change during development, we will be using this measure to ensure that any changes that are made do not overwhelm the team, or undermine our development schedule. Keeping a measurement of requirements volatility will help the team maintain the stability of the project.

| Sprint | Number of Changed Requirements | Total Number of Requirements | Change Percentage |
| --- | --- | --- | --- |
| 1 | 7 | 19 | 36.84% |
| 2 | 2 | 20 | 10.00% |
| 3 | 1 | 22 | 4.55% |
| 4 | 0 | 22 | 0.00% |
| 5 | 0 | 22 | 0.00% |

- Process Details

Scrum
    Beginning the first week of 2008, our team will use the Scrum method of project management.  In this methodology, work is organized in project sprints, which we have decided will be two weeks in length.  Since our project is evolutionary and not from-scratch, we feel this will provide the best level of customer satisfaction and feedback.  Tasks are organized into a prioritized list called the backlog.  From this list, we will select a handful of tasks to address over the sprint at our bi-weekly sprint planning meetings, which will be a subset of our weekly team meetings.  Development will take place in the days between that meeting and our meeting with our sponsors, where we will demonstrate our accomplishments and receive feedback, which will be integrated into the backlog for future consideration.  During every day of development, we will have a daily stand-up meeting, which is a short (15 minute) gathering where each teammate relays what they accomplished that day and what was on their agenda for the next.  Finally, we will have a bi-weekly breakdown meeting, where the team discusses the events of the sprint, files tasks as completed or still in-progress, and takes into consideration successes and failures for the planning of the next sprint.  This step will be the first order of business at our weekly team meeting.

Test Plan
    The team will test the software on a variety of levels.  The first is at the unit level, where unit tests will be written for crucial components of code at a minimum.  This will include code that interacts with the database.  The team will make use of the NUnit application to accomplish this.  The second level is at the functionality level.  These tests are more abstract in that they do not test the code directly, but will help ensure that the website functions as it was designed.  Where possible, a test automation tool called WatiN will be used to automate this test.  The third level is the usability and acceptance level, where the sponsors and/or other people who may be users of the site will attempt to accomplish certain tasks.  From there the team will assess the intuitiveness of the interface and the ease of use for the site.  This may be assessed by measuring the time taken to complete a task or the number of times the user deviated to a different area of the site.

Meeting Schedule
    Our team will meet weekly on Thursdays at 4 p.m.  The purpose of this meeting will be twofold - we will combine our breakdown meeting, wherein we file completed tasks and discuss the past week's efforts, and our sprint panning meeting, wherein we assign tasks from the backlog for development over the coming week.  We will have daily stand-up meetings from Friday until the following Monday, discussing our work in progress.  Finally, on Tuesdays at 4:15 pm we will meet with our sponsors to demonstrate our results, and query for feedback, which we will integrate into our project backlog for planning the next sprint.

- Appendix

  - Sprint 1 Tasks

| Task | Classification | Task Description | Sprint | Assigned Priority | Effort Points | Earned Value | Status |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Name change | Improvement | Add team Rain Delay to the development team list | 1 | 1 | 1 | 16 | Complete |
| Name change | Improvement | Change URL references to www.EmergencyServicesDirectory.org | 1 | 1 | 1 | 16 | Complete |
| Name change | Improvement | Change the logo of the Directory to reflect name change | 1 | 1 | 2 | 32 | Complete |
| Name change | Improvement | Change name references from EMS Directory to Emergency Services Directory | 1 | 1 | 2 | 32 | Complete |
| Set up development environment | Setup | Get access to a Virtual Machine from Kurt | 1 | 0 | 1 | 16 | Complete |
| Set up development environment | Setup | Get access to install necessary software from Kurt (VS 2003, SQL Server 2005, IIS) | 1 | 0 | 1 | 16 | Complete |
| Set up development environment | Setup | Install IIS, VS 2003. and SQL Server 2005 | 1 | 0 | 1 | 16 | Complete |
| Set up development environment | Setup | Get a copy of code on the Virtual Machine | 1 | 0 | 1 | 16 | Complete |
| Set up development environment | Setup | Configure SQL Server to run a backup copy of the Directory Database | 1 | 0 | 2 | 32 | Complete |
| Set up development environment | Setup | Change code to login to test database server | 1 | 0 | 2 | 32 | Complete |
| Set up development environment | Setup | Publicly host sandbox Directory on Virtual Machine | 1 | 0 | 2 | 32 | Complete |
| Set up development environment | Setup | Directory completely functional on Virtual Machine | 1 | 0 | 4 | 64 | Complete |

  - Sprint 2 Tasks

| Task | Classification | Task Description | Sprint | Assigned Priority | Effort Points | Earned Value | Status |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Content improvements | Improvement | Get outside reviews/research of website for improvements | 2 | 6 | 1 | 2.67 | Complete |
| Content improvements | Improvement | Evaluate text on website for change | 2 | 6 | 2 | 5.33 | Complete |
| Modify search results | Improvement | Display the city in search results table | 2 | 15 | 1 | 1.07 | Complete |

  - Sprint 3 Tasks

| Task | Classification | Task Description | Sprint | Assigned Priority | Effort Points | Earned Value | Status |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Editors can create new users | Improvement | Add a link to default.aspx to the registration page | 3 | 4 | 1 | 4.00 | Complete |
| Links Page | Feature | Create new page for links | 3 | 13 | 1 | 1.23 | Complete |
| Links Page | Feature | Add links page to sidebar | 3 | 13 | 1 | 1.23 | Complete |
| Modify search results | Improvement | Fix page number navigation functionality | 3 | 15 | 4 | 4.27 | Complete |
| Organization registration | Improvement | Add more instruction on what preview information means to the user | 3 | 9 | 2 | 3.56 | Complete |
| Organization registration | Improvement | Modify database to allow organizations to have multiple types | 3 | 9 | 4 | 7.11 | Complete |
| Remove unwanted mail recipients from mailer | Improvement | add opt-out messate to all auto-generated e-mails with link to remove | 3 | -1 | 2 | 32.00 | Complete |
| Remove unwanted mail recipients from mailer | Improvement | create interface for editor to remove user from mailing list | 3 | -1 | 2 | 32.00 | Complete |
| Remove unwanted mail recipients from mailer | Improvement | create script to remove recipient from mailing list | 3 | -1 | 4 | 64.00 | Complete |
| User Data Verification | Feature | Add means of tagging an entry as "outdated" to page | 3 | 3 | 2 | 10.67 | Complete |
| User Data Verification | Feature | Add explaination for new functionality | 3 | 3 | 1 | 5.33 | Complete |
| User Data Verification | Feature | Add means to notify editors of change to "outdated" tag | 3 | 3 | 4 | 21.33 | Complete |
| User Data Verification | Feature | Add indicator of Verified/Outdated status to entries | 3 | 3 | 2 | 10.67 | Complete |
| User Data Verification | Feature | Edit database to include "outdated" tag | 3 | 3 | 4 | 21.33 | Complete |
| User Registration | Improvement | Modify user registration so password creation is done at the same step | 3 | 2 | 4 | 32.00 | Complete |

  - Sprint 4 Tasks

| Task | Classification | Task Description | Sprint | Assigned Priority | Effort Points | Earned Value | Status |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Alphabetical browsing | Improvement | Implement letter query function in test site | 4 | 7 | 2 | 4.57 | Complete |
| Alphabetical browsing | Improvement | Create a protoype to test out queries by letter | 4 | 7 | 4 | 9.14 | Complete |
| Alphabetical browsing | Improvement | Create a "Browse the Directory" webpage | 4 | 7 | 4 | 9.14 | Complete |
| Content improvements | Improvement | Implement new page wording | 4 | 6 | 2 | 5.33 | Complete |
| Content improvements | Improvement | Instructions for registration to be rewritten | 4 | 6 | 2 | 5.33 | Complete |
| Create Spreadsheets from Database Information | Feature | Add button to search page to export the results to Excel | 4 | 12 | 2 | 2.67 | Complete |
| Emergency Shelter | Feature | Determine what new information is needed for refuge types | 4 | 16 | 1 | 1.00 | Complete |
| Google Maps on Organization Information Page | Feature | Add google maps to the pages and link in information from the script | 4 | 11 | 4 | 5.82 | Complete |
| Google Maps on Organization Information Page | Feature | parse information into format google maps requires | 4 | 11 | 2 | 2.91 | Complete |
| Google Maps on Organization Information Page | Feature | Read google maps api | 4 | 11 | 1 | 1.45 | Complete |
| Modify search results | Improvement | Categorize search results by type | 4 | 15 | 2 | 2.13 | Complete |
| Organization registration | Improvement | Modify registration process so that the duplication checking only happens once | 4 | 9 | 2 | 3.56 | Complete |
| Organization registration | Improvement | Add * to all required fields in the registration page | 4 | 9 | 1 | 1.78 | Complete |
| Secure Data Zone | Feature | implement security permissions associated with each page | 4 | 10 | 8 | 12.80 | Complete |
| Secure Data Zone | Feature | research security issues and vulnerabilities to ensure that security is implemented properly | 4 | 10 | 4 | 6.40 | Complete |
| Secure Data Zone | Feature | Implement security permissions associated with each user | 4 | 10 | 8 | 12.80 | Complete |
| Secure Data Zone | Feature | evaluate current password storage/verification method for possible replacement | 4 | 10 | 2 | 3.20 | Complete |
| Secure Data Zone | Feature | create interface for editors to change permissions for a user | 4 | 10 | 2 | 3.20 | Complete |

# Text boxes

| Risk ID | Description | Probability | Impact | Exposure | Classification | Owner | Mitigation Strategy | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Differences between the sandbox and Production | .5 | High | 5 | Technical | Test Lead | Extensive acceptance testing | Unknown |
| 2 | Feature/ Scope Creep | 1 | Med | 5 | Requireme-nts | Team Lead | Requirements management and a solid project schedule for negotiation | Unknown |
| 3 | Database Performance | .25 | Low | .25 | Technical | Dev. Lead | Performance testing | Unknown |
| 4 | Unnecessary Requirements | .25 | Low | .25 | Requireme-nts | Team Lead | Adequate requirements analysis. Evaluate requirements according to project goals. | Unknown |
| 5 | Unfamiliar with development technologies | .25 | Med | .25 | Research | Entire Team | Research must be done ahead of time so team has the knowledge to provide a solution on par with previous development | Mitigation in progress |
| 6 | Inadequate communication with sponsor | .3 | Med | 1.5 | Communic-ation | Entire Team | Backup methods of communication necessary. | Email, telephone, and Skype are all being used |
| 7 | Bad weather | .5 | High | 5 | Act of God | Entire Team | Alternative communications could be used for meetings such as everyone using Skype. Could just reschedule meetings as well. | Probably will happen eventually |