## Activities
Activity Name | Type | Week | Responsible | Estimated Hours | Actual Hours | Status | Comments | Estimation error | Estimation error %
See Instructions sheet for usage
Week 1
Learn Eclipse | Preparation | 1 |  |  |  |  | Learning SVN, Eclipse well critical to project success
Role preferences | Coordination | 1
Learn SVN | Preparation | 1
Wiki setup | Preparation | 1
Team formation | Preparation | 1
Brainstorm project concept | Requirements | 1
Project concept writeup | Documentation | 1
Identify role owners | Preparation | 1 |  |  |  |  | Multiple roles are OK - think about role & reponsibility distribution
Team Roster | Documentation | 1
Weekly team meeting | Coordination | 1
Weekly report | Documentation | 1
Week 2
Repository setup | Preparation | 2
Define requirements | Requirements | 2
Create, share paper prototype | Requirements | 2
Requirements document | Requirements | 2
Plan R1 | Coordination | 2 |  |  |  |  | Also start GUI work early, even though it is only for R2
Update activity tracker | Documentation | 2
Create acceptance tests | Testing | 2
Choose processes | Coordination | 2
Update risk/issues on Wiki | Coordination | 2
Weekly team meeting | Coordination | 2
Weekly report | Documentation | 2
Week 3
Note on C1: swami: This is useful for generating subtotals and reports
Note on D1: SE: The person responsible for ensuring completion, not necessarily all the people doing it
Note on H1: swami: Insert your own comments
Note on I1: SE: This field is updated automatically

## SummaryData
Note: All data on this sheet updated automatically
Item |  | Week |  | Total Estimation Error % | Count | Average Estimation Error %
Criteria
Week | Week | Week | Week | Week | Week | Week | Week | Week | Week
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
EstimationError
Week1 |  | 1 |  | 0 | 0 | 0
Week2 |  | 2 |  | 0 | 0 | 0
Week3 |  | 3 |  | 0 | 0 | 0
Week4 |  | 4 |  | 0 | 0 | 0
Week5 |  | 5 |  | 0 | 0 | 0
Week6 |  | 6 |  | 0 | 0 | 0
Week7 |  | 7 |  | 0 | 0 | 0
Week8 |  | 8 |  | 0 | 0 | 0
Week9 |  | 9 |  | 0 | 0 | 0
Week10 |  | 10 |  | 0 | 0 | 0
Activity |  |  |  |  | Actual Effort
Requirements |  |  |  |  | 0
Design |  |  |  |  | 0
Development |  |  |  |  | 0
Testing |  |  |  |  | 0
Interfaces |  |  |  |  | 0
Documentation |  |  |  |  | 0
Coordination |  |  |  |  | 0
Preparation |  |  |  |  | 0
Delivery |  |  |  |  | 0
Criteria
Type | Type | Type | Type | Type | Type | Type | Type | Type
Requirements | Design | Development | Testing | Interfaces | Documentation | Coordination | Preparation | Delivery
EstimationError |  | Total | Count | Average
Requirements |  | 0 | 0 | 0
Design |  | 0 | 0 | 0
Development |  | 0 | 0 | 0
Testing |  | 0 | 0 | 0
Interfaces |  | 0 | 0 | 0
Documentation |  | 0 | 0 | 0
Coordination |  | 0 | 0 | 0
Preparation |  | 0 | 0 | 0
Delivery |  | 0 | 0 | 0
Week-wise-Effort
Week1 |  | 1 |  |  | 0
Week2 |  | 2 |  |  | 0
Week3 |  | 3 |  |  | 0
Week4 |  | 4 |  |  | 0
Week5 |  | 5 |  |  | 0
Week6 |  | 6 |  |  | 0
Week7 |  | 7 |  |  | 0
Week8 |  | 8 |  |  | 0
Week9 |  | 9 |  |  | 0
Week10 |  | 10 |  |  | 0
Total effort |  |  |  |  | 0

## Reports
The charts here update automatically

## Instructions
Using the activity tracker
At the end of each week, update the status of all activities completed during the week
Fill in hours spent on each activity during the current week
If 5 team members each spent an hour, that counts as 5 hours
Fill in time for activities not fully completed ("ongoing") as well, then update these values during following weeks
During the planning phases, identify the activities to be done during each week
If you spend time on an activity not listed in the tracker, add the activity and list actual hours (need not fill in estimated hours if you didn't estimate it up front)
For new activities, identify the type of activity - documentation, coordination, estimation etc.
At the end of each week, plan ahead for the following week
Identify people responsible for each activity
Estimate the hours needed for the activity
After each release, look at the "reports" section to see charts of how much time has been spent so far, and what activities it has been spent on
Use the charts and data to identify needs for improvement