## Instructions
Your Name: | #NoName!
Instructions
Enter your name above.
At the end of each week:
Under "Accomplished this week"
Make sure planned tasks from last week copied correctly with estimated times
Fill in the actual amount of time spent on each task and indicate whether it is done.
Add any other tasks you worked on this week
Teams seem to relate better to times in hours down to the 1/4 hour, but feel free to use minutes if that has more meaning to you.
Under "Planned for next week"
Enter unfinished tasks from this week that you will continue next week
Enter other planned tasks for next week
Estimate the time you will spend on each task. Estimate your time in minutes or hours down to the 1/4 hour.
Tasks and estimates will copy to next week's accomplished section
Under "Issues"
Enter any unexpected problems you encountered
Enter any issues that require discussion with your team

## Example
First Term - Week 1
Accomplished this week
Done? | ACT | EST | Task
Y | 0.5 |  | Attended expectations talk
Y | 1 |  | Prepared for first meeting with sponsor
Y | 1.75 |  | Met with sponsor
Y | 5.25 |  | Researched webservices
Y | 2 |  | Team meeting to assign initial roles and responsibilities
| 10.5 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Regular team meeting
|  | 2 | Meeting with project sponsor
|  | 1 | Write draft synopsis with Kate
|  | 4 | Look for webservices tutorials and work through them
|  | 2.5 | Work with Adam to make list of requirements questions
|  | 11.5 | TOTAL TIME
Issues
Hard disk on my computer died, had to restore from backup
Team is having trouble finding time to meet together
May need help coding error-handling subsystem

## 1-Wk1
First Term - Week 1
Accomplished this week
Done? | ACT |  | Task
Y | 2 |  | Regular team meeting
Y | 2 |  | Meeting with project sponsor
Y | 3 |  | Initial Project Research
Y | 0.5 |  | Establishment of team name
Y | 0.5 |  | Identifying initial questions for sponsor
| 8 |  | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Regular team meeting
|  | 2 | Meeting with project sponsor
|  | 2 | Start Team website
|  | 2 | Publish team documents on website
|  | 2 | Complete project information survey form
|  | 10 | TOTAL TIME
Issues
N/A

## 1-Wk2
First Term - Week 2
Accomplished this week
Done? | ACT | EST | Task
Y | 2.5 | 2 | Regular team meeting
Y | 2 | 2 | Meeting with project sponsor
Y | 1 | 1 | Develop Thin Vertical Slice
Y | 0.5 | 0.5 | Synopsis Revision
Y | 1 | 1 | Retrieving previous team deliverables
Y | 1 | 1 | Setup server
Y | 1 | 1 | Subversion Setup and configuration
Y | 2 | 2 | Other server installs
| 11 | 10.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2.5 | Regular team meeting
|  | 2 | Meeting with project sponsor
|  | 2 | Project Plan
|  | 1.5 | Review previous team deliverables
|  | 2 | Increment 1 Architecture
|  | 1 | Website tweaks
|  | 11 | TOTAL TIME
Issues

## 1-Wk3
First Term - Week 3
Accomplished this week
Done? | ACT | EST | Task
Y | 2.5 | 2.5 | Regular team meeting
Y | 2 | 2 | Meeting with project sponsor
Y | 2 | 2 | Project Plan
Y | 1.5 | 1.5 | Review previous team deliverables
Y | 2 | 2 | Increment 1 Architecture
N | 0 | 1 | Website tweaks
| 0.5 | 0.5 | Deploy Thin Vertical Slice
| 10.5 | 11.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1 | Website tweaks
|  | 2 | Develop Servlets
|  | 2 | Update Architecture
|  | 5 | User Home JSP
|  | 4 | Password Resetting
|  | 14 | TOTAL TIME
Issues

## 1-Wk4
First Term - Week 4
Accomplished this week
Done? | ACT | EST | Task
N | 0 | 1 | Website tweaks
Y | 2 | 2 | Develop Servlets
Y | 2 | 2 | Update Architecture
N | 7 | 5 | User Home JSP
Y | 4 | 4 | Password Resetting
Y | 2 | 2 | Regular Team Meeting
Y | 2 | 2 | Meeting with Project Sponsor
| 19 | 18 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Regular Team Meeting
|  | 2 | Meeting with Project Sponsor
|  | 2 | Research for Hosting Plans
|  | 2 | SRS
|  | 5 | Begin work on Admin/Editor Pages
|  | 13 | TOTAL TIME
Issues

## 1-Wk5
First Term - Week 5
Accomplished this week
Done? | ACT | EST | Task
Y | 2 | 2 | Regular Team Meeting
Y | 0 | 2 | Meeting with Project Sponsor
Y | 2 | 2 | Research for Hosting Plans
Y | 0 | 2 | SRS
Y | 1 | 5 | Begin work on Admin/Editor Pages
Y | 4 | 0 | Architecture Document
Y | 2 | 0 | Use Cases
Y | 2 | 0 | Design Phase II
| 13 | 13 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Meeting with Project Sponsor
|  | 4 | Write tests
|  | 3 | Begin Phase II Development
|  | 3 | Finish Admin/Editor pages
|  | 12 | TOTAL TIME
Issues

## 1-Wk6
First Term - Week 6
Accomplished this week
Done? | ACT | EST | Task
Y | 2 | 2 | Meeting with Project Sponsor
N | 0 | 4 | Write tests
N | 0 | 3 | Begin Phase II Development
N | 0 | 3 | Finish Admin/Editor pages
Y | 5 | 0 | Documentation
| 7 | 12 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 8 | Dynamic Content Updating
|  | 2 | Look up how to test Servlets
|  | 2 | User Guide
|  | 2 | Meeting with Project Sponsor
|  | 14 | TOTAL TIME
Issues

## 1-Wk7
First Term - Week 7
Accomplished this week
Done? | ACT | EST | Task
Y | 10 | 8 | Dynamic Content Updating
|  | 2 | Look up how to test Servlets
Y | 2 | 2 | User Guide
Y | 2 | 2 | Meeting with Project Sponsor
Y | 1 | 0 | Minor JSP fixes
| 3 | 0 | Make code fault-tolerant
| 18 | 14 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 4 | Write Tests for Servlets
|  | 4 | Work on admin capabilities
|  | 3 | Merge Word xml with java strings
|  | 2 | Meeting with Project Sponsor
|  | 2 | Regular Team Meeting
|  | 15 | TOTAL TIME
Issues

## 1-Wk8
First Term - Week 8
Accomplished this week
Done? | ACT | EST | Task
N | 2 | 4 | Write Tests for Servlets
N | 1 | 4 | Work on admin capabilities
N | 0 | 3 | Merge Word xml with java strings
Y | 2 | 2 | Meeting with Project Sponsor
Y | 2 | 2 | Regular Team Meeting
| 7 | 15 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 4 | Work on admin capabilities
|  | 3 | Merge Word xml with java strings
|  | 4 | Presentations
|  | 1 | Help setup webex for presentation
|  | 2 | Revise documents for Phase II
|  | 14 | TOTAL TIME
Issues

## 1-Wk9
First Term - Week 9
Accomplished this week
Done? | ACT | EST | Task
N | 1 | 4 | Work on admin capabilities
N | 0 | 3 | Merge Word xml with java strings
Y | 4 | 4 | Presentations
Y | 1 | 1 | Help setup webex for presentation
N | 2 | 2 | Revise documents for Phase II
| 8 | 14 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Regular Team Meeting
|  | 2 | Meeting with Project Sponsor
|  | 3 | Work on Table Generator
|  | 3 | Admin Capabilities
|  | 1 | Look over Shedule
|  | 2 | Revise documents for phase 2
|  | 13 | TOTAL TIME
Issues

## 1-Wk10
First Term - Week 10
Accomplished this week
Done? | ACT | EST | Task
Y | 2 | 2 | Regular Team Meeting
Y | 2 | 2 | Meeting with Project Sponsor
N | 3 | 3 | Work on Table Generator
N | 1 | 3 | Admin Capabilities
Y | 1 | 1 | Look over Shedule
N | 2 | 2 | Revise documents for phase 2
| 11 | 13 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Admin Capabilities
|  | 4 | Bullet proof code
|  | 2 | Revise Documents
|  | 8 | TOTAL TIME
Issues

## 1-Finals
First Term - Finals Week
Accomplished this week
Done? | ACT | EST | Task
Y | 2 | 2 | Admin Capabilities
N | 4 | 4 | Bullet proof code
Y | 2 | 2 | Revise Documents
| 8 | 8 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 5 | Context Sensitive User Interface by Roles
|  | 3 | Update Documentation
|  | 1 | Status Report Creation
|  | 9 | TOTAL TIME
Issues

## 2-Wk1
Second Term - Week 1
Accomplished this week
Done? | ACT | EST | Task
Y | 6 | 5 | Context Sensitive User Interface by Roles
N | 3 | 3 | Update Documentation
Y | 1 | 1 | Status Report Creation
| 10 | 9 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Regular Team Meeting
|  | 2 | Meeting with Project Sponsor
|  | 3 | Phase 3 Architecture/Design
|  | 1 | Installation Guide
|  | 0.5 | Status Document Update
|  | 1 | Unit Tests
|  | 9.5 | TOTAL TIME
Issues

## 2-Wk2
Second Term - Week 2
Accomplished this week
Done? | ACT | EST | Task
Y | 2 | 2 | Regular Team Meeting
Y | 2 | 2 | Meeting with Project Sponsor
Y | 2 | 3 | Phase 3 Architecture/Design
N | 1 | 1 | Installation Guide
Y | 0.5 | 0.5 | Status Document Update
N | 0 | 1 | Unit Tests
N | 2 | 0 | Update User Guides
Y | 1 | 0 | Update Architecture
| 10.5 | 9.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Regular Team Meeting
|  | 2 | Meeting with Project Sponsor
|  | 1 | Installation Guide
|  | 3 | Popup Notifications
|  | 2 | Default Admin Account
|  | 0.5 | Status Document Update
|  | 2 | Unit Tests
|  | 12.5 | TOTAL TIME
Issues

## 2-Wk3
Second Term - Week 3
Accomplished this week
Done? | ACT | EST | Task
Y | 2 | 2 | Regular Team Meeting
Y | 2 | 2 | Meeting with Project Sponsor
Y | 1 | 1 | Installation Guide
N | 1 | 3 | Popup Notifications
Y | 1 | 2 | Default Admin Account
Y | 0.5 | 0.5 | Status Document Update
N | 2 | 2 | Unit Tests
Y | 10 | 0 | Change Requests
Y | 1 | 0 | New Menu
Y | 0.5 | 0 | Revamped Error Page
Y | 2 | 0 | Bug fixes
Y | 4 | 3 | Scheduled Notification Frontend
| 27 | 15.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 3 | Change Requests for Addresses & Phone Numbers
|  | 3 | Unit Tests
|  | 2 | Regular Team Meeting
|  | 2 | Meeting with Project Sponsor
|  | 3 | Scheduled Notification Servlet
|  | 2 | Forward all servlets to the error page in case of an exception
|  | 15 | TOTAL TIME
Issues

## 2-Wk4
Second Term - Week 4
Accomplished this week
Done? | ACT | EST | Task
Y | 0 | 3 | Change Requests for Addresses & Phone Numbers
N | 1 | 3 | Unit Tests
Y | 2 | 2 | Regular Team Meeting
Y | 2 | 2 | Meeting with Project Sponsor
N | 1 | 3 | Scheduled Notification Servlet
N | 0 | 2 | Forward all servlets to the error page in case of an exception
Y | 3 | 0 | Various Change Requests
N | 7 | 0 | Revamp of Doc Submission
| 16 | 15 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Meeting with Project Sponsor
|  | 2 | Regular Team Meeting
|  | 1 | Unit Tests
|  | 3 | Scheduled Notification Servlet
|  | 2 | Forward all servlets to the error page in case of an excpetion
|  | 8 | Revamp of Doc Submission (Back-End)
|  | 18 | TOTAL TIME
Issues

## 2-Wk5
Second Term - Week 5
Accomplished this week
Done? | ACT | EST | Task
Y | 2 | 2 | Meeting with Project Sponsor
Y | 2 | 2 | Regular Team Meeting
N | 0 | 1 | Unit Tests
N | 1 | 3 | Scheduled Notification Servlet
N | 2 | 2 | Forward all servlets to the error page in case of an excpetion
N | 3 | 8 | Revamp of Doc Submission (Back-End)
| 10 | 18 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Meeting with Project Sponsor
|  | 2 | Regular Team Meeting
|  | 5 | Revamp of Doc Submission (Back-End)
|  | 1 | Unit Tests
|  | 2 | Scheduled Notification Servlet
|  | 1 | Forward all servlets to the error page in case of an exception
|  | 0.5 | Update Status Doc
|  | 2 | Poster Work
|  | 15.5 | TOTAL TIME
Issues

## 2-Wk6
Second Term - Week 6
Accomplished this week
Done? | ACT | EST | Task
Y | 2 | 2 | Meeting with Project Sponsor
Y | 2 | 2 | Regular Team Meeting
N | 3 | 5 | Revamp of Doc Submission (Back-End)
N | 0 | 1 | Unit Tests
N | 0 | 2 | Scheduled Notification Servlet
N | 0 | 1 | Forward all servlets to the error page in case of an exception
Y | 0.5 | 0.5 | Update Status Doc
Y | 6.5 | 2 | Poster Work
| 14 | 15.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Meeting with Project Sponsor
|  | 2 | Regular Team Meeting
|  | 2 | Revamp of Doc Submission (Back-End)
|  | 1 | Unit Tests
|  | 2 | Scheduled Notification Servlet
|  | 1 | Forward all servlets to the error page in case of an exception
|  | 0.5 | Update Status Doc
|  | 1 | Poster Touchups
|  | 11.5 | TOTAL TIME
Issues

## 2-Wk7
Second Term - Week 7
Accomplished this week
Done? | ACT | EST | Task
Y | 2 | 2 | Meeting with Project Sponsor
Y | 2 | 2 | Regular Team Meeting
N | 3 | 2 | Revamp of Doc Submission (Back-End)
N | 0 | 1 | Unit Tests
N | 0 | 2 | Scheduled Notification Servlet
N | 0 | 1 | Forward all servlets to the error page in case of an exception
Y | 0.5 | 0.5 | Update Status Doc
Y | 2 | 1 | Poster Touchups
| 9.5 | 11.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Meeting with Project Sponsor
|  | 2 | Regular Team Meeting
|  | 4 | Fixing AJAX problem with Doc Submission
|  | 2 | Scheduled Notification Servlet
|  | 1 | Forward all servlets to the error page in case of an exception
|  | 0.5 | Update Status Doc
|  | 11.5 | TOTAL TIME
Issues

## 2-Wk8
Second Term - Week 8
Accomplished this week
Done? | ACT | EST | Task
Y | 2 | 2 | Meeting with Project Sponsor
Y | 2 | 2 | Regular Team Meeting
Y | 5 | 4 | Fixing AJAX problem with Doc Submission
Y | 2 | 2 | Scheduled Notification Servlet
N | 0 | 1 | Forward all servlets to the error page in case of an exception
Y | 0.5 | 0.5 | Update Status Doc
Y | 3 | 3 | Poster Presentation
| 14.5 | 14.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Meeting with Project Sponsor
|  | 2 | Regular Team Meeting
|  | 3 | Update Documentation
|  | 2 | Mouseover for Sigsoft Logo
|  | 0.5 | Update Status Doc
|  | 1 | Forward all servlets to the error page in case of an exception
|  | 2 | Fix Scheduled Notifications Front end
|  | 12.5 | TOTAL TIME
Issues

## 2-Wk9
Second Term - Week 9
Accomplished this week
Done? | ACT | EST | Task
Y | 2 | 2 | Meeting with Project Sponsor
Y | 2 | 2 | Regular Team Meeting
N | 4 | 3 | Update Documentation
N | 0 | 2 | Mouseover for Sigsoft Logo
Y | 0.5 | 0.5 | Update Status Doc
N | 0 | 1 | Forward all servlets to the error page in case of an exception
Y | 2 | 2 | Fix Scheduled Notifications Front end
| 10.5 | 12.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 4 | Final Presentations
|  | 1 | Presentation Prep
|  | 2 | Update Documentation
|  | 2 | Mouseover for Sigsoft Logo
|  | 0.5 | Update Status Doc
|  | 1 | Forward all servlets to the error page in case of an exception
|  | 3 | Package up project for delivery
|  | 13.5 | TOTAL TIME
Issues

## 2-Wk10
Second Term - Week 10
Accomplished this week
Done? | ACT | EST | Task
Y | 4 | 4 | Final Presentations
Y | 1 | 1 | Presentation Prep
Y | 3 | 2 | Update Documentation
N | 0 | 2 | Mouseover for Sigsoft Logo
Y | 0.5 | 0.5 | Update Status Doc
Y | 1 | 1 | Forward all servlets to the error page in case of an exception
|  | 3 | Package up project for delivery
| 9.5 | 13.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1 | Reflection Meeting
|  | 2 | Mouseover for Sigsoft Logo
|  | 3 | Bug Fixes
|  | 2 | Technical Report
|  | 8 | Server Configuration and Deployment
|  | 16 | TOTAL TIME
Issues

## 2-Finals
Second Term - Finals Week
Accomplished this week
Done? | ACT | EST | Task
Y | 1 | 1 | Reflection Meeting
N | 0 | 2 | Mouseover for Sigsoft Logo
Y | 4 | 3 | Bug Fixes
Y | 2 | 2 | Technical Report
Y | 10 | 8 | Server Configuration and Deployment
| 17 | 16 | TOTAL TIME
Issues

## AllData
t1-1a | t1-2e | t1-2a | t1-3e | t1-3a | t1-4e | t1-4a | t1-5e | t1-5a | t1-6e | t1-6a | t1-7e | t1-7a | t1-8e | t1-8a | t1-9e | t1-9a | t1-10e | t1-10a | wt1-fe | t1-fa
8 | 10.5 | 11 | 11.5 | 10.5 | 18 | 19 | 13 | 13 | 12 | 7 | 14 | 18 | 15 | 7 | 14 | 8 | 13 | 11 | 8 | 8
t2-1e | t2-1a | t2-2e | t2-2a | t2-3e | t2-3a | t2-4e | t2-4a | t2-5e | t2-5a | t2-6e | t2-6a | t2-7e | t2-7a | t2-8e | t2-8a | t2-9e | t2-9a | t2-10e | t2-10a | t2-fe | t2-fa
9 | 10 | 9.5 | 10.5 | 15.5 | 27 | 15 | 16 | 18 | 10 | 15.5 | 14 | 11.5 | 9.5 | 14.5 | 14.5 | 12.5 | 10.5 | 13.5 | 9.5 | 16 | 17