## Final Delivery
TERM 1 | Week4Iter2(12/04-12/11) | Week3Iter2(11/29-12/04) | Week2Iter2(11/21-11/28) | Week1Iter2(11/14-11/20) | Iteration 2 | Iteration 1 | Iteration 0
Project: | 34.6833 | 27.88 | 26.25 | 48.5 | 137.3133 | 85.8003 | 169.87
Product: | 64.0093 | 10.25 | 24.911 | 0 | 99.1703 | 32.5
Total: | 99.9426 | 38.13 | 51.161 | 48.5 | 237.7336 | 121.3003 | 169.87
Estimated Hours: | 104.05 | 24.15 | 43.5 | 41 | 212.7 | 108.497 | 158.62
Curtis Burtner | 29.41 | 13.87 | 19.317 | 16 | 78.597 | 33.75 | 40.83
Michael Yeaple | 36.5426 | 7.52 | 12.037 | 10 | 66.0996 | 57.5503 | 55.83
Jeremy Shulman | 19.74 | 7.37 | 13.537 | 9.5 | 50.147 | 23.25 | 38.08
Mustafa Al-Salihi | 14.25 | 9.37 | 6.27 | 13 | 42.89 | 6.75 | 35.13
TERM 2 | Week1Sprint1 | Week2Sprint1 | Sprint1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6 | Sprint 7
Project: | 6.5667 | 9.95 | 16.5167 | 8.75 | 6.25 | 5.2167 | 2.85 | 3.7 | 1.2
Product: | 16.5833 | 65.83 | 82.4133 | 72.5833 | 97.1433 | 86.9667 | 74.5 | 114.05 | 143.5
Total: | 23.15 | 75.78 | 98.93 | 81.3333 | 103.3933 | 92.1834 | 77.35 | 117.75 | 144.7
Estimated Hours: | 21.1833 | 68.4 | 89.5833 | 68.25 | 67.9 | 77 | 64.7 | 112.5 | 108.25
Curtis Burtner | 10.1 | 16.9 | 27 | 16.75 | 27.65 | 20.4 | 25.25 | 14.7 | 50.7
Michael Yeaple | 7 | 21.48 | 28.48 | 25.1333 | 37.76 | 26.45 | 67.9167 | 39.25 | 54.5
Jeremy Shulman | 4.75 | 17.25 | 22 | 15.25 | 20.5 | 13 | 14.25 | 14.5 | 31.75
Mustafa Al-Salihi | 2.75 | 20.15 | 22.9 | 1 | 23.45 | 2.3 | 22.5 | 21.55 | 14.75
Total: | 1284.035
Estimated Hours: | 1125.967
Curtis Burtner | 346.79
Michael Yeaple | 487.018
Jeremy Shulman | 244.057
Mustafa Al-Salihi | 194.47

## Effort Tracking
ID | Work Item Type | Title | State | Assigned To | Original Estimate | Remaining Work | Completed Work | Closed Date | Iteration Path | Tags |  | Week1Sprint1 | Week2Sprint1 | Sprint1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6 | Sprint 7 | All Time |  | Week1Sprint 1 | Week2Sprint1 | Sprint2 | Sprint3 | Sprint4 | Sprint5 | Sprint6 | Sprint7
740 | Task | IT Manager Meeting 5/20 | Closed | Michael Yeaple | 1 | 0 | 2 | 2015-05-21 13:10 | Simpply\Iteration 9 |  | Project: | 6.56667 | 9.95000 | 16.51667 | 8.75 | 6.25 | 5.21667 | 2.85 | 3.7 | 1.2 |  | Start: | >01/29/2015 | >02/05/2015 | >02/13/2015 | >02/27/2015 | >03/12/2015 | >04/02/2015 | >04/16/2015 | >04/30/2015
792 | Task | Wegmans Presentation Meeting | Closed | Jeremy Shulman |  |  | 2 | 2015-05-21 13:10 | Simpply\Iteration 9 | Planning Meeting | Product: | 16.58333 | 65.83000 | 82.41333 | 72.58334 | 97.14333 | 86.96670 | 74.50000 | 114.05000 | 143.50000 |  | End: | <02/05/2015 | <02/13/2015 | <02/26/2015 | <03/12/2015 | <04/02/2015 | <04/16/2015 | <04/30/2015 | <05/22/2015
743 | Task | IT Manager Meeting 5/20 | Closed | Mustafa Al-Salihi | 1 | 0 | 2 | 2015-05-21 13:10 | Simpply\Iteration 9 |  | Total: | 23.15000 | 75.78000 | 98.93000 | 81.33334 | 103.39333 | 92.18337 | 77.35000 | 117.75000 | 144.70000 | 1114.164903
750 | Task | Technical Report Meeting | Closed | Mustafa Al-Salihi | 1.25 | 1.25 | 0 | 2015-05-21 13:10 | Simpply\Iteration 9 | Academic Work Meeting | Estimated Hours: | 21.18333 | 68.4 | 89.58333 | 68.25 | 67.9 | 77 | 64.7 | 112.5 | 108.25 | 967.34733
683 | Task | Technical Report Work | Closed | Michael Yeaple | 10 | 0 | 11 | 2015-05-21 13:09 | Simpply\Iteration 9 | Academic Work Effort
773 | Task | Deployment Help | Closed | Michael Yeaple |  |  | 2.75 | 2015-05-21 13:09 | Simpply\Iteration 9 | Deployment | Curtis Burtner | 10.1 | 16.9 | 27.00000 | 16.75 | 27.65 | 20.4 | 25.25 | 14.7 | 50.7 | 305.9603
761 | Task | Presentation Adjustment + Practice | Closed | Jeremy Shulman | 1.5 | 0 | 1.5 | 2015-05-21 13:09 | Simpply\Iteration 9 | Academic Work Meeting | Michael Yeaple | 7 | 21.48 | 28.48000 | 25.133337 | 37.76 | 26.45 | 67.9167 | 39.25 | 54.5 | 431.1876033
741 | Task | IT Manager Meeting 5/20 | Closed | Jeremy Shulman | 1 | 0 | 2 | 2015-05-21 13:09 | Simpply\Iteration 9 |  | Jeremy Shulman | 4.75 | 17.25 | 22.00000 | 15.25 | 20.5 | 13 | 14.25 | 14.5 | 31.75 | 205.977
749 | Task | Technical Report Meeting | Closed | Jeremy Shulman | 1.25 |  | 4.5 | 2015-05-21 13:09 | Simpply\Iteration 9 | Academic Work Meeting | Mustafa Al-Salihi | 2.75 | 20.15 | 22.90000 | 1 | 23.45 | 2.3 | 22.5 | 21.55 | 14.75 | 159.34
742 | Task | IT Manager Meeting 5/20 | Closed | Curtis Burtner | 1 | 0 | 2 | 2015-05-21 13:09 | Simpply\Iteration 9
699 | Task | Technical Report Work | Closed | Curtis Burtner | 10 | 0 | 10 | 2015-05-21 13:08 | Simpply\Iteration 9 | Academic Work Effort | TFS Source Query: http://simpply.se.rit.edu:8080/tfs/DefaultCollection/Simpply/_workitems#path=Shared+Queries%2FIndividual+Report+(WiP)&_a=query
793 | Task | 5/19 Customer Status Update Email | Closed | Curtis Burtner | 0.75 | 0 | 0.75 | 2015-05-19 11:00 | Simpply | Process/Project Management Effort
735 | Task | Post-Mortem Internal Team Meeting | Closed | Mustafa Al-Salihi | 2.5 | 0 | 3 | 2015-05-19 10:33 | Simpply\Iteration 9 | Academic Work Meeting
780 | Task | Delete From Finalized Distribution Information table during import | Closed | Curtis Burtner | 0.5 | 0.5 | 0 | 2015-05-19 10:33 | Simpply\Iteration 9 | Bug
790 | Task | Wegmans Presentation Meeting | Closed | Michael Yeaple |  |  | 1 | 2015-05-19 10:32 | Simpply\Iteration 9 | Planning Meeting | Tags | Total | Curtis Butner | Jeremy Shulman | Michael Yeaple | Mustafa Al-Salihi
791 | Task | Wegmans Presentation Meeting | Closed | Curtis Burtner |  |  | 1 | 2015-05-19 10:32 | Simpply\Iteration 9 | Planning Meeting | Academic Work Effort | 57.317 | 16.5 | 0 | 23.5 | 0
751 | Task | Technical Report Meeting | Closed | Curtis Burtner | 1.25 | 0 | 2 | 2015-05-18 22:56 | Simpply\Iteration 9 | Academic Work Meeting | Academic Work Meeting | 117.23 | 18.5 | 21 | 22.5 | 8.75
748 | Task | Technical Report Meeting | Closed | Michael Yeaple | 1.25 | 0 | 2 | 2015-05-18 22:55 | Simpply\Iteration 9 | Academic Work Meeting | Bugs | 37.41666 | 6.5 | 2.25 | 27.16666 | 1.5
753 | Task | Time & Effort Tracking, Metrics | Closed | Curtis Burtner | 4 | 0 | 4 | 2015-05-15 16:18 | Simpply\Iteration 9 | Process/Project Management Effort | Code/Design Review | 13.25 | 1.5 | 0 | 0 | 0
788 | Task | Bug Fixes Post On-site Meeting | Closed | Michael Yeaple |  |  | 0.25 | 2015-05-15 09:32 | Simpply\Iteration 9 | Bugs | Design Effort | 55.366667 | 11.75 | 10.25 | 16.866667 | 7
787 | Task | Bug fixes from 5/14 on-site meeting notes | Closed | Curtis Burtner |  | 0 | 0.5 | 2015-05-15 08:43 | Simpply\Iteration 9 | Bug | Design Meeting | 50.9676 | 15.0603 | 14.527 | 15.1103 | 4.77
707 | Task | Log Error States | Closed | Jeremy Shulman | 1 | 0 | 2 | 2015-05-15 03:50 | Simpply\Iteration 9 | Implementation | Implementation | 329.7269663 | 83.1 | 38.75 | 141.4263663 | 12.3
739 | Task | Post-Mortem Meeting | Closed | Mustafa Al-Salihi | 1.25 | 0 | 1.25 | 2015-05-14 19:41 | Simpply\Iteration 9 | Academic Work Meeting | Planning Meeting | 83 | 13.75 | 19.75 | 21.5 | 3
746 | Task | Deployment Meeting at Wegmans | Closed | Mustafa Al-Salihi | 4 | 0 | 4.5 | 2015-05-14 19:41 | Simpply\Iteration 9 | Deployment | Process/Project Management Effort | 70.76667 | 18.6 | 0 | 1.16667 | 0
778 | Task | Prepare for Wegmans Deployment Meeting | Closed | Mustafa Al-Salihi | 0.5 | 0 | 0 | 2015-05-14 19:41 | Simpply\Iteration 9 | Planning Meeting | Process/Project Management Meeting | 7.75 | 5.25 | 1.25 | 1.25 | 0
776 | Task | Prepare for Wegmans Deployment Meeting | Closed | Michael Yeaple | 1 | 0 | 1 | 2015-05-14 19:41 | Simpply\Iteration 9 | Planning Meeting | Project Setup | 33 | 1.25 | 0 | 4.25 | 0
744 | Task | Deployment Meeting at Wegmans | Closed | Michael Yeaple | 4 | 0 | 4.5 | 2015-05-14 19:41 | Simpply\Iteration 9 | Deployment | Progress Meeting | 11.25 | 0 | 1.25 | 1.25 | 0
736 | Task | Post-Mortem Meeting | Closed | Michael Yeaple | 1.25 | 0 | 1.25 | 2015-05-14 19:41 | Simpply\Iteration 9 | Academic Work Meeting | Refactoring | 8.75 | 0 | 0 | 0 | 0
737 | Task | Post-Mortem Meeting | Closed | Jeremy Shulman | 1.25 | 0 | 1.25 | 2015-05-14 19:40 | Simpply\Iteration 9 | Academic Work Meeting | Requirements Effort | 0.5 | 0.5 | 0 | 0 | 0
747 | Task | Deployment Meeting at Wegmans | Closed | Jeremy Shulman | 4 | 0 | 4.5 | 2015-05-14 19:40 | Simpply\Iteration 9 | Deployment | Requirements Meeting | 23.5 | 2.5 | 4 | 5 | 1
779 | Task | Prepare for Wegmans Deployment Meeting | Closed | Jeremy Shulman | 0.5 | 0 | 0.5 | 2015-05-14 19:40 | Simpply\Iteration 9 | Planning Meeting | Testing Effort | 22.11667 | 0 | 0.5 | 17.61667 | 0
745 | Task | Deployment Meeting at Wegmans | Closed | Curtis Burtner | 4 | 0 | 4.5 | 2015-05-14 19:39 | Simpply\Iteration 9 | Deployment
738 | Task | Post-Mortem Meeting | Closed | Curtis Burtner | 1.25 | 0 | 1.25 | 2015-05-14 19:39 | Simpply\Iteration 9 | Academic Work Meeting | Total: | 899.7915633 | 194.7603 | 113.027 | 280.9866633 | 38.32
777 | Task | Prepare for Wegmans Deployment Meeting | Closed | Curtis Burtner | 1 | 0 | 1 | 2015-05-14 18:28 | Simpply\Iteration 9 | Planning Meeting | All Tasks: | 1114.164903
775 | Task | 5/12 Presentation Watching | Closed | Curtis Burtner | 2.5 | 0 | 2.5 | 2015-05-14 09:37 | Simpply\Iteration 9 | Academic Work Effort
774 | Task | Attend presentations | Closed | Michael Yeaple | 5 | 0 | 5 | 2015-05-14 09:36 | Simpply\Iteration 9 | Academic Work Effort | Meeting Hours: | 293.6976
768 | Task | Run algorithm doesn't work when an item is finalized | Closed | Michael Yeaple |  |  | 0.5 | 2015-05-14 09:06 | Simpply\Iteration 9 | Bugs
762 | Task | Presentation Adjustment + Practice | Closed | Mustafa Al-Salihi | 1.5 | 0 | 1.5 | 2015-05-12 06:34 | Simpply\Iteration 9 | Academic Work Meeting
763 | Task | Presentation practice | Closed | Jeremy Shulman | 4 | 0 | 4 | 2015-05-12 06:33 | Simpply\Iteration 9 | Academic Work Meeting
772 | Task | 5/11 Self Assessment Meeting | Closed | Curtis Burtner | 3.5 | 0 | 3.5 | 2015-05-11 21:57 | Simpply\Iteration 9 | Academic Work Meeting
771 | Task | 5/11 reflection and post mordem work | Closed | Jeremy Shulman | 3 |  | 3 | 2015-05-11 21:56 | Simpply\Iteration 9 | Academic Work Meeting | Tags | Total
732 | Task | Post-Mortem Internal Team Meeting | Closed | Michael Yeaple | 2.5 | 0 | 3.5 | 2015-05-11 21:55 | Simpply\Iteration 9 | Academic Work Meeting | Academic Work Effort | 0
730 | Task | Practice Presentation | Closed | Michael Yeaple | 1.5 | 0 | 3 | 2015-05-10 08:49 | Simpply\Iteration 9 | Academic Work Meeting | Academic Work Meeting | 70.75
770 | Task | 5/9 Email to Martinez | Closed | Curtis Burtner | 0.45 | 0 | 0.45 | 2015-05-09 20:29 | Simpply | Process/Project Management Effort | Bugs | 37.41666
769 | Task | 5/7 Presentation Day | Closed | Curtis Burtner | 2.5 | 0 | 2.5 | 2015-05-09 12:45 | Simpply\Iteration 9 | Academic Work Effort | Code/Design Review | 0
767 | Task | Item details bugs | Closed | Curtis Burtner | 1 | 0 | 2 | 2015-05-09 12:44 | Simpply\Iteration 9 | Bugs | Design Effort | 26.366667
760 | Task | Presentation Adjustment + Practice | Closed | Michael Yeaple | 1.5 | 0 | 3 | 2015-05-06 19:40 | Simpply\Iteration 9 | Academic Work Meeting | Design Meeting | 0
764 | Task | 5/5 meeting | Closed | Jeremy Shulman | 1.25 | 0 | 2.5 | 2015-05-06 19:15 | Simpply\Iteration 9 | Academic Work Meeting | Implementation | 233.9567
759 | Task | Presentation Adjustment + Practice | Closed | Curtis Burtner | 1.5 | 0 | 1.5 | 2015-05-06 18:55 | Simpply\Iteration 9 | Academic Work Meeting | Planning Meeting | 0
758 | Task | Practice Presentation | Closed | Curtis Burtner | 1.5 | 1 | 2.25 | 2015-05-06 14:22 | Simpply\Iteration 9 | Academic Work Meeting | Process/Project Management Effort | 19.76667
757 | Task | Presentation Meeting | Closed | Mustafa Al-Salihi | 1.25 | 0 | 2.5 | 2015-05-05 19:24 | Simpply\Iteration 9 | Academic Work Meeting | Process/Project Management Meeting | 0
756 | Task | Presentation Meeting | Closed | Jeremy Shulman | 1.25 | 0 | 2.5 | 2015-05-05 19:24 | Simpply\Iteration 9 | Academic Work Meeting | Project Setup | 0
755 | Task | Presentation Meeting | Closed | Curtis Burtner | 1.25 | 0 | 3.5 | 2015-05-05 19:24 | Simpply\Iteration 9 | Academic Work Meeting | Progress Meeting | 0
754 | Task | Presentation Meeting | Closed | Michael Yeaple | 1.25 | 0 | 3.5 | 2015-05-05 19:22 | Simpply\Iteration 9 | Academic Work Meeting | Refactoring | 0
728 | Task | Presentation Template | Closed | Michael Yeaple | 1 | 1 | 0 | 2015-05-05 19:21 | Simpply\Iteration 9 | Academic Work Effort | Requirements Effort | 0
725 | Task | Log Complex Code Sections | Closed | Michael Yeaple | 1 | 0 | 1 | 2015-05-04 19:57 | Simpply\Iteration 9 | Implementation | Requirements Meeting | 0
722 | Task | Log User Flow | Closed | Michael Yeaple | 1 | 0 | 1.5 | 2015-05-04 19:57 | Simpply\Iteration 9 | Implementation | Testing Effort | 18.11667
720 | Task | Log Error States | Closed | Michael Yeaple | 1 | 0 | 1.5 | 2015-05-04 19:57 | Simpply\Iteration 9 | Implementation
588 | User Story | Technical Report 1st Draft | Closed |  |  |  |  | 2015-05-04 10:21 | Simpply\Iteration 8
646 | Task | Set up template/outline | Closed | Jeremy Shulman |  |  |  | 2015-04-07 17:50 | Simpply\Iteration 8 | Academic Work Effort | Meeting Hours: | 70.75
647 | Task | Set up template/outline | Closed | Michael Yeaple |  |  |  | 2015-04-07 17:50 | Simpply\Iteration 8 | Academic Work Effort | Individual Hours: | 335.623367
648 | Task | Set up template/outline | Closed | Mustafa Al-Salihi |  |  |  | 2015-04-07 17:50 | Simpply\Iteration 8 | Academic Work Effort
649 | Task | Set up template/outline | Closed | Curtis Burtner |  |  |  | 2015-04-07 17:50 | Simpply\Iteration 8 | Academic Work Effort
580 | User Story | Have Wegmans Data Import Job Calculate Static Data | Closed | Curtis Burtner |  |  |  | 2015-05-04 10:21 | Simpply\Iteration 8 | Refactoring | Tags | Total
632 | Task | Implement for Items Table | Closed | Curtis Burtner | 2 | 0 | 2.5 | 2015-05-04 10:20 | Simpply\Iteration 8 | Implementation | Academic Work Effort | 0
589 | User Story | Poster 1st Draft | Closed |  |  |  |  | 2015-05-04 10:21 | Simpply\Iteration 8 |  | Academic Work Meeting | 0
698 | Task | Poster Final Revision | Closed | Mustafa Al-Salihi | 2.5 | 0 | 2.3 | 2015-04-22 11:26 | Simpply\Iteration 8 |  | Bugs | 0
697 | Task | Poster 2nd Draft | Closed | Mustafa Al-Salihi | 7 | 0 | 6.5 | 2015-04-22 11:25 | Simpply\Iteration 8 |  | Code/Design Review | 0
696 | Task | Poster 1st Draft | Closed | Mustafa Al-Salihi | 10.5 | 0 | 9.25 | 2015-04-22 11:24 | Simpply\Iteration 8 |  | Design Effort | 0
691 | Task | Group effort at Mustafa's | Closed | Jeremy Shulman | 3 | 0 | 4.5 | 2015-04-21 17:07 | Simpply\Iteration 8 |  | Design Meeting | 0
663 | Task | Screenshots of UI Evolution | Closed | Curtis Burtner | 1 | 0 | 0.5 | 2015-04-20 09:14 | Simpply\Iteration 8 |  | Implementation | 0
635 | Task | Decide included content | Closed | Jeremy Shulman |  |  |  | 2015-04-20 09:14 | Simpply\Iteration 8 | Planning Effort | Planning Meeting | 0
641 | Task | Decide included content | Closed | Curtis Burtner |  |  |  | 2015-04-20 09:14 | Simpply\Iteration 8 | Planning Effort | Process/Project Management Effort | 0
639 | Task | Decide included content | Closed | Mustafa Al-Salihi | 3 | 0 | 3 | 2015-04-20 09:14 | Simpply\Iteration 8 | Planning Effort | Process/Project Management Meeting | 0
640 | Task | Decide included content | Closed | Michael Yeaple |  |  |  | 2015-04-18 15:20 | Simpply\Iteration 8 | Planning Effort | Project Setup | 0
603 | User Story | Fix Bugs (Individual Tasks Tagged) | Closed |  |  |  |  | 2015-05-04 10:21 | Simpply\Iteration 8 |  | Progress Meeting | 0
624 | Task | Add indexes to tables where necessary for performance improvement | Closed | Michael Yeaple | 2.5 | 0 | 5 | 2015-04-23 15:07 | Simpply\Iteration 8 | Implementation | Refactoring | 0
595 | Task | Item explorer displaying all items errors | Closed | Mustafa Al-Salihi | 0.5 | 0 | 1.5 | 2015-04-14 21:25 | Simpply\Iteration 8 | Bugs | Requirements Effort | 0
626 | Task | Job completion message on item details | Closed | Jeremy Shulman | 1 | 0 | 1 | 2015-04-13 22:13 | Simpply\Iteration 8 | Bugs | Requirements Meeting | 0
591 | Task | Sorting does not work on the season/pog explorer | Closed | Curtis Burtner | 1 | 0 | 0.25 | 2015-04-10 15:02 | Simpply\Iteration 8 | Bugs | Testing Effort | 0
600 | Task | Item explorer columns are not all sortable | Closed | Curtis Burtner | 3 | 0 | 1.25 | 2015-04-10 13:44 | Simpply\Iteration 8 | Bug
601 | Task | Sell-Thru Algorithm does not run after the Import Data Job Runs | Closed | Curtis Burtner | 1 | 0 | 0.25 | 2015-04-09 20:17 | Simpply\Iteration 8 | Bugs
618 | Task | Navigate away from the item details when data has changed doesn’t prompt about unsaved changes anymore | Closed | Michael Yeaple | 0.5 | 0 | 0.5 | 2015-04-08 16:08 | Simpply\Iteration 8 | Bugs
599 | Task | Forms currently are able to be submitted multiple times | Closed | Michael Yeaple | 1 | 0 | 1 | 2015-04-08 14:34 | Simpply\Iteration 8 | Bugs
604 | User Story | UI Improvements (Individual Tasks Tagged) | Closed |  |  |  |  | 2015-05-04 10:21 | Simpply\Iteration 8
625 | Task | Make sure all columns have data | Closed | Curtis Burtner | 1 | 0 | 1 | 2015-05-04 10:21 | Simpply\Iteration 8 | Implementation
621 | Task | Standardize column names | Closed | Curtis Burtner | 1 | 1 | 0 | 2015-05-04 10:20 | Simpply\Iteration 8 | Implementation
616 | Task | Reduce table cell padding/font size/margins | Closed | Michael Yeaple | 0.5 | 0 | 0.5 | 2015-04-28 12:25 | Simpply\Iteration 8 | Implementation
671 | Task | Border around ship amount | Closed | Jeremy Shulman | 0.5 |  | 0.5 | 2015-04-14 21:47 | Simpply\Iteration 8 | Implementation
670 | Task | Number formatting improvements | Closed | Jeremy Shulman | 0.5 | 0 | 0.5 | 2015-04-14 21:21 | Simpply\Iteration 8 | Implementation
731 | Task | Sprint Planning | Closed | Michael Yeaple | 0.5 | 0 | 0.75 | 2015-05-04 10:03 | Simpply\Iteration 9 | Planning Effort
20 | Task | New user stories from on site shadowing | Closed |  |  |  |  | 2015-05-04 09:58 | Simpply\Iteration 1 | Requirements Effort
21 | Task | New wireframes from on site shadowing | Closed |  |  |  |  | 2015-05-04 09:58 | Simpply\Iteration 1 | Requirements Effort | Tags |  |  | Wk3Iteration 2 | Wk2Iteration 2 | Wk1Iteration 2 | Iteration 2 | Iteration 1 | Iteration 0
22 | Task | Jessi will send us screenshots of excel + powerpoint | Closed | Wegmans |  |  |  | 2015-05-04 09:58 | Simpply\Iteration 1 | Requirements Effort | Academic Work Effort |  |  | 0 | 0 | 0 | 0 | 0 | 0
24 | Task | Write use cases | Closed |  |  |  |  | 2015-05-04 09:58 | Simpply\Iteration 1 | Requirements Effort | Academic Work Meeting |  |  | 0 | 0 | 0 | 0 | 0 | 0
28 | Task | Make functional requirements | Closed |  |  |  |  | 2015-05-04 09:58 | Simpply\Iteration 1 | Requirements Effort | Bugs |  |  | 0.25 | 0 | 3.25 | 6.48333 | 14.85 | 0
29 | Task | Architecturally significant requirements | Closed |  |  |  |  | 2015-05-04 09:58 | Simpply\Iteration 1 | Requirements Effort | Code/Design Review |  |  | 1.5 | 0 | 0 | 0 | 0 | 0
727 | Task | Import into Items and Sales Information fixes | Closed | Curtis Burtner | 2 | 0 | 2 | 2015-05-01 07:03 | Simpply\Iteration 9 | Implementation | Design Effort |  |  | 8.5 | 3.866667 | 9 | 3 | 1 | 0
726 | Task | Bug fixes post-demo | Closed | Michael Yeaple | 1.5 | 0 | 3.5 | 2015-05-01 01:31 | Simpply\Iteration 9 | Bugs | Design Meeting |  |  | 0 | 3.5 | 3 | 0 | 3.75 | 0
705 | Task | 4/30 Meeting | Closed | Michael Yeaple | 1.25 | 0 | 1.25 | 2015-04-30 23:38 | Simpply\Iteration 8 | Progress Meeting | Implementation |  |  | 32.23 | 23.4 | 46.91 | 27.6 | 64.8667 | 0
676 | Task | Deploy | Closed | Michael Yeaple | 1.5 | 0 | 0.75 | 2015-04-30 14:49 | Simpply\Iteration 8 | Deployment | Planning Meeting |  |  | 9.75 | 4.5 | 6.5 | 10 | 2.25 | 0
713 | Task | Job Conflict Checks | Closed | Jeremy Shulman | 1.5 | 0 | 1.5 | 2015-04-30 00:05 | Simpply\Iteration 8 | Implementation | Process/Project Management Effort |  |  | 1.4 | 3.75 | 1.5 | 4.56667 | 1.5 | 0
657 | Task | Pair Program Mike/Jeremy | Closed | Jeremy Shulman | 2 | 0 | 2.5 | 2015-04-29 22:04 | Simpply\Iteration 8 | Implementation | Process/Project Management Meeting |  |  | 0 | 0 | 0 | 1.75 | 2.25 | 0
654 | Task | Pair Program Algorithms with Jeremy | Closed | Michael Yeaple | 5 | 3.5 | 2.5 | 2015-04-29 16:03 | Simpply\Iteration 8 | Implementation | Project Setup |  |  | 0 | 0 | 0 | 0 | 0 | 0
711 | Task | UI Consistency/Formatting Fixes/Tweaks | Closed | Michael Yeaple | 1 | 0 | 4.75 | 2015-04-29 16:01 | Simpply\Iteration 8 | Implementation | Progress Meeting |  |  | 0 | 0 | 0 | 0 | 1.25 | 0
613 | Task | Test application in 1366x768 and note other improvements | Closed | Jeremy Shulman | 1 | 0 |  | 2015-04-29 15:01 | Simpply\Polish And Fix (Iteration 7) | Testing Effort | Refactoring |  |  | 0 | 0 | 0 | 0 | 0 | 0
678 | Task | Make progress bars dismissible upon completion | Closed | Jeremy Shulman | 1 | 0 | 1 | 2015-04-29 13:19 | Simpply\Iteration 8 | Implementation | Requirements Effort |  |  | 0 | 0 | 0.5 | 0 | 0 | 0
717 | Task | 4/29 Customer Email | Closed | Curtis Burtner | 0.5 | 0 | 0.5 | 2015-04-29 03:20 | Simpply\Iteration 8 | Process/Project Management Effort | Requirements Meeting |  |  | 0 | 3 | 0 | 0 | 5 | 0
716 | Task | 4/28 Meeting | Closed | Curtis Burtner | 1.25 | 0 | 1.25 | 2015-04-29 02:54 | Simpply\Iteration 8 | Implementation | Testing Effort |  |  | 2 | 5.11667 | 0 | 0.5 | 9.5 | 0
712 | Task | 4/28 Meeting | Closed | Jeremy Shulman | 1.25 | 0 | 1.25 | 2015-04-28 18:05 | Simpply\Iteration 8 | Academic Work Meeting
706 | Task | 4/28 Meeting | Closed | Michael Yeaple | 1.25 | 0 | 1.25 | 2015-04-28 18:04 | Simpply\Iteration 8 | Academic Work Meeting | Total: |  |  | 53.63 | 42.016667 | 70.66 | 53.4 | 96.7167 | 0
679 | Task | Finalize Distribution Tweaks | Closed | Michael Yeaple | 0.5 | 0 | 0.75 | 2015-04-28 11:46 | Simpply\Iteration 8 | Implementation
710 | Task | 4/22 + 4/27 Customer Emails | Closed | Curtis Burtner | 0.45 | 0 | 0.45 | 2015-04-28 06:09 | Simpply | Process/Project Management Effort
703 | Task | 4/23 Meeting | Closed | Jeremy Shulman | 1.25 | 0 | 1.25 | 2015-04-23 18:10 | Simpply\Iteration 8 | Planning Meeting
704 | Task | 4/23 Meeting | Closed | Curtis Burtner | 1.25 | 0 | 1.25 | 2015-04-23 18:10 | Simpply\Iteration 8 | Planning Meeting
702 | Task | 4/23 Meeting | Closed | Michael Yeaple | 1.25 | 0 | 1.25 | 2015-04-23 18:10 | Simpply\Iteration 8 | Planning Meeting
665 | Task | Check for broken links | Closed | Michael Yeaple | 0.75 | 0 | 3.25 | 2015-04-23 16:11 | Simpply\Iteration 8 | Bugs
701 | Task | Clean up unused code | Closed | Michael Yeaple | 1.5 | 0 | 1.5 | 2015-04-23 16:10 | Simpply\Iteration 8 | Implementation
700 | Task | 4/21 Poster Session Online | Closed | Curtis Burtner | 1.5 | 0 | 1.5 | 2015-04-22 11:57 | Simpply\Iteration 8 | Academic Work Effort
695 | Task | 4/21 Meeting | Closed | Michael Yeaple | 1.25 | 0 | 1.25 | 2015-04-21 22:25 | Simpply\Iteration 8 | Planning Meeting
694 | Task | 4/21 meeting | Closed | Jeremy Shulman | 1.25 | 0 | 1.25 | 2015-04-21 17:14 | Simpply\Iteration 8 | Planning Meeting
688 | Task | Review Poster Mock Up v2.0 | Closed | Curtis Burtner | 0.5 | 0 | 0.5 | 2015-04-20 20:38 | Simpply\Iteration 8 | Academic Work Meeting
689 | Task | Review Poster Mock Up v2.0 | Closed | Jeremy Shulman | 0.5 | 0 | 0.5 | 2015-04-20 20:38 | Simpply\Iteration 8 | Academic Work Meeting
687 | Task | Review Poster Mock Up v2.0 | Closed | Michael Yeaple | 0.5 | 0 | 0.5 | 2015-04-20 20:37 | Simpply\Iteration 8 | Academic Work Meeting
690 | Task | Review Poster Mock Up v2.0 | Closed | Mustafa Al-Salihi | 0.5 | 0 | 0.5 | 2015-04-20 20:37 | Simpply\Iteration 8 | Academic Work Meeting
686 | Task | Poster Mock Up - Redo | Closed | Michael Yeaple | 3 | 0 | 4 | 2015-04-20 20:35 | Simpply\Iteration 8 | Academic Work Effort
685 | Task | Poster - Architecture Diagram - Redo | Closed | Michael Yeaple | 1 | 0 | 2 | 2015-04-20 20:34 | Simpply\Iteration 8 | Academic Work Effort
651 | Task | 4/16 Customer Meeting + Demo | Closed | Jeremy Shulman | 1.25 | 0 | 1.25 | 2015-04-20 17:31 | Simpply\Polish And Fix (Iteration 7) | Planning Meeting
684 | Task | 4/18 Poster Session | Closed | Curtis Burtner | 3 | 0 | 4 | 2015-04-20 09:58 | Simpply\Iteration 8 | Academic Work Meeting
680 | Task | Item Details - Edit Column Preferences - Include Algorithm Columns | Closed | Curtis Burtner | 2 | 0 | 1.5 | 2015-04-20 09:57 | Simpply\Iteration 8 | Implementation
681 | Task | “Units Remaining” instead of “Calculated Inventory” | Closed | Michael Yeaple | 0.5 | 0 | 0.25 | 2015-04-20 09:37 | Simpply\Iteration 8 | Implementation
674 | Task | Poster Meeting | Closed | Michael Yeaple | 3 | 0 | 4.5 | 2015-04-19 20:06 | Simpply\Iteration 8 | Academic Work Meeting
675 | Task | Poster - Architecture Section | Closed | Michael Yeaple | 1 | 0 | 1.5 | 2015-04-18 16:03 | Simpply\Iteration 8 | Academic Work Effort
645 | Task | 4/16 Meeting | Closed | Michael Yeaple | 1.25 | 0 | 1.25 | 2015-04-18 15:20 | Simpply\Polish And Fix (Iteration 7) | Planning Meeting
667 | Task | Deploy | Closed | Michael Yeaple | 2.5 | 0 | 2 | 2015-04-18 15:20 | Simpply\Polish And Fix (Iteration 7) | Deployment
669 | Task | Assist Wegmans Team with Deployment Issues | Closed | Michael Yeaple | 1 | 0 | 1.25 | 2015-04-18 15:19 | Simpply | Deployment
25 | Task | Figure out exactly what Jessi wants to see as far as data items | Closed | Curtis Burtner |  |  |  | 2015-04-18 09:52 | Simpply\Iteration 1 | Requirements Effort
26 | Task | Ask if they have any kind of internal web graphing tools | Closed | Curtis Burtner |  |  |  | 2015-04-18 09:52 | Simpply\Iteration 1 | Requirements Effort
512 | Task | 3/10 Planning Meeting | Closed | Curtis Burtner | 1.25 | 0 | 2 | 2015-04-18 09:52 | Simpply | Planning Meeting
546 | Task | Integration Testing | Closed | Curtis Burtner | 2 | 2 | 0 | 2015-04-18 09:52 | Simpply\Iteration 6 | Testing Effort
644 | Task | 4/16 Customer Meeting + Demo | Closed | Curtis Burtner | 1.25 | 0 | 1.25 | 2015-04-18 09:51 | Simpply\Polish And Fix (Iteration 7) | Planning Meeting
629 | User Story | Last Week Data -> Exactly 7 Days | Closed | Jeremy Shulman |  |  |  | 2015-04-18 09:46 | Simpply\Polish And Fix (Iteration 7)
660 | Task | Implementation | Closed | Jeremy Shulman | 5 | 0 | 3.5 | 2015-04-14 21:21 | Simpply\Polish And Fix (Iteration 7) | Implementation
659 | Task | Plan changes | Closed | Jeremy Shulman | 2 | 0 | 1 | 2015-04-13 23:18 | Simpply\Polish And Fix (Iteration 7) | Planning Effort
619 | User Story | Finalize Item Information | Closed | Michael Yeaple |  |  |  | 2015-04-18 09:46 | Simpply\Polish And Fix (Iteration 7)
633 | Task | Test Feature & Fix Bugs | Closed | Michael Yeaple | 1 | 0 | 6.5 | 2015-04-14 12:00 | Simpply\Polish And Fix (Iteration 7) | Testing Effort
631 | Task | Implementation | Closed | Michael Yeaple | 5 | 0 | 7.5 | 2015-04-13 23:14 | Simpply\Polish And Fix (Iteration 7) | Implementation
630 | Task | Design | Closed | Michael Yeaple | 1 | 0 | 1 | 2015-04-13 19:34 | Simpply\Polish And Fix (Iteration 7) | Design Effort
36 | User Story | Display Job Progress | Closed | Mustafa Al-Salihi |  |  |  | 2015-04-18 09:46 | Simpply\Polish And Fix (Iteration 7)
467 | Task | Integration | Closed |  | 1 | 0 | 2 | 2015-04-14 08:36 | Simpply\Polish And Fix (Iteration 7)
464 | Task | Unit Test | Closed |  | 2.5 | 0 | 0 | 2015-04-14 08:35 | Simpply\Polish And Fix (Iteration 7)
463 | Task | Class Design | Closed |  | 2 | 0 | 0.9 | 2015-04-14 08:35 | Simpply\Polish And Fix (Iteration 7)
468 | Task | Demo | Closed |  | 1.25 | 0 | 1.25 | 2015-04-14 08:35 | Simpply\Polish And Fix (Iteration 7)
465 | Task | Design Review | Closed |  | 1.25 | 0 | 1.3 | 2015-04-14 08:35 | Simpply\Polish And Fix (Iteration 7)
420 | Task | Implement GetJobStatus | Closed | Mustafa Al-Salihi | 1 | 0 | 2.3 | 2015-03-31 01:35 | Simpply\Polish And Fix (Iteration 7) | Implementation
590 | User Story | Edit Column Preferences for Item Details | Closed | Curtis Burtner |  |  |  | 2015-04-18 09:46 | Simpply\Polish And Fix (Iteration 7) | Implementation
655 | Task | Implement | Closed | Curtis Burtner | 5 | 0 | 5 | 2015-04-12 13:58 | Simpply\Polish And Fix (Iteration 7) | Implementation
672 | Task | Deployment tasks | Closed | Jeremy Shulman | 0.5 | 0 | 1 | 2015-04-16 15:54 | Simpply\Polish And Fix (Iteration 7) | Deployment
634 | Task | 4/7 Meeting | Closed | Curtis Burtner | 1.25 |  | 1.25 | 2015-04-14 22:04 | Simpply\Polish And Fix (Iteration 7) | Design Meeting
638 | Task | 4/09 Customer Meeting + Demo | Closed | Curtis Burtner | 1.25 | 0 | 1.25 | 2015-04-14 22:04 | Simpply\Polish And Fix (Iteration 7) | Process/Project Management Meeting
643 | Task | 4/14 Integration Meeting | Closed | Curtis Burtner | 1.25 | 0 | 1.25 | 2015-04-14 22:04 | Simpply\Polish And Fix (Iteration 7) | Testing Meeting
650 | Task | 4/14 Meeting | Closed | Jeremy Shulman | 1.25 | 0 | 1.25 | 2015-04-14 21:22 | Simpply\Polish And Fix (Iteration 7) | Testing Meeting
653 | Task | 4/9 Meeting | Closed | Jeremy Shulman | 1.25 | 0 | 1.25 | 2015-04-14 21:22 | Simpply\Polish And Fix (Iteration 7) | Requirements Meeting
642 | Task | 4/14 Meeting | Closed | Michael Yeaple | 1.25 | 0 | 1.25 | 2015-04-14 18:22 | Simpply\Polish And Fix (Iteration 7) | Testing Meeting
637 | Task | 4/9 Meeting | Closed | Michael Yeaple | 1.25 | 0 | 1.25 | 2015-04-14 17:48 | Simpply\Polish And Fix (Iteration 7) | Requirements Meeting
617 | Task | Smaller browser fixes for layout | Closed | Michael Yeaple | 3 | 0 | 5.75 | 2015-04-14 13:21 | Simpply\Polish And Fix (Iteration 7) | Bugs
668 | Task | Remove Spinner from Number Inputs in Distribution Grid | Closed | Michael Yeaple | 1 | 0 | 1.5 | 2015-04-14 13:21 | Simpply\Polish And Fix (Iteration 7) | Bugs
611 | Task | Test application in 1366x768 and note other improvements | Closed | Michael Yeaple | 1 | 0 | 1 | 2015-04-14 12:03 | Simpply\Polish And Fix (Iteration 7) | Testing Effort
547 | Task | Integration Testing | Closed | Jeremy Shulman | 2 | 2 | 0 | 2015-04-14 08:39 | Simpply\Iteration 6 | Testing Effort
548 | Task | Integration Testing | Closed | Mustafa Al-Salihi | 2 | 2 | 0 | 2015-04-14 08:39 | Simpply\Iteration 6 | Testing Effort
490 | Task | 3/3 Emails | Closed | Curtis Burtner | 0.5 | 0 | 0.5 | 2015-04-14 08:38 | Simpply | Process/Project Management Effort
666 | Task | Responsive Tables Wrong Title in Distribution Grid | Closed | Michael Yeaple | 0.5 | 0 | 0.5 | 2015-04-09 15:58 | Simpply\Polish And Fix (Iteration 7) | Implementation
664 | Task | Bug in Chart | Closed | Michael Yeaple | 0.5 | 0 | 1.25 | 2015-04-08 22:43 | Simpply\Polish And Fix (Iteration 7) | Bugs
381 | Task | Make Tables More Mobile Responsive | Closed | Michael Yeaple | 2 | 0 | 4 | 2015-04-08 22:43 | Simpply\Polish And Fix (Iteration 7) | Implementation
608 | Task | Shrink item details graph and put it next to aggregate info | Closed | Michael Yeaple | 0.5 | 0 | 0.5 | 2015-04-08 15:53 | Simpply\Polish And Fix (Iteration 7) | Bugs
615 | Task | Column Title Fixes | Closed | Michael Yeaple | 0.2 | 0 | 0.5 | 2015-04-08 15:53 | Simpply\Polish And Fix (Iteration 7) | Bugs
636 | Task | 4/7 Meeting | Closed | Michael Yeaple | 1.25 | 0 | 1.25 | 2015-04-07 18:19 | Simpply\Polish And Fix (Iteration 7) | Design Meeting
652 | Task | 4/7 Meeting | Closed | Jeremy Shulman | 1.25 | 0 | 1.25 | 2015-04-07 17:50 | Simpply\Polish And Fix (Iteration 7) | Design Meeting
662 | Task | 4/6 Status Update | Closed | Curtis Burtner | 0.5 | 0 | 0.5 | 2015-04-06 23:32 | Simpply | Process/Project Management Effort
661 | Task | User Testing 4/3 | Closed | Michael Yeaple | 1 | 0 | 1 | 2015-04-06 13:23 | Simpply\Polish And Fix (Iteration 7) | Testing Meeting
628 | Task | 4/4 Planning | Closed | Jeremy Shulman | 1 | 0 | 1 | 2015-04-04 08:57 | Simpply\Polish And Fix (Iteration 7) | Planning Meeting
534 | Task | Iteration 7 Planning/Validation Criteria | Closed | Michael Yeaple | 0.75 | 0 | 1 | 2015-04-04 08:57 | Simpply\Iteration 6 | Planning Effort
622 | Task | Quick fixes before 4/03 Meeting | Closed | Curtis Burtner | 0.75 | 0 | 0.75 | 2015-04-04 08:31 | Simpply\Iteration 6 | Implementation
620 | Task | 4/02 Customer Email | Closed | Curtis Burtner | 0.5 | 0 | 0.5 | 2015-04-04 08:30 | Simpply | Process/Project Management Effort
605 | Task | Customer Meeting + Demo | Closed | Curtis Burtner | 1 | 0 | 1 | 2015-04-04 08:15 | Simpply\Iteration 6 | Process/Project Management Meeting
602 | Task | Friday Customer Meeting 4/3 | Closed | Curtis Burtner | 1 | 0 | 1 | 2015-04-04 08:14 | Simpply | Testing Meeting
508 | User Story | Display Other Item Data on Item Explorer | Closed | Mustafa Al-Salihi |  |  |  | 2015-04-04 08:11 | Simpply\Iteration 6
552 | Task | Demo | Closed |  | 1.25 | 1.25 |  | 2015-04-14 08:39 | Simpply\Iteration 6
553 | Task | Code Review | Closed |  | 1.25 | 0 | 1.25 | 2015-04-02 16:06 | Simpply\Iteration 6
550 | Task | Unit Test | Closed |  | 2 | 2 | 0.5 | 2015-04-02 16:06 | Simpply\Iteration 6
549 | Task | Class Design | Closed |  | 1 | 0 | 1 | 2015-04-02 16:06 | Simpply\Iteration 6
551 | Task | Implementation | Closed | Mustafa Al-Salihi | 9 | 0 | 10 | 2015-04-02 16:05 | Simpply\Iteration 6 | Implementation
594 | Task | Collaboration with mustafa | Closed | Jeremy Shulman | 0.5 | 0 | 0.5 | 2015-04-02 16:03 | Simpply\Iteration 6 | Implementation
523 | User Story | Fix Search | Closed | Michael Yeaple |  |  |  | 2015-04-04 08:10 | Simpply\Iteration 6 | Implementation
532 | Task | Implementation | Closed | Michael Yeaple | 0.25 | 0 | 0.5 | 2015-03-14 14:43 | Simpply\Iteration 6 | Implementation
30 | User Story | View Historical Data on Graph | Closed | Michael Yeaple |  |  |  | 2015-04-04 08:09 | Simpply\Iteration 6
539 | Task | Demo/Sprint Planning Meeting 4/2/15 | Closed | Michael Yeaple | 1.25 | 0 | 1.25 | 2015-04-03 09:25 | Simpply\Iteration 6 | Planning Meeting
537 | Task | Implementation | Closed | Michael Yeaple | 5 | 0 | 21.6167 | 2015-04-02 12:22 | Simpply\Iteration 6 | Implementation
538 | Task | Implementation Integration/Sprint Planning Meeting 3/31/15 | Closed | Michael Yeaple | 1.25 | 0 | 1.25 | 2015-03-31 20:08 | Simpply\Iteration 6 | Planning Meeting
535 | Task | Design Feature | Closed | Michael Yeaple | 1 | 0 | 3 | 2015-03-31 15:58 | Simpply\Iteration 6 | Design Effort
536 | Task | Planning Meeting 3/17/15 | Closed | Michael Yeaple | 1.25 | 0 | 1.5 | 2015-03-18 09:21 | Simpply\Iteration 6 | Planning Meeting
527 | User Story | Run Algorithms from Web Role Adjustments | Closed | Michael Yeaple |  |  |  | 2015-04-04 08:09 | Simpply\Iteration 6
531 | Task | Implementation | Closed | Michael Yeaple | 3 | 0 | 4.15 | 2015-03-19 12:48 | Simpply\Iteration 6 | Implementation
598 | Task | Prep for Usability Testing 4/3/2015 | Closed | Michael Yeaple | 1.5 | 0 | 1.5 | 2015-04-03 11:52 | Simpply\Polish And Fix (Iteration 7) | Testing Effort
509 | User Story | Statuses for Planograms on Planogram Explorer | Closed | Jeremy Shulman |  |  |  | 2015-04-03 11:47 | Simpply\Iteration 6
610 | Task | 4/3 meeting | Closed | Jeremy Shulman | 1 | 0 | 1.25 | 2015-04-04 08:25 | Simpply\Iteration 6 | Requirements Meeting
609 | Task | 4/2 meeting | Closed | Jeremy Shulman | 1.25 | 0 | 1.25 | 2015-04-04 08:24 | Simpply\Iteration 6 | Progress Meeting
562 | Task | Unit test | Closed | Jeremy Shulman | 1 | 0 | 0 | 2015-03-31 20:15 | Simpply\Iteration 6
561 | Task | Implementation | Closed | Jeremy Shulman | 2 | 0 | 3 | 2015-03-31 20:02 | Simpply\Iteration 6 | Implementation
597 | Task | Import new data into production 4/3/2015 | Closed | Michael Yeaple | 0.5 | 0 | 0.75 | 2015-04-03 11:31 | Simpply\Polish And Fix (Iteration 7) | Deployment
593 | Task | Support Wegmans Team in Deploying the Application | Closed | Michael Yeaple | 1 | 0 | 0.35 | 2015-04-03 09:25 | Simpply | Deployment
524 | User Story | Account for Warehouse -> In store unit conversion | Closed | Curtis Burtner |  |  |  | 2015-04-02 17:08 | Simpply\Iteration 6
570 | Task | Requirements Deambiguation | Closed |  | 2 | 0 | 0 | 2015-03-31 | Simpply\Iteration 6 | Requirements Effort
571 | Task | Implementation | Closed |  | 2 | 0 | 1.5 | 2015-03-18 16:07 | Simpply\Iteration 6 | Implementation
525 | User Story | Sort Columns on Item Details | Closed | Curtis Burtner |  |  |  | 2015-04-02 17:08 | Simpply\Iteration 6
568 | Task | Implementation | Closed | Curtis Burtner | 6 | 0 | 8 | 2015-03-26 18:43 | Simpply\Iteration 6 | Implementation
521 | User Story | Item Details Adjustments | Closed | Curtis Burtner |  |  |  | 2015-04-02 17:07 | Simpply\Iteration 6
596 | User Story | Implement Running Total | Closed | Curtis Burtner |  |  |  | 2015-04-18 09:46 | Simpply\Polish And Fix (Iteration 7)
627 | Task | Implement | Closed | Curtis Burtner | 5 | 0 | 5 | 2015-04-05 23:16 | Simpply\Polish And Fix (Iteration 7) | Implementation
574 | Task | Fix Distribution Grid | Closed | Curtis Burtner | 4 | 0 | 5.5 | 2015-04-02 06:37 | Simpply\Iteration 6 | Implementation
573 | Task | Top of Page CSS | Closed | Curtis Burtner | 2 | 0 | 0.5 | 2015-03-31 | Simpply\Iteration 6 | Implementation
586 | Task | Aggregate Information | Closed | Curtis Burtner | 1.5 | 0 | 1.5 | 2015-03-29 09:25 | Simpply\Iteration 6 | Implementation
575 | Task | Navigation Between Item Changes | Closed | Curtis Burtner | 2 | 0 | 1 | 2015-03-20 15:13 | Simpply\Iteration 6 | Implementation
572 | Task | Put New Information at Top of Page | Closed | Curtis Burtner | 1.5 | 0 | 1 | 2015-03-18 16:06 | Simpply\Iteration 6 | Implementation
556 | Task | Unit Test | Closed |  | 2 | 0 | 0.7 | 2015-04-02 16:07 | Simpply\Iteration 8
557 | Task | Implementation | Closed | Mustafa Al-Salihi | 12 | 3 | 11 | 2015-04-02 16:07 | Simpply\Iteration 8
555 | Task | Class Design | Closed |  | 1.25 | 0 | 1.3 | 2015-04-02 16:07 | Simpply\Iteration 8
543 | Task | Integration Testing | Closed | Michael Yeaple | 2 | 0 | 0.5 | 2015-04-02 15:36 | Simpply\Iteration 6 | Testing Effort
545 | Task | Bug Fixes | Closed | Michael Yeaple | 1.5 | 0 | 0.85 | 2015-04-02 15:36 | Simpply\Iteration 6 | Bugs
544 | Task | Deploy to Production | Closed | Michael Yeaple | 2 | 0 | 2.6 | 2015-04-02 15:36 | Simpply\Iteration 6 | Deployment
540 | Task | Demo/Requirements Meeting 3/19/15 | Closed | Michael Yeaple | 1.25 | 0 | 1.25 | 2015-04-02 14:46 | Simpply\Iteration 6 | Requirements Meeting
566 | Task | Implement conversion changes | Closed | Jeremy Shulman | 2 | 0 | 3.25 | 2015-04-01 20:05 | Simpply\Iteration 8
567 | Task | Update unit tests | Closed | Jeremy Shulman | 2 | 0 | 0.5 | 2015-04-01 20:04 | Simpply\Iteration 8 | Testing Effort
592 | Task | 3/31 Poster + Planning Meeting | Closed | Curtis Burtner | 1.25 | 0 | 1.25 | 2015-04-01 02:51 | Simpply | Process/Project Management Effort
563 | Task | Colab with curtis | Closed | Jeremy Shulman | 2 | 0 | 0 | 2015-03-31 20:41 | Simpply\Iteration 8 | Design Effort
587 | Task | 3/31 Customer Status Update | Closed | Curtis Burtner | 0.45 | 0 | 0.45 | 2015-03-31 01:52 | Simpply | Process/Project Management Effort
585 | Task | 3/19 Meeting | Closed | Curtis Burtner | 1.25 | 0 | 1.25 | 2015-03-21 14:21 | Simpply\Iteration 6 | Process/Project Management Effort
584 | Task | 3/20 Customer Communication | Closed | Curtis Burtner | 0.5 | 0 | 0.5 | 2015-03-21 14:21 | Simpply\Iteration 6 | Process/Project Management Effort
583 | Task | Import new data into production | Closed | Michael Yeaple | 1 | 0 | 1 | 2015-03-19 14:44 | Simpply\Iteration 6 | Deployment
582 | Task | Hide Item Explorer Buttons | Closed | Michael Yeaple | 0.25 | 0 | 0.4 | 2015-03-19 13:04 | Simpply | Implementation
542 | Task | Investigate Using Windows Authentication for SQL Server | Closed | Michael Yeaple | 3 | 0 | 3.5 | 2015-03-19 12:46 | Simpply\Iteration 6 | Deployment
565 | Task | Adjust Sellthrough distribution | Closed | Jeremy Shulman | 2 | 0 | 1 | 2015-03-18 17:57 | Simpply\Iteration 8 | Implementation
579 | Task | Customer Emails | Closed | Curtis Burtner | 0.45 | 0 | 0.45 | 2015-03-18 08:50 | Simpply | Process/Project Management Effort
578 | Task | Adjust setup distribution to match information from front end | Closed | Jeremy Shulman | 1 | 0 | 1 | 2015-03-18 01:24 | Simpply\Iteration 8 | Implementation
564 | Task | Adjust push all distribution | Closed | Jeremy Shulman | 0.5 | 0 | 0.5 | 2015-03-18 01:06 | Simpply\Iteration 8 | Implementation
576 | Task | 3/17 meeting | Closed | Jeremy Shulman | 1.25 | 0 | 1.5 | 2015-03-18 01:03 | Simpply\Iteration 8 | Planning Meeting
577 | Task | 3/17 Meeting | Closed | Curtis Burtner | 1.25 | 0 | 1.25 | 2015-03-17 18:09 | Simpply\Iteration 6 | Implementation
533 | Task | Iteration 6 Planning | Closed | Michael Yeaple | 0.5 | 0 | 0.5 | 2015-03-13 11:35 | Simpply\Iteration 6 | Planning Effort
530 | Task | 3/12/2015 Planning Meeting Post-Demo | Closed | Michael Yeaple | 0.5 | 0 | 0.75 | 2015-03-12 21:49 | Simpply | Planning Meeting
529 | Task | Iteration 6 Online Planning Meeting | Closed | Curtis Burtner | 1 | 0 | 1 | 2015-03-12 21:49 | Simpply | Planning Meeting
479 | Task | Demo/Sprint Planning Meeting 03/12/2015 | Closed | Michael Yeaple | 1.25 | 0 | 1.75 | 2015-03-12 21:49 | Simpply\Iteration 5 | Planning Meeting
336 | User Story | View Seasonal Sell-Thru Distribution | Closed | Jeremy Shulman |  |  |  | 2015-03-12 21:11 | Simpply\Iteration 5
486 | Task | Unit testing | Closed | Jeremy Shulman | 2 | 0 | 0 | 2015-03-12 23:44 | Simpply\Iteration 5
528 | Task | 3/12 planning meeting | Closed | Jeremy Shulman | 1 | 0 | 0.5 | 2015-03-12 23:44 | Simpply\Iteration 5 | Planning Meeting
515 | Task | 3/12 customer meeting | Closed | Jeremy Shulman | 1.25 | 0 | 1.75 | 2015-03-12 21:37 | Simpply\Iteration 5 | Planning Meeting
485 | Task | Implementation | Closed | Jeremy Shulman | 3 | 0 | 8.5 | 2015-03-11 19:46 | Simpply\Iteration 5
513 | Task | Help mustafa with engine interaction | Closed | Jeremy Shulman | 1 | 0 | 2 | 2015-03-11 16:32 | Simpply\Iteration 5 | Implementation
511 | Task | 3/10 meeting | Closed | Jeremy Shulman | 1.25 | 0 | 2 | 2015-03-10 23:55 | Simpply\Iteration 5 | Planning Meeting
504 | Task | Exception when front end doesn't provide all segmentations of stores | Closed | Jeremy Shulman | 1 | 0 | 1 | 2015-03-09 21:32 | Simpply\Iteration 5 | Bugs
495 | Task | Working with curtis on database interaction | Closed | Jeremy Shulman | 1.5 | 0 | 2 | 2015-03-05 21:13 | Simpply\Iteration 5 | Implementation
494 | Task | Add progress updates to existing distribution jobs | Closed | Jeremy Shulman | 2 | 0 | 2 | 2015-03-05 00:13 | Simpply\Iteration 5
484 | Task | Add logging standards to design doc | Closed | Jeremy Shulman | 0.5 | 0 | 0.5 | 2015-03-04 23:27 | Simpply\Iteration 5
492 | Task | 3/3 meeting | Closed | Jeremy Shulman | 1 |  | 1 | 2015-03-03 18:59 | Simpply\Iteration 5 | Design Meeting
488 | Task | Add logging table back to creation script | Closed | Jeremy Shulman | 0.25 |  | 0.25 | 2015-02-27 21:17 | Simpply\Iteration 5 | Bugs
391 | User Story | Import Wegmans Data Job | Closed | Curtis Burtner |  |  |  | 2015-03-12 21:04 | Simpply\Iteration 5
399 | Task | Implement design | Closed | Curtis Burtner | 2 | 0 | 4 | 2015-03-05 23:26 | Simpply\Iteration 5 | Implementation
499 | Task | Pair Programmed With Jeremy | Closed | Curtis Burtner | 2 | 0 | 2 | 2015-03-05 23:26 | Simpply\Iteration 5 | Implementation
462 | Task | Ask Questions | Closed | Curtis Burtner | 0.5 | 0 | 0.5 | 2015-03-05 21:14 | Simpply\Iteration 5 | Requirements Effort
397 | Task | Map Wegmans' schema to Simpply Schema | Closed | Curtis Burtner | 2 | 0 | 3.25 | 2015-03-05 21:13 | Simpply\Iteration 5 | Design Effort
401 | Task | 02/26/15 Customer Meeting | Closed | Curtis Burtner | 1.25 | 0 | 1.5 | 2015-02-24 22:17 | Simpply\Iteration 5 | Planning Meeting
398 | Task | Design Job | Closed | Curtis Burtner | 1 | 0 | 0.75 | 2015-02-18 09:17 | Simpply\Iteration 5 | Design Effort
400 | Task | 02/17/15 Design Integration Meeting | Closed | Curtis Burtner | 1.25 | 0 | 1.25 | 2015-02-17 23:42 | Simpply\Iteration 5 | Design Meeting
442 | Task | Initial Import | Closed | Curtis Burtner | 3 | 0 | 4 | 2015-02-17 23:42 | Simpply\Iteration 5 | Implementation
446 | User Story | Work from Item Explorer Level | Closed | Michael Yeaple |  |  |  | 2015-03-12 17:55 | Simpply\Iteration 5
481 | Task | Add Design to Design Doc | Closed | Michael Yeaple | 0.5 | 0 | 0.75 | 2015-03-10 01:21 | Simpply\Iteration 5 | Design Effort
482 | Task | Unit Testing | Closed | Michael Yeaple | 3 | 0 | 0 | 2015-03-10 00:13 | Simpply\Iteration 5 | Testing Effort
483 | Task | Implementation | Closed | Michael Yeaple | 3 | 0 | 7.5 | 2015-03-10 00:12 | Simpply\Iteration 5 | Implementation
480 | Task | Class Design | Closed | Michael Yeaple | 1.5 | 0 | 1.5 | 2015-03-02 22:50 | Simpply\Iteration 5 | Design Effort
3 | User Story | Modify Calculation Parameters | Closed | Michael Yeaple |  |  |  | 2015-03-12 17:55 | Simpply\Iteration 5
475 | Task | Implementation | Closed | Michael Yeaple | 3 | 0.5 | 12.26 | 2015-03-11 18:58 | Simpply\Iteration 5 | Implementation
473 | Task | Add Design to Design Doc | Closed | Michael Yeaple | 0.5 | 0 | 0.5 | 2015-03-10 00:45 | Simpply\Iteration 5 | Design Effort
474 | Task | Unit Testing | Closed | Michael Yeaple | 2 | 0 | 0 | 2015-03-10 00:14 | Simpply\Iteration 5 | Testing Effort
471 | Task | Class Design | Closed | Michael Yeaple | 1 | 0 | 1 | 2015-03-02 22:50 | Simpply\Iteration 5 | Design Effort
519 | Task | Update Risks Document | Closed | Michael Yeaple | 0.25 | 0 | 0.16667 | 2015-03-12 16:04 | Simpply | Process/Project Management Effort
477 | Task | Integration Testing | Closed | Michael Yeaple | 1 | 0 | 0 | 2015-03-12 15:59 | Simpply\Iteration 5 | Testing Effort
478 | Task | Bug Fixes (if applicable) | Closed | Michael Yeaple | 1 | 0 | 6.4833 | 2015-03-12 15:58 | Simpply\Iteration 5 | Bugs
489 | Task | Deploy to Production | Closed | Michael Yeaple | 1.5 | 0 | 1.25 | 2015-03-12 15:56 | Simpply\Iteration 5 | Deployment
518 | Task | Validation Criteria for Sprint 6 | Closed | Michael Yeaple | 0.5 | 0 | 0.25 | 2015-03-12 15:50 | Simpply | Planning Effort
516 | Task | 3/12 Customer Email | Closed | Curtis Burtner | 0.5 | 0 | 0.5 | 2015-03-12 01:13 | Simpply | Process/Project Management Effort
514 | Task | Pair Programming/Assistance | Closed | Michael Yeaple | 1 | 0 | 2 | 2015-03-11 22:40 | Simpply | Implementation
445 | User Story | Navigate Between Item Details Without ItemExplorer | Closed | Curtis Burtner |  |  |  | 2015-03-11 07:58 | Simpply\Iteration 5
461 | Task | 3/12 Customer Demo/Sprint Planning Meeting | Closed | Curtis Burtner | 1.25 | 0 | 1.75 | 2015-03-12 21:49 | Simpply\Iteration 5 | Process/Project Management Meeting
459 | Task | Implement | Closed | Curtis Burtner | 4 | 0 | 12 | 2015-03-07 20:22 | Simpply\Iteration 5 | Implementation
460 | Task | 3/3 Design Integration Meeting | Closed | Curtis Burtner | 1.25 | 0 | 1 | 2015-03-03 23:42 | Simpply\Iteration 5 | Design Meeting
458 | Task | Design | Closed | Curtis Burtner | 5 | 0 | 2 | 2015-03-03 23:41 | Simpply\Iteration 5 | Design Effort
476 | Task | Integration/Planning Meeting 03/10/2015 | Closed | Michael Yeaple | 1.25 | 0 | 2 | 2015-03-10 22:26 | Simpply\Iteration 5 | Planning Meeting
510 | Task | Touched up the stored procedure | Closed | Curtis Burtner | 0.4 | 0 | 0.4 | 2015-03-10 19:56 | Simpply\Iteration 5 | Implementation
506 | Task | Write Deployment Guide | Closed | Michael Yeaple | 1 | 0 | 2.75 | 2015-03-10 12:25 | Simpply | Documentation
502 | Task | Fix Parse Wegmans Data Job | Closed | Curtis Burtner | 1 | 0 | 0.5 | 2015-03-09 21:56 | Simpply\Iteration 5 | Bugs
501 | Task | Fix Foreign Key Naming Constraints | Closed | Michael Yeaple | 1 | 0 | 1 | 2015-03-09 21:06 | Simpply\Iteration 5 | Bugs
503 | Task | Fix Javascript Error for Navigate Items | Closed | Curtis Burtner | 0.5 | 0 | 0.5 | 2015-03-09 20:55 | Simpply\Iteration 5 | Bugs
500 | Task | 3/5 Emails | Closed | Curtis Burtner | 1 | 0 | 1 | 2015-03-06 02:12 | Simpply | Process/Project Management Effort
493 | Task | 3/2 Emails | Closed | Curtis Burtner | 0.5 | 0 | 0.5 | 2015-03-03 23:44 | Simpply | Process/Project Management Effort
472 | Task | Design Integration Meeting | Closed | Michael Yeaple | 1.25 | 0 | 1 | 2015-03-03 19:00 | Simpply\Iteration 5 | Design Meeting
470 | Task | Implement Customer Feedback | Closed | Michael Yeaple | 2.5 | 0 | 2.75 | 2015-03-02 14:48 | Simpply\Iteration 5 | Implementation
13 | User Story | Finalize Item Distribution | Closed | Mustafa Al-Salihi |  |  |  | 2015-02-27 16:31 | Simpply\Iteration 4
415 | Task | Demo | Closed | Mustafa Al-Salihi | 1.25 | 0 | 1.25 | 2015-02-27 11:13 | Simpply\Iteration 4
414 | Task | Integration Test | Closed | Mustafa Al-Salihi | 0.25 | 0 | 1.5 | 2015-02-27 11:13 | Simpply\Iteration 4
413 | Task | Implementation | Closed | Mustafa Al-Salihi | 6 | 0 | 7 | 2015-02-27 11:13 | Simpply\Iteration 4
410 | Task | Class Design Review | Closed | Mustafa Al-Salihi | 1.25 | 0 | 1.25 | 2015-02-27 11:12 | Simpply\Iteration 4
408 | Task | Class design | Closed | Mustafa Al-Salihi | 2 | 0 | 2 | 2015-02-27 11:11 | Simpply\Iteration 4
341 | User Story | Save Distribution Progress Periodically | Closed | Mustafa Al-Salihi |  |  |  | 2015-02-27 16:31 | Simpply\Iteration 4
417 | Task | Class design review | Closed | Mustafa Al-Salihi | 1.5 | 0 | 1.5 | 2015-02-27 11:16 | Simpply\Iteration 4
405 | Task | Integration Test | Closed | Mustafa Al-Salihi | 0.5 | 0 | 1.4 | 2015-02-27 11:16 | Simpply\Iteration 4
406 | Task | Demo | Closed | Mustafa Al-Salihi | 1.25 | 0 | 1.25 | 2015-02-27 11:16 | Simpply\Iteration 4
404 | Task | Implementation | Closed | Mustafa Al-Salihi | 7 | 0 | 6.3 | 2015-02-27 11:15 | Simpply\Iteration 4
337 | User Story | View Push All Distribution | Closed | Jeremy Shulman |  |  |  | 2015-02-27 16:31 | Simpply\Iteration 4
407 | Task | 02/26/15 Customer Meeting | Closed | Jeremy Shulman | 1.25 | 0 | 1.25 | 2015-02-27 16:32 | Simpply\Iteration 4 | Planning Meeting
421 | Task | Unit Testing | Closed | Jeremy Shulman | 5 | 0 | 2.5 | 2015-02-25 19:44 | Simpply\Iteration 4
412 | Task | Implement PushAll | Closed | Jeremy Shulman | 2 | 0 | 2 | 2015-02-25 17:44 | Simpply\Iteration 4 | Implementation
456 | Task | Fix setup distribution to adhere to new distribution model | Closed | Jeremy Shulman | 1 | 0 | 1 | 2015-02-25 01:00 | Simpply\Iteration 4
453 | Task | 2/14/15 meeting | Closed | Jeremy Shulman | 1.25 | 0 | 1.5 | 2015-02-24 19:31 | Simpply\Iteration 4 | Planning Meeting
416 | Task | Fix Setup so it isn't 25% per store | Closed | Jeremy Shulman | 1 | 0 | 1.5 | 2015-02-18 19:11 | Simpply\Iteration 4
409 | Task | 02/17/15 Design Integration Meeting | Closed | Jeremy Shulman | 1.25 | 0 | 1.25 | 2015-02-18 09:17 | Simpply\Iteration 4 | Design Meeting
438 | Task | Add setup design to design doc | Closed | Jeremy Shulman | 1 | 0 | 0.5 | 2015-02-17 00:15 | Simpply\Iteration 4
11 | User Story | Debug Logging | Closed | Jeremy Shulman |  |  |  | 2015-02-27 16:31 | Simpply\Iteration 4 | High Priority
419 | Task | Implement Logging for in depth tasks in the system | Closed | Jeremy Shulman | 2 | 0 | 1.25 | 2015-02-20 22:22 | Simpply\Iteration 4
10 | User Story | Logging | Closed | Jeremy Shulman |  |  |  | 2015-02-27 16:31 | Simpply\Iteration 4 | High Priority
437 | Task | Implement logging for user actions | Closed | Jeremy Shulman | 1.5 |  | 1.5 | 2015-02-25 00:17 | Simpply\Iteration 4
418 | Task | Research logging Tech | Closed | Jeremy Shulman | 1.5 | 0 | 2.25 | 2015-02-19 19:03 | Simpply\Iteration 4
469 | Task | Sprint Planning | Closed | Michael Yeaple | 0.5 | 0 | 0.5 | 2015-02-27 11:56 | Simpply\Iteration 5 | Planning Effort
16 | User Story | Save Item Distribution | Closed | Michael Yeaple |  |  |  | 2015-02-27 11:54 | Simpply\Iteration 4
430 | Task | Implementation | Closed | Michael Yeaple | 1.5 | 0 | 2.65 | 2015-02-25 17:49 | Simpply\Iteration 4 | Implementation
429 | Task | Unit Testing | Closed | Michael Yeaple | 1 | 0 | 1.25 | 2015-02-19 15:32 | Simpply\Iteration 4 | Testing Effort
435 | Task | Add Design to Design Doc | Closed | Michael Yeaple | 0.5 | 0 | 0.5 | 2015-02-16 20:09 | Simpply\Iteration 4 | Design Effort
428 | Task | Class Design | Closed | Michael Yeaple | 0.5 | 0 | 0.61667 | 2015-02-16 19:41 | Simpply\Iteration 4 | Design Effort
14 | User Story | Modify Item Distribution | Closed | Michael Yeaple |  |  |  | 2015-02-27 11:54 | Simpply\Iteration 4
427 | Task | 02/26/15 Customer Meeting | Closed | Michael Yeaple | 1.25 | 0 | 1.25 | 2015-02-27 11:21 | Simpply\Iteration 4 | Planning Meeting
426 | Task | Integration Testing | Closed | Michael Yeaple | 1 | 0 | 1 | 2015-02-26 15:49 | Simpply\Iteration 4 | Testing Effort
425 | Task | Implementation | Closed | Michael Yeaple | 3 | 0 | 8.75 | 2015-02-24 11:32 | Simpply\Iteration 4 | Implementation
424 | Task | Unit Testing | Closed | Michael Yeaple | 1.5 | 0 | 1.6167 | 2015-02-19 14:27 | Simpply\Iteration 4 | Testing Effort
423 | Task | Design Integration Meeting | Closed | Michael Yeaple | 1.25 | 0 | 1 | 2015-02-17 18:49 | Simpply\Iteration 4 | Design Meeting
434 | Task | Add Design to Design Doc | Closed | Michael Yeaple | 0.5 | 0 | 0.5 | 2015-02-16 20:09 | Simpply\Iteration 4 | Design Effort
422 | Task | Class Design | Closed | Michael Yeaple | 1 | 0 | 1 | 2015-02-16 19:19 | Simpply\Iteration 4 | Design Effort
433 | Task | Deploy to Production | Closed | Michael Yeaple | 1.5 | 0 | 1 | 2015-02-27 11:25 | Simpply\Iteration 4 | Deployment
432 | Task | Pair Programming/Assistance | Closed | Michael Yeaple | 2 | 0 | 2.75 | 2015-02-26 15:49 | Simpply\Iteration 4 | Implementation
457 | Task | Create Validation Criteria | Closed | Michael Yeaple | 0.5 | 0 | 0.5 | 2015-02-26 12:12 | Simpply | Planning Effort
353 | Task | Improve Old Unit Tests | Closed | Michael Yeaple | 6 | 0 | 2.25 | 2015-02-25 22:26 | Simpply\Iteration 4 | Testing Effort
455 | Task | Sprint Planning Meeting 02/24/2015 | Closed | Michael Yeaple | 1.25 | 0 | 1.5 | 2015-02-24 22:37 | Simpply | Planning Meeting
12 | User Story | Undo | Closed |  |  |  |  | 2015-02-24 18:59 | Simpply
452 | Task | 2/20 Customer Email | Closed | Curtis Burtner | 0.5 | 0 | 0.5 | 2015-02-20 01:54 | Simpply | Process/Project Management Effort
396 | Task | Fix Breadcrumbs | Closed | Curtis Burtner | 5 | 0 | 5.5 | 2015-02-19 23:46 | Simpply\Iteration 4 | Implementation
450 | Task | Emails to Martinez | Closed | Curtis Burtner | 0.5 | 0 | 0.5 | 2015-02-18 13:44 | Simpply | Process/Project Management Effort
449 | Task | 02/17/2015 Online Customer Meeting | Closed | Mustafa Al-Salihi | 1 | 0 | 1 | 2015-02-18 10:09 | Simpply | Requirements Meeting
448 | Task | 02/17 Online Customer Meeting | Closed | Curtis Burtner | 1 | 0 | 1 | 2015-02-18 10:09 | Simpply | Requirements Meeting
447 | Task | 02/18 Emails | Closed | Curtis Burtner | 0.75 | 0 | 0.75 | 2015-02-18 10:07 | Simpply | Process/Project Management Effort
444 | Task | Customer Meeting 2/17/2015 | Closed | Michael Yeaple | 1 | 0 | 1 | 2015-02-17 18:01 | Simpply | Requirements Meeting
443 | Task | SponsorEmail | Closed | Curtis Burtner | 1 | 0 | 1 | 2015-02-17 09:44 | Simpply | Process/Project Management Effort
441 | Task | Risk Assessment | Closed | Michael Yeaple | 1 | 0 | 1 | 2015-02-16 20:43 | Simpply | Process/Project Management Effort
439 | Task | Implement Customer Feedback/Bug Fixes From Term 2 Sprint 1 | Closed | Michael Yeaple | 0.75 | 0 | 0.5 | 2015-02-16 19:56 | Simpply | Implementation
436 | Task | Update Design Doc for Sprint 3 | Closed | Michael Yeaple | 0.5 | 0 | 0.5 | 2015-02-14 12:04 | Simpply\Iteration 4 | Design Effort
431 | Task | Sprint 4 Planning | Closed | Michael Yeaple | 0.5 | 0 | 0.5 | 2015-02-14 10:31 | Simpply\Iteration 4 | Planning Effort
327 | User Story | Display Breadcrumbs | Closed | Curtis Burtner |  |  |  | 2015-02-12 21:16 | Simpply\Iteration 3
362 | Task | Demo/Sprint Planning Customer Meeting 02/12/15 | Closed | Curtis Burtner | 1.25 | 0 | 1.25 | 2015-02-12 23:23 | Simpply\Iteration 3 | Planning Meeting
363 | Task | Breadcrumbs Unit Tests | Closed | Curtis Burtner | 4 | 4 | 0 | 2015-02-12 18:06 | Simpply\Iteration 3 | Testing Effort
360 | Task | Breadcrumbs Implementation | Closed | Curtis Burtner | 6 | 0 | 8 | 2015-02-12 13:37 | Simpply\Iteration 3 | Implementation
359 | Task | Breadcrumbs Class Design | Closed | Curtis Burtner | 2.5 | 0 | 3.25 | 2015-02-05 22:13 | Simpply\Iteration 3 | Design Effort
361 | Task | Design Implementation Meeting 02/03/15 | Closed | Curtis Burtner | 1.25 | 0 | 1.25 | 2015-02-03 21:57 | Simpply\Iteration 3 | Design Meeting
328 | User Story | Plan-o-Gram Explorer | Closed | Michael Yeaple |  |  |  | 2015-02-12 21:16 | Simpply\Iteration 3
357 | Task | Demo/Sprint Planning Customer Meeting 02/12/15 | Closed | Michael Yeaple | 1.25 | 0 | 1.25 | 2015-02-12 21:15 | Simpply\Iteration 3 | Planning Meeting
350 | Task | PoG Explorer Implementation | Closed | Michael Yeaple | 3 | 0 | 13.48 | 2015-02-10 10:27 | Simpply\Iteration 3 | Implementation
349 | Task | PoG Explorer Unit Tests | Closed | Michael Yeaple | 2 | 0 | 2 | 2015-02-05 12:41 | Simpply\Iteration 3 | Testing Effort
351 | Task | Design Integration Meeting 02/03/15 | Closed | Michael Yeaple | 1.25 | 0 | 1.25 | 2015-02-03 21:57 | Simpply\Iteration 3 | Design Meeting
348 | Task | PoG Explorer Class Design | Closed | Michael Yeaple | 1 | 0 | 1 | 2015-02-03 12:41 | Simpply\Iteration 3 | Design Effort
329 | User Story | Season Explorer | Closed | Mustafa Al-Salihi |  |  |  | 2015-02-12 21:15 | Simpply\Iteration 3
395 | Task | Demo/Sprint Planning Meeting 02/12/15 | Closed | Mustafa Al-Salihi | 1.25 | 0 | 1.25 | 2015-02-12 21:15 | Simpply\Iteration 3
380 | Task | Code Review by the team | Closed | Mustafa Al-Salihi | 0.2 | 0.2 | 0 | 2015-02-12 18:10 | Simpply\Iteration 3
377 | Task | Unit Test | Closed | Mustafa Al-Salihi | 2 | 2 | 0 | 2015-02-12 18:06 | Simpply\Iteration 3
379 | Task | Integration Test | Closed | Mustafa Al-Salihi | 1.25 | 0 | 1 | 2015-02-12 01:20 | Simpply\Iteration 3
378 | Task | Implementation | Closed | Mustafa Al-Salihi | 8 | 0 | 14.4 | 2015-02-12 01:19 | Simpply\Iteration 3
375 | Task | Class Design | Closed | Mustafa Al-Salihi | 2 | 0 | 2 | 2015-02-09 21:13 | Simpply\Iteration 3
376 | Task | Class Design Review | Closed | Mustafa Al-Salihi | 1.25 | 0 | 1.25 | 2015-02-03 21:57 | Simpply\Iteration 3
335 | User Story | View Set-up Distribution | Closed | Jeremy Shulman |  |  |  | 2015-02-12 21:15 | Simpply\Iteration 3
372 | Task | Demo/Sprint Planning Customer Meeting 02/12/15 | Closed | Jeremy Shulman | 1.25 | 0 | 1.25 | 2015-02-12 21:15 | Simpply\Iteration 3 | Planning Meeting
365 | Task | Unit Tests | Closed | Jeremy Shulman | 5 | 5 |  | 2015-02-12 18:05 | Simpply\Iteration 3 | Testing Effort
370 | Task | Algorithm implementation | Closed | Jeremy Shulman | 3.5 | 0 | 2.75 | 2015-02-11 22:13 | Simpply\Iteration 3 | Implementation
367 | Task | Threading Implementation | Closed | Jeremy Shulman | 3 |  | 4 | 2015-02-10 01:02 | Simpply\Iteration 3 | Implementation
368 | Task | JSON Implementation | Closed | Jeremy Shulman | 1.5 | 0 | 2.5 | 2015-02-06 04:04 | Simpply\Iteration 3 | Implementation
366 | Task | Threading Design | Closed | Jeremy Shulman | 5 | 0 | 3.5 | 2015-02-06 01:28 | Simpply\Iteration 3 | Design Effort
364 | Task | JSON Design | Closed | Jeremy Shulman | 2.5 | 0 | 1.75 | 2015-02-06 01:02 | Simpply\Iteration 3 | Design Effort
371 | Task | Design Integration Meeting 02/03/15 | Closed | Jeremy Shulman | 1.25 | 0 | 1.25 | 2015-02-03 21:57 | Simpply\Iteration 3 | Design Meeting
373 | Task | Plan story tasks | Closed | Jeremy Shulman | 0.75 | 0 | 0.75 | 2015-01-30 18:36 | Simpply\Iteration 3 | Planning Effort
394 | Task | Deploy to Production | Closed | Michael Yeaple | 0.25 | 0 | 1.5 | 2015-02-12 16:15 | Simpply | Deployment
393 | Task | Pair Programming With Mustafa | Closed | Curtis Burtner | 1 | 0 | 1.5 | 2015-02-11 14:41 | Simpply | Code/Design Review
352 | Task | Pair Programming/Assistance | Closed | Michael Yeaple | 3 | 0 | 1.5 | 2015-02-11 10:42 | Simpply\Iteration 3 | Implementation
392 | Task | 2/11 Email To Customer | Closed | Curtis Burtner | 0.75 | 0 | 0.5 | 2015-02-11 09:36 | Simpply | Process/Project Management Effort
387 | Task | 2/10 Integration/Planning Meeting | Closed | Curtis Burtner | 1.25 | 0 | 1.5 | 2015-02-11 08:52 | Simpply | Planning Meeting
388 | Task | 2/10 Integration/Planning Meeting | Closed | Jeremy Shulman | 1.25 | 0 | 1.5 | 2015-02-11 08:52 | Simpply | Planning Meeting
389 | Task | 2/10 Integration/Planning Meeting | Closed | Michael Yeaple | 1.25 | 0 | 1.5 | 2015-02-11 08:52 | Simpply | Planning Meeting
390 | Task | 2/10 Integration/Planning Meeting | Closed | Mustafa Al-Salihi | 1.25 | 0 | 1.5 | 2015-02-11 08:52 | Simpply | Planning Meeting
356 | Task | jQuery Load Error | Closed | Michael Yeaple | 0.5 | 0 | 0.25 | 2015-02-10 10:39 | Simpply\Iteration 3 | Bugs
386 | Task | 2/09 Status Update Email | Closed | Curtis Burtner | 1 |  | 0.45 | 2015-02-10 09:52 | Simpply | Process/Project Management Effort
385 | Task | 2/05 Status Update | Closed | Curtis Burtner | 0.45 | 0 | 0.45 | 2015-02-05 22:47 | Simpply\Iteration 3 | Process/Project Management Effort
384 | Task | Sponsor Emails | Closed | Curtis Burtner | 0.45 | 0 | 0.45 | 2015-02-03 22:56 | Simpply | Process/Project Management Effort
344 | Task | Customer Meeting/Sprint Planning 01/29/15 | Closed | Mustafa Al-Salihi | 1.5 | 0 | 1.5 | 2015-02-03 21:57 | Simpply | Planning Meeting
383 | Task | Customer Status Update Email | Closed | Curtis Burtner | 0.45 | 0 | 0.45 | 2015-02-03 00:27 | Simpply | Process/Project Management Effort
382 | Task | Fixed Bug 334 | Closed | Curtis Burtner | 3 | 0 | 3 | 2015-02-01 18:35 | Simpply\Iteration 3 | Bugs
317 | Task | UI Overhaul Item Explorer Implementation | Closed | Curtis Burtner | 0.45 | 0 | 1.45 | 2015-01-30 18:23 | Simpply\Interim Sprint | Implementation
346 | Task | Customer Meeting/Sprint Planning 01/29/15 | Closed | Jeremy Shulman | 1.25 | 0 | 1.25 | 2015-01-30 18:12 | Simpply\Iteration 3 | Planning Meeting
345 | Task | Customer Meeting/Sprint Planning 01/29/15 | Closed | Curtis Burtner | 1.5 | 0 | 2 | 2015-01-30 14:10 | Simpply\Iteration 3 | Planning Meeting
358 | Task | Compose Team Email About Sprint Planning | Closed | Michael Yeaple | 0.25 | 0 | 0.5 | 2015-01-30 13:15 | Simpply | Planning Effort
355 | Task | UI Overhaul Merge | Closed | Michael Yeaple | 0.25 | 0 | 0.25 | 2015-01-30 12:58 | Simpply\Iteration 3 | Implementation
347 | Task | Sprint Planning | Closed | Michael Yeaple | 0.5 | 0 | 0.66667 | 2015-01-30 12:38 | Simpply | Planning Effort
343 | Task | Customer Meeting/Sprint Planning 01/29/15 | Closed | Michael Yeaple | 1.5 | 0 | 1.75 | 2015-01-30 12:37 | Simpply\Iteration 3 | Planning Meeting
354 | Task | Fix search to use 6 digit IDs | Closed | Michael Yeaple | 0.08333 | 0 | 0.08333 | 2015-01-30 12:29 | Simpply\Iteration 3 | Bugs
5 | User Story | Search | Closed |  |  |  |  | 2015-01-30 12:19 | Simpply\Iteration 2
204 | Task | Implement Feature | Closed | Curtis Burtner | 2 | 0 | 8 | 2014-12-10 06:38 | Simpply\Iteration 2 | Implementation
202 | Task | Class Design Review | Closed | Jeremy Shulman | 0.5 | 0 | 0.967 | 2014-11-25 18:16 | Simpply\Iteration 2 | Design Meeting
201 | Task | Class Design Review | Closed | Curtis Burtner | 0.5 | 0 | 0.967 | 2014-11-25 18:16 | Simpply\Iteration 2 | Design Meeting
200 | Task | Class Design Review | Closed | Michael Yeaple | 0.5 | 0 | 0.967 | 2014-11-25 18:15 | Simpply\Iteration 2 | Design Meeting
203 | Task | Class Design Review | Closed | Mustafa Al-Salihi | 0.5 | 0 | 0.55 | 2014-11-24 22:04 | Simpply\Iteration 2 | Design Meeting
194 | Task | User Experience Design | Closed | Jeremy Shulman | 1 | 0 | 0.5 | 2014-11-24 21:31 | Simpply\Iteration 2 | Design Effort
199 | Task | Class Design | Closed | Mustafa Al-Salihi | 0.5 | 0 | 1.5 | 2014-11-24 21:31 | Simpply\Iteration 2 | Design Effort
198 | Task | User Experience Design Review | Closed | Mustafa Al-Salihi | 0.5 | 0 | 0.67 | 2014-11-24 21:31 | Simpply\Iteration 2 | Design Meeting
196 | Task | User Experience Design Review | Closed | Curtis Burtner | 0.5 | 0 | 0.7 | 2014-11-24 21:29 | Simpply\Iteration 2 | Design Meeting
195 | Task | User Experience Design Review | Closed | Michael Yeaple | 0.5 | 0 | 0.67 | 2014-11-24 21:29 | Simpply\Iteration 2 | Design Meeting
197 | Task | User Experience Design Review | Closed | Jeremy Shulman | 0.5 | 0 | 0.67 | 2014-11-24 21:29 | Simpply\Iteration 2 | Design Meeting
7 | User Story | View Calculated Item Distribution | Closed |  |  |  |  | 2015-01-30 12:19 | Simpply\Iteration 2
130 | Task | Implement Web Role Design | Closed | Jeremy Shulman | 1.5 | 0 | 1 | 2014-12-12 00:16 | Simpply\Iteration 2 | Implementation
163 | Task | Design Distribution Algorithms | Closed | Jeremy Shulman | 5 | 0 | 1.5 | 2014-12-11 19:30 | Simpply\Iteration 2 | Design Effort
133 | Task | Implement Engine Class Design | Closed | Jeremy Shulman | 8 | 0 | 5 | 2014-12-11 19:30 | Simpply\Iteration 2 | Implementation
207 | Task | Review Distribution Algorithms | Closed | Mustafa Al-Salihi | 1.5 | 0 |  | 2014-12-11 17:05 | Simpply\Iteration 2 | Design Meeting
206 | Task | Review Distribution Algorithms | Closed | Jeremy Shulman | 1.5 | 0 | 0.66 | 2014-12-11 17:05 | Simpply\Iteration 2 | Design Meeting
205 | Task | Review Distribution Algorithms | Closed | Curtis Burtner | 1.5 | 0 | 0.33 | 2014-12-11 17:05 | Simpply\Iteration 2 | Design Meeting
164 | Task | Design Distribution Algorithms | Closed | Mustafa Al-Salihi | 5 | 0 | 3 | 2014-12-11 17:04 | Simpply\Iteration 2 | Design Effort
143 | Task | Review Distribution Algorithms | Closed | Michael Yeaple | 1.5 | 0 | 0.66 | 2014-12-11 17:04 | Simpply\Iteration 2 | Design Meeting
162 | Task | Design Distribution Algorithms | Closed | Curtis Burtner | 5 | 0 |  | 2014-12-11 16:11 | Simpply\Iteration 2 | Design Effort
142 | Task | Design Distribution Algorithms | Closed | Michael Yeaple | 5 | 0 | 1 | 2014-12-11 12:04 | Simpply\Iteration 2 | Design Effort
137 | Task | Implement Database | Closed | Michael Yeaple | 1.5 | 0 | 1.5833 | 2014-12-10 01:24 | Simpply\Iteration 2 | Implementation
155 | Task | Comprehend Data | Closed | Mustafa Al-Salihi | 2 | 0 | 0 | 2014-12-09 22:31 | Simpply\Iteration 2 | Design Effort
129 | Task | Design Web Role Class Interaction | Closed | Curtis Burtner | 1.25 | 0 | 1.5 | 2014-12-09 18:51 | Simpply\Iteration 2 | Design Effort
135 | Task | Review Web Role Design | Closed | Michael Yeaple | 0.75 | 0 | 1.08 | 2014-12-09 18:50 | Simpply\Iteration 2 | Design Meeting
158 | Task | Review Web Role Design | Closed | Mustafa Al-Salihi | 0.75 | 0 | 0.75 | 2014-12-09 18:50 | Simpply\Iteration 2 | Design Meeting
156 | Task | Review Web Role Design | Closed | Curtis Burtner | 0.75 | 0 | 1.08 | 2014-12-09 18:48 | Simpply\Iteration 2 | Design Meeting
157 | Task | Review Web Role Design | Closed | Jeremy Shulman | 0.75 | 0 | 1.08 | 2014-12-09 18:48 | Simpply\Iteration 2 | Design Meeting
134 | Task | Design Database | Closed | Michael Yeaple | 2 | 0 | 2.5 | 2014-12-09 18:25 | Simpply\Iteration 2 | Design Meeting
151 | Task | Design Database | Closed | Mustafa Al-Salihi | 2 | 0 | 0 | 2014-12-09 18:25 | Simpply\Iteration 2 | Design Meeting
149 | Task | Design Database | Closed | Curtis Burtner | 2 | 0 | 2.5 | 2014-12-09 18:24 | Simpply\Iteration 2 | Design Meeting
150 | Task | Design Database | Closed | Jeremy Shulman | 2 | 0 | 2.5 | 2014-12-09 18:24 | Simpply\Iteration 2 | Design Meeting
136 | Task | Review Engine Class Design | Closed | Michael Yeaple | 1 | 0 | 0.75 | 2014-11-28 13:16 | Simpply\Iteration 2 | Design Meeting
160 | Task | Review Engine Class Design | Closed | Jeremy Shulman | 1 | 0 | 0.75 | 2014-11-28 13:16 | Simpply\Iteration 2 | Design Meeting
161 | Task | Review Engine Class Design | Closed | Mustafa Al-Salihi | 1 | 0 | 0.75 | 2014-11-28 13:15 | Simpply\Iteration 2 | Design Meeting
159 | Task | Review Engine Class Design | Closed | Curtis Burtner | 1 | 0 | 0.75 | 2014-11-28 13:15 | Simpply\Iteration 2 | Design Meeting
153 | Task | Comprehend Data | Closed | Curtis Burtner | 2 | 0 | 1 | 2014-11-25 19:24 | Simpply\Iteration 2 | Design Effort
154 | Task | Comprehend Data | Closed | Jeremy Shulman | 2 | 0 | 1 | 2014-11-25 17:56 | Simpply\Iteration 2 | Design Effort
152 | Task | Comprehend Data | Closed | Michael Yeaple | 2 | 0 | 1 | 2014-11-25 17:55 | Simpply\Iteration 2 | Design Effort
132 | Task | Engine Class Design | Closed | Jeremy Shulman | 2 | 0 | 2 | 2014-11-24 20:03 | Simpply\Iteration 2 | Design Effort
146 | Task | Design Engine Architecture | Closed | Curtis Burtner | 0.75 | 0 | 0.85 | 2014-11-21 18:09 | Simpply\Iteration 2 | Design Meeting
131 | Task | Design Engine Architecture | Closed | Michael Yeaple | 0.75 | 0 | 0.85 | 2014-11-21 18:08 | Simpply\Iteration 2 | Design Meeting
147 | Task | Design Engine Architecture | Closed | Jeremy Shulman | 0.75 | 0 | 0.85 | 2014-11-21 18:08 | Simpply\Iteration 2 | Design Meeting
331 | Task | 1/28 Online Meeting | Closed | Jeremy Shulman | 1.5 | 0 | 1.5 | 2015-01-29 19:06 | Simpply | Requirements Meeting
330 | Task | 1/28 Online Meeting | Closed | Curtis Burtner | 1.5 | 0 | 1.5 | 2015-01-29 18:51 | Simpply | Requirements Meeting
342 | Task | Deploy to Production | Closed | Michael Yeaple | 0.25 | 0 | 1.5 | 2015-01-29 14:17 | Simpply\Iteration 3 | Deployment
332 | Task | 1/28 Online Meeting | Closed | Michael Yeaple | 1.5 | 0 | 1.5 | 2015-01-28 18:28 | Simpply | Requirements Meeting
325 | Task | 1/27 Meeting | Closed | Jeremy Shulman | 1.25 | 0 | 1.25 | 2015-01-28 17:24 | Simpply | Process/Project Management Meeting
323 | Task | 1/27 Meeting | Closed | Michael Yeaple | 1.25 | 0 | 1.25 | 2015-01-28 17:23 | Simpply | Process/Project Management Meeting
322 | Task | 1/27 Meeting | Closed | Curtis Burtner | 1.25 | 0 | 1.25 | 2015-01-28 01:29 | Simpply | Process/Project Management Meeting
318 | Task | UI Overhaul Item Detail Implementation | Closed | Michael Yeaple | 1.5 | 0 | 2.817 | 2015-01-27 18:28 | Simpply\Interim Sprint | Implementation
321 | Task | Add Default Functionality to Column Preferences | Closed | Michael Yeaple | 1 | 0 | 0.85 | 2015-01-27 18:27 | Simpply\Iteration 3 | Implementation
39 | Task | Request more harddrive space from Kurt | Closed | Curtis Burtner | 0.5 | 0 | 1.25 | 2015-01-27 18:05 | Simpply\Iteration 1 | Project Setup
320 | Task | Fix VM Post-Migration | Closed | Michael Yeaple | 2 | 0 | 4.25 | 2015-01-27 18:03 | Simpply\Iteration 3 | Project Setup
315 | Task | UI Overhaul Design | Closed | Curtis Burtner | 1 | 0 | 0.8333 | 2015-01-25 23:49 | Simpply\Interim Sprint | Design Meeting
316 | Task | UI Overhaul Design | Closed | Michael Yeaple | 1 | 0 | 0.8333 | 2015-01-25 23:49 | Simpply\Interim Sprint | Design Meeting
319 | Task | Fix UI Post-Bootstrap | Closed | Michael Yeaple | 3 |  | 4.3333 | 2015-01-25 21:07 | Simpply\Interim Sprint | Implementation
313 | Task | Bootstrap it! | Closed | Michael Yeaple | 1 | 0 | 1.25 | 2015-01-25 15:49 | Simpply\Interim Sprint | Implementation
314 | Task | Investigate front-end frameworks | Closed | Michael Yeaple | 3 | 0 | 3 | 2015-01-25 10:40 | Simpply\Interim Sprint | Design Effort
312 | Task | Implement Search by ID | Closed | Michael Yeaple | 1 | 0 | 0.75 | 2015-01-11 21:37 | Simpply\Interim Sprint | Implementation
15 | User Story | Compare Aggregate Store Data to Individual Store Data | Closed |  |  |  |  | 2014-12-18 17:30 | Simpply\Iteration 2
192 | Task | Feature Implementation | Closed | Mustafa Al-Salihi | 8 | 0 | 8 | 2014-12-11 20:53 | Simpply\Iteration 2
187 | Task | Class Design | Closed | Mustafa Al-Salihi | 0.5 | 0 | 0.5 | 2014-12-09 18:32 | Simpply\Iteration 2 | Design Effort
191 | Task | Class Design Review | Closed | Mustafa Al-Salihi | 0.5 |  | 0.5 | 2014-12-09 18:31 | Simpply\Iteration 2 | Design Meeting
186 | Task | Review User Experience | Closed | Mustafa Al-Salihi | 0.5 | 0 | 0.5 | 2014-11-28 12:30 | Simpply\Iteration 2 | Design Meeting
185 | Task | Review User Experience | Closed | Jeremy Shulman | 0.5 | 0 | 0.5 | 2014-11-28 12:30 | Simpply\Iteration 2 | Design Meeting
184 | Task | Review User Experience | Closed | Curtis Burtner | 0.5 | 0 | 0.5 | 2014-11-28 12:29 | Simpply\Iteration 2 | Design Meeting
183 | Task | Review User Experience | Closed | Michael Yeaple | 0.5 | 0 | 0.5 | 2014-11-28 12:29 | Simpply\Iteration 2 | Design Meeting
182 | Task | Design User Experience | Closed | Mustafa Al-Salihi | 1.5 | 0 | 2 | 2014-11-28 12:17 | Simpply\Iteration 2 | Design Effort
190 | Task | Class Design Review | Closed | Jeremy Shulman | 0.5 | 0 | 0.75 | 2014-11-25 19:23 | Simpply\Iteration 2 | Design Meeting
188 | Task | Class Design Review | Closed | Michael Yeaple | 0.5 | 0 | 0.75 | 2014-11-25 19:22 | Simpply\Iteration 2 | Design Meeting
189 | Task | Class Design Review | Closed | Curtis Burtner | 0.5 | 0 | 0.75 | 2014-11-25 19:22 | Simpply\Iteration 2 | Design Meeting
34 | User Story | Customize Item Explorer | Closed |  |  |  |  | 2014-12-18 17:27 | Simpply\Iteration 2
181 | Task | Implement Feature | Closed | Michael Yeaple | 1.5 | 0 | 17.536 | 2014-12-12 00:06 | Simpply\Iteration 2 | Implementation
180 | Task | Review Class Design | Closed | Mustafa Al-Salihi | 0.5 | 0 | 0.5 | 2014-11-28 13:45 | Simpply\Iteration 2 | Design Meeting
179 | Task | Review Class Design | Closed | Jeremy Shulman | 0.5 | 0 | 0.5 | 2014-11-28 13:45 | Simpply\Iteration 2 | Design Meeting
178 | Task | Review Class Design | Closed | Curtis Burtner | 0.5 | 0 | 0.5 | 2014-11-28 13:44 | Simpply\Iteration 2 | Design Meeting
177 | Task | Review Class Design | Closed | Michael Yeaple | 0.5 | 0 | 0.5 | 2014-11-28 13:44 | Simpply\Iteration 2 | Design Meeting
175 | Task | Review User Experience Design | Closed | Mustafa Al-Salihi | 0.5 | 0 | 0.55 | 2014-11-24 21:30 | Simpply\Iteration 2 | Design Meeting
172 | Task | Review User Experience Design | Closed | Michael Yeaple | 0.5 | 0 | 0.55 | 2014-11-24 20:59 | Simpply\Iteration 2 | Design Meeting
174 | Task | Review User Experience Design | Closed | Jeremy Shulman | 0.5 | 0 | 0.55 | 2014-11-24 20:58 | Simpply\Iteration 2 | Design Meeting
173 | Task | Review User Experience Design | Closed | Curtis Burtner | 0.5 | 0 | 0.55 | 2014-11-24 20:58 | Simpply\Iteration 2 | Design Meeting
176 | Task | Class Design for Customize Item Explorer | Closed | Michael Yeaple | 2 | 0 | 2.25 | 2014-11-24 15:47 | Simpply\Iteration 2 | Design Effort
171 | Task | Design User Experience | Closed | Curtis Burtner | 1 | 0 | 2.5 | 2014-11-23 17:43 | Simpply\Iteration 2 | Design Effort
311 | Task | Compose Email to Martinez | Closed | Michael Yeaple | 0.167 | 0 | 0.167 | 2014-12-17 21:45 | Simpply | Academic Work Effort
263 | Task | Update Website with Deliverables on Machine | Closed | Jeremy Shulman | 0.5 | 0 | 0.25 | 2014-12-17 21:22 | Simpply | Academic Work Effort
310 | Task | Update Interim Artifacts | Closed | Curtis Burtner | 1 | 0 | 0.75 | 2014-12-17 21:20 | Simpply | Academic Work Meeting
309 | Task | Update Interim Artifacts | Closed | Mustafa Al-Salihi | 1 | 0 | 0.75 | 2014-12-17 21:20 | Simpply | Academic Work Meeting
308 | Task | Update Interim Artifacts | Closed | Jeremy Shulman | 1 | 0 | 0.75 | 2014-12-17 21:20 | Simpply | Academic Work Meeting
307 | Task | Update Interim Artifacts | Closed | Michael Yeaple | 1 | 0 | 0.75 | 2014-12-17 21:20 | Simpply | Academic Work Meeting
306 | Task | Interim Assessment Planning Meeting | Closed | Mustafa Al-Salihi | 1 | 0 | 0.25 | 2014-12-17 21:18 | Simpply | Planning Meeting
305 | Task | Interim Assessment Planning Meeting | Closed | Jeremy Shulman | 1 | 0 | 0.5 | 2014-12-17 21:18 | Simpply | Planning Meeting
304 | Task | Interim Assessment Planning Meeting | Closed | Curtis Burtner | 1 | 0 | 0.5 | 2014-12-17 21:18 | Simpply | Planning Meeting
303 | Task | Interim Assessment Planning Meeting | Closed | Michael Yeaple | 1 | 0 | 0.5 | 2014-12-17 21:18 | Simpply | Planning Meeting
267 | Task | Write Acceptance Tests For all user stories for this iteration. | Closed | Mustafa Al-Salihi | 0.5 | 0 | 0 | 2014-12-17 19:51 | Simpply | Testing Meeting
266 | Task | Write Acceptance Tests For all user stories for this iteration. | Closed | Jeremy Shulman | 0.5 | 0 | 0.33 | 2014-12-17 19:51 | Simpply | Testing Meeting
265 | Task | Write Acceptance Tests For all user stories for this iteration. | Closed | Curtis Burtner | 0.5 | 0 | 0.33 | 2014-12-17 19:51 | Simpply | Testing Meeting
264 | Task | Write Acceptance Tests For all user stories for this iteration. | Closed | Michael Yeaple | 1 | 0 | 0.88 | 2014-12-17 19:50 | Simpply | Testing Meeting
302 | Task | Merge to Master | Closed | Michael Yeaple | 0.25 | 0 | 0.25 | 2014-12-17 18:46 | Simpply | Process/Project Management Effort
296 | Task | Update Artifacts | Closed | Michael Yeaple | 1 | 0 | 0.5 | 2014-12-17 17:54 | Simpply | Academic Work Effort
301 | Task | Updated Metrics | Closed | Curtis Burtner | 0.5 | 0 | 0.5 | 2014-12-17 00:51 | Simpply
300 | Task | Update Design Document | Closed | Jeremy Shulman | 2 | 0 | 1.5 | 2014-12-16 23:26 | Simpply | Process/Project Management Effort
299 | Task | Email to Customer for meeting details and effort report | Closed | Curtis Burtner | 0.5 | 0 | 1 | 2014-12-16 23:09 | Simpply | Process/Project Management Effort
298 | Task | Plan Customer Meeting | Closed | Michael Yeaple | 0.5 | 0 | 0.5 | 2014-12-16 19:39 | Simpply\Iteration 2 | Process/Project Management Effort
262 | Task | Investigate complex data mapping for Dapper | Closed | Curtis Burtner | 1 | 0 | 3 | 2014-12-16 19:22 | Simpply | Project Setup
297 | Task | Finish Hooking Up To The Database | Closed | Curtis Burtner | 2 | 0 | 2 | 2014-12-16 19:22 | Simpply | Implementation
292 | Task | Team Self-Assessment | Closed | Michael Yeaple | 2 | 0 | 3 | 2014-12-15 22:05 | Simpply | Academic Work Meeting
295 | Task | Team Self-Assessment | Closed | Mustafa Al-Salihi | 2 | 0 | 3 | 2014-12-15 22:05 | Simpply | Academic Work Meeting
294 | Task | Team Self-Assessment | Closed | Jeremy Shulman | 2 | 0 | 3 | 2014-12-15 22:04 | Simpply | Academic Work Meeting
293 | Task | Team Self-Assessment | Closed | Curtis Burtner | 2 | 0 | 3 | 2014-12-15 22:04 | Simpply | Academic Work Meeting
291 | Task | Implement Complex Mapping for ItemDetails Page | Closed | Curtis Burtner | 1 | 0 | 3 | 2014-12-13 15:20 | Simpply | Implementation
288 | Task | Code Review With Wegmans | Closed | Curtis Burtner | 1.5 | 0 | 1.5 | 2014-12-13 15:19 | Simpply | Code/Design Review
290 | Task | Refactor based on code review | Closed | Michael Yeaple | 0.75 | 0 | 1 | 2014-12-12 19:55 | Simpply | Refactoring
289 | Task | Code Review With Wegmans | Closed | Michael Yeaple | 1.5 | 0 | 1.5 | 2014-12-12 13:04 | Simpply | Code/Design Review
287 | Task | Mocked Data For Database Tables | Closed | Curtis Burtner | 0.5 | 0 | 0.5 | 2014-12-12 02:54 | Simpply | Implementation
286 | Task | Code Merge from Unstable to Stable | Closed | Michael Yeaple | 0.25 | 0 | 0.25 | 2014-12-12 01:23 | Simpply | Implementation
279 | Task | Pair Programming | Closed | Michael Yeaple | 2 | 1 | 2.917 | 2014-12-12 01:17 | Simpply | Implementation
285 | Task | Code Review | Closed | Jeremy Shulman | 0.5 | 0 | 0.5 | 2014-12-11 22:11 | Simpply | Code/Design Review
284 | Task | Code Review | Closed | Michael Yeaple | 0.5 | 0 | 0.5 | 2014-12-11 22:11 | Simpply | Code/Design Review
281 | Task | Customer Emails | Closed | Curtis Burtner | 0.5 | 0 | 0.5 | 2014-12-11 17:18 | Simpply | Process/Project Management Effort
280 | Task | Added Dapper Examples Using Stored Procedures. Also Added New Connection String | Closed | Curtis Burtner | 2 | 0 | 6 | 2014-12-11 17:04 | Simpply | Implementation
248 | Task | Implement connection string so that it changes with mode project is run in | Closed | Curtis Burtner | 0.75 | 0 | 0.75 | 2014-12-11 15:55 | Simpply\Iteration 2 | Implementation
85 | Task | Use Autofac in code | Closed | Curtis Burtner | 1 | 1 | 0 | 2014-12-11 15:53 | Simpply\Iteration 1 | Implementation
106 | Task | NUnit Mock | Closed | Mustafa Al-Salihi |  |  |  | 2014-12-11 15:53 | Simpply\Iteration 1 | Project Setup
278 | Task | Make updates to SQL Creation | Closed | Michael Yeaple | 0.25 | 0 | 0.5 | 2014-12-11 15:39 | Simpply | Implementation
277 | Task | Fix target framework of engine | Closed | Jeremy Shulman | 1 | 0 | 1 | 2014-12-10 05:44 | Simpply
276 | Task | Fix AccountController SaveColumnPreferences Unit Test | Closed | Michael Yeaple | 0.25 | 0 | 0.25 | 2014-12-10 01:48 | Simpply | Implementation
275 | Task | Email Team | Closed | Michael Yeaple | 0.3 | 0 | 0.3 | 2014-12-10 01:35 | Simpply | Implementation
274 | Task | 12/09 Customer Email | Closed | Curtis Burtner | 1 | 0 | 1 | 2014-12-09 23:21 | Simpply\Iteration 2 | Process/Project Management Effort
273 | Task | 12/09 Meeting | Closed | Michael Yeaple | 2 | 0 | 0.5 | 2014-12-09 20:04 | Simpply | Design Meeting
272 | Task | 12/09 Meeting | Closed | Jeremy Shulman | 2 | 0 | 0.5 | 2014-12-09 20:04 | Simpply | Design Meeting
260 | Task | 12/09 Meeting | Closed | Curtis Burtner | 2 | 0 | 0.5 | 2014-12-09 20:02 | Simpply | Design Meeting
261 | Task | 12/09 Meeting | Closed | Mustafa Al-Salihi | 2 | 0 | 0 | 2014-12-09 20:02 | Simpply | Design Meeting
271 | Task | Code Review Jeremy's Engine and Michael's Providers | Closed | Michael Yeaple | 1 | 0 | 1 | 2014-12-09 19:56 | Simpply | Code/Design Review
270 | Task | Code Review Jeremy's Engine and Michael's Providers | Closed | Jeremy Shulman | 1 | 0 | 1 | 2014-12-09 19:55 | Simpply | Code/Design Review
269 | Task | Code Review Jeremy's Engine and Michael's Providers | Closed | Curtis Burtner | 1 | 0 | 1 | 2014-12-09 19:55 | Simpply | Code/Design Review
118 | Task | 11/13 End of Iteration Customer Meeting | Closed | Curtis Burtner | 1.25 | 0 | 1.25 | 2014-12-09 17:58 | Simpply\Iteration 1 | Progress Meeting
250 | Task | Make Calendar to Track Due Dates | Closed | Michael Yeaple | 1.5 | 0 | 0.9 | 2014-12-09 11:24 | Simpply | Academic Work Effort
246 | Task | Implement Dependency Injection using AutoFac | Closed | Michael Yeaple | 3 | 2.766 | 4.2333 | 2014-12-07 18:18 | Simpply | Implementation
259 | Task | 12/05 Online Meeting With Mike | Closed | Jeremy Shulman | 1 | 0 | 1 | 2014-12-05 12:54 | Simpply | Requirements Meeting
258 | Task | 12/05 Online Meeting With Mike | Closed | Curtis Burtner | 1 | 0 | 1 | 2014-12-05 12:54 | Simpply | Requirements Meeting
257 | Task | Attend 12/02 Presentations (And Give Presentation | Closed | Mustafa Al-Salihi | 1.5 | 0 | 1.5 | 2014-12-04 21:15 | Simpply | Academic Work Effort
256 | Task | Attend 12/02 Presentations (And Give Presentation | Closed | Jeremy Shulman | 1.5 | 0 | 1.5 | 2014-12-04 21:15 | Simpply | Academic Work Effort
255 | Task | Attend 12/02 Presentations (And Give Presentation | Closed | Michael Yeaple | 1.5 | 0 | 1.5 | 2014-12-04 21:15 | Simpply | Academic Work Effort
254 | Task | Attend 12/02 Presentations (And Give Presentation | Closed | Curtis Burtner | 1.5 | 0 | 1.5 | 2014-12-04 21:15 | Simpply | Academic Work Effort
27 | Task | Quality requirements | Closed | Curtis Burtner |  |  |  | 2014-12-04 21:14 | Simpply\Iteration 1 | Requirements Effort
253 | Task | Attend 12/04 Presentations | Closed | Jeremy Shulman | 2.5 | 0 | 2.5 | 2014-12-04 21:11 | Simpply | Academic Work Effort
252 | Task | Attend 12/04 Presentations | Closed | Michael Yeaple | 2.5 | 0 | 2.5 | 2014-12-04 21:11 | Simpply | Academic Work Effort
251 | Task | Attend Presentations | Closed | Curtis Burtner | 2.5 | 0 | 2.5 | 2014-12-04 21:10 | Simpply | Academic Work Effort
140 | Task | Practice Presentation with Team | Closed | Jeremy Shulman | 2.5 | 0 | 5.37 | 2014-12-02 21:57 | Simpply | Academic Work Meeting
141 | Task | Practice Presentation with Team | Closed | Mustafa Al-Salihi | 2.5 | 0 | 5.37 | 2014-12-02 16:50 | Simpply | Academic Work Meeting
138 | Task | Practice Presentation with Team | Closed | Michael Yeaple | 2.5 | 0 | 5.37 | 2014-12-02 16:49 | Simpply | Academic Work Meeting
139 | Task | Practice Presentation with Team | Closed | Curtis Burtner | 2.5 | 0 | 5.37 | 2014-12-02 16:49 | Simpply | Academic Work Meeting
249 | Task | Added Week by Week Tag Hour Break Out | Closed | Curtis Burtner | 1.25 | 0 | 1.25 | 2014-12-01 20:10 | Simpply\Iteration 2 | Process/Project Management Effort
247 | Task | Generated Charts | Closed | Curtis Burtner | 0.5 | 0 | 1 | 2014-11-30 19:38 | Simpply | Academic Work Effort
235 | Task | Add Simpply.Global | Closed | Michael Yeaple | 0.15 | 0 | 0.15 | 2014-11-30 18:48 | Simpply | Implementation
245 | Task | Tagged Historical Data, Setup Historical Data Spreadsheet | Closed | Curtis Burtner | 1 | 0 | 2.5 | 2014-11-29 18:48 | Simpply | Process/Project Management Effort
244 | Task | Adjusted Effort Task Tracking Spreadsheet | Closed | Curtis Burtner | 0.25 | 0 | 1 | 2014-11-29 13:35 | Simpply | Process/Project Management Effort
243 | Task | Went through backlog and repathed old tasks to Simpply | Closed | Curtis Burtner | 0.5 | 0 | 0.75 | 2014-11-29 12:42 | Simpply | Process/Project Management Effort
241 | Task | Planning Meeting 11/28 | Closed | Curtis Burtner | 0.25 | 0 | 0.25 | 2014-11-28 14:00 | Simpply | Planning Meeting
242 | Task | Planning Meeting 11/28 | Closed | Mustafa Al-Salihi | 0.25 | 0 | 0.25 | 2014-11-28 14:00 | Simpply | Planning Meeting
240 | Task | Planning Meeting 11/28 | Closed | Jeremy Shulman | 0.25 | 0 | 0.25 | 2014-11-28 14:00 | Simpply | Planning Meeting
239 | Task | Planning Meeting 11/28 | Closed | Michael Yeaple | 0.25 | 0 | 0.25 | 2014-11-28 14:00 | Simpply | Planning Meeting
238 | Task | Update Effort Task Tracking Spreadsheet | Closed | Curtis Burtner | 1 | 0 | 1 | 2014-11-27 02:00 | Simpply | Process/Project Management Effort
237 | Task | Reformatted Historical Task Data | Closed | Curtis Burtner | 1 | 0 | 1 | 2014-11-26 02:02 | Simpply | Process/Project Management Effort
236 | Task | Email to customer | Closed | Curtis Burtner | 0.5 | 0 | 0.75 | 2014-11-26 01:20 | Simpply | Process/Project Management Effort
232 | Task | Task Assignment Meeting | Closed | Jeremy Shulman | 0.5 | 0 | 0.75 | 2014-11-25 20:01 | Simpply | Planning Meeting
233 | Task | Task Assignment Meeting | Closed | Curtis Burtner | 0.5 | 0 | 0.75 | 2014-11-25 20:01 | Simpply | Planning Meeting
234 | Task | Task Assignment Meeting | Closed | Mustafa Al-Salihi | 0.5 | 0 | 0.75 | 2014-11-25 20:01 | Simpply | Planning Meeting
231 | Task | Task Assignment Meeting | Closed | Michael Yeaple | 0.5 | 0.25 | 0.75 | 2014-11-25 20:00 | Simpply | Planning Meeting
87 | Task | Investigate Providing a "Real" Burndown | Closed | Curtis Burtner | 2 | 0.5 | 1.5 | 2014-11-25 10:38 | Simpply | Process/Project Management Effort
230 | Task | Email to Martinez | Closed | Curtis Burtner | 0.5 | 0 | 0.5 | 2014-11-25 01:36 | Simpply | Process/Project Management Effort
224 | Task | Email to Martinez about backdating in TFS | Closed | Curtis Burtner | 1 | 0 | 1 | 2014-11-25 00:12 | Simpply | Process/Project Management Effort
229 | Task | Reviewed and Updated risks | Closed | Curtis Burtner | 0.5 | 0 | 0.5 | 2014-11-24 11:31 | Simpply | Process/Project Management Effort
223 | Task | Planning Meeting 11/21 | Closed | Jeremy Shulman | 1 | 0 | 2 | 2014-11-21 21:31 | Simpply | Planning Meeting
222 | Task | Planning Meeting 11/21 | Closed | Curtis Burtner | 1 | 0 | 2 | 2014-11-21 21:31 | Simpply | Planning Meeting
221 | Task | Planning Meeting 11/21 | Closed | Michael Yeaple | 1 | 0 | 2 | 2014-11-21 21:31 | Simpply | Planning Meeting
119 | Task | 11/13 End of Iteration Customer Meeting | Closed | Jeremy Shulman | 1.25 | 0 | 1.25 | 2014-11-21 17:22 | Simpply | Progress Meeting
228 | Task | On-site Wegmans Algorithms Meeting | Closed | Mustafa Al-Salihi | 2 | 0 | 2.25 | 2014-11-21 17:22 | Simpply | Requirements Meeting
227 | Task | On-site Wegmans Algorithms Meeting | Closed | Jeremy Shulman | 2 | 0 | 2.25 | 2014-11-21 17:21 | Simpply | Requirements Meeting
226 | Task | On-site Wegmans Algorithms Meeting | Closed | Curtis Burtner | 2 | 0 | 2.25 | 2014-11-21 17:21 | Simpply | Requirements Meeting
225 | Task | On-site Wegmans Algorithms Meeting | Closed | Michael Yeaple | 2 | 0 | 2.25 | 2014-11-21 17:21 | Simpply | Requirements Meeting
220 | Task | Email to Martinez | Closed | Curtis Burtner | 0.5 | 0 | 0.75 | 2014-11-21 01:08 | Simpply | Process/Project Management Effort
219 | Task | Design Document | Closed | Jeremy Shulman | 3 | 0 | 3 | 2014-11-21 00:47 | Simpply | Process/Project Management Effort
218 | Task | Investigate task back-dating | Closed | Curtis Burtner | 1 | 0 | 1 | 2014-11-21 00:18 | Simpply | Process/Project Management Effort
212 | Task | Presentation Meeting | Closed | Michael Yeaple | 1.75 | 0 | 2.5 | 2014-11-20 20:03 | Simpply | Academic Work Meeting
214 | Task | Presentation Meeting | Closed | Jeremy Shulman | 1.75 | 0 | 2.5 | 2014-11-20 20:03 | Simpply | Academic Work Meeting
215 | Task | Presentation Meeting | Closed | Mustafa Al-Salihi | 1.75 | 0 | 2.5 | 2014-11-20 20:03 | Simpply | Academic Work Meeting
213 | Task | Presentation Meeting | Closed | Curtis Burtner | 1.75 | 0 | 2.5 | 2014-11-20 20:03 | Simpply | Academic Work Meeting
104 | Task | 11/11 Meeting | Closed | Mustafa Al-Salihi | 1.25 | 0 | 1.25 | 2014-11-20 20:00 | Simpply | Process/Project Management Effort
170 | Task | 11/19 Meeting - Finish Story/Task Planning | Closed | Mustafa Al-Salihi | 1.5 | 0 | 1.5 | 2014-11-19 18:17 | Simpply | Planning Meeting
169 | Task | 11/19 Meeting - Finish Story/Task Planning | Closed | Curtis Burtner | 1.5 | 0 | 1.5 | 2014-11-19 18:17 | Simpply | Planning Meeting
168 | Task | 11/19 Meeting - Finish Story/Task Planning | Closed | Jeremy Shulman | 1.5 | 0 | 2 | 2014-11-19 18:17 | Simpply | Planning Meeting
167 | Task | 11/19 Meeting - Finish Story/Task Planning | Closed | Michael Yeaple | 1.5 | 0 | 1.5 | 2014-11-19 18:17 | Simpply | Planning Meeting
126 | Task | Planning Meeting 11/18 | Closed | Curtis Burtner | 1.25 | 0 | 1.5 | 2014-11-19 18:15 | Simpply | Planning Meeting
193 | Task | Rename tasks for consistency and Update Remaining field. | Closed | Michael Yeaple | 0.5 | 0 | 1 | 2014-11-19 18:09 | Simpply | Process/Project Management Effort
166 | Task | Adjusted task queries | Closed | Curtis Burtner | 0.5 | 0 | 0.5 | 2014-11-19 14:30 | Simpply | Process/Project Management Effort
144 | Task | Take care of task tagging/linking/duplication From 11/18 Meeting | Closed | Michael Yeaple | 0.5 | 0 | 1 | 2014-11-19 11:47 | Simpply | Process/Project Management Effort
17 | Task | Change Schedule | Closed | Mustafa Al-Salihi | 1 | 0 | 1 | 2014-11-19 11:27 | Simpply | Process/Project Management Effort
83 | Task | Create a test plan using TFS | Closed | Mustafa Al-Salihi | 4 | 0 | 4 | 2014-11-19 11:27 | Simpply | Testing Effort
120 | Task | 11/13 End of Iteration Customer Meeting | Closed | Mustafa Al-Salihi | 1.25 | 0 | 1.25 | 2014-11-19 11:26 | Simpply | Progress Meeting
145 | Task | Email to customer | Closed | Curtis Burtner | 0.5 | 0 | 0.75 | 2014-11-18 20:39 | Simpply | Process/Project Management Effort
127 | Task | Planning Meeting 11/18 | Closed | Jeremy Shulman | 1.25 | 0 | 2 | 2014-11-18 19:41 | Simpply | Planning Meeting
128 | Task | Planning Meeting 11/18 | Closed | Mustafa Al-Salihi | 1.25 | 0 | 1.5 | 2014-11-18 19:41 | Simpply | Planning Meeting
125 | Task | Planning Meeting 11/18 | Closed | Michael Yeaple | 1.25 | 0 | 1.75 | 2014-11-18 19:38 | Simpply | Planning Meeting
124 | Task | Investigate Interim Presentation | Closed | Michael Yeaple | 0.75 | 0 | 1 | 2014-11-17 19:41 | Simpply | Academic Work Effort
121 | Task | 11/13 End of Iteration Customer Meeting | Closed | Michael Yeaple | 1.25 | 0 | 1.25 | 2014-11-17 18:56 | Simpply | Progress Meeting
73 | Task | Set Up Individual Effort Reports | Closed | Curtis Burtner | 1.5 | 0 | 2 | 2014-11-16 18:28 | Simpply | Process/Project Management Effort
41 | Task | Manage Risks | Closed | Curtis Burtner | 6 | 0 | 6.25 | 2014-11-14 16:03 | Simpply | Process/Project Management Effort
117 | Task | Page Styling/Refactoring Meeting | Closed | Curtis Burtner | 2.5 | 0 | 2.5 | 2014-11-13 16:13 | Simpply | Refactoring
122 | Task | CSS Touch up with Michael | Closed | Jeremy Shulman | 1.25 | 0 | 1.25 | 2014-11-13 16:10 | Simpply | Refactoring
116 | Task | Page Styling/Refactoring Meeting | Closed | Michael Yeaple | 2.5 | 0 | 3.25 | 2014-11-13 16:04 | Simpply | Refactoring
101 | Task | 11/11 Meeting | Closed | Curtis Burtner | 1.25 | 0 | 1.25 | 2014-11-13 14:10 | Simpply | Process/Project Management Effort
35 | User Story | Sort Summary of All Items | Closed | Michael Yeaple |  |  |  | 2014-11-13 11:56 | Simpply\Iteration 1
114 | Task | Style Column Headers based on Sort | Closed | Michael Yeaple | 1 | 0 | 0.5 | 2014-11-12 14:30 | Simpply\Iteration 1 | Implementation
67 | Task | Implementation | Closed | Michael Yeaple | 1.5 | 0 | 1.75 | 2014-11-12 13:59 | Simpply\Iteration 1 | Implementation
66 | Task | Design Classes | Closed | Michael Yeaple | 0.75 | 0 | 0.75 | 2014-11-12 12:15 | Simpply\Iteration 1 | Design Effort
1 | User Story | View Basic Item Information | Closed | Jeremy Shulman |  |  |  | 2014-11-13 11:56 | Simpply\Iteration 1 | Implementation
115 | Task | Sales Information Logic | Closed | Jeremy Shulman | 3.5 | 0 | 3.5 | 2014-11-12 23:57 | Simpply\Iteration 1 | Implementation
33 | User Story | View Summary of All Items | Closed | Curtis Burtner |  |  |  | 2014-11-13 11:55 | Simpply\Iteration 1
105 | Task | Style Page | Closed | Curtis Burtner | 2 | 0 | 4.5 | 2014-11-13 04:13 | Simpply\Iteration 1 | Implementation
61 | Task | Style Page | Closed | Michael Yeaple | 2 | 0 | 0.25 | 2014-11-11 18:21 | Simpply\Iteration 1 | Implementation
58 | Task | Implement Design | Closed | Michael Yeaple | 4 | 0 | 6 | 2014-11-03 18:46 | Simpply\Iteration 1 | Implementation
57 | Task | Design Classes | Closed | Michael Yeaple | 1 | 0 | 1.25 | 2014-11-03 13:55 | Simpply\Iteration 1 | Design Effort
37 | User Story | Create Detailed Item Data View | Closed | Jeremy Shulman |  |  |  | 2014-11-13 11:55 | Simpply\Iteration 1 | Implementation
60 | Bug | ItemDetail Null Reference Error | Resolved | Jeremy Shulman |  |  |  |  | Simpply\Iteration 1 | Bugs
88 | Task | Fix Null Reference Error (60) | Closed | Jeremy Shulman | 1 | 0 | 0.75 | 2014-11-06 17:54 | Simpply\Iteration 1 | Implementation
80 | Task | Implementation w/mock data | Closed | Mustafa Al-Salihi | 5 |  | 3 | 2014-11-12 23:53 | Simpply\Iteration 1 | Implementation
50 | Task | Implementation w/mock data | Closed | Jeremy Shulman | 5 |  | 4 | 2014-11-12 23:50 | Simpply\Iteration 1 | Implementation
49 | Task | Wireframes/Mockups | Closed | Mustafa Al-Salihi | 1 | 1.3 | 1 | 2014-11-04 18:09 | Simpply\Iteration 1 | Design Effort;Requirements Effort
48 | Task | Class Diagram | Closed | Jeremy Shulman | 1 |  | 1 | 2014-11-04 18:09 | Simpply\Iteration 1 | Design Effort
38 | User Story | Create Item Summary View | Closed | Michael Yeaple |  |  |  | 2014-11-13 11:55 | Simpply\Iteration 1
62 | Task | Add Missing Placeholders | Closed | Michael Yeaple | 0.5 |  |  | 2014-11-04 00:42 | Simpply\Iteration 1 | Implementation
45 | Task | Implement View with Dummy Data (Item Summary View) | Closed | Michael Yeaple | 4 | 0 | 0.5 | 2014-11-03 17:46 | Simpply\Iteration 1 | Implementation
43 | Task | Design Classes (Item Summary View) | Closed | Michael Yeaple | 1 |  | 1.25 | 2014-10-28 15:07 | Simpply\Iteration 1 | Design Effort
44 | Task | Create Mockups (Item Summary View) | Closed | Michael Yeaple | 1 |  | 0.5 | 2014-10-28 15:07 | Simpply\Iteration 1 | Design Effort
47 | Task | Task Breakdown (Item Summary View) | Closed | Michael Yeaple | 1 | 0 | 1 | 2014-10-21 13:16 | Simpply\Iteration 1 | Process/Project Management Effort
102 | Task | 11/11 Meeting | Closed | Jeremy Shulman | 1.25 | 0 | 1.25 | 2014-11-12 23:50 | Simpply | Process/Project Management Effort
75 | Task | Fix ItemController Code for Failed Unit Tests | Closed | Michael Yeaple | 0.167 | 0.5 | 1.5503 | 2014-11-12 15:54 | Simpply | Implementation
113 | Task | Quick Review with Michael | Closed | Curtis Burtner | 1 | 0 | 1 | 2014-11-12 13:00 | Simpply | Code/Design Review
103 | Task | 11/11 Meeting | Closed | Michael Yeaple | 1.25 | 0 | 1.25 | 2014-11-11 19:06 | Simpply | Process/Project Management Effort
99 | Task | Email to Team | Closed | Curtis Burtner | 1 | 0 | 0.75 | 2014-11-11 16:18 | Simpply | Process/Project Management Effort
92 | Task | Setup FTP Server | Closed | Michael Yeaple | 0.5 | 0 | 1.5 | 2014-11-10 14:01 | Simpply | Project Setup
100 | Task | Setup FTP Server | Closed | Jeremy Shulman | 0.5 | 0 | 0.5 | 2014-11-10 14:01 | Simpply | Project Setup
91 | Task | Customer Progress Meeting | Closed | Jeremy Shulman | 1.25 | 0 | 1.25 | 2014-11-10 13:57 | Simpply | Progress Meeting
72 | Task | Team Meeting | Closed | Curtis Burtner | 1.25 | 0 | 2 | 2014-11-08 22:07 | Simpply | Process/Project Management Effort
98 | Task | Refactor Code Based on Code Review | Closed | Michael Yeaple | 0.33 | 0 | 0.75 | 2014-11-08 16:20 | Simpply | Refactoring
89 | Task | Customer Progress Meeting | Closed | Michael Yeaple | 1.25 | 0 | 1.25 | 2014-11-08 15:46 | Simpply | Progress Meeting
97 | Task | Post Code Review Notes | Closed | Michael Yeaple | 0.25 | 0 | 0.25 | 2014-11-08 15:44 | Simpply | Code/Design Review
95 | Task | Code Review | Closed | Michael Yeaple | 1 | 0 | 1 | 2014-11-08 15:43 | Simpply | Code/Design Review
96 | Task | Code Review | Closed | Jeremy Shulman | 1 | 0 | 1 | 2014-11-08 15:22 | Simpply | Code/Design Review
90 | Task | Customer Progress Meeting | Closed | Curtis Burtner | 1.25 | 0 | 1.25 | 2014-11-07 19:34 | Simpply | Progress Meeting
94 | Task | Create calendar notification for interim presentation | Closed | Curtis Burtner | 0.5 | 0 | 0.5 | 2014-11-07 19:33 | Simpply | Process/Project Management Effort
86 | Task | Use Dapper in code | Closed | Curtis Burtner | 1 | 0 | 3.5 | 2014-11-07 18:16 | Simpply | Implementation
54 | Task | Set Up Autofac | Closed | Curtis Burtner | 3 | 0 | 3 | 2014-11-07 11:21 | Simpply | Project Setup
78 | Task | Tag All Previous Work Items | Closed | Curtis Burtner | 1 | 0 | 1 | 2014-11-06 22:56 | Simpply | Process/Project Management Effort
93 | Task | Add All Tags | Closed | Curtis Burtner | 0.5 | 0 | 0.5 | 2014-11-06 22:05 | Simpply | Academic Work Effort;Academic Work Meeting;Design Effort;Design Meeting;Implementation;Process/Project Management Effort;Process/Project Management Meeting;Project Setup;Refactoring;Requirements Effort;Requirements Meeting;Testing Effort;Testing Meeting
81 | Task | Research Standards for CSS File Organization | Closed | Jeremy Shulman | 0.5 | 0 | 0.5 | 2014-11-06 02:22 | Simpply | Project Setup
71 | Task | Team Meeting | Closed | Jeremy Shulman | 1.25 |  | 2 | 2014-11-05 00:55 | Simpply | Process/Project Management Effort
55 | Task | Set Up Dapper | Closed | Curtis Burtner | 1.5 | 0 | 1.5 | 2014-11-05 00:15 | Simpply | Project Setup
82 | Task | Email Customer | Closed | Curtis Burtner | 0.75 | 0 | 0.75 | 2014-11-04 23:39 | Simpply | Process/Project Management Effort
70 | Task | Team Meeting | Closed | Michael Yeaple | 1.25 | 0 | 2 | 2014-11-04 19:53 | Simpply | Process/Project Management Effort
79 | Task | Clarify Action URL Generation in Code | Closed | Michael Yeaple | 0.5 | 0 | 0.5 | 2014-11-04 19:37 | Simpply | Implementation
77 | Task | Code Review With Michael | Closed | Curtis Burtner | 0.5 | 0 | 0.5 | 2014-11-04 16:27 | Simpply | Code/Design Review
68 | Task | Fix TFS Installation | Closed | Michael Yeaple | 3 |  | 3.5 | 2014-11-04 16:26 | Simpply | Project Setup
59 | Task | Review Code Changes with Team | Closed | Michael Yeaple | 1.5 | 0 | 1 | 2014-11-04 16:26 | Simpply | Code/Design Review
76 | Task | Work on AutoFac/Dapper | Closed | Michael Yeaple | 0.5 | 0 | 0.5 | 2014-11-04 16:25 | Simpply | Implementation
63 | Task | Determine How to Track Time More Efficiently | Closed | Michael Yeaple | 0.5 |  | 0.5 | 2014-11-04 00:44 | Simpply | Process/Project Management Effort
65 | Task | Add Risks | Closed | Michael Yeaple | 0.25 |  | 0.25 | 2014-11-03 23:12 | Simpply | Process/Project Management Effort
64 | Task | Set Up Branches | Closed | Michael Yeaple | 1 |  | 1 | 2014-11-03 22:18 | Simpply | Project Setup
53 | Task | Set Up Project Skeleton | Closed | Michael Yeaple | 3 |  | 3 | 2014-10-28 15:14 | Simpply | Project Setup
42 | Task | Research and Implement Template Layout | Closed | Michael Yeaple | 3 |  | 1 | 2014-10-28 09:13 | Simpply | Implementation
19 | Task | Request more hard-drive space | Closed | Curtis Burtner |  |  |  | 2014-10-27 11:25 | Simpply | Project Setup
46 | Task | Write Blurb About Why We Chose Data Layer Technology | Closed | Curtis Burtner | 0.5 | 0 | 1 | 2014-10-22 11:32 | Simpply | Process/Project Management Effort
23 | Task | Set Up VM | Closed | Michael Yeaple | 3 | 0 | 10 | 2014-10-21 13:12 | Simpply | Project Setup
40 | Task | Make sure we can commit code from TFS | Closed | Michael Yeaple | 1 | 0 | 0.5 | 2014-10-21 12:40 | Simpply | Process/Project Management Effort
18 | Task | Risk chart status column needs to be meaningful | Closed | Curtis Burtner |  |  |  | 2014-10-20 16:10 | Simpply | Process/Project Management Effort

## Term1Effort Tracking
ID | Work Item Type | Title | State | Assigned To | Original Estimate | Remaining Work | Completed Work | Closed Date | Iteration Path | Tags |  | Week4Iter2(12/04-12/11) | Week3Iter2(11/29-12/04) | Week2Iter2(11/21-11/28) | Week1Iter2(11/14-11/20) | Iteration 2 | Iteration 1 | Iteration 0 | All Time |  | Week4Iter2 | Week3Iter2 | Week2Iter2 | Week1Iter2 | Iteration 2 | Iteration 1 | Iteration 0
382 | Task | Fixed Bug 334 | Closed | Curtis Burtner | 3 | 0 | 3 | 2015-02-01 17:35 | Simpply\Iteration 3 | Bugs | Project: | 34.68330 | 27.88000 | 26.25000 | 48.5 | 137.3133 | 85.8003 | 169.87 | 440.52427 | Start: | >12/04/2014 | >11/28/2014 | >11/21/2014 | >11/14/2014 | >11/14/2014 | >10/14/2014
373 | Task | Plan story tasks | Closed | Jeremy Shulman | 0.75 | 0 | 0.75 | 2015-01-30 17:36 | Simpply\Iteration 3 | Planning Effort | Product: | 64.00933 | 10.25000 | 24.91100 | 0.00000 | 99.17033333 | 32.5 |  | 100.6703333 | End: | <12/12/2014 | <12/04/2014 | <11/28/2014 | <11/21/2014 | <12/12/2014 | <11/14/2014 | <10/14/2014
317 | Task | UI Overhaul Item Explorer Implementation | Closed | Curtis Burtner | 0.45 | 0 | 1.45 | 2015-01-30 17:23 | Simpply\Interim Sprint | Implementation | Total: | 99.94263333 | 38.13 | 51.161 | 48.5 | 237.7336333 | 121.3003 | 169.87 | 609.1448663
346 | Task | Customer Meeting/Sprint Planning 01/29/15 | Closed | Jeremy Shulman | 1.25 | 0 | 1.25 | 2015-01-30 17:12 | Simpply\Iteration 3 | Planning Meeting | Estimated Hours: | 104.05 | 24.15 | 43.5 | 41 | 212.7 | 108.497 | 158.62 | 547.26733
345 | Task | Customer Meeting/Sprint Planning 01/29/15 | Closed | Curtis Burtner | 1.5 | 0 | 2 | 2015-01-30 13:10 | Simpply\Iteration 3 | Planning Meeting
358 | Task | Compose Team Email About Sprint Planning | Closed | Michael Yeaple | 0.25 | 0 | 0.5 | 2015-01-30 12:15 | Simpply | Planning Effort | Curtis Burtner | 29.41 | 13.87 | 19.317 | 16 | 78.597 | 33.75 | 40.83 | 180.5403
355 | Task | UI Overhaul Merge | Closed | Michael Yeaple | 0.25 | 0 | 0.25 | 2015-01-30 11:58 | Simpply\Iteration 3 | Implementation | Michael Yeaple | 36.54263333 | 7.52 | 12.037 | 10 | 66.09963333 | 57.5503 | 55.83 | 217.2775663
347 | Task | Sprint Planning | Closed | Michael Yeaple | 0.5 | 0 | 0.66667 | 2015-01-30 11:38 | Simpply | Planning Effort | Jeremy Shulman | 19.74 | 7.37 | 13.537 | 9.5 | 50.147 | 23.25 | 38.08 | 122.557
343 | Task | Customer Meeting/Sprint Planning 01/29/15 | Closed | Michael Yeaple | 1.5 | 0 | 1.75 | 2015-01-30 11:37 | Simpply\Iteration 3 | Planning Meeting | Mustafa Al-Salihi | 14.25 | 9.37 | 6.27 | 13 | 42.89 | 6.75 | 35.13 | 88.77
354 | Task | Fix search to use 6 digit IDs | Closed | Michael Yeaple | 0.08333 | 0 | 0.08333 | 2015-01-30 11:29 | Simpply\Iteration 3 | Bugs
5 | User Story | Search | Closed |  |  |  |  | 2015-01-30 11:19 | Simpply\Iteration 2 |  | TFS Source Query: http://simpply.se.rit.edu:8080/tfs/DefaultCollection/Simpply/_workitems#path=Shared+Queries%2FIndividual+Report+(WiP)&_a=query
204 | Task | Implement Feature | Closed | Curtis Burtner | 2 | 0 | 8 | 2014-12-10 05:38 | Simpply\Iteration 2 | Implementation
202 | Task | Class Design Review | Closed | Jeremy Shulman | 0.5 | 0 | 0.967 | 2014-11-25 17:16 | Simpply\Iteration 2 | Design Meeting
201 | Task | Class Design Review | Closed | Curtis Burtner | 0.5 | 0 | 0.967 | 2014-11-25 17:16 | Simpply\Iteration 2 | Design Meeting
200 | Task | Class Design Review | Closed | Michael Yeaple | 0.5 | 0 | 0.967 | 2014-11-25 17:15 | Simpply\Iteration 2 | Design Meeting | Tags | Total | Curtis Butner | Jeremy Shulman | Michael Yeaple | Mustafa Al-Salihi
203 | Task | Class Design Review | Closed | Mustafa Al-Salihi | 0.5 | 0 | 0.55 | 2014-11-24 21:04 | Simpply\Iteration 2 | Design Meeting | Academic Work Effort | 17.317 | 5 | 4.25 | 6.567 | 1.5
194 | Task | User Experience Design | Closed | Jeremy Shulman | 1 | 0 | 0.5 | 2014-11-24 20:31 | Simpply\Iteration 2 | Design Effort | Academic Work Meeting | 46.48 | 11.62 | 11.62 | 11.62 | 11.62
199 | Task | Class Design | Closed | Mustafa Al-Salihi | 0.5 | 0 | 1.5 | 2014-11-24 20:31 | Simpply\Iteration 2 | Design Effort | Bugs | 3.08333 | 3 | 0 | 0.08333 | 0
198 | Task | User Experience Design Review | Closed | Mustafa Al-Salihi | 0.5 | 0 | 0.67 | 2014-11-24 20:31 | Simpply\Iteration 2 | Design Meeting | Code/Design Review | 11.75 | 4 | 2.5 | 5.25 | 0
196 | Task | User Experience Design Review | Closed | Curtis Burtner | 0.5 | 0 | 0.7 | 2014-11-24 20:29 | Simpply\Iteration 2 | Design Meeting | Design Effort | 29 | 5 | 6 | 11 | 7
195 | Task | User Experience Design Review | Closed | Michael Yeaple | 0.5 | 0 | 0.67 | 2014-11-24 20:29 | Simpply\Iteration 2 | Design Meeting | Design Meeting | 76.9676 | 20.8103 | 20.277 | 21.1103 | 14.77
197 | Task | User Experience Design Review | Closed | Jeremy Shulman | 0.5 | 0 | 0.67 | 2014-11-24 20:29 | Simpply\Iteration 2 | Design Meeting | Implementation | 98.47026633 | 29.7 | 14.25 | 51.52026633 | 3
7 | User Story | View Calculated Item Distribution | Closed |  |  |  |  | 2015-01-30 11:19 | Simpply\Iteration 2 |  | Planning Meeting | 47.5 | 13.75 | 14 | 13.75 | 6
130 | Task | Implement Web Role Design | Closed | Jeremy Shulman | 1.5 | 0 | 1 | 2014-12-11 23:16 | Simpply\Iteration 2 | Implementation | Process/Project Management Effort | 83.5 | 43 | 15.25 | 14 | 11.25
163 | Task | Design Distribution Algorithms | Closed | Jeremy Shulman | 5 | 0 | 1.5 | 2014-12-11 18:30 | Simpply\Iteration 2 | Design Effort | Process/Project Management Meeting | 22.32 | 7.33 | 4.83 | 7.33 | 2.83
133 | Task | Implement Engine Class Design | Closed | Jeremy Shulman | 8 | 0 | 5 | 2014-12-11 18:30 | Simpply\Iteration 2 | Implementation | Project Setup | 49.5 | 9.75 | 2 | 36.75 | 1
207 | Task | Review Distribution Algorithms | Closed | Mustafa Al-Salihi | 1.5 | 0 |  | 2014-12-11 16:05 | Simpply\Iteration 2 | Design Meeting | Progress Meeting | 17.75 | 4.75 | 4.75 | 4.75 | 3.5
206 | Task | Review Distribution Algorithms | Closed | Jeremy Shulman | 1.5 | 0 | 0.66 | 2014-12-11 16:05 | Simpply\Iteration 2 | Design Meeting | Refactoring | 8.75 | 2.5 | 1.25 | 5 | 0
205 | Task | Review Distribution Algorithms | Closed | Curtis Burtner | 1.5 | 0 | 0.33 | 2014-12-11 16:05 | Simpply\Iteration 2 | Design Meeting | Requirements Effort | 11.55 | 1.25 | 1.25 | 7.75 | 1.3
164 | Task | Design Distribution Algorithms | Closed | Mustafa Al-Salihi | 5 | 0 | 3 | 2014-12-11 16:04 | Simpply\Iteration 2 | Design Effort | Requirements Meeting | 65.25 | 17.75 | 18.25 | 17.25 | 12
143 | Task | Review Distribution Algorithms | Closed | Michael Yeaple | 1.5 | 0 | 0.66 | 2014-12-11 16:04 | Simpply\Iteration 2 | Design Meeting | Testing Effort | 4 | 0 | 0 | 0 | 4
162 | Task | Design Distribution Algorithms | Closed | Curtis Burtner | 5 | 0 |  | 2014-12-11 15:11 | Simpply\Iteration 2 | Design Effort
142 | Task | Design Distribution Algorithms | Closed | Michael Yeaple | 5 | 0 | 1 | 2014-12-11 11:04 | Simpply\Iteration 2 | Design Effort | Total: | 589.1881963 | 179.2103 | 120.477 | 213.7308963 | 75.77
137 | Task | Implement Database | Closed | Michael Yeaple | 1.5 | 0 | 1.5833 | 2014-12-10 00:24 | Simpply\Iteration 2 | Implementation | All Tasks: | 609.1448663
155 | Task | Comprehend Data | Closed | Mustafa Al-Salihi | 2 | 0 | 0 | 2014-12-09 21:31 | Simpply\Iteration 2 | Design Effort
129 | Task | Design Web Role Class Interaction | Closed | Curtis Burtner | 1.25 | 0 | 1.5 | 2014-12-09 17:51 | Simpply\Iteration 2 | Design Effort | Meeting Hours: | 276.2676
135 | Task | Review Web Role Design | Closed | Michael Yeaple | 0.75 | 0 | 1.08 | 2014-12-09 17:50 | Simpply\Iteration 2 | Design Meeting | Individual Hours: | 301.1705963
158 | Task | Review Web Role Design | Closed | Mustafa Al-Salihi | 0.75 | 0 | 0.75 | 2014-12-09 17:50 | Simpply\Iteration 2 | Design Meeting
156 | Task | Review Web Role Design | Closed | Curtis Burtner | 0.75 | 0 | 1.08 | 2014-12-09 17:49 | Simpply\Iteration 2 | Design Meeting
157 | Task | Review Web Role Design | Closed | Jeremy Shulman | 0.75 | 0 | 1.08 | 2014-12-09 17:48 | Simpply\Iteration 2 | Design Meeting
134 | Task | Design Database | Closed | Michael Yeaple | 2 | 0 | 2.5 | 2014-12-09 17:25 | Simpply\Iteration 2 | Design Meeting
151 | Task | Design Database | Closed | Mustafa Al-Salihi | 2 | 0 | 0 | 2014-12-09 17:25 | Simpply\Iteration 2 | Design Meeting | Tags | Total
149 | Task | Design Database | Closed | Curtis Burtner | 2 | 0 | 2.5 | 2014-12-09 17:24 | Simpply\Iteration 2 | Design Meeting | Academic Work Effort | 63
150 | Task | Design Database | Closed | Jeremy Shulman | 2 | 0 | 2.5 | 2014-12-09 17:24 | Simpply\Iteration 2 | Design Meeting | Academic Work Meeting | 0
136 | Task | Review Engine Class Design | Closed | Michael Yeaple | 1 | 0 | 0.75 | 2014-11-28 12:16 | Simpply\Iteration 2 | Design Meeting | Bugs | 0
160 | Task | Review Engine Class Design | Closed | Jeremy Shulman | 1 | 0 | 0.75 | 2014-11-28 12:16 | Simpply\Iteration 2 | Design Meeting | Code/Design Review | 0
161 | Task | Review Engine Class Design | Closed | Mustafa Al-Salihi | 1 | 0 | 0.75 | 2014-11-28 12:15 | Simpply\Iteration 2 | Design Meeting | Design Effort | 105
159 | Task | Review Engine Class Design | Closed | Curtis Burtner | 1 | 0 | 0.75 | 2014-11-28 12:15 | Simpply\Iteration 2 | Design Meeting | Design Meeting | 0
153 | Task | Comprehend Data | Closed | Curtis Burtner | 2 | 0 | 1 | 2014-11-25 18:24 | Simpply\Iteration 2 | Design Effort | Implementation | 120
154 | Task | Comprehend Data | Closed | Jeremy Shulman | 2 | 0 | 1 | 2014-11-25 16:56 | Simpply\Iteration 2 | Design Effort | Planning Meeting | 47.5
152 | Task | Comprehend Data | Closed | Michael Yeaple | 2 | 0 | 1 | 2014-11-25 16:55 | Simpply\Iteration 2 | Design Effort | Process/Project Management Effort | 83
132 | Task | Engine Class Design | Closed | Jeremy Shulman | 2 | 0 | 2 | 2014-11-24 19:03 | Simpply\Iteration 2 | Design Effort | Process/Project Management Meeting | 0
146 | Task | Design Engine Architecture | Closed | Curtis Burtner | 0.75 | 0 | 0.85 | 2014-11-21 17:09 | Simpply\Iteration 2 | Design Meeting | Project Setup | 49.5
131 | Task | Design Engine Architecture | Closed | Michael Yeaple | 0.75 | 0 | 0.85 | 2014-11-21 17:08 | Simpply\Iteration 2 | Design Meeting | Progress Meeting | 0
147 | Task | Design Engine Architecture | Closed | Jeremy Shulman | 0.75 | 0 | 0.85 | 2014-11-21 17:08 | Simpply\Iteration 2 | Design Meeting | Refactoring | 0
331 | Task | 1/28 Online Meeting | Closed | Jeremy Shulman | 1.5 | 0 | 1.5 | 2015-01-29 18:06 | Simpply | Requirements Meeting | Requirements Effort | 44
330 | Task | 1/28 Online Meeting | Closed | Curtis Burtner | 1.5 | 0 | 1.5 | 2015-01-29 17:51 | Simpply | Requirements Meeting | Requirements Meeting | 0
342 | Task | Deploy to Production | Closed | Michael Yeaple | 0.25 | 0 | 1.5 | 2015-01-29 13:17 | Simpply\Iteration 3 | Deployment | Testing Effort | 0
332 | Task | 1/28 Online Meeting | Closed | Michael Yeaple | 1.5 | 0 | 1.5 | 2015-01-28 17:28 | Simpply | Requirements Meeting
325 | Task | 1/27 Meeting | Closed | Jeremy Shulman | 1.25 | 0 | 1.25 | 2015-01-28 16:24 | Simpply | Process/Project Management Meeting
323 | Task | 1/27 Meeting | Closed | Michael Yeaple | 1.25 | 0 | 1.25 | 2015-01-28 16:23 | Simpply | Process/Project Management Meeting
322 | Task | 1/27 Meeting | Closed | Curtis Burtner | 1.25 | 0 | 1.25 | 2015-01-28 00:29 | Simpply | Process/Project Management Meeting
318 | Task | UI Overhaul Item Detail Implementation | Closed | Michael Yeaple | 1.5 | 0 | 2.817 | 2015-01-27 17:28 | Simpply\Interim Sprint | Implementation
321 | Task | Add Default Functionality to Column Preferences | Closed | Michael Yeaple | 1 | 0 | 0.85 | 2015-01-27 17:27 | Simpply\Iteration 3 | Implementation
39 | Task | Request more harddrive space from Kurt | Closed | Curtis Burtner | 0.5 | 0 | 1.25 | 2015-01-27 17:05 | Simpply\Iteration 1 | Project Setup
320 | Task | Fix VM Post-Migration | Closed | Michael Yeaple | 2 | 0 | 4.25 | 2015-01-27 17:03 | Simpply\Iteration 3 | Project Setup
315 | Task | UI Overhaul Design | Closed | Curtis Burtner | 1 | 0 | 0.8333 | 2015-01-25 22:49 | Simpply\Interim Sprint | Design Meeting
316 | Task | UI Overhaul Design | Closed | Michael Yeaple | 1 | 0 | 0.8333 | 2015-01-25 22:49 | Simpply\Interim Sprint | Design Meeting
319 | Task | Fix UI Post-Bootstrap | Closed | Michael Yeaple | 3 |  | 4.3333 | 2015-01-25 20:07 | Simpply\Interim Sprint | Implementation
313 | Task | Bootstrap it! | Closed | Michael Yeaple | 1 | 0 | 1.25 | 2015-01-25 14:49 | Simpply\Interim Sprint | Implementation
314 | Task | Investigate front-end frameworks | Closed | Michael Yeaple | 3 | 0 | 3 | 2015-01-25 09:40 | Simpply\Interim Sprint | Design Effort
312 | Task | Implement Search by ID | Closed | Michael Yeaple | 1 | 0 | 0.75 | 2015-01-11 20:37 | Simpply\Interim Sprint | Implementation
15 | User Story | Compare Aggregate Store Data to Individual Store Data | Closed |  |  |  |  | 2014-12-18 16:30 | Simpply\Iteration 2
192 | Task | Feature Implementation | Closed | Mustafa Al-Salihi | 8 | 0 | 8 | 2014-12-11 19:53 | Simpply\Iteration 2
187 | Task | Class Design | Closed | Mustafa Al-Salihi | 0.5 | 0 | 0.5 | 2014-12-09 17:32 | Simpply\Iteration 2 | Design Effort
191 | Task | Class Design Review | Closed | Mustafa Al-Salihi | 0.5 |  | 0.5 | 2014-12-09 17:31 | Simpply\Iteration 2 | Design Meeting
186 | Task | Review User Experience | Closed | Mustafa Al-Salihi | 0.5 | 0 | 0.5 | 2014-11-28 11:30 | Simpply\Iteration 2 | Design Meeting
185 | Task | Review User Experience | Closed | Jeremy Shulman | 0.5 | 0 | 0.5 | 2014-11-28 11:30 | Simpply\Iteration 2 | Design Meeting
184 | Task | Review User Experience | Closed | Curtis Burtner | 0.5 | 0 | 0.5 | 2014-11-28 11:29 | Simpply\Iteration 2 | Design Meeting
183 | Task | Review User Experience | Closed | Michael Yeaple | 0.5 | 0 | 0.5 | 2014-11-28 11:29 | Simpply\Iteration 2 | Design Meeting
182 | Task | Design User Experience | Closed | Mustafa Al-Salihi | 1.5 | 0 | 2 | 2014-11-28 11:17 | Simpply\Iteration 2 | Design Effort
190 | Task | Class Design Review | Closed | Jeremy Shulman | 0.5 | 0 | 0.75 | 2014-11-25 18:23 | Simpply\Iteration 2 | Design Meeting
188 | Task | Class Design Review | Closed | Michael Yeaple | 0.5 | 0 | 0.75 | 2014-11-25 18:22 | Simpply\Iteration 2 | Design Meeting
189 | Task | Class Design Review | Closed | Curtis Burtner | 0.5 | 0 | 0.75 | 2014-11-25 18:22 | Simpply\Iteration 2 | Design Meeting
34 | User Story | Customize Item Explorer | Closed |  |  |  |  | 2014-12-18 16:27 | Simpply\Iteration 2
181 | Task | Implement Feature | Closed | Michael Yeaple | 1.5 | 0 | 17.536 | 2014-12-11 23:06 | Simpply\Iteration 2 | Implementation
180 | Task | Review Class Design | Closed | Mustafa Al-Salihi | 0.5 | 0 | 0.5 | 2014-11-28 12:45 | Simpply\Iteration 2 | Design Meeting
179 | Task | Review Class Design | Closed | Jeremy Shulman | 0.5 | 0 | 0.5 | 2014-11-28 12:45 | Simpply\Iteration 2 | Design Meeting
178 | Task | Review Class Design | Closed | Curtis Burtner | 0.5 | 0 | 0.5 | 2014-11-28 12:44 | Simpply\Iteration 2 | Design Meeting
177 | Task | Review Class Design | Closed | Michael Yeaple | 0.5 | 0 | 0.5 | 2014-11-28 12:44 | Simpply\Iteration 2 | Design Meeting
175 | Task | Review User Experience Design | Closed | Mustafa Al-Salihi | 0.5 | 0 | 0.55 | 2014-11-24 20:30 | Simpply\Iteration 2 | Design Meeting
172 | Task | Review User Experience Design | Closed | Michael Yeaple | 0.5 | 0 | 0.55 | 2014-11-24 19:59 | Simpply\Iteration 2 | Design Meeting
174 | Task | Review User Experience Design | Closed | Jeremy Shulman | 0.5 | 0 | 0.55 | 2014-11-24 19:58 | Simpply\Iteration 2 | Design Meeting | Tags |  |  | Wk3Iteration 2 | Wk2Iteration 2 | Wk1Iteration 2 | Iteration 2 | Iteration 1 | Iteration 0
173 | Task | Review User Experience Design | Closed | Curtis Burtner | 0.5 | 0 | 0.55 | 2014-11-24 19:58 | Simpply\Iteration 2 | Design Meeting | Academic Work Effort |  |  | 1 | 0 | 1 | 16.4 | 0 | 0
176 | Task | Class Design for Customize Item Explorer | Closed | Michael Yeaple | 2 | 0 | 2.25 | 2014-11-24 14:47 | Simpply\Iteration 2 | Design Effort | Academic Work Meeting |  |  | 21.48 | 0 | 10 | 31.48 | 0 | 0
171 | Task | Design User Experience | Closed | Curtis Burtner | 1 | 0 | 2.5 | 2014-11-23 16:43 | Simpply\Iteration 2 | Design Effort | Bugs |  |  | 0 | 0 | 0 | 0 | 0 | 0
311 | Task | Compose Email to Martinez | Closed | Michael Yeaple | 0.167 | 0 | 0.167 | 2014-12-17 20:45 | Simpply | Academic Work Effort | Code/Design Review |  |  | 0 | 0 | 0 | 4 | 4.75 | 0
263 | Task | Update Website with Deliverables on Machine | Closed | Jeremy Shulman | 0.5 | 0 | 0.25 | 2014-12-17 20:22 | Simpply | Academic Work Effort | Design Effort |  |  | 2 | 11.75 | 0 | 21.25 | 4.75 | 0
310 | Task | Update Interim Artifacts | Closed | Curtis Burtner | 1 | 0 | 0.75 | 2014-12-17 20:20 | Simpply | Academic Work Meeting | Design Meeting |  |  | 7 | 13.161 | 0 | 35.301 | 4 | 0
309 | Task | Update Interim Artifacts | Closed | Mustafa Al-Salihi | 1 | 0 | 0.75 | 2014-12-17 20:20 | Simpply | Academic Work Meeting | Implementation |  |  | 0.15 | 0 | 0 | 45.30263333 | 32.8003 | 0
308 | Task | Update Interim Artifacts | Closed | Jeremy Shulman | 1 | 0 | 0.75 | 2014-12-17 20:20 | Simpply | Academic Work Meeting | Planning Meeting |  |  | 1 | 9 | 13.25 | 23.25 | 17.5 | 0
307 | Task | Update Interim Artifacts | Closed | Michael Yeaple | 1 | 0 | 0.75 | 2014-12-17 20:20 | Simpply | Academic Work Meeting | Process/Project Management Effort |  |  | 5.5 | 7 | 17.75 | 31.75 | 16 | 0
306 | Task | Interim Assessment Planning Meeting | Closed | Mustafa Al-Salihi | 1 | 0 | 0.25 | 2014-12-17 20:18 | Simpply | Planning Meeting | Process/Project Management Meeting |  |  | 0 | 0 | 0 | 0 | 4 | 0
305 | Task | Interim Assessment Planning Meeting | Closed | Jeremy Shulman | 1 | 0 | 0.5 | 2014-12-17 20:18 | Simpply | Planning Meeting | Project Setup |  |  | 0 | 0 | 0 | 0 | 24.5 | 0
304 | Task | Interim Assessment Planning Meeting | Closed | Curtis Burtner | 1 | 0 | 0.5 | 2014-12-17 20:18 | Simpply | Planning Meeting | Progress Meeting |  |  | 0 | 1.25 | 2.5 | 5 | 3.75 | 0
303 | Task | Interim Assessment Planning Meeting | Closed | Michael Yeaple | 1 | 0 | 0.5 | 2014-12-17 20:18 | Simpply | Planning Meeting | Refactoring |  |  | 0 | 0 | 0 | 0 | 7.75 | 0
267 | Task | Write Acceptance Tests For all user stories for this iteration. | Closed | Mustafa Al-Salihi | 0.5 | 0 | 0 | 2014-12-17 18:51 | Simpply | Testing Meeting | Requirements Effort |  |  | 0 | 0 | 0 | 0 | 0 | 0
266 | Task | Write Acceptance Tests For all user stories for this iteration. | Closed | Jeremy Shulman | 0.5 | 0 | 0.33 | 2014-12-17 18:51 | Simpply | Testing Meeting | Requirements Meeting |  |  | 0 | 9 | 0 | 11 | 0 | 0
265 | Task | Write Acceptance Tests For all user stories for this iteration. | Closed | Curtis Burtner | 0.5 | 0 | 0.33 | 2014-12-17 18:51 | Simpply | Testing Meeting | Testing Effort |  |  | 0 | 0 | 4 | 4 | 0 | 0
264 | Task | Write Acceptance Tests For all user stories for this iteration. | Closed | Michael Yeaple | 1 | 0 | 0.88 | 2014-12-17 18:50 | Simpply | Testing Meeting
302 | Task | Merge to Master | Closed | Michael Yeaple | 0.25 | 0 | 0.25 | 2014-12-17 17:46 | Simpply | Process/Project Management Effort | Total: |  |  | 38.13 | 51.161 | 44.5 | 224.7336333 | 119.8003 | 0
296 | Task | Update Artifacts | Closed | Michael Yeaple | 1 | 0 | 0.5 | 2014-12-17 16:54 | Simpply | Academic Work Effort
301 | Task | Updated Metrics | Closed | Curtis Burtner | 0.5 | 0 | 0.5 | 2014-12-16 23:51 | Simpply
300 | Task | Update Design Document | Closed | Jeremy Shulman | 2 | 0 | 1.5 | 2014-12-16 22:26 | Simpply | Process/Project Management Effort
299 | Task | Email to Customer for meeting details and effort report | Closed | Curtis Burtner | 0.5 | 0 | 1 | 2014-12-16 22:09 | Simpply | Process/Project Management Effort
298 | Task | Plan Customer Meeting | Closed | Michael Yeaple | 0.5 | 0 | 0.5 | 2014-12-16 18:39 | Simpply\Iteration 2 | Process/Project Management Effort
262 | Task | Investigate complex data mapping for Dapper | Closed | Curtis Burtner | 1 | 0 | 3 | 2014-12-16 18:22 | Simpply | Project Setup
297 | Task | Finish Hooking Up To The Database | Closed | Curtis Burtner | 2 | 0 | 2 | 2014-12-16 18:22 | Simpply | Implementation
292 | Task | Team Self-Assessment | Closed | Michael Yeaple | 2 | 0 | 3 | 2014-12-15 21:05 | Simpply | Academic Work Meeting
295 | Task | Team Self-Assessment | Closed | Mustafa Al-Salihi | 2 | 0 | 3 | 2014-12-15 21:05 | Simpply | Academic Work Meeting
294 | Task | Team Self-Assessment | Closed | Jeremy Shulman | 2 | 0 | 3 | 2014-12-15 21:04 | Simpply | Academic Work Meeting
293 | Task | Team Self-Assessment | Closed | Curtis Burtner | 2 | 0 | 3 | 2014-12-15 21:04 | Simpply | Academic Work Meeting
291 | Task | Implement Complex Mapping for ItemDetails Page | Closed | Curtis Burtner | 1 | 0 | 3 | 2014-12-13 14:20 | Simpply | Implementation
288 | Task | Code Review With Wegmans | Closed | Curtis Burtner | 1.5 | 0 | 1.5 | 2014-12-13 14:19 | Simpply | Code/Design Review
290 | Task | Refactor based on code review | Closed | Michael Yeaple | 0.75 | 0 | 1 | 2014-12-12 18:55 | Simpply | Refactoring
289 | Task | Code Review With Wegmans | Closed | Michael Yeaple | 1.5 | 0 | 1.5 | 2014-12-12 12:04 | Simpply | Code/Design Review
287 | Task | Mocked Data For Database Tables | Closed | Curtis Burtner | 0.5 | 0 | 0.5 | 2014-12-12 01:54 | Simpply | Implementation
286 | Task | Code Merge from Unstable to Stable | Closed | Michael Yeaple | 0.25 | 0 | 0.25 | 2014-12-12 00:23 | Simpply | Implementation
279 | Task | Pair Programming | Closed | Michael Yeaple | 2 | 1 | 2.917 | 2014-12-12 00:17 | Simpply | Implementation
285 | Task | Code Review | Closed | Jeremy Shulman | 0.5 | 0 | 0.5 | 2014-12-11 21:11 | Simpply | Code/Design Review
284 | Task | Code Review | Closed | Michael Yeaple | 0.5 | 0 | 0.5 | 2014-12-11 21:11 | Simpply | Code/Design Review
281 | Task | Customer Emails | Closed | Curtis Burtner | 0.5 | 0 | 0.5 | 2014-12-11 16:18 | Simpply | Process/Project Management Effort
280 | Task | Added Dapper Examples Using Stored Procedures. Also Added New Connection String | Closed | Curtis Burtner | 2 | 0 | 6 | 2014-12-11 16:04 | Simpply | Implementation
248 | Task | Implement connection string so that it changes with mode project is run in | Closed | Curtis Burtner | 0.75 | 0 | 0.75 | 2014-12-11 14:55 | Simpply\Iteration 2 | Implementation
85 | Task | Use Autofac in code | Closed | Curtis Burtner | 1 | 1 | 0 | 2014-12-11 14:53 | Simpply\Iteration 1 | Implementation
106 | Task | NUnit Mock | Closed | Mustafa Al-Salihi |  |  |  | 2014-12-11 14:53 | Simpply\Iteration 1 | Project Setup
278 | Task | Make updates to SQL Creation | Closed | Michael Yeaple | 0.25 | 0 | 0.5 | 2014-12-11 14:39 | Simpply | Implementation
277 | Task | Fix target framework of engine | Closed | Jeremy Shulman | 1 | 0 | 1 | 2014-12-10 04:44 | Simpply
276 | Task | Fix AccountController SaveColumnPreferences Unit Test | Closed | Michael Yeaple | 0.25 | 0 | 0.25 | 2014-12-10 00:48 | Simpply | Implementation
275 | Task | Email Team | Closed | Michael Yeaple | 0.3 | 0 | 0.3 | 2014-12-10 00:35 | Simpply | Implementation
274 | Task | 12/09 Customer Email | Closed | Curtis Burtner | 1 | 0 | 1 | 2014-12-09 22:21 | Simpply\Iteration 2 | Process/Project Management Effort
273 | Task | 12/09 Meeting | Closed | Michael Yeaple | 2 | 0 | 0.5 | 2014-12-09 19:04 | Simpply | Design Meeting
272 | Task | 12/09 Meeting | Closed | Jeremy Shulman | 2 | 0 | 0.5 | 2014-12-09 19:04 | Simpply | Design Meeting
260 | Task | 12/09 Meeting | Closed | Curtis Burtner | 2 | 0 | 0.5 | 2014-12-09 19:02 | Simpply | Design Meeting
261 | Task | 12/09 Meeting | Closed | Mustafa Al-Salihi | 2 | 0 | 0 | 2014-12-09 19:02 | Simpply | Design Meeting
271 | Task | Code Review Jeremy's Engine and Michael's Providers | Closed | Michael Yeaple | 1 | 0 | 1 | 2014-12-09 18:56 | Simpply | Code/Design Review
270 | Task | Code Review Jeremy's Engine and Michael's Providers | Closed | Jeremy Shulman | 1 | 0 | 1 | 2014-12-09 18:55 | Simpply | Code/Design Review
269 | Task | Code Review Jeremy's Engine and Michael's Providers | Closed | Curtis Burtner | 1 | 0 | 1 | 2014-12-09 18:55 | Simpply | Code/Design Review
118 | Task | 11/13 End of Iteration Customer Meeting | Closed | Curtis Burtner | 1.25 | 0 | 1.25 | 2014-12-09 16:58 | Simpply\Iteration 1 | Progress Meeting
250 | Task | Make Calendar to Track Due Dates | Closed | Michael Yeaple | 1.5 | 0 | 0.9 | 2014-12-09 10:24 | Simpply | Academic Work Effort
246 | Task | Implement Dependency Injection using AutoFac | Closed | Michael Yeaple | 3 | 2.766 | 4.2333 | 2014-12-07 17:18 | Simpply | Implementation
259 | Task | 12/05 Online Meeting With Mike | Closed | Jeremy Shulman | 1 | 0 | 1 | 2014-12-05 11:54 | Simpply | Requirements Meeting
258 | Task | 12/05 Online Meeting With Mike | Closed | Curtis Burtner | 1 | 0 | 1 | 2014-12-05 11:54 | Simpply | Requirements Meeting
257 | Task | Attend 12/02 Presentations (And Give Presentation | Closed | Mustafa Al-Salihi | 1.5 | 0 | 1.5 | 2014-12-04 20:15 | Simpply | Academic Work Effort
256 | Task | Attend 12/02 Presentations (And Give Presentation | Closed | Jeremy Shulman | 1.5 | 0 | 1.5 | 2014-12-04 20:15 | Simpply | Academic Work Effort
255 | Task | Attend 12/02 Presentations (And Give Presentation | Closed | Michael Yeaple | 1.5 | 0 | 1.5 | 2014-12-04 20:15 | Simpply | Academic Work Effort
254 | Task | Attend 12/02 Presentations (And Give Presentation | Closed | Curtis Burtner | 1.5 | 0 | 1.5 | 2014-12-04 20:15 | Simpply | Academic Work Effort
27 | Task | Quality requirements | Closed | Curtis Burtner |  |  |  | 2014-12-04 20:14 | Simpply\Iteration 1 | Requirements Effort
253 | Task | Attend 12/04 Presentations | Closed | Jeremy Shulman | 2.5 | 0 | 2.5 | 2014-12-04 20:11 | Simpply | Academic Work Effort
252 | Task | Attend 12/04 Presentations | Closed | Michael Yeaple | 2.5 | 0 | 2.5 | 2014-12-04 20:11 | Simpply | Academic Work Effort
251 | Task | Attend Presentations | Closed | Curtis Burtner | 2.5 | 0 | 2.5 | 2014-12-04 20:10 | Simpply | Academic Work Effort
140 | Task | Practice Presentation with Team | Closed | Jeremy Shulman | 2.5 | 0 | 5.37 | 2014-12-02 20:57 | Simpply | Academic Work Meeting
141 | Task | Practice Presentation with Team | Closed | Mustafa Al-Salihi | 2.5 | 0 | 5.37 | 2014-12-02 15:50 | Simpply | Academic Work Meeting
138 | Task | Practice Presentation with Team | Closed | Michael Yeaple | 2.5 | 0 | 5.37 | 2014-12-02 15:49 | Simpply | Academic Work Meeting
139 | Task | Practice Presentation with Team | Closed | Curtis Burtner | 2.5 | 0 | 5.37 | 2014-12-02 15:49 | Simpply | Academic Work Meeting
249 | Task | Added Week by Week Tag Hour Break Out | Closed | Curtis Burtner | 1.25 | 0 | 1.25 | 2014-12-01 19:10 | Simpply\Iteration 2 | Process/Project Management Effort
247 | Task | Generated Charts | Closed | Curtis Burtner | 0.5 | 0 | 1 | 2014-11-30 18:38 | Simpply | Academic Work Effort
235 | Task | Add Simpply.Global | Closed | Michael Yeaple | 0.15 | 0 | 0.15 | 2014-11-30 17:48 | Simpply | Implementation
245 | Task | Tagged Historical Data, Setup Historical Data Spreadsheet | Closed | Curtis Burtner | 1 | 0 | 2.5 | 2014-11-29 17:48 | Simpply | Process/Project Management Effort
244 | Task | Adjusted Effort Task Tracking Spreadsheet | Closed | Curtis Burtner | 0.25 | 0 | 1 | 2014-11-29 12:35 | Simpply | Process/Project Management Effort
243 | Task | Went through backlog and repathed old tasks to Simpply | Closed | Curtis Burtner | 0.5 | 0 | 0.75 | 2014-11-29 11:42 | Simpply | Process/Project Management Effort
241 | Task | Planning Meeting 11/28 | Closed | Curtis Burtner | 0.25 | 0 | 0.25 | 2014-11-28 13:00 | Simpply | Planning Meeting
242 | Task | Planning Meeting 11/28 | Closed | Mustafa Al-Salihi | 0.25 | 0 | 0.25 | 2014-11-28 13:00 | Simpply | Planning Meeting
240 | Task | Planning Meeting 11/28 | Closed | Jeremy Shulman | 0.25 | 0 | 0.25 | 2014-11-28 13:00 | Simpply | Planning Meeting
239 | Task | Planning Meeting 11/28 | Closed | Michael Yeaple | 0.25 | 0 | 0.25 | 2014-11-28 13:00 | Simpply | Planning Meeting
238 | Task | Update Effort Task Tracking Spreadsheet | Closed | Curtis Burtner | 1 | 0 | 1 | 2014-11-27 01:00 | Simpply | Process/Project Management Effort
237 | Task | Reformatted Historical Task Data | Closed | Curtis Burtner | 1 | 0 | 1 | 2014-11-26 01:02 | Simpply | Process/Project Management Effort
236 | Task | Email to customer | Closed | Curtis Burtner | 0.5 | 0 | 0.75 | 2014-11-26 00:20 | Simpply | Process/Project Management Effort
232 | Task | Task Assignment Meeting | Closed | Jeremy Shulman | 0.5 | 0 | 0.75 | 2014-11-25 19:01 | Simpply | Planning Meeting
233 | Task | Task Assignment Meeting | Closed | Curtis Burtner | 0.5 | 0 | 0.75 | 2014-11-25 19:01 | Simpply | Planning Meeting
234 | Task | Task Assignment Meeting | Closed | Mustafa Al-Salihi | 0.5 | 0 | 0.75 | 2014-11-25 19:01 | Simpply | Planning Meeting
231 | Task | Task Assignment Meeting | Closed | Michael Yeaple | 0.5 | 0.25 | 0.75 | 2014-11-25 19:00 | Simpply | Planning Meeting
87 | Task | Investigate Providing a "Real" Burndown | Closed | Curtis Burtner | 2 | 0.5 | 1.5 | 2014-11-25 09:38 | Simpply | Process/Project Management Effort
230 | Task | Email to Martinez | Closed | Curtis Burtner | 0.5 | 0 | 0.5 | 2014-11-25 00:36 | Simpply | Process/Project Management Effort
224 | Task | Email to Martinez about backdating in TFS | Closed | Curtis Burtner | 1 | 0 | 1 | 2014-11-24 23:12 | Simpply | Process/Project Management Effort
229 | Task | Reviewed and Updated risks | Closed | Curtis Burtner | 0.5 | 0 | 0.5 | 2014-11-24 10:31 | Simpply | Process/Project Management Effort
223 | Task | Planning Meeting 11/21 | Closed | Jeremy Shulman | 1 | 0 | 2 | 2014-11-21 20:31 | Simpply | Planning Meeting
222 | Task | Planning Meeting 11/21 | Closed | Curtis Burtner | 1 | 0 | 2 | 2014-11-21 20:31 | Simpply | Planning Meeting
221 | Task | Planning Meeting 11/21 | Closed | Michael Yeaple | 1 | 0 | 2 | 2014-11-21 20:31 | Simpply | Planning Meeting
119 | Task | 11/13 End of Iteration Customer Meeting | Closed | Jeremy Shulman | 1.25 | 0 | 1.25 | 2014-11-21 16:22 | Simpply | Progress Meeting
228 | Task | On-site Wegmans Algorithms Meeting | Closed | Mustafa Al-Salihi | 2 | 0 | 2.25 | 2014-11-21 16:22 | Simpply | Requirements Meeting
227 | Task | On-site Wegmans Algorithms Meeting | Closed | Jeremy Shulman | 2 | 0 | 2.25 | 2014-11-21 16:21 | Simpply | Requirements Meeting
226 | Task | On-site Wegmans Algorithms Meeting | Closed | Curtis Burtner | 2 | 0 | 2.25 | 2014-11-21 16:21 | Simpply | Requirements Meeting
225 | Task | On-site Wegmans Algorithms Meeting | Closed | Michael Yeaple | 2 | 0 | 2.25 | 2014-11-21 16:21 | Simpply | Requirements Meeting
220 | Task | Email to Martinez | Closed | Curtis Burtner | 0.5 | 0 | 0.75 | 2014-11-21 00:08 | Simpply | Process/Project Management Effort
219 | Task | Design Document | Closed | Jeremy Shulman | 3 | 0 | 3 | 2014-11-20 23:47 | Simpply | Process/Project Management Effort
218 | Task | Investigate task back-dating | Closed | Curtis Burtner | 1 | 0 | 1 | 2014-11-20 23:18 | Simpply | Process/Project Management Effort
212 | Task | Presentation Meeting | Closed | Michael Yeaple | 1.75 | 0 | 2.5 | 2014-11-20 19:03 | Simpply | Academic Work Meeting
214 | Task | Presentation Meeting | Closed | Jeremy Shulman | 1.75 | 0 | 2.5 | 2014-11-20 19:03 | Simpply | Academic Work Meeting
215 | Task | Presentation Meeting | Closed | Mustafa Al-Salihi | 1.75 | 0 | 2.5 | 2014-11-20 19:03 | Simpply | Academic Work Meeting
213 | Task | Presentation Meeting | Closed | Curtis Burtner | 1.75 | 0 | 2.5 | 2014-11-20 19:03 | Simpply | Academic Work Meeting
104 | Task | 11/11 Meeting | Closed | Mustafa Al-Salihi | 1.25 | 0 | 1.25 | 2014-11-20 19:00 | Simpply | Process/Project Management Effort
170 | Task | 11/19 Meeting - Finish Story/Task Planning | Closed | Mustafa Al-Salihi | 1.5 | 0 | 1.5 | 2014-11-19 17:17 | Simpply | Planning Meeting
169 | Task | 11/19 Meeting - Finish Story/Task Planning | Closed | Curtis Burtner | 1.5 | 0 | 1.5 | 2014-11-19 17:17 | Simpply | Planning Meeting
168 | Task | 11/19 Meeting - Finish Story/Task Planning | Closed | Jeremy Shulman | 1.5 | 0 | 2 | 2014-11-19 17:17 | Simpply | Planning Meeting
167 | Task | 11/19 Meeting - Finish Story/Task Planning | Closed | Michael Yeaple | 1.5 | 0 | 1.5 | 2014-11-19 17:17 | Simpply | Planning Meeting
126 | Task | Planning Meeting 11/18 | Closed | Curtis Burtner | 1.25 | 0 | 1.5 | 2014-11-19 17:15 | Simpply | Planning Meeting
193 | Task | Rename tasks for consistency and Update Remaining field. | Closed | Michael Yeaple | 0.5 | 0 | 1 | 2014-11-19 17:09 | Simpply | Process/Project Management Effort
166 | Task | Adjusted task queries | Closed | Curtis Burtner | 0.5 | 0 | 0.5 | 2014-11-19 13:30 | Simpply | Process/Project Management Effort
144 | Task | Take care of task tagging/linking/duplication From 11/18 Meeting | Closed | Michael Yeaple | 0.5 | 0 | 1 | 2014-11-19 10:47 | Simpply | Process/Project Management Effort
17 | Task | Change Schedule | Closed | Mustafa Al-Salihi | 1 | 0 | 1 | 2014-11-19 10:27 | Simpply | Process/Project Management Effort
83 | Task | Create a test plan using TFS | Closed | Mustafa Al-Salihi | 4 | 0 | 4 | 2014-11-19 10:27 | Simpply | Testing Effort
120 | Task | 11/13 End of Iteration Customer Meeting | Closed | Mustafa Al-Salihi | 1.25 | 0 | 1.25 | 2014-11-19 10:26 | Simpply | Progress Meeting
145 | Task | Email to customer | Closed | Curtis Burtner | 0.5 | 0 | 0.75 | 2014-11-18 19:39 | Simpply | Process/Project Management Effort
127 | Task | Planning Meeting 11/18 | Closed | Jeremy Shulman | 1.25 | 0 | 2 | 2014-11-18 18:41 | Simpply | Planning Meeting
128 | Task | Planning Meeting 11/18 | Closed | Mustafa Al-Salihi | 1.25 | 0 | 1.5 | 2014-11-18 18:41 | Simpply | Planning Meeting
125 | Task | Planning Meeting 11/18 | Closed | Michael Yeaple | 1.25 | 0 | 1.75 | 2014-11-18 18:38 | Simpply | Planning Meeting
124 | Task | Investigate Interim Presentation | Closed | Michael Yeaple | 0.75 | 0 | 1 | 2014-11-17 18:41 | Simpply | Academic Work Effort
121 | Task | 11/13 End of Iteration Customer Meeting | Closed | Michael Yeaple | 1.25 | 0 | 1.25 | 2014-11-17 17:56 | Simpply | Progress Meeting
73 | Task | Set Up Individual Effort Reports | Closed | Curtis Burtner | 1.5 | 0 | 2 | 2014-11-16 17:28 | Simpply | Process/Project Management Effort
41 | Task | Manage Risks | Closed | Curtis Burtner | 6 | 0 | 6.25 | 2014-11-14 15:03 | Simpply | Process/Project Management Effort
117 | Task | Page Styling/Refactoring Meeting | Closed | Curtis Burtner | 2.5 | 0 | 2.5 | 2014-11-13 15:13 | Simpply | Refactoring
122 | Task | CSS Touch up with Michael | Closed | Jeremy Shulman | 1.25 | 0 | 1.25 | 2014-11-13 15:10 | Simpply | Refactoring
116 | Task | Page Styling/Refactoring Meeting | Closed | Michael Yeaple | 2.5 | 0 | 3.25 | 2014-11-13 15:04 | Simpply | Refactoring
101 | Task | 11/11 Meeting | Closed | Curtis Burtner | 1.25 | 0 | 1.25 | 2014-11-13 13:10 | Simpply | Process/Project Management Effort
35 | User Story | Sort Summary of All Items | Closed | Michael Yeaple |  |  |  | 2014-11-13 10:56 | Simpply\Iteration 1
114 | Task | Style Column Headers based on Sort | Closed | Michael Yeaple | 1 | 0 | 0.5 | 2014-11-12 13:30 | Simpply\Iteration 1 | Implementation
67 | Task | Implementation | Closed | Michael Yeaple | 1.5 | 0 | 1.75 | 2014-11-12 12:59 | Simpply\Iteration 1 | Implementation
66 | Task | Design Classes | Closed | Michael Yeaple | 0.75 | 0 | 0.75 | 2014-11-12 11:15 | Simpply\Iteration 1 | Design Effort
1 | User Story | View Basic Item Information | Closed | Jeremy Shulman |  |  |  | 2014-11-13 10:56 | Simpply\Iteration 1 | Implementation
115 | Task | Sales Information Logic | Closed | Jeremy Shulman | 3.5 | 0 | 3.5 | 2014-11-12 22:57 | Simpply\Iteration 1 | Implementation
33 | User Story | View Summary of All Items | Closed | Curtis Burtner |  |  |  | 2014-11-13 10:55 | Simpply\Iteration 1
105 | Task | Style Page | Closed | Curtis Burtner | 2 | 0 | 4.5 | 2014-11-13 03:13 | Simpply\Iteration 1 | Implementation
61 | Task | Style Page | Closed | Michael Yeaple | 2 | 0 | 0.25 | 2014-11-11 17:21 | Simpply\Iteration 1 | Implementation
58 | Task | Implement Design | Closed | Michael Yeaple | 4 | 0 | 6 | 2014-11-03 17:46 | Simpply\Iteration 1 | Implementation
57 | Task | Design Classes | Closed | Michael Yeaple | 1 | 0 | 1.25 | 2014-11-03 12:55 | Simpply\Iteration 1 | Design Effort
37 | User Story | Create Detailed Item Data View | Closed | Jeremy Shulman |  |  |  | 2014-11-13 10:55 | Simpply\Iteration 1 | Implementation
60 | Bug | ItemDetail Null Reference Error | Resolved | Jeremy Shulman |  |  |  |  | Simpply\Iteration 1 | Bugs
88 | Task | Fix Null Reference Error (60) | Closed | Jeremy Shulman | 1 | 0 | 0.75 | 2014-11-06 16:54 | Simpply\Iteration 1 | Implementation
80 | Task | Implementation w/mock data | Closed | Mustafa Al-Salihi | 5 |  | 3 | 2014-11-12 22:53 | Simpply\Iteration 1 | Implementation
50 | Task | Implementation w/mock data | Closed | Jeremy Shulman | 5 |  | 4 | 2014-11-12 22:50 | Simpply\Iteration 1 | Implementation
49 | Task | Wireframes/Mockups | Closed | Mustafa Al-Salihi | 1 | 1.3 | 1 | 2014-11-04 17:09 | Simpply\Iteration 1 | Design Effort;Requirements Effort
48 | Task | Class Diagram | Closed | Jeremy Shulman | 1 |  | 1 | 2014-11-04 17:09 | Simpply\Iteration 1 | Design Effort
38 | User Story | Create Item Summary View | Closed | Michael Yeaple |  |  |  | 2014-11-13 10:55 | Simpply\Iteration 1
62 | Task | Add Missing Placeholders | Closed | Michael Yeaple | 0.5 |  |  | 2014-11-03 23:42 | Simpply\Iteration 1 | Implementation
45 | Task | Implement View with Dummy Data (Item Summary View) | Closed | Michael Yeaple | 4 | 0 | 0.5 | 2014-11-03 16:46 | Simpply\Iteration 1 | Implementation
43 | Task | Design Classes (Item Summary View) | Closed | Michael Yeaple | 1 |  | 1.25 | 2014-10-28 14:07 | Simpply\Iteration 1 | Design Effort
44 | Task | Create Mockups (Item Summary View) | Closed | Michael Yeaple | 1 |  | 0.5 | 2014-10-28 14:07 | Simpply\Iteration 1 | Design Effort
47 | Task | Task Breakdown (Item Summary View) | Closed | Michael Yeaple | 1 | 0 | 1 | 2014-10-21 12:16 | Simpply\Iteration 1 | Process/Project Management Effort
102 | Task | 11/11 Meeting | Closed | Jeremy Shulman | 1.25 | 0 | 1.25 | 2014-11-12 22:50 | Simpply | Process/Project Management Effort
75 | Task | Fix ItemController Code for Failed Unit Tests | Closed | Michael Yeaple | 0.167 | 0.5 | 1.5503 | 2014-11-12 14:54 | Simpply | Implementation
113 | Task | Quick Review with Michael | Closed | Curtis Burtner | 1 | 0 | 1 | 2014-11-12 12:00 | Simpply | Code/Design Review
103 | Task | 11/11 Meeting | Closed | Michael Yeaple | 1.25 | 0 | 1.25 | 2014-11-11 18:06 | Simpply | Process/Project Management Effort
99 | Task | Email to Team | Closed | Curtis Burtner | 1 | 0 | 0.75 | 2014-11-11 15:18 | Simpply | Process/Project Management Effort
92 | Task | Setup FTP Server | Closed | Michael Yeaple | 0.5 | 0 | 1.5 | 2014-11-10 13:01 | Simpply | Project Setup
100 | Task | Setup FTP Server | Closed | Jeremy Shulman | 0.5 | 0 | 0.5 | 2014-11-10 13:01 | Simpply | Project Setup
91 | Task | Customer Progress Meeting | Closed | Jeremy Shulman | 1.25 | 0 | 1.25 | 2014-11-10 12:57 | Simpply | Progress Meeting
72 | Task | Team Meeting | Closed | Curtis Burtner | 1.25 | 0 | 2 | 2014-11-08 21:07 | Simpply | Process/Project Management Effort
98 | Task | Refactor Code Based on Code Review | Closed | Michael Yeaple | 0.33 | 0 | 0.75 | 2014-11-08 15:20 | Simpply | Refactoring
89 | Task | Customer Progress Meeting | Closed | Michael Yeaple | 1.25 | 0 | 1.25 | 2014-11-08 14:46 | Simpply | Progress Meeting
97 | Task | Post Code Review Notes | Closed | Michael Yeaple | 0.25 | 0 | 0.25 | 2014-11-08 14:44 | Simpply | Code/Design Review
95 | Task | Code Review | Closed | Michael Yeaple | 1 | 0 | 1 | 2014-11-08 14:43 | Simpply | Code/Design Review
96 | Task | Code Review | Closed | Jeremy Shulman | 1 | 0 | 1 | 2014-11-08 14:22 | Simpply | Code/Design Review
90 | Task | Customer Progress Meeting | Closed | Curtis Burtner | 1.25 | 0 | 1.25 | 2014-11-07 18:34 | Simpply | Progress Meeting
94 | Task | Create calendar notification for interim presentation | Closed | Curtis Burtner | 0.5 | 0 | 0.5 | 2014-11-07 18:33 | Simpply | Process/Project Management Effort
86 | Task | Use Dapper in code | Closed | Curtis Burtner | 1 | 0 | 3.5 | 2014-11-07 17:16 | Simpply | Implementation
54 | Task | Set Up Autofac | Closed | Curtis Burtner | 3 | 0 | 3 | 2014-11-07 10:21 | Simpply | Project Setup
78 | Task | Tag All Previous Work Items | Closed | Curtis Burtner | 1 | 0 | 1 | 2014-11-06 21:56 | Simpply | Process/Project Management Effort
93 | Task | Add All Tags | Closed | Curtis Burtner | 0.5 | 0 | 0.5 | 2014-11-06 21:05 | Simpply | Academic Work Effort;Academic Work Meeting;Design Effort;Design Meeting;Implementation;Process/Project Management Effort;Process/Project Management Meeting;Project Setup;Refactoring;Requirements Effort;Requirements Meeting;Testing Effort;Testing Meeting
81 | Task | Research Standards for CSS File Organization | Closed | Jeremy Shulman | 0.5 | 0 | 0.5 | 2014-11-06 01:22 | Simpply | Project Setup
71 | Task | Team Meeting | Closed | Jeremy Shulman | 1.25 |  | 2 | 2014-11-04 23:55 | Simpply | Process/Project Management Effort
55 | Task | Set Up Dapper | Closed | Curtis Burtner | 1.5 | 0 | 1.5 | 2014-11-04 23:15 | Simpply | Project Setup
82 | Task | Email Customer | Closed | Curtis Burtner | 0.75 | 0 | 0.75 | 2014-11-04 22:39 | Simpply | Process/Project Management Effort
70 | Task | Team Meeting | Closed | Michael Yeaple | 1.25 | 0 | 2 | 2014-11-04 18:53 | Simpply | Process/Project Management Effort
79 | Task | Clarify Action URL Generation in Code | Closed | Michael Yeaple | 0.5 | 0 | 0.5 | 2014-11-04 18:37 | Simpply | Implementation
77 | Task | Code Review With Michael | Closed | Curtis Burtner | 0.5 | 0 | 0.5 | 2014-11-04 15:27 | Simpply | Code/Design Review
68 | Task | Fix TFS Installation | Closed | Michael Yeaple | 3 |  | 3.5 | 2014-11-04 15:26 | Simpply | Project Setup
59 | Task | Review Code Changes with Team | Closed | Michael Yeaple | 1.5 | 0 | 1 | 2014-11-04 15:26 | Simpply | Code/Design Review
76 | Task | Work on AutoFac/Dapper | Closed | Michael Yeaple | 0.5 | 0 | 0.5 | 2014-11-04 15:25 | Simpply | Implementation
63 | Task | Determine How to Track Time More Efficiently | Closed | Michael Yeaple | 0.5 |  | 0.5 | 2014-11-03 23:44 | Simpply | Process/Project Management Effort
65 | Task | Add Risks | Closed | Michael Yeaple | 0.25 |  | 0.25 | 2014-11-03 22:12 | Simpply | Process/Project Management Effort
64 | Task | Set Up Branches | Closed | Michael Yeaple | 1 |  | 1 | 2014-11-03 21:18 | Simpply | Project Setup
53 | Task | Set Up Project Skeleton | Closed | Michael Yeaple | 3 |  | 3 | 2014-10-28 14:14 | Simpply | Project Setup
42 | Task | Research and Implement Template Layout | Closed | Michael Yeaple | 3 |  | 1 | 2014-10-28 08:13 | Simpply | Implementation
19 | Task | Request more hard-drive space | Closed | Curtis Burtner |  |  |  | 2014-10-27 10:25 | Simpply | Project Setup
46 | Task | Write Blurb About Why We Chose Data Layer Technology | Closed | Curtis Burtner | 0.5 | 0 | 1 | 2014-10-22 10:32 | Simpply | Process/Project Management Effort
23 | Task | Set Up VM | Closed | Michael Yeaple | 3 | 0 | 10 | 2014-10-21 12:12 | Simpply | Project Setup
40 | Task | Make sure we can commit code from TFS | Closed | Michael Yeaple | 1 | 0 | 0.5 | 2014-10-21 11:40 | Simpply | Process/Project Management Effort
18 | Task | Risk chart status column needs to be meaningful | Closed | Curtis Burtner |  |  |  | 2014-10-20 15:10 | Simpply | Process/Project Management Effort
|  | Kick-Off Meeting | Closed | Curtis Burtner | 1.25 |  | 1.25 | 2014-08-28 | Simpply | Requirements Meeting
|  | Kick-Off Meeting | Closed | Michael Yeaple | 1.25 |  | 1.25 | 2014-08-28 | Simpply | Requirements Meeting
|  | Kick-Off Meeting | Closed | Mustafa Al-Salihi | 1.25 |  | 1.25 | 2014-08-28 | Simpply | Requirements Meeting
|  | Kick-Off Meeting | Closed | Jeremy Shulman | 1.25 |  | 1.25 | 2014-08-28 | Simpply | Requirements Meeting
|  | Set Up JIRA | Closed | Michael Yeaple | 3 |  | 3 | 2014-09-05 | Simpply | Project Setup
|  | Emails to customer | Closed | Curtis Burtner | 1 |  | 1 | 2014-09-04 | Simpply | Process/Project Management Effort
|  | Searched how to build enterprise software | Closed | Mustafa Al-Salihi | 2 |  | 2 | 2014-09-04 | Simpply | Process/Project Management Effort
|  | Meeting | Closed | Curtis Burtner | 1.5 |  | 1.5 | 2014-09-04 | Simpply | Requirements Meeting
|  | Meeting | Closed | Michael Yeaple | 1.5 |  | 1.5 | 2014-09-04 | Simpply | Requirements Meeting
|  | Meeting | Closed | Jeremy Shulman | 1.5 |  | 1.5 | 2014-09-04 | Simpply | Requirements Meeting
|  | Meeting | Closed | Mustafa Al-Salihi | 1.5 |  | 1.5 | 2014-09-04 | Simpply | Requirements Meeting
|  | Meeting | Closed | Michael Yeaple | 2 |  | 2 | 2014-09-03 | Simpply | Requirements Meeting
|  | Meeting | Closed | Curtis Burtner | 2 |  | 2 | 2014-09-03 | Simpply | Requirements Meeting
|  | Meeting | Closed | Mustafa Al-Salihi | 2 |  | 2 | 2014-09-03 | Simpply | Requirements Meeting
|  | Meeting | Closed | Jeremy Shulman | 2 |  | 2 | 2014-09-03 | Simpply | Requirements Meeting
|  | Meeting | Closed | Michael Yeaple | 1.25 |  | 1.25 | 2014-09-02 | Simpply | Requirements Meeting
|  | Meeting | Closed | Curtis Burtner | 1.25 |  | 1.25 | 2014-09-02 | Simpply | Requirements Meeting
|  | Meeting | Closed | Mustafa Al-Salihi | 1.25 |  | 1.25 | 2014-09-02 | Simpply | Requirements Meeting
|  | Meeting | Closed | Jeremy Shulman | 1.25 |  | 1.25 | 2014-09-02 | Simpply | Requirements Meeting
|  | Project schedule | Closed | Mustafa Al-Salihi | 2 |  | 2 | 2014-09-13 | Simpply | Process/Project Management Effort
|  | Work on team website and time tracking sheet | Closed | Jeremy Shulman | 1.5 |  | 1.5 | 2014-09-13 | Simpply | Process/Project Management Effort
|  | Set Up & Fill Out Time Tracking | Closed | Michael Yeaple | 0.25 |  | 0.25 | 2014-09-13 | Simpply | Process/Project Management Effort
|  | Emails to customer | Closed | Curtis Burtner | 1 |  | 1 | 2014-09-11 | Simpply | Process/Project Management Effort
|  | Meeting | Closed | Curtis Burtner | 1.25 |  | 1.25 | 2014-09-11 | Simpply | Requirements Meeting
|  | Meeting | Closed | Michael Yeaple | 1.25 |  | 1.25 | 2014-09-11 | Simpply | Requirements Meeting
|  | Meeting | Closed | Jeremy Shulman | 1.25 |  | 1.25 | 2014-09-11 | Simpply | Requirements Meeting
|  | Meeting | Closed | Mustafa Al-Salihi | 1.25 |  | 1.25 | 2014-09-11 | Simpply | Requirements Meeting
|  | Setup project plan template | Closed | Mustafa Al-Salihi | 0.5 |  | 0.5 | 2014-09-10 | Simpply | Process/Project Management Effort
|  | Project Plan Sections | Closed | Jeremy Shulman | 2 |  | 2 | 2014-09-10 | Simpply | Process/Project Management Effort
|  | Project Plan Meeting | Closed | Jeremy Shulman | 1.5 |  | 1.5 | 2014-09-08 | Simpply | Process/Project Management Meeting
|  | Project Plan Meeting | Closed | Mustafa Al-Salihi | 1.5 |  | 1.5 | 2014-09-08 | Simpply | Process/Project Management Meeting
|  | Project Plan Meeting | Closed | Michael Yeaple | 1.5 |  | 1.5 | 2014-09-08 | Simpply | Process/Project Management Meeting
|  | Project Plan Meeting | Closed | Curtis Burtner | 1.5 |  | 1.5 | 2014-09-08 | Simpply | Process/Project Management Meeting
|  | User Stories & Use Cases | Closed | Michael Yeaple | 3.5 |  | 3.5 | 2014-09-08 | Simpply | Requirements Effort
|  | Project Plan Meeting | Closed | Jeremy Shulman | 1.33 |  | 1.33 | 2014-09-09 | Simpply | Process/Project Management Meeting
|  | Project Plan Meeting | Closed | Mustafa Al-Salihi | 1.33 |  | 1.33 | 2014-09-09 | Simpply | Process/Project Management Meeting
|  | Project Plan Meeting | Closed | Michael Yeaple | 1.33 |  | 1.33 | 2014-09-09 | Simpply | Process/Project Management Meeting
|  | Project Plan Meeting | Closed | Curtis Burtner | 1.33 |  | 1.33 | 2014-09-09 | Simpply | Process/Project Management Meeting
|  | Project Plan | Closed | Jeremy Shulman | 2 |  | 2 | 2014-09-09 | Simpply | Process/Project Management Effort
|  | Project Plan | Closed | Mustafa Al-Salihi | 2 |  | 2 | 2014-09-09 | Simpply | Process/Project Management Effort
|  | Project Plan | Closed | Michael Yeaple | 2 |  | 2 | 2014-09-09 | Simpply | Process/Project Management Effort
|  | Project Plan | Closed | Curtis Burtner | 2 |  | 2 | 2014-09-09 | Simpply | Process/Project Management Effort
|  | Project Plan Meeting | Closed | Jeremy Shulman | 1.5 |  | 1.5 | 2014-09-10 | Simpply | Process/Project Management Effort
|  | Project Plan Meeting | Closed | Mustafa Al-Salihi | 1.5 |  | 1.5 | 2014-09-10 | Simpply | Process/Project Management Effort
|  | Project Plan Meeting | Closed | Michael Yeaple | 1.5 |  | 1.5 | 2014-09-10 | Simpply | Process/Project Management Effort
|  | Project Plan Meeting | Closed | Curtis Burtner | 1.5 |  | 1.5 | 2014-09-10 | Simpply | Process/Project Management Effort
|  | Planning Next Meeting | Closed | Michael Yeaple | 0.5 |  | 0.5 | 2014-09-10 | Simpply | Process/Project Management Meeting
|  | Planning Next Meeting | Closed | Curtis Burtner | 0.5 |  | 0.5 | 2014-09-10 | Simpply | Process/Project Management Meeting
|  | Development Methodology Artifact (for website) | Closed | Curtis Burtner | 0.5 |  | 0.75 | 2014-09-21 | Simpply | Process/Project Management Meeting
|  | Development Methodology Artifact (for website) | Closed | Jeremy Shulman | 0.5 |  | 0.75 | 2014-09-21 | Simpply | Process/Project Management Meeting
|  | Development Methodology Artifact (for website) | Closed | Michael Yeaple | 0.5 |  | 0.75 | 2014-09-21 | Simpply | Process/Project Management Meeting
|  | Set Up TFS | Closed | Michael Yeaple | 0.5 |  | 1 | 2014-09-19 | Simpply | Project Setup
|  | Updating website | Closed | Jeremy Shulman |  |  | 0.5 | 2014-09-18 | Simpply | Process/Project Management Effort
|  | Email to Wegmans Team | Closed | Curtis Burtner | 0.5 |  | 0.75 | 2014-09-18 | Simpply | Process/Project Management Effort
|  | Created initial document to enter metrics | Closed | Curtis Burtner | 0.5 |  | 1 | 2014-09-17 | Simpply | Process/Project Management Effort
|  | Completed Initial Wireframes | Closed | Michael Yeaple | 1 |  | 1.25 | 2014-09-17 | Simpply | Requirements Effort
|  | Wireframe Meeting | Closed | Curtis Burtner | 0.5 |  | 0.5 | 2014-09-17 | Simpply | Requirements Meeting
|  | Wireframe Meeting | Closed | Jeremy Shulman | 1 |  | 1 | 2014-09-17 | Simpply | Requirements Meeting
|  | Wireframe Meeting | Closed | Michael Yeaple | 1 |  | 1 | 2014-09-17 | Simpply | Requirements Meeting
|  | Initial Wireframes | Closed | Michael Yeaple | 2 |  | 3 | 2014-09-17 | Simpply | Requirements Effort
|  | Import user stroies into the software | Closed | Mustafa Al-Salihi |  |  | 1 | 2014-09-17 | Simpply | Process/Project Management Effort
|  | User Stories Meeting | Closed | Jeremy Shulman | 1.25 |  | 1.25 | 2014-09-16 | Simpply | Requirements Meeting
|  | User Stories Meeting | Closed | Mustafa Al-Salihi | 1.25 |  | 1.25 | 2014-09-16 | Simpply | Requirements Meeting
|  | User Stories Meeting | Closed | Michael Yeaple | 1.25 |  | 1.25 | 2014-09-16 | Simpply | Requirements Meeting
|  | User Stories Meeting | Closed | Curtis Burtner | 1.25 |  | 1.25 | 2014-09-16 | Simpply | Requirements Meeting
|  | Initial Wireframes | Closed | Jeremy Shulman | 1.25 |  | 1.25 | 2014-09-15 | Simpply | Requirements Effort
|  | Initial Wireframes | Closed | Curtis Burtner | 1.25 |  | 1.25 | 2014-09-15 | Simpply | Requirements Effort
|  | Wireframes | Closed | Mustafa Al-Salihi | 1.3 |  | 1.3 | 2014-09-15 | Simpply | Requirements Effort
|  | VM Set Up | Closed | Michael Yeaple | 3 |  | 5 | 2014-09-27 | Simpply | Project Setup
|  | Customer Meeting | Closed | Curtis Burtner | 1.25 |  | 1.75 | 2014-09-25 | Simpply | Requirements Meeting
|  | Customer Meeting | Closed | Jeremy Shulman | 1.25 |  | 1.75 | 2014-09-25 | Simpply | Requirements Meeting
|  | Customer Meeting | Closed | Michael Yeaple | 1.25 |  | 1.75 | 2014-09-25 | Simpply | Requirements Meeting
|  | ORM Presentation Slides | Closed | Curtis Burtner | 1 |  | 1 | 2014-09-25 | Simpply | Process/Project Management Effort
|  | ORM Presentation Slides | Closed | Michael Yeaple | 1 |  | 1 | 2014-09-25 | Simpply | Process/Project Management Effort
|  | Emails to Customer | Closed | Curtis Burtner | 1 |  | 1 | 2014-09-25 | Simpply | Process/Project Management Effort
|  | Wireframe Revision/Planning for Customer Meeting | Closed | Curtis Burtner | 1 |  | 1 | 2014-09-24 | Simpply | Requirements Meeting
|  | Wireframe Revision/Planning for Customer Meeting | Closed | Jeremy Shulman | 1 |  | 1 | 2014-09-24 | Simpply | Requirements Meeting
|  | Wireframe Revision/Planning for Customer Meeting | Closed | Michael Yeaple | 1 |  | 1 | 2014-09-24 | Simpply | Requirements Meeting
|  | Environment Set Up Meeting | Closed | Jeremy Shulman | 1 |  | 1 | 2014-09-23 | Simpply | Project Setup
|  | Environment Set Up Meeting | Closed | Mustafa Al-Salihi | 1 |  | 1 | 2014-09-23 | Simpply | Project Setup
|  | Environment Set Up Meeting | Closed | Michael Yeaple | 1 |  | 1 | 2014-09-23 | Simpply | Project Setup
|  | Environment Set Up Meeting | Closed | Curtis Burtner | 1 |  | 1 | 2014-09-23 | Simpply | Project Setup
|  | Software Design Document Set Up/Update Project Plan | Closed | Michael Yeaple | 1 |  | 1 | 2014-09-22 | Simpply | Process/Project Management Effort
|  | Emails to Kurt | Closed | Curtis Burtner | 1 |  | 1 | 2014-09-22 | Simpply | Process/Project Management Effort
|  | Onsite meeting with customer. | Closed | Jeremy Shulman | 2 |  | 2 | 2014-10-03 | Simpply | Design Meeting
|  | Onsite meeting with customer. | Closed | Mustafa Al-Salihi | 2 |  | 2 | 2014-10-03 | Simpply | Design Meeting
|  | Onsite meeting with customer. | Closed | Michael Yeaple | 2 |  | 2 | 2014-10-03 | Simpply | Design Meeting
|  | Onsite meeting with customer. | Closed | Curtis Burtner | 2 |  | 2 | 2014-10-03 | Simpply | Design Meeting
|  | Team Meeting - User Stories in TFS; Architecture | Closed | Jeremy Shulman | 3 |  | 3 | 2014-10-02 | Simpply | Design Meeting
|  | Team Meeting - User Stories in TFS; Architecture | Closed | Mustafa Al-Salihi | 3 |  | 3 | 2014-10-02 | Simpply | Design Meeting
|  | Team Meeting - User Stories in TFS; Architecture | Closed | Michael Yeaple | 3 |  | 3 | 2014-10-02 | Simpply | Design Meeting
|  | Team Meeting - User Stories in TFS; Architecture | Closed | Curtis Burtner | 3 |  | 3 | 2014-10-02 | Simpply | Design Meeting
|  | TFS Setup - Project and Users | Closed | Michael Yeaple | 1 |  | 3 | 2014-09-30 | Simpply | Project Setup
|  | Team Meeting - Mind Map | Closed | Jeremy Shulman | 1.25 |  | 1.25 | 2014-09-30 | Simpply | Requirements Meeting
|  | Team Meeting - Mind Map | Closed | Mustafa Al-Salihi | 1.25 |  | 1.25 | 2014-09-30 | Simpply | Requirements Meeting
|  | Team Meeting - Mind Map | Closed | Michael Yeaple | 1.25 |  | 1.25 | 2014-09-30 | Simpply | Requirements Meeting
|  | Team Meeting - Mind Map | Closed | Curtis Burtner | 1.25 |  | 1.25 | 2014-09-30 | Simpply | Requirements Meeting
|  | EA Review of Architecture | Closed | Jeremy Shulman | 2 |  | 2 | 2014-10-10 | Simpply | Design Meeting
|  | EA Review of Architecture | Closed | Mustafa Al-Salihi | 2 |  | 2 | 2014-10-10 | Simpply | Design Meeting
|  | EA Review of Architecture | Closed | Michael Yeaple | 2 |  | 2 | 2014-10-10 | Simpply | Design Meeting
|  | EA Review of Architecture | Closed | Curtis Burtner | 2 |  | 2 | 2014-10-10 | Simpply | Design Meeting
|  | Customer Meeting; Update and Practice Presentation | Closed | Jeremy Shulman | 2 |  | 2.25 | 2014-10-09 | Simpply | Progress Meeting
|  | Customer Meeting; Update and Practice Presentation | Closed | Mustafa Al-Salihi | 2 |  | 2.25 | 2014-10-09 | Simpply | Progress Meeting
|  | Customer Meeting; Update and Practice Presentation | Closed | Michael Yeaple | 2 |  | 2.25 | 2014-10-09 | Simpply | Progress Meeting
|  | Customer Meeting; Update and Practice Presentation | Closed | Curtis Burtner | 2 |  | 2.25 | 2014-10-09 | Simpply | Progress Meeting
|  | Regular Tuesday meeting | Closed | Jeremy Shulman | 2 |  | 2 | 2014-10-07 | Simpply | Design Meeting
|  | Regular Tuesday meeting | Closed | Mustafa Al-Salihi | 2 |  | 2 | 2014-10-07 | Simpply | Design Meeting
|  | Regular Tuesday meeting | Closed | Michael Yeaple | 2 |  | 2 | 2014-10-07 | Simpply | Design Meeting
|  | Regular Tuesday meeting | Closed | Curtis Burtner | 2 |  | 2 | 2014-10-07 | Simpply | Design Meeting
|  | Customer Meeting - Sprint Planning | Closed | Jeremy Shulman | 1.25 |  | 1.75 | 2014-10-16 | Simpply | Planning Meeting
|  | Customer Meeting - Sprint Planning | Closed | Mustafa Al-Salihi | 1.25 |  | 1.75 | 2014-10-16 | Simpply | Planning Meeting
|  | Customer Meeting - Sprint Planning | Closed | Michael Yeaple | 1.25 |  | 1.75 | 2014-10-16 | Simpply | Planning Meeting
|  | Customer Meeting - Sprint Planning | Closed | Curtis Burtner | 1.25 |  | 1.75 | 2014-10-16 | Simpply | Planning Meeting
|  | User Story Meeting (Break down, Pointing) | Closed | Curtis Burtner | 2 |  | 3.5 | 2014-10-15 | Simpply | Planning Meeting
|  | User Story Meeting (Break down, Pointing) | Closed | Jeremy Shulman | 2 |  | 3.5 | 2014-10-15 | Simpply | Planning Meeting
|  | User Story Meeting (Break down, Pointing) | Closed | Michael Yeaple | 2 |  | 3.5 | 2014-10-15 | Simpply | Planning Meeting
|  | TFS Permissions Issues | Closed | Michael Yeaple | 0.5 |  | 0.5 | 2014-10-13 | Simpply | Project Setup
|  | Team Meeting - Finish Design for Sprint 1 | Closed | Jeremy Shulman | 1 |  | 1 | 2014-10-21 | Simpply\Iteration 1 | Design Meeting
|  | Team Meeting - Finish Design for Sprint 1 | Closed | Mustafa Al-Salihi | 1 |  | 1 | 2014-10-21 | Simpply\Iteration 2 | Design Meeting
|  | Team Meeting - Finish Design for Sprint 1 | Closed | Michael Yeaple | 1 |  | 1 | 2014-10-21 | Simpply\Iteration 3 | Design Meeting
|  | Team Meeting - Finish Design for Sprint 1 | Closed | Curtis Burtner | 1 |  | 1 | 2014-10-21 | Simpply\Iteration 4 | Design Meeting
|  | Meeting with Michael - User Story Breakdown/Tasks | Closed | Curtis Burtner | 2 |  | 2 | 2014-10-20 | Simpply | Process/Project Management Meeting
|  | Meeting with Curtis - User Story Breakdown/Tasks | Closed | Michael Yeaple | 2 |  | 2 | 2014-10-20 | Simpply | Process/Project Management Meeting
|  | Template layout implementation | Closed | Michael Yeaple | 3 |  | 1 | 2014-10-28 | Simpply | Implementation

## Historical Effort Tracking
ID | Work Item Type | Title | State | Assigned To | Original Estimate | Remaining Work | Completed Work | Closed Date | Iteration Path | Tags |  | Week3Iter2(11/21-11/25) | Week2Iter2(11/14-11/20) | Iteration 0 | Iteration 1 | All Time |  |  | Week3Iter2 | Week2Iter2 | Iteration 1
|  | Kick-Off Meeting | Closed | Curtis Burtner | 1.25 |  | 1.25 | 2014-08-28 | Simpply | Requirements Meeting | Process: | 0.00000 | 0 |  | 22.5 | 192.37 |  | Start: | >11/21/2014 | >11/14/2014 | >10/14/2014
|  | Kick-Off Meeting | Closed | Michael Yeaple | 1.25 |  | 1.25 | 2014-08-28 | Simpply | Requirements Meeting | Product: | 0.00000 | 0.00000 |  | 1 | 4 |  | End: | <11/28/2014 | <11/21/2014 | <11/14/2014
|  | Kick-Off Meeting | Closed | Mustafa Al-Salihi | 1.25 |  | 1.25 | 2014-08-28 | Simpply | Requirements Meeting | Total: | 0 | 0 |  | 26.5 | 196.37
|  | Kick-Off Meeting | Closed | Jeremy Shulman | 1.25 |  | 1.25 | 2014-08-28 | Simpply | Requirements Meeting | Estimated Hours: | 0 | 0 |  | 22
|  | Set Up JIRA | Closed | Michael Yeaple | 3 |  | 3 | 2014-09-05 | Simpply | Project Setup
|  | Emails to customer | Closed | Curtis Burtner | 1 |  | 1 | 2014-09-04 | Simpply | Process/Project Management Effort | Curtis Burtner | 0 | 0 |  | 8.25 | 49.08
|  | Searched how to build enterprise software | Closed | Mustafa Al-Salihi | 2 |  | 2 | 2014-09-04 | Simpply | Process/Project Management Effort | Michael Yeaple | 0 | 0 |  | 9.25 | 65.08
|  | Meeting | Closed | Curtis Burtner | 1.5 |  | 1.5 | 2014-09-04 | Simpply | Requirements Meeting | Jeremy Shulman | 0 | 0 |  | 6.25 | 44.33
|  | Meeting | Closed | Michael Yeaple | 1.5 |  | 1.5 | 2014-09-04 | Simpply | Requirements Meeting | Mustafa Al-Salihi | 0 | 0 |  | 2.75 | 37.88
|  | Meeting | Closed | Jeremy Shulman | 1.5 |  | 1.5 | 2014-09-04 | Simpply | Requirements Meeting
|  | Meeting | Closed | Mustafa Al-Salihi | 1.5 |  | 1.5 | 2014-09-04 | Simpply | Requirements Meeting
|  | Meeting | Closed | Michael Yeaple | 2 |  | 2 | 2014-09-03 | Simpply | Requirements Meeting
|  | Meeting | Closed | Curtis Burtner | 2 |  | 2 | 2014-09-03 | Simpply | Requirements Meeting
|  | Meeting | Closed | Mustafa Al-Salihi | 2 |  | 2 | 2014-09-03 | Simpply | Requirements Meeting
|  | Meeting | Closed | Jeremy Shulman | 2 |  | 2 | 2014-09-03 | Simpply | Requirements Meeting
|  | Meeting | Closed | Michael Yeaple | 1.25 |  | 1.25 | 2014-09-02 | Simpply | Requirements Meeting
|  | Meeting | Closed | Curtis Burtner | 1.25 |  | 1.25 | 2014-09-02 | Simpply | Requirements Meeting | Tags |  | Total | Curtis Butner | Jeremy Shulman | Michael Yeaple | Mustafa Al-Salihi
|  | Meeting | Closed | Mustafa Al-Salihi | 1.25 |  | 1.25 | 2014-09-02 | Simpply | Requirements Meeting | Academic Work Effort |  | 0
|  | Meeting | Closed | Jeremy Shulman | 1.25 |  | 1.25 | 2014-09-02 | Simpply | Requirements Meeting | Academic Work Meeting |  | 0
|  | Project schedule | Closed | Mustafa Al-Salihi | 2 |  | 2 | 2014-09-13 | Simpply | Process/Project Management Effort | Bugs |  | 0
|  | Work on team website and time tracking sheet | Closed | Jeremy Shulman | 1.5 |  | 1.5 | 2014-09-13 | Simpply | Process/Project Management Effort | Code/Design Review |  | 0
|  | Set Up & Fill Out Time Tracking | Closed | Michael Yeaple | 0.25 |  | 0.25 | 2014-09-13 | Simpply | Process/Project Management Effort | Design Effort |  | 0
|  | Emails to customer | Closed | Curtis Burtner | 1 |  | 1 | 2014-09-11 | Simpply | Process/Project Management Effort | Design Meeting |  | 40 | 10 | 10 | 10 | 10
|  | Meeting | Closed | Curtis Burtner | 1.25 |  | 1.25 | 2014-09-11 | Simpply | Requirements Meeting | Implementation |  | 1 | 0 | 1 | 0 | 0
|  | Meeting | Closed | Michael Yeaple | 1.25 |  | 1.25 | 2014-09-11 | Simpply | Requirements Meeting | Planning Meeting |  | 17.5 | 5.25 | 5.25 | 5.25 | 1.75
|  | Meeting | Closed | Jeremy Shulman | 1.25 |  | 1.25 | 2014-09-11 | Simpply | Requirements Meeting | Process/Project Management Effort |  | 32.5 | 10.25 | 7.5 | 5.75 | 9
|  | Meeting | Closed | Mustafa Al-Salihi | 1.25 |  | 1.25 | 2014-09-11 | Simpply | Requirements Meeting | Process/Project Management Meeting |  | 18.57 | 6.08 | 3.58 | 6.08 | 2.83
|  | Setup project plan template | Closed | Mustafa Al-Salihi | 0.5 |  | 0.5 | 2014-09-10 | Simpply | Process/Project Management Effort | Project Setup |  | 16.5 | 1 | 1 | 13.5 | 1
|  | Project Plan Sections | Closed | Jeremy Shulman | 2 |  | 2 | 2014-09-10 | Simpply | Process/Project Management Effort | Progress Meeting |  | 9
|  | Project Plan Meeting | Closed | Jeremy Shulman | 1.5 |  | 1.5 | 2014-09-08 | Simpply | Process/Project Management Meeting | Refactoring |  | 0
|  | Project Plan Meeting | Closed | Mustafa Al-Salihi | 1.5 |  | 1.5 | 2014-09-08 | Simpply | Process/Project Management Meeting | Requirements Effort |  | 11.55 | 11.55 | 11.55 | 11.55 | 11.55
|  | Project Plan Meeting | Closed | Michael Yeaple | 1.5 |  | 1.5 | 2014-09-08 | Simpply | Process/Project Management Meeting | Requirements Meeting |  | 49.75 | 49.75 | 49.75 | 49.75 | 49.75
|  | Project Plan Meeting | Closed | Curtis Burtner | 1.5 |  | 1.5 | 2014-09-08 | Simpply | Process/Project Management Meeting | Testing Effort |  | 0
|  | User Stories & Use Cases | Closed | Michael Yeaple | 3.5 |  | 3.5 | 2014-09-08 | Simpply | Requirements Effort
|  | Project Plan Meeting | Closed | Jeremy Shulman | 1.33 |  | 1.33 | 2014-09-09 | Simpply | Process/Project Management Meeting | Total= |  | 196.37
|  | Project Plan Meeting | Closed | Mustafa Al-Salihi | 1.33 |  | 1.33 | 2014-09-09 | Simpply | Process/Project Management Meeting | All Tasks= |  | 196.37
|  | Project Plan Meeting | Closed | Michael Yeaple | 1.33 |  | 1.33 | 2014-09-09 | Simpply | Process/Project Management Meeting
|  | Project Plan Meeting | Closed | Curtis Burtner | 1.33 |  | 1.33 | 2014-09-09 | Simpply | Process/Project Management Meeting | Meeting Hours: |  | 125.82
|  | Project Plan | Closed | Jeremy Shulman | 2 |  | 2 | 2014-09-09 | Simpply | Process/Project Management Effort
|  | Project Plan | Closed | Mustafa Al-Salihi | 2 |  | 2 | 2014-09-09 | Simpply | Process/Project Management Effort
|  | Project Plan | Closed | Michael Yeaple | 2 |  | 2 | 2014-09-09 | Simpply | Process/Project Management Effort
|  | Project Plan | Closed | Curtis Burtner | 2 |  | 2 | 2014-09-09 | Simpply | Process/Project Management Effort
|  | Project Plan Meeting | Closed | Jeremy Shulman | 1.5 |  | 1.5 | 2014-09-10 | Simpply | Process/Project Management Effort
|  | Project Plan Meeting | Closed | Mustafa Al-Salihi | 1.5 |  | 1.5 | 2014-09-10 | Simpply | Process/Project Management Effort
|  | Project Plan Meeting | Closed | Michael Yeaple | 1.5 |  | 1.5 | 2014-09-10 | Simpply | Process/Project Management Effort
|  | Project Plan Meeting | Closed | Curtis Burtner | 1.5 |  | 1.5 | 2014-09-10 | Simpply | Process/Project Management Effort
|  | Planning Next Meeting | Closed | Michael Yeaple | 0.5 |  | 0.5 | 2014-09-10 | Simpply | Process/Project Management Meeting
|  | Planning Next Meeting | Closed | Curtis Burtner | 0.5 |  | 0.5 | 2014-09-10 | Simpply | Process/Project Management Meeting
|  | Development Methodology Artifact (for website) | Closed | Curtis Burtner | 0.5 |  | 0.75 | 2014-09-21 | Simpply | Process/Project Management Meeting
|  | Development Methodology Artifact (for website) | Closed | Jeremy Shulman | 0.5 |  | 0.75 | 2014-09-21 | Simpply | Process/Project Management Meeting
|  | Development Methodology Artifact (for website) | Closed | Michael Yeaple | 0.5 |  | 0.75 | 2014-09-21 | Simpply | Process/Project Management Meeting
|  | Set Up TFS | Closed | Michael Yeaple | 0.5 |  | 1 | 2014-09-19 | Simpply | Project Setup
|  | Updating website | Closed | Jeremy Shulman |  |  | 0.5 | 2014-09-18 | Simpply | Process/Project Management Effort
|  | Email to Wegmans Team | Closed | Curtis Burtner | 0.5 |  | 0.75 | 2014-09-18 | Simpply | Process/Project Management Effort
|  | Created initial document to enter metrics | Closed | Curtis Burtner | 0.5 |  | 1 | 2014-09-17 | Simpply | Process/Project Management Effort
|  | Completed Initial Wireframes | Closed | Michael Yeaple | 1 |  | 1.25 | 2014-09-17 | Simpply | Requirements Effort
|  | Wireframe Meeting | Closed | Curtis Burtner | 0.5 |  | 0.5 | 2014-09-17 | Simpply | Requirements Meeting
|  | Wireframe Meeting | Closed | Jeremy Shulman | 1 |  | 1 | 2014-09-17 | Simpply | Requirements Meeting
|  | Wireframe Meeting | Closed | Michael Yeaple | 1 |  | 1 | 2014-09-17 | Simpply | Requirements Meeting
|  | Initial Wireframes | Closed | Michael Yeaple | 2 |  | 3 | 2014-09-17 | Simpply | Requirements Effort
|  | Import user stroies into the software | Closed | Mustafa Al-Salihi |  |  | 1 | 2014-09-17 | Simpply | Process/Project Management Effort
|  | User Stories Meeting | Closed | Jeremy Shulman | 1.25 |  | 1.25 | 2014-09-16 | Simpply | Requirements Meeting
|  | User Stories Meeting | Closed | Mustafa Al-Salihi | 1.25 |  | 1.25 | 2014-09-16 | Simpply | Requirements Meeting
|  | User Stories Meeting | Closed | Michael Yeaple | 1.25 |  | 1.25 | 2014-09-16 | Simpply | Requirements Meeting
|  | User Stories Meeting | Closed | Curtis Burtner | 1.25 |  | 1.25 | 2014-09-16 | Simpply | Requirements Meeting
|  | Initial Wireframes | Closed | Jeremy Shulman | 1.25 |  | 1.25 | 2014-09-15 | Simpply | Requirements Effort
|  | Initial Wireframes | Closed | Curtis Burtner | 1.25 |  | 1.25 | 2014-09-15 | Simpply | Requirements Effort
|  | Wireframes | Closed | Mustafa Al-Salihi | 1.3 |  | 1.3 | 2014-09-15 | Simpply | Requirements Effort
|  | VM Set Up | Closed | Michael Yeaple | 3 |  | 5 | 2014-09-27 | Simpply | Project Setup
|  | Customer Meeting | Closed | Curtis Burtner | 1.25 |  | 1.75 | 2014-09-25 | Simpply | Requirements Meeting
|  | Customer Meeting | Closed | Jeremy Shulman | 1.25 |  | 1.75 | 2014-09-25 | Simpply | Requirements Meeting
|  | Customer Meeting | Closed | Michael Yeaple | 1.25 |  | 1.75 | 2014-09-25 | Simpply | Requirements Meeting
|  | ORM Presentation Slides | Closed | Curtis Burtner | 1 |  | 1 | 2014-09-25 | Simpply | Process/Project Management Effort
|  | ORM Presentation Slides | Closed | Michael Yeaple | 1 |  | 1 | 2014-09-25 | Simpply | Process/Project Management Effort
|  | Emails to Customer | Closed | Curtis Burtner | 1 |  | 1 | 2014-09-25 | Simpply | Process/Project Management Effort
|  | Wireframe Revision/Planning for Customer Meeting | Closed | Curtis Burtner | 1 |  | 1 | 2014-09-24 | Simpply | Requirements Meeting
|  | Wireframe Revision/Planning for Customer Meeting | Closed | Jeremy Shulman | 1 |  | 1 | 2014-09-24 | Simpply | Requirements Meeting
|  | Wireframe Revision/Planning for Customer Meeting | Closed | Michael Yeaple | 1 |  | 1 | 2014-09-24 | Simpply | Requirements Meeting
|  | Environment Set Up Meeting | Closed | Jeremy Shulman | 1 |  | 1 | 2014-09-23 | Simpply | Project Setup
|  | Environment Set Up Meeting | Closed | Mustafa Al-Salihi | 1 |  | 1 | 2014-09-23 | Simpply | Project Setup
|  | Environment Set Up Meeting | Closed | Michael Yeaple | 1 |  | 1 | 2014-09-23 | Simpply | Project Setup
|  | Environment Set Up Meeting | Closed | Curtis Burtner | 1 |  | 1 | 2014-09-23 | Simpply | Project Setup
|  | Software Design Document Set Up/Update Project Plan | Closed | Michael Yeaple | 1 |  | 1 | 2014-09-22 | Simpply | Process/Project Management Effort
|  | Emails to Kurt | Closed | Curtis Burtner | 1 |  | 1 | 2014-09-22 | Simpply | Process/Project Management Effort
|  | Onsite meeting with customer. | Closed | Jeremy Shulman | 2 |  | 2 | 2014-10-03 | Simpply | Design Meeting
|  | Onsite meeting with customer. | Closed | Mustafa Al-Salihi | 2 |  | 2 | 2014-10-03 | Simpply | Design Meeting
|  | Onsite meeting with customer. | Closed | Michael Yeaple | 2 |  | 2 | 2014-10-03 | Simpply | Design Meeting
|  | Onsite meeting with customer. | Closed | Curtis Burtner | 2 |  | 2 | 2014-10-03 | Simpply | Design Meeting
|  | Team Meeting - User Stories in TFS; Architecture | Closed | Jeremy Shulman | 3 |  | 3 | 2014-10-02 | Simpply | Design Meeting
|  | Team Meeting - User Stories in TFS; Architecture | Closed | Mustafa Al-Salihi | 3 |  | 3 | 2014-10-02 | Simpply | Design Meeting
|  | Team Meeting - User Stories in TFS; Architecture | Closed | Michael Yeaple | 3 |  | 3 | 2014-10-02 | Simpply | Design Meeting
|  | Team Meeting - User Stories in TFS; Architecture | Closed | Curtis Burtner | 3 |  | 3 | 2014-10-02 | Simpply | Design Meeting
|  | TFS Setup - Project and Users | Closed | Michael Yeaple | 1 |  | 3 | 2014-09-30 | Simpply | Project Setup
|  | Team Meeting - Mind Map | Closed | Jeremy Shulman | 1.25 |  | 1.25 | 2014-09-30 | Simpply | Requirements Meeting
|  | Team Meeting - Mind Map | Closed | Mustafa Al-Salihi | 1.25 |  | 1.25 | 2014-09-30 | Simpply | Requirements Meeting
|  | Team Meeting - Mind Map | Closed | Michael Yeaple | 1.25 |  | 1.25 | 2014-09-30 | Simpply | Requirements Meeting
|  | Team Meeting - Mind Map | Closed | Curtis Burtner | 1.25 |  | 1.25 | 2014-09-30 | Simpply | Requirements Meeting
|  | EA Review of Architecture | Closed | Jeremy Shulman | 2 |  | 2 | 2014-10-10 | Simpply | Design Meeting
|  | EA Review of Architecture | Closed | Mustafa Al-Salihi | 2 |  | 2 | 2014-10-10 | Simpply | Design Meeting
|  | EA Review of Architecture | Closed | Michael Yeaple | 2 |  | 2 | 2014-10-10 | Simpply | Design Meeting
|  | EA Review of Architecture | Closed | Curtis Burtner | 2 |  | 2 | 2014-10-10 | Simpply | Design Meeting
|  | Customer Meeting; Update and Practice Presentation | Closed | Jeremy Shulman | 2 |  | 2.25 | 2014-10-09 | Simpply | Progress Meeting
|  | Customer Meeting; Update and Practice Presentation | Closed | Mustafa Al-Salihi | 2 |  | 2.25 | 2014-10-09 | Simpply | Progress Meeting
|  | Customer Meeting; Update and Practice Presentation | Closed | Michael Yeaple | 2 |  | 2.25 | 2014-10-09 | Simpply | Progress Meeting
|  | Customer Meeting; Update and Practice Presentation | Closed | Curtis Burtner | 2 |  | 2.25 | 2014-10-09 | Simpply | Progress Meeting
|  | Regular Tuesday meeting | Closed | Jeremy Shulman | 2 |  | 2 | 2014-10-07 | Simpply | Design Meeting
|  | Regular Tuesday meeting | Closed | Mustafa Al-Salihi | 2 |  | 2 | 2014-10-07 | Simpply | Design Meeting
|  | Regular Tuesday meeting | Closed | Michael Yeaple | 2 |  | 2 | 2014-10-07 | Simpply | Design Meeting
|  | Regular Tuesday meeting | Closed | Curtis Burtner | 2 |  | 2 | 2014-10-07 | Simpply | Design Meeting
|  | Customer Meeting - Sprint Planning | Closed | Jeremy Shulman | 1.25 |  | 1.75 | 2014-10-16 | Simpply | Planning Meeting
|  | Customer Meeting - Sprint Planning | Closed | Mustafa Al-Salihi | 1.25 |  | 1.75 | 2014-10-16 | Simpply | Planning Meeting
|  | Customer Meeting - Sprint Planning | Closed | Michael Yeaple | 1.25 |  | 1.75 | 2014-10-16 | Simpply | Planning Meeting
|  | Customer Meeting - Sprint Planning | Closed | Curtis Burtner | 1.25 |  | 1.75 | 2014-10-16 | Simpply | Planning Meeting
|  | User Story Meeting (Break down, Pointing) | Closed | Curtis Burtner | 2 |  | 3.5 | 2014-10-15 | Simpply | Planning Meeting
|  | User Story Meeting (Break down, Pointing) | Closed | Jeremy Shulman | 2 |  | 3.5 | 2014-10-15 | Simpply | Planning Meeting
|  | User Story Meeting (Break down, Pointing) | Closed | Michael Yeaple | 2 |  | 3.5 | 2014-10-15 | Simpply | Planning Meeting
|  | TFS Permissions Issues | Closed | Michael Yeaple | 0.5 |  | 0.5 | 2014-10-13 | Simpply | Project Setup
|  | Team Meeting - Finish Design for Sprint 1 | Closed | Jeremy Shulman | 1 |  | 1 | 2014-10-21 | Simpply\Iteration 1 | Design Meeting
|  | Team Meeting - Finish Design for Sprint 1 | Closed | Mustafa Al-Salihi | 1 |  | 1 | 2014-10-21 | Simpply\Iteration 2 | Design Meeting
|  | Team Meeting - Finish Design for Sprint 1 | Closed | Michael Yeaple | 1 |  | 1 | 2014-10-21 | Simpply\Iteration 3 | Design Meeting
|  | Team Meeting - Finish Design for Sprint 1 | Closed | Curtis Burtner | 1 |  | 1 | 2014-10-21 | Simpply\Iteration 4 | Design Meeting
|  | Meeting with Michael - User Story Breakdown/Tasks | Closed | Curtis Burtner | 2 |  | 2 | 2014-10-20 | Simpply | Process/Project Management Meeting
|  | Meeting with Curtis - User Story Breakdown/Tasks | Closed | Michael Yeaple | 2 |  | 2 | 2014-10-20 | Simpply | Process/Project Management Meeting
|  | Template layout implementation | Closed | Michael Yeaple | 3 |  | 1 | 2014-10-28 | Simpply | Implementation

## Process Metrics
Iteration # | Date Start/End | Hours Estimated | Hours Actual | Hours Slipped | Percent Slippage\ | Velocity (story points) | Iteration Length (weeks) | StoryPoints/Week | Hours in Product | Hours Per Point | Web Role Metrics: | Complexity Min | Complexity Max | Complexity Avg | Engines Metrics: | Complexity Min | Complexity Max | Complexity Avg | Data Access Metrics: | Complexity Min | Complexity Max | Complexity Avg
1 | October 16 - November 13 | 108 | 121.3 | 13.3 | 10% | 18 | 4 | 4.5 | 32 | 1.78 |  | 1 | 29 | 1.86 |  | 1 | 4 | 1.0938 |  | 1 | 20 | 2.4783
2 | November 14 - December 12 | 212.7 | 237.7336 | 25.03363333 | 11% | 14 | 4 | 3.5 | 99.1703 | 7.1 |  | 1 | 26 | 1.9433 |  | 1 | 8 | 1.1653 |  | 1 | 6 | 1.54
3 | January 26 - February 12 | 89.5833 | 98.93 | 9.34667 | 9.45% | 24 | 2 | 12 | 82.4133 | 3.43388875 |  | 1 | 31 | 1.9379 |  | 1 | 8 | 1.4177 |  | 1 | 8 | 1.7447
4 | February 13 - February 26 | 68.25 | 72.5833 | 4.333337 | 5.97% | 20 | 2 | 10 | 41.8833 | 2.09416685 |  | 1 | 32 | 1.9553 |  | 1 | 8 | 1.5204 |  | 1 | 10 | 1.8269
5 | February 13 - February 26 | 67.9 | 97.1433 | 29.24333 | 30.10% | 22 | 2 | 11 | 76.16 | 3.461818182 |  | 1 | 34 | 1.9127 |  | 1 | 12 | 1.6951 |  | 1 | 10 | 1.807
6 | February 13 - February 26 | 77 | 86.9667 | 9.9667 | 11.46% | 19 | 2 | 9.5 | 34.9 | 1.836842105 |  | 1 | 48 | 1.9 |  | 1 | 9 | 1.3508 |  | 1 | 10 | 1.7895
7 | April 02 - April 16 | 64.7 | 74.5 | 9.8 | 13.15% | 16 | 2 | 8 | 65.45 | 4.090625 |  | 1 | 54 | 1.9339 |  | 1 | 12 | 1.4009 |  | 1 | 10 | 1.9111
8 | April 16 - April 30 | 112.5 | 114.05 | 1.55 | 1.36% | 5 | 2 | 2.5 | 79.55 | 15.91
9 | April 30 - May 14 |  |  | 0 |  | 0 | 2 | 0 | 19.75

## Code Metrics Iteration 2
Scope | Project | Namespace | Type | Member | Maintainability Index | Cyclomatic Complexity | Depth of Inheritance | Class Coupling | Lines of Code | Web | Engine | Access
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | ItemDetailModel(Item, List<Store>, List<SalesInformation>, List<Distribution>) | 22 | 29 |  | 23 | 154 | 1.853932584 | 1.09375 | 2.47826087
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ColumnPreferenceModel(string, string, string, List<string>, List<ColumnPreference>) | 38 | 16 |  | 14 | 51
Member | Simpply (Debug) | Simpply.Models | ItemExplorerModel | ItemExplorerModel(List<Item>, string, bool, List<ColumnPreference>) | 43 | 10 |  | 10 | 32
Member | Simpply (Debug) | Simpply.Controllers | ItemController | ItemDetail(long) : ActionResult | 56 | 7 |  | 19 | 12
Member | Simpply (Debug) | Simpply.Models | ItemExplorerModel | CreateHeaderCell(string, string, string, bool) : GridCellModel | 77 | 5 |  | 2 | 2
Member | Simpply (Debug) | Simpply.Helpers | WebHelper | GenerateActionUrl(string, string, Dictionary<string, string>) : string | 63 | 5 |  | 4 | 8
Member | Simpply (Debug) | Simpply.Controllers | AccountController | SaveColumnPreferences(ColumnPreferenceModel) : ActionResult | 55 | 4 |  | 9 | 12
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | GetColumnId(string) : long? | 67 | 3 |  | 1 | 7
Member | Simpply (Debug) | Simpply.Controllers | ItemController | ItemExplorer(string, bool) : ActionResult | 63 | 3 |  | 18 | 7
Member | Simpply (Debug) | Simpply.Helpers | WebHelper | GenerateActionUrl(string, string, string) : string | 73 | 2 |  | 1 | 4
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | GetColumnName(string) : string | 69 | 2 |  | 0 | 6
Member | Simpply (Debug) | Simpply.Controllers | ItemController | Search(string) : ActionResult | 66 | 2 |  | 7 | 7
Member | Simpply (Debug) | Simpply.Controllers | AccountController | AccountController(IColumnPreferenceProvider) | 87 | 1 |  | 2 | 2
Member | Simpply (Debug) | Simpply.Models | GridCellModel | ActionUrl.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | ActionUrl.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridRowModel | Aggregate_Cells.get() : List<GridCellModel> | 98 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | GridRowModel | Aggregate_Cells.set(List<GridCellModel>) : void | 95 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | Aggregate.get() : GridModel | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | Aggregate.set(GridModel) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel.AggregateModel | AggregateModel() | 100 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply | MvcApplication | Application_Start() : void | 69 | 1 |  | 11 | 7
Member | Simpply (Debug) | Simpply.Controllers | BaseController | BaseController() | 100 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply | BundleConfig | BundleConfig() | 100 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel.AggregateModel | CalculatedInventory.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel.AggregateModel | CalculatedInventory.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridRowModel | Cells.get() : List<GridCellModel> | 98 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | GridRowModel | Cells.set(List<GridCellModel>) : void | 95 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ColumnPreferenceModel() | 73 | 1 |  | 2 | 5
Member | Simpply (Debug) | Simpply.Models | ItemExplorerModel | ColumnPreferences.get() : ColumnPreferenceModel | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ItemExplorerModel | ColumnPreferences.set(ColumnPreferenceModel) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Controllers | StoreController | CompareToMultiplestores() : ActionResult | 89 | 1 |  | 2 | 2
Member | Simpply (Debug) | Simpply.Controllers | StoreController | CompareTostore() : ActionResult | 89 | 1 |  | 2 | 2
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ControllerAction.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ControllerAction.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ControllerName.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ControllerName.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | CssClasses.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridRowModel | CssClasses.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | CssClasses.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridRowModel | CssClasses.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply | FilterConfig | FilterConfig() | 100 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | Grid.get() : GridModel | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ItemExplorerModel | Grid.get() : GridModel | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | Grid.set(GridModel) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ItemExplorerModel | Grid.set(GridModel) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | GridCellModel() | 100 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | GridModel() | 78 | 1 |  | 2 | 3
Member | Simpply (Debug) | Simpply.Models | GridRowModel | GridRowModel() | 87 | 1 |  | 2 | 2
Member | Simpply (Debug) | Simpply.Models | GridModel | Header.get() : GridRowModel | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | Header.set(GridRowModel) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | HiddenColumns.get() : List<string> | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | HiddenColumns.set(List<string>) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | HiddenColumnsList.get() : List<SelectListItem> | 98 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | HiddenColumnsList.set(List<SelectListItem>) : void | 95 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | GridRowModel | IsHeader.get() : bool | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridRowModel | IsHeader.set(bool) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Controllers | ItemController | ItemController(IItemProvider, IStoreProvider, ISalesInformationProvider, IDistributionProvider, IColumnPreferenceProvider) | 71 | 1 |  | 6 | 6
Member | Simpply (Debug) | Simpply.Controllers | BaseController | JsonActionResult(JsonReturnType, string, string, string, object) : ActionResult | 68 | 1 |  | 5 | 6
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel.AggregateModel | LastYearSales.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel.AggregateModel | LastYearSales.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply | MvcApplication | MvcApplication() | 100 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | Name.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | Name.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel.AggregateModel | PercentageTotal.get() : double | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel.AggregateModel | PercentageTotal.set(double) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply | WebApiConfig | Register(HttpConfiguration) : void | 89 | 1 |  | 4 | 1
Member | Simpply (Debug) | Simpply | AuthConfig | RegisterAuth() : void | 100 | 1 |  | 0 | 0
Member | Simpply (Debug) | Simpply | BundleConfig | RegisterBundles(BundleCollection) : void | 64 | 1 |  | 4 | 6
Member | Simpply (Debug) | Simpply.App_Start | AutofacConfig | RegisterComponents() : void | 70 | 1 |  | 10 | 5
Member | Simpply (Debug) | Simpply | FilterConfig | RegisterGlobalFilters(GlobalFilterCollection) : void | 94 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply | RouteConfig | RegisterRoutes(RouteCollection) : void | 82 | 1 |  | 3 | 2
Member | Simpply (Debug) | Simpply | RouteConfig | RouteConfig() | 100 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | Rows.get() : List<GridRowModel> | 98 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | Rows.set(List<GridRowModel>) : void | 95 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel.AggregateModel | Sellthrough.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel.AggregateModel | Sellthrough.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ShownColumns.get() : List<string> | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ShownColumns.set(List<string>) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ShownColumnsList.get() : List<SelectListItem> | 98 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ShownColumnsList.set(List<SelectListItem>) : void | 95 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Controllers | StoreController | StoreController() | 100 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | Table.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | Table.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel.AggregateModel | UnitsReceived.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel.AggregateModel | UnitsReceived.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel.AggregateModel | UnitsSold.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel.AggregateModel | UnitsSold.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | Value.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | Value.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | CalculatedInventory.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | CalculatedInventory.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Account | ColumnPreference | Column.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Account | ColumnPreference | Column.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Account | ColumnPreference | ColumnPreference() | 100 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Account | ColumnPreference | Controller.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Account | ColumnPreference | Controller.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Account | ColumnPreference | ControllerAction.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Account | ColumnPreference | ControllerAction.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Item | Description.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Item | Description.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Store | Distribution.get() : Distribution | 98 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Store | Distribution.set(Distribution) : void | 95 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Distribution | Distribution() | 100 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Example | Example() | 100 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Distribution | Id.get() : long | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Example | Id.get() : long | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Item | Id.get() : long | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | Id.get() : long | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Store | Id.get() : long | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Account | ColumnPreference | Id.get() : long? | 98 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Account | ColumnPreference | Id.set(long?) : void | 95 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Distribution | Id.set(long) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Example | Id.set(long) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Item | Id.set(long) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | Id.set(long) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Store | Id.set(long) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Item | Item() | 100 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Distribution | ItemAmount.get() : long | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Distribution | ItemAmount.set(long) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Distribution | ItemId.get() : long | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | ItemId.get() : long | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Distribution | ItemId.set(long) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | ItemId.set(long) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | LastYearsSales.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | LastYearsSales.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Item | Name.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Store | Name.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Item | Name.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Store | Name.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Account | ColumnPreference | Order.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Account | ColumnPreference | Order.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | PercentageOfTotal.get() : double | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | PercentageOfTotal.set(double) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Store | Sales.get() : SalesInformation | 98 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Store | Sales.set(SalesInformation) : void | 95 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | SalesInformation() | 100 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Store | Segmentation.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Store | Segmentation.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | Sellthrough.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | Sellthrough.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Account | ColumnPreference | ShowColumn.get() : bool | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Account | ColumnPreference | ShowColumn.set(bool) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Store | Store() | 100 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Distribution | StoreId.get() : long | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | StoreId.get() : long | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Distribution | StoreId.set(long) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | StoreId.set(long) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Item | stores.get() : List<Store> | 98 | 1 |  | 2 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Item | stores.set(List<Store>) : void | 95 | 1 |  | 2 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Account | ColumnPreference | Table.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Account | ColumnPreference | Table.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Distribution | Type.get() : AlgorithmType | 98 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Distribution | Type.set(AlgorithmType) : void | 95 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | UnitsReceived.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | UnitsReceived.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | UnitsSold.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | UnitsSold.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ItemProvider | Get(string, bool) : List<Item> | 46 | 20 |  | 4 | 26
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ItemProvider | GetDetailsDapper(long) : Item | 55 | 5 |  | 15 | 13
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ColumnPreferenceProvider | Save(List<ColumnPreference>) : void | 52 | 4 |  | 15 | 15
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | SalesInformationProvider | Get(long, long) : SalesInformation | 70 | 3 |  | 5 | 5
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ItemProvider | Get(long) : Item | 73 | 2 |  | 5 | 4
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | DistributionProvider | Get(long) : List<Distribution> | 69 | 2 |  | 10 | 5
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | StoreProvider | Get(long) : Store | 71 | 2 |  | 5 | 5
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ColumnPreferenceProvider | Get(string, string, string) : List<ColumnPreference> | 66 | 2 |  | 10 | 7
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ItemProvider | GetDapper(long?, string, string, bool?) : List<Item> | 69 | 2 |  | 10 | 5
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ExampleProvider | SelectExample(int) : Example | 70 | 2 |  | 9 | 5
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access | AccessModule | AccessModule() | 100 | 1 |  | 1 | 1
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | BaseProvider | BaseProvider() | 83 | 1 |  | 3 | 2
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ColumnPreferenceProvider | ColumnPreferenceProvider() | 100 | 1 |  | 1 | 1
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | BaseProvider | connectionString.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | BaseProvider | connectionString.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | DistributionProvider | DistributionProvider() | 100 | 1 |  | 1 | 1
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ExampleProvider | ExampleProvider() | 100 | 1 |  | 1 | 1
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | ISalesInformationProvider | Get() : List<SalesInformation> | 100 | 1 |  | 2 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | SalesInformationProvider | Get() : List<SalesInformation> | 91 | 1 |  | 2 | 2
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IStoreProvider | Get() : List<Store> | 100 | 1 |  | 2 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | StoreProvider | Get() : List<Store> | 91 | 1 |  | 2 | 2
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | ISalesInformationProvider | Get(long, long) : SalesInformation | 100 | 1 |  | 1 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IItemProvider | Get(long) : Item | 100 | 1 |  | 1 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IDistributionProvider | Get(long) : List<Distribution> | 100 | 1 |  | 2 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IStoreProvider | Get(long) : Store | 100 | 1 |  | 1 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IItemProvider | Get(string, bool) : List<Item> | 100 | 1 |  | 2 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IColumnPreferenceProvider | Get(string, string, string) : List<ColumnPreference> | 100 | 1 |  | 2 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IItemProvider | GetDapper(long?, string, string, bool?) : List<Item> | 100 | 1 |  | 3 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IItemProvider | GetDetailsDapper(long) : Item | 100 | 1 |  | 1 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ItemProvider | ItemProvider() | 74 | 1 |  | 3 | 2
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access | AccessModule | Load(ContainerBuilder) : void | 65 | 1 |  | 16 | 6
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | SalesInformationProvider | SalesInformationProvider() | 68 | 1 |  | 3 | 2
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IItemProvider | Save(Item) : void | 100 | 1 |  | 1 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ItemProvider | Save(Item) : void | 100 | 1 |  | 1 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IColumnPreferenceProvider | Save(List<ColumnPreference>) : void | 100 | 1 |  | 2 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IItemProvider | Save(List<Item>) : void | 100 | 1 |  | 2 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ItemProvider | Save(List<Item>) : void | 100 | 1 |  | 2 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | StoreProvider | StoreProvider() | 76 | 1 |  | 3 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Controllers | JobsController | Post(JobRequest) : object | 55 | 4 |  | 9 | 15
Member | Simpply.Engine (Debug) | Simpply.Engine | WebApiApplication | Application_Start() : void | 73 | 1 |  | 9 | 5
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | BaseJob | BaseJob() | 87 | 1 |  | 0 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | BaseJob | BaseJob(string) | 87 | 1 |  | 0 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine | BundleConfig | BundleConfig() | 100 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobRequest | Data.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobRequest | Data.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | BaseJob | Execute() : bool | 100 | 1 |  | 0 | 0
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunAlgorithm | Execute() : bool | 91 | 1 |  | 0 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | ParseWegmansData | Execute() : bool | 86 | 1 |  | 1 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine | FilterConfig | FilterConfig() | 100 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Controllers | JobsController | Get() : string | 91 | 1 |  | 1 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Controllers | HomeController | HomeController() | 100 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Controllers | HomeController | Index() : ActionResult | 89 | 1 |  | 2 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobRequest | Job.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobRequest | Job.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | JobInvoker | JobInvoker() | 100 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobRequest | JobRequest() | 100 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Controllers | JobsController | JobsController() | 100 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | ParseWegmansData | ParseWegmansData(string) | 84 | 1 |  | 3 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | ParseWegmansDataModel | ParseWegmansDataModel() | 100 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | ParseWegmansData | ReadWegmansData() : void | 100 | 1 |  | 0 | 0
Member | Simpply.Engine (Debug) | Simpply.Engine | WebApiConfig | Register(HttpConfiguration) : void | 82 | 1 |  | 5 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine | BundleConfig | RegisterBundles(BundleCollection) : void | 100 | 1 |  | 1 | 0
Member | Simpply.Engine (Debug) | Simpply.Engine | FilterConfig | RegisterGlobalFilters(GlobalFilterCollection) : void | 94 | 1 |  | 2 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine | RouteConfig | RegisterRoutes(RouteCollection) : void | 82 | 1 |  | 4 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine | RouteConfig | RouteConfig() | 100 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunAlgorithm | RunAlgorithm(string) | 98 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | JobInvoker | ScheduleJob(BaseJob) : bool | 87 | 1 |  | 1 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | ParseWegmansDataModel | Test.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | ParseWegmansDataModel | Test.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine | WebApiApplication | WebApiApplication() | 100 | 1 |  | 1 | 1
Member | Simpply.Global (Debug) | Simpply.Global | Constants.ControllerAction.Account | Account() | 100 | 1 |  | 0 | 1
Member | Simpply.Global (Debug) | Simpply.Global | Constants | Constants() | 100 | 1 |  | 0 | 1
Member | Simpply.Global (Debug) | Simpply.Global | Constants.Controller | Controller() | 100 | 1 |  | 0 | 1
Member | Simpply.Global (Debug) | Simpply.Global | Constants.ControllerAction | ControllerAction() | 100 | 1 |  | 0 | 1
Member | Simpply.Global (Debug) | Simpply.Global | Constants.ControllerAction.Item | Item() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | AccountControllerTest | SaveColumnPreferences() : void | 55 | 5 |  | 22 | 12
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | ItemControllerTest | ItemDetail() : void | 62 | 3 |  | 21 | 7
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | ItemControllerTest | ItemExplorer() : void | 60 | 3 |  | 19 | 8
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | AccountControllerTest | AccountControllerTest() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | BaseProviderTest | BaseProviderTest() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ColumnPreferenceProviderTest | ColumnPreferenceProviderTest() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ColumnPreferenceProviderTest | Get() : void | 82 | 1 |  | 6 | 2
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ItemProviderTest | GetItem() : void | 100 | 1 |  | 1 | 0
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ItemProviderTest | GetItems() : void | 72 | 1 |  | 6 | 5
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | SalesInformationProviderTest | GetSale() : void | 100 | 1 |  | 1 | 0
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | SalesInformationProviderTest | GetSales() : void | 100 | 1 |  | 1 | 0
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | StoreProviderTest | GetStore() : void | 100 | 1 |  | 1 | 0
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | StoreProviderTest | GetStores() : void | 100 | 1 |  | 1 | 0
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | ItemControllerTest | ItemControllerTest() | 73 | 1 |  | 1 | 3
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ItemProviderTest | ItemProviderTest() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | SalesInformationProviderTest | SalesInformationProviderTest() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ColumnPreferenceProviderTest | Save() : void | 75 | 1 |  | 4 | 2
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ItemProviderTest | SaveItem() : void | 100 | 1 |  | 1 | 0
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ItemProviderTest | SaveItems() : void | 100 | 1 |  | 1 | 0
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | StoreProviderTest | StoreProviderTest() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | BaseProviderTest | TestInit() : void | 94 | 1 |  | 3 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ColumnPreferenceProviderTest | TestInit() : void | 94 | 1 |  | 3 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ItemProviderTest | TestInit() : void | 94 | 1 |  | 3 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | SalesInformationProviderTest | TestInit() : void | 94 | 1 |  | 3 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | StoreProviderTest | TestInit() : void | 94 | 1 |  | 3 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | AccountControllerTest | TestInit() : void | 92 | 1 |  | 3 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | ItemControllerTest | TestInit() : void | 67 | 1 |  | 8 | 6
Member | Simpply.Util (Debug) | Simpply.Util.Extensions | CollectionExtensions | IsEmpty<T>(this ICollection<T>) : bool | 84 | 2 |  | 2 | 2
Member | Simpply.Util (Debug) | Simpply.Util.Extensions | StringExtensions | IsNullOrWhiteSpace(this string) : bool | 87 | 1 |  | 1 | 2

## Code Metrics Iteration 3
Scope | Project | Namespace | Type | Member | Maintainability Index | Cyclomatic Complexity | Depth of Inheritance | Class Coupling | Lines of Code | Web | Engine | Access
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | ItemDetailModel(Item, List<Store>, List<SalesInformation>, List<Distribution>) | 23 | 26 |  | 23 | 145 | 1.943262411 | 1.165289256 | 1.54
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ColumnPreferenceModel(string, string, string, List<Column>, List<ColumnPreference>) | 32 | 25 |  | 17 | 77
Member | Simpply (Debug) | Simpply.Models | SeasonExplorerModel | SeasonExplorerModel(List<SeasonInfo>, string, bool, bool, List<ColumnPreference>) | 33 | 20 |  | 15 | 59
Member | Simpply (Debug) | Simpply.Models.POG | PlanogramExplorerModel | PlanogramExplorerModel(List<Planogram>, string, bool, bool, List<ColumnPreference>, int?) | 36 | 16 |  | 16 | 48
Member | Simpply (Debug) | Simpply.Models | ItemExplorerModel | ItemExplorerModel(List<Item>, string, int?, string, bool, List<ColumnPreference>) | 44 | 9 |  | 12 | 31
Member | Simpply (Debug) | Simpply.Models | BreadcrumbTrailModel | AdjustBreadcrumbsTrail(string, string) : void | 55 | 7 |  | 3 | 17
Member | Simpply (Debug) | Simpply.Controllers | ItemController | ItemDetail(long) : ActionResult | 56 | 7 |  | 19 | 12
Member | Simpply (Debug) | Simpply.Models | ItemExplorerModel | CreateHeaderCell(string, string, int?, string, string, bool) : GridCellModel | 63 | 5 |  | 4 | 7
Member | Simpply (Debug) | Simpply.Helpers | WebHelper | GenerateActionUrl(string, string, Dictionary<string, string>) : string | 63 | 5 |  | 4 | 8
Member | Simpply (Debug) | Simpply.Controllers | AccountController | SaveColumnPreferences(ColumnPreferenceModel) : ActionResult | 55 | 4 |  | 9 | 12
Member | Simpply (Debug) | Simpply.Models.POG | PlanogramExplorerModel | FormatActionUrl(string, string, bool, bool, int?) : string | 67 | 3 |  | 2 | 6
Member | Simpply (Debug) | Simpply.Controllers | BreadcrumbController | GetBreadCrumbs() : ActionResult | 59 | 3 |  | 6 | 12
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | GetColumnId(string) : long? | 67 | 3 |  | 1 | 7
Member | Simpply (Debug) | Simpply.Controllers | ItemController | ItemExplorer(string, int?, string, bool) : ActionResult | 63 | 3 |  | 18 | 7
Member | Simpply (Debug) | Simpply.Controllers | PlanogramController | PlanogramExplorer(int?, bool, string, bool) : ActionResult | 63 | 3 |  | 19 | 7
Member | Simpply (Debug) | Simpply.Controllers | SeasonController | SeasonExplorer(bool, string, bool) : ActionResult | 63 | 3 |  | 17 | 7
Member | Simpply (Debug) | Simpply.Models.POG | PlanogramExplorerModel | CreateHeaderCell(string, string, string, bool, bool, int?) : GridCellModel | 78 | 2 |  | 2 | 2
Member | Simpply (Debug) | Simpply.Models | SeasonExplorerModel | CreateHeaderCell(string, string, string, bool, bool) : GridCellModel | 78 | 2 |  | 1 | 2
Member | Simpply (Debug) | Simpply.Models | SeasonExplorerModel | FormatActionUrl(string, string, bool, bool) : string | 73 | 2 |  | 1 | 4
Member | Simpply (Debug) | Simpply.Helpers | WebHelper | GenerateActionUrl(string, string, string) : string | 73 | 2 |  | 1 | 4
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | GetColumnName(string) : string | 69 | 2 |  | 0 | 6
Member | Simpply (Debug) | Simpply.Helpers | WebHelper | GetControllerActionParameters(string) : string | 72 | 2 |  | 0 | 5
Member | Simpply (Debug) | Simpply.Controllers | ItemController | Search(string) : ActionResult | 64 | 2 |  | 7 | 8
Member | Simpply (Debug) | Simpply.Controllers | AccountController | AccountController(IColumnPreferenceProvider) | 87 | 1 |  | 2 | 2
Member | Simpply (Debug) | Simpply.Models | BreadcrumbModel | ActionUrl.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | ActionUrl.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | BreadcrumbModel | ActionUrl.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | ActionUrl.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | SeasonExplorerModel | ActiveOnly.get() : bool | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models.POG | PlanogramExplorerModel | ActiveOnly.get() : bool | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | SeasonExplorerModel | ActiveOnly.set(bool) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models.POG | PlanogramExplorerModel | ActiveOnly.set(bool) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridRowModel | Aggregate_Cells.get() : List<GridCellModel> | 98 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | GridRowModel | Aggregate_Cells.set(List<GridCellModel>) : void | 95 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | Aggregate.get() : GridModel | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | Aggregate.set(GridModel) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel.AggregateModel | AggregateModel() | 100 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply | MvcApplication | Application_Start() : void | 69 | 1 |  | 11 | 7
Member | Simpply (Debug) | Simpply.Controllers | BaseController | BaseController() | 100 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Controllers | BreadcrumbController | BreadcrumbController() | 100 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | BreadcrumbModel | BreadcrumbModel() | 100 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | BreadcrumbTrailModel | BreadcrumbTrailModel() | 62 | 1 |  | 3 | 8
Member | Simpply (Debug) | Simpply | BundleConfig | BundleConfig() | 100 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel.AggregateModel | CalculatedInventory.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel.AggregateModel | CalculatedInventory.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridRowModel | Cells.get() : List<GridCellModel> | 98 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | GridRowModel | Cells.set(List<GridCellModel>) : void | 95 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | Column | Column() | 100 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ColumnPreferenceModel() | 71 | 1 |  | 2 | 6
Member | Simpply (Debug) | Simpply.Models | ItemExplorerModel | ColumnPreferences.get() : ColumnPreferenceModel | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | SeasonExplorerModel | ColumnPreferences.get() : ColumnPreferenceModel | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models.POG | PlanogramExplorerModel | ColumnPreferences.get() : ColumnPreferenceModel | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ItemExplorerModel | ColumnPreferences.set(ColumnPreferenceModel) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | SeasonExplorerModel | ColumnPreferences.set(ColumnPreferenceModel) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models.POG | PlanogramExplorerModel | ColumnPreferences.set(ColumnPreferenceModel) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Controllers | StoreController | CompareToMultiplestores() : ActionResult | 89 | 1 |  | 2 | 2
Member | Simpply (Debug) | Simpply.Controllers | StoreController | CompareTostore() : ActionResult | 89 | 1 |  | 2 | 2
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ControllerAction.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ControllerAction.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ControllerName.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ControllerName.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | CssClasses.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridRowModel | CssClasses.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | CssClasses.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridRowModel | CssClasses.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | Column | DisplayName.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | Column | DisplayName.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply | FilterConfig | FilterConfig() | 100 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Helpers | WebHelper | GetControllerActionName(string) : string | 78 | 1 |  | 0 | 3
Member | Simpply (Debug) | Simpply.Helpers | WebHelper | GetControllerName(string) : string | 78 | 1 |  | 0 | 3
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | Grid.get() : GridModel | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ItemExplorerModel | Grid.get() : GridModel | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | SeasonExplorerModel | Grid.get() : GridModel | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models.POG | PlanogramExplorerModel | Grid.get() : GridModel | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | Grid.set(GridModel) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ItemExplorerModel | Grid.set(GridModel) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | SeasonExplorerModel | Grid.set(GridModel) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models.POG | PlanogramExplorerModel | Grid.set(GridModel) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | GridCellModel() | 82 | 1 |  | 0 | 3
Member | Simpply (Debug) | Simpply.Models | GridModel | GridModel() | 75 | 1 |  | 2 | 4
Member | Simpply (Debug) | Simpply.Models | GridRowModel | GridRowModel() | 87 | 1 |  | 2 | 2
Member | Simpply (Debug) | Simpply.Models | GridModel | Header.get() : GridRowModel | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | Header.set(GridRowModel) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | HiddenColumns.get() : List<string> | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | HiddenColumns.set(List<string>) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | HiddenColumnsList.get() : List<SelectListItem> | 98 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | HiddenColumnsList.set(List<SelectListItem>) : void | 95 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models.POG | PlanogramExplorerModel | InactivePlanogramURL.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models.POG | PlanogramExplorerModel | InactivePlanogramURL.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | SeasonExplorerModel | InactiveSeasonURL.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | SeasonExplorerModel | InactiveSeasonURL.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridRowModel | IsHeader.get() : bool | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridRowModel | IsHeader.set(bool) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | IsSorted.get() : bool | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | IsSorted.set(bool) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | IsSortedDescending.get() : bool | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | IsSortedDescending.set(bool) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Controllers | ItemController | ItemController(IItemProvider, IStoreProvider, ISalesInformationProvider, IDistributionProvider, IColumnPreferenceProvider) | 71 | 1 |  | 6 | 6
Member | Simpply (Debug) | Simpply.Controllers | BaseController | JsonActionResult(JsonReturnType, string, string, string, object) : ActionResult | 68 | 1 |  | 5 | 6
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel.AggregateModel | LastYearSales.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel.AggregateModel | LastYearSales.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply | MvcApplication | MvcApplication() | 100 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | Column | Name.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | Name.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | Column | Name.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | Name.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel.AggregateModel | PercentageTotal.get() : double | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel.AggregateModel | PercentageTotal.set(double) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Controllers | PlanogramController | PlanogramController(IPlanogramProvider, IColumnPreferenceProvider) | 81 | 1 |  | 3 | 3
Member | Simpply (Debug) | Simpply | WebApiConfig | Register(HttpConfiguration) : void | 89 | 1 |  | 4 | 1
Member | Simpply (Debug) | Simpply | AuthConfig | RegisterAuth() : void | 100 | 1 |  | 0 | 0
Member | Simpply (Debug) | Simpply | BundleConfig | RegisterBundles(BundleCollection) : void | 64 | 1 |  | 4 | 6
Member | Simpply (Debug) | Simpply.App_Start | AutofacConfig | RegisterComponents() : void | 70 | 1 |  | 10 | 5
Member | Simpply (Debug) | Simpply | FilterConfig | RegisterGlobalFilters(GlobalFilterCollection) : void | 94 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply | RouteConfig | RegisterRoutes(RouteCollection) : void | 82 | 1 |  | 3 | 2
Member | Simpply (Debug) | Simpply.Controllers | BaseController | Root() : ActionResult | 86 | 1 |  | 2 | 2
Member | Simpply (Debug) | Simpply | RouteConfig | RouteConfig() | 100 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | Rows.get() : List<GridRowModel> | 98 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | Rows.set(List<GridRowModel>) : void | 95 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Controllers | SeasonController | SeasonController(ISeasonProvider, IColumnPreferenceProvider) | 81 | 1 |  | 3 | 3
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel.AggregateModel | Sellthrough.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel.AggregateModel | Sellthrough.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ShownColumns.get() : List<string> | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ShownColumns.set(List<string>) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ShownColumnsDefault.get() : List<SelectListItem> | 98 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ShownColumnsDefault.set(List<SelectListItem>) : void | 95 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ShownColumnsList.get() : List<SelectListItem> | 98 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ShownColumnsList.set(List<SelectListItem>) : void | 95 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Controllers | StoreController | StoreController() | 100 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | Table.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | Table.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | tableCondensed.get() : bool | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | tableCondensed.set(bool) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel.AggregateModel | UnitsReceived.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel.AggregateModel | UnitsReceived.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel.AggregateModel | UnitsSold.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel.AggregateModel | UnitsSold.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | BreadcrumbModel | Value.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | Value.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | BreadcrumbModel | Value.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | Value.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SeasonInfo | AggregateData7Days.get() : AggregateItemData | 98 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SeasonInfo | AggregateData7Days.set(AggregateItemData) : void | 95 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SeasonInfo | AggregateDataSeasonToDate.get() : AggregateItemData | 98 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data.POG | Planogram | AggregateDataSeasonToDate.get() : AggregateItemData | 98 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SeasonInfo | AggregateDataSeasonToDate.set(AggregateItemData) : void | 95 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data.POG | Planogram | AggregateDataSeasonToDate.set(AggregateItemData) : void | 95 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Shared | AggregateItemData | AggregateItemData() | 100 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SeasonInfo | BalanceOnHand.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.POG | Planogram | BalanceOnHand.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Item | BalanceOnHand.get() : long | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SeasonInfo | BalanceOnHand.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.POG | Planogram | BalanceOnHand.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Item | BalanceOnHand.set(long) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | CalculatedInventory.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | CalculatedInventory.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Account | ColumnPreference | Column.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Account | ColumnPreference | Column.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Account | ColumnPreference | ColumnPreference() | 100 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Account | ColumnPreference | Controller.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Account | ColumnPreference | Controller.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Account | ColumnPreference | ControllerAction.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Account | ColumnPreference | ControllerAction.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Item | Description.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Item | Description.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Store | Distribution.get() : Distribution | 98 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Store | Distribution.set(Distribution) : void | 95 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Distribution | Distribution() | 100 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SeasonInfo | EndDate.get() : DateTime | 98 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data.POG | Planogram | EndDate.get() : DateTime | 98 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SeasonInfo | EndDate.set(DateTime) : void | 95 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data.POG | Planogram | EndDate.set(DateTime) : void | 95 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Example | Example() | 100 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SeasonInfo | Id.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.POG | Planogram | Id.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Distribution | Id.get() : long | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Example | Id.get() : long | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Item | Id.get() : long | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Job | Id.get() : long | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | Id.get() : long | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Store | Id.get() : long | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Account | ColumnPreference | Id.get() : long? | 98 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SeasonInfo | Id.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.POG | Planogram | Id.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Account | ColumnPreference | Id.set(long?) : void | 95 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Distribution | Id.set(long) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Example | Id.set(long) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Item | Id.set(long) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Job | Id.set(long) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | Id.set(long) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Store | Id.set(long) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Item | Item() | 100 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Distribution | ItemAmount.get() : long | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Distribution | ItemAmount.set(long) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Distribution | ItemId.get() : long | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | ItemId.get() : long | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Distribution | ItemId.set(long) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | ItemId.set(long) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Job | Job() | 100 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | LastYearsSales.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | LastYearsSales.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Item | Name.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Job | Name.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SeasonInfo | Name.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Store | Name.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.POG | Planogram | Name.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Item | Name.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Job | Name.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SeasonInfo | Name.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Store | Name.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.POG | Planogram | Name.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Account | ColumnPreference | Order.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Account | ColumnPreference | Order.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | PercentageOfTotal.get() : double | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | PercentageOfTotal.set(double) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.POG | Planogram | Planogram() | 100 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Job | Progress.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Job | Progress.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Job | ProgressPercent.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Job | ProgressPercent.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Store | Sales.get() : SalesInformation | 98 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Store | Sales.set(SalesInformation) : void | 95 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | SalesInformation() | 100 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SeasonInfo | SeasonInfo() | 100 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Store | Segmentation.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Store | Segmentation.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Shared | AggregateItemData | SellThrough.get() : decimal | 98 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | Sellthrough.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Shared | AggregateItemData | SellThrough.set(decimal) : void | 95 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | Sellthrough.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Account | ColumnPreference | ShowColumn.get() : bool | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Account | ColumnPreference | ShowColumn.set(bool) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SeasonInfo | StartDate.get() : DateTime | 98 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data.POG | Planogram | StartDate.get() : DateTime | 98 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SeasonInfo | StartDate.set(DateTime) : void | 95 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data.POG | Planogram | StartDate.set(DateTime) : void | 95 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Store | Store() | 100 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Distribution | StoreId.get() : long | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | StoreId.get() : long | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Distribution | StoreId.set(long) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | StoreId.set(long) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Item | Stores.get() : List<Store> | 98 | 1 |  | 2 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Item | Stores.set(List<Store>) : void | 95 | 1 |  | 2 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Account | ColumnPreference | Table.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Account | ColumnPreference | Table.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Distribution | Type.get() : AlgorithmType | 98 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Distribution | Type.set(AlgorithmType) : void | 95 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | UnitsReceived.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Shared | AggregateItemData | UnitsReceived.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | UnitsReceived.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Shared | AggregateItemData | UnitsReceived.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Shared | AggregateItemData | UnitsShrunk.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Shared | AggregateItemData | UnitsShrunk.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | UnitsSold.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Shared | AggregateItemData | UnitsSold.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | UnitsSold.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Shared | AggregateItemData | UnitsSold.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ItemProvider | GetDetails(long) : Item | 54 | 6 |  | 15 | 15
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | PlanogramProvider | Get(bool, int?, string, bool) : List<Planogram> | 60 | 4 |  | 13 | 10
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | SeasonProvider | Get(bool, string, bool) : List<SeasonInfo> | 60 | 4 |  | 13 | 10
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ColumnPreferenceProvider | Save(List<ColumnPreference>) : void | 52 | 4 |  | 15 | 15
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | DistributionProvider | SaveMultiple(List<Distribution>) : void | 53 | 4 |  | 14 | 15
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | SalesInformationProvider | Get(long, long) : SalesInformation | 70 | 3 |  | 5 | 5
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ItemProvider | Get(long?, string, int?, string, bool?) : List<Item> | 69 | 2 |  | 10 | 5
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | DistributionProvider | Get(long) : List<Distribution> | 69 | 2 |  | 10 | 5
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | StoreProvider | Get(long) : Store | 71 | 2 |  | 5 | 5
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ColumnPreferenceProvider | Get(string, string, string) : List<ColumnPreference> | 66 | 2 |  | 10 | 7
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ItemProvider | GetIds() : List<long> | 69 | 2 |  | 9 | 5
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | JobProvider | Insert(string) : long | 69 | 2 |  | 8 | 5
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ExampleProvider | SelectExample(int) : Example | 70 | 2 |  | 9 | 5
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | JobProvider | UpdateProgress(long, string, int) : void | 72 | 2 |  | 7 | 4
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access | AccessModule | AccessModule() | 100 | 1 |  | 1 | 1
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | BaseProvider | BaseProvider() | 83 | 1 |  | 3 | 2
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ColumnPreferenceProvider | ColumnPreferenceProvider() | 100 | 1 |  | 1 | 1
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | BaseProvider | connectionString.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | BaseProvider | connectionString.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | DistributionProvider | DistributionProvider() | 100 | 1 |  | 1 | 1
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ExampleProvider | ExampleProvider() | 100 | 1 |  | 1 | 1
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | ISalesInformationProvider | Get() : List<SalesInformation> | 100 | 1 |  | 2 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | SalesInformationProvider | Get() : List<SalesInformation> | 91 | 1 |  | 2 | 2
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IStoreProvider | Get() : List<Store> | 100 | 1 |  | 2 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | StoreProvider | Get() : List<Store> | 91 | 1 |  | 2 | 2
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IPlanogramProvider | Get(bool, int?, string, bool) : List<Planogram> | 100 | 1 |  | 3 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | ISeasonProvider | Get(bool, string, bool) : List<SeasonInfo> | 100 | 1 |  | 2 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | ISalesInformationProvider | Get(long, long) : SalesInformation | 100 | 1 |  | 1 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IItemProvider | Get(long?, string, int?, string, bool?) : List<Item> | 100 | 1 |  | 3 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IJobProvider | Get(long) : Job | 100 | 1 |  | 1 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | JobProvider | Get(long) : Job | 91 | 1 |  | 1 | 2
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IDistributionProvider | Get(long) : List<Distribution> | 100 | 1 |  | 2 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IStoreProvider | Get(long) : Store | 100 | 1 |  | 1 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IColumnPreferenceProvider | Get(string, string, string) : List<ColumnPreference> | 100 | 1 |  | 2 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IItemProvider | GetDetails(long) : Item | 100 | 1 |  | 1 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IJobProvider | Insert(string) : long | 100 | 1 |  | 0 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ItemProvider | ItemProvider() | 100 | 1 |  | 1 | 1
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | JobProvider | JobProvider() | 100 | 1 |  | 1 | 1
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access | AccessModule | Load(ContainerBuilder) : void | 61 | 1 |  | 20 | 8
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | PlanogramProvider | PlanogramProvider() | 100 | 1 |  | 1 | 1
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | SalesInformationProvider | SalesInformationProvider() | 68 | 1 |  | 3 | 2
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IItemProvider | Save(Item) : void | 100 | 1 |  | 1 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ItemProvider | Save(Item) : void | 100 | 1 |  | 1 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IColumnPreferenceProvider | Save(List<ColumnPreference>) : void | 100 | 1 |  | 2 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IItemProvider | Save(List<Item>) : void | 100 | 1 |  | 2 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ItemProvider | Save(List<Item>) : void | 100 | 1 |  | 2 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IDistributionProvider | SaveMultiple(List<Distribution>) : void | 100 | 1 |  | 2 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | SeasonProvider | SeasonProvider() | 100 | 1 |  | 1 | 1
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | StoreProvider | StoreProvider() | 76 | 1 |  | 3 | 2
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IJobProvider | UpdateProgress(long, string, int) : void | 100 | 1 |  | 0 | 0
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | JobInvoker | ScheduleJob(BaseJob) : JobResponse | 48 | 8 |  | 9 | 27
Member | Simpply.Engine (Debug) | Simpply.Engine.Controllers | JobsController | Post(JobRequest) : object | 54 | 6 |  | 13 | 17
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | JobInvoker | GetInstance() : JobInvoker | 67 | 4 |  | 1 | 8
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunSetupJob | ValidateParameters() : bool | 67 | 3 |  | 4 | 7
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | BaseJob | BaseJob(string) | 73 | 2 |  | 1 | 5
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunSetupJob | Execute() : bool | 63 | 2 |  | 9 | 9
Member | Simpply.Engine (Debug) | Simpply.Engine.Algorithms | SetupAlgorithm | Execute(Item, List<double>) : List<Distribution> | 59 | 2 |  | 8 | 11
Member | Simpply.Engine (Debug) | Simpply.Engine | WebApiApplication | Application_Start() : void | 73 | 1 |  | 9 | 5
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | BaseJob | BaseJob() | 87 | 1 |  | 0 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine | BundleConfig | BundleConfig() | 100 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobRequest | Data.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobRequest | Data.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobResponse | ErrorCode.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobResponse | ErrorCode.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | BaseJob | Execute() : bool | 100 | 1 |  | 0 | 0
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | ParseWegmansData | Execute() : bool | 86 | 1 |  | 1 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Algorithms | BaseAlgorithm | Execute(Item, List<double>) : List<Distribution> | 100 | 1 |  | 3 | 0
Member | Simpply.Engine (Debug) | Simpply.Engine | FilterConfig | FilterConfig() | 100 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Controllers | JobsController | Get() : string | 91 | 1 |  | 1 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | BaseJob | GetName() : string | 100 | 1 |  | 0 | 0
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | ParseWegmansData | GetName() : string | 91 | 1 |  | 0 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunSetupJob | GetName() : string | 91 | 1 |  | 0 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | BaseJob | GetValidParameters() : string | 100 | 1 |  | 0 | 0
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | ParseWegmansData | GetValidParameters() : string | 98 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunSetupJob | GetValidParameters() : string | 91 | 1 |  | 0 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Controllers | HomeController | HomeController() | 100 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | Ids.get() : List<long> | 98 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | Ids.set(List<long>) : void | 95 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Controllers | HomeController | Index() : ActionResult | 89 | 1 |  | 2 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobRequest | Job.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobRequest | Job.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobRequest | Job.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobRequest | Job.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobResponse | JobId.get() : long | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobResponse | JobId.get() : long | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobResponse | JobId.set(long) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobResponse | JobId.set(long) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | JobInvoker | JobInvoker() | 79 | 1 |  | 4 | 3
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | JobInvoker | JobInvoker() | 94 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | JobInvoker | JobInvoker() | 76 | 1 |  | 5 | 4
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | JobInvoker | JobInvoker() | 77 | 1 |  | 4 | 3
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobRequest | JobRequest() | 82 | 1 |  | 0 | 3
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobRequest | JobRequest() | 82 | 1 |  | 0 | 3
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobResponse | JobResponse(bool, int, string, long) | 74 | 1 |  | 0 | 5
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobResponse | JobResponse(bool, int, string, long) | 74 | 1 |  | 0 | 5
Member | Simpply.Engine (Debug) | Simpply.Engine.Controllers | JobsController | JobsController() | 100 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Controllers | JobsController | JobsController() | 100 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Controllers | JobsController | JobsController() | 90 | 1 |  | 4 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobResponse | Message.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobResponse | Message.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobResponse | Message.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobResponse | Message.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | ParseWegmansData | ParseWegmansData() | 90 | 1 |  | 4 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | ParseWegmansData | ParseWegmansData(string) | 84 | 1 |  | 3 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | ParseWegmansData | ParseWegmansData(string) | 87 | 1 |  | 2 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | ParseWegmansDataModel | ParseWegmansDataModel() | 100 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Algorithms | PushAllAlgorithm | PushAllAlgorithm() | 100 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | ParseWegmansData | ReadWegmansData() : void | 100 | 1 |  | 0 | 0
Member | Simpply.Engine (Debug) | Simpply.Engine | WebApiConfig | Register(HttpConfiguration) : void | 82 | 1 |  | 5 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine | WebApiConfig | Register(HttpConfiguration) : void | 75 | 1 |  | 9 | 3
Member | Simpply.Engine (Debug) | Simpply.Engine | BundleConfig | RegisterBundles(BundleCollection) : void | 100 | 1 |  | 1 | 0
Member | Simpply.Engine (Debug) | Simpply.Engine | BundleConfig | RegisterBundles(BundleCollection) : void | 100 | 1 |  | 1 | 0
Member | Simpply.Engine (Debug) | Simpply.Engine | FilterConfig | RegisterGlobalFilters(GlobalFilterCollection) : void | 94 | 1 |  | 2 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine | FilterConfig | RegisterGlobalFilters(GlobalFilterCollection) : void | 94 | 1 |  | 2 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine | RouteConfig | RegisterRoutes(RouteCollection) : void | 82 | 1 |  | 4 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine | RouteConfig | RegisterRoutes(RouteCollection) : void | 82 | 1 |  | 4 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine | RouteConfig | RouteConfig() | 100 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine | RouteConfig | RouteConfig() | 100 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunPushAllJob | RunPushAllJob(string) | 79 | 1 |  | 4 | 3
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunPushAllJobModel | RunPushAllJobModel() | 100 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunSellthroughJob | RunSellthroughJob(string) | 79 | 1 |  | 4 | 3
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | RunSellthroughJobModel() | 100 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunSetupJob | RunSetupJob(string) | 75 | 1 |  | 5 | 4
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunSetupJob | RunSetupJob(string) | 79 | 1 |  | 4 | 3
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | RunSetupJobModel() | 100 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | RunSetupJobModel() | 100 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | SegmentADistributionPercent.get() : double | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | SegmentADistributionPercent.get() : double | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | SegmentADistributionPercent.set(double) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | SegmentADistributionPercent.set(double) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | SegmentationPercents.get() : Dictionary<string, double> | 98 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | SegmentationPercents.set(Dictionary<string, double>) : void | 95 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | SegmentBDistributionPercent.get() : double | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | SegmentBDistributionPercent.get() : double | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | SegmentBDistributionPercent.set(double) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | SegmentBDistributionPercent.set(double) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | SegmentCDistributionPercent.get() : double | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | SegmentCDistributionPercent.get() : double | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | SegmentCDistributionPercent.set(double) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | SegmentCDistributionPercent.set(double) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Algorithms | SellthroughAlgorithm | SellthroughAlgorithm() | 100 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunPushAllJobModel | SellthroughPercentTrigger.get() : double | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | SellthroughPercentTrigger.get() : double | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunPushAllJobModel | SellthroughPercentTrigger.set(double) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | SellthroughPercentTrigger.set(double) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Algorithms | SetupAlgorithm | SetupAlgorithm() | 100 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Algorithms | SetupAlgorithm | SetupAlgorithm() | 100 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | SetupDistributionPercent.get() : double | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | SetupDistributionPercent.get() : double | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | SetupDistributionPercent.set(double) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | SetupDistributionPercent.set(double) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobResponse | Success.get() : bool | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobResponse | Success.get() : bool | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobResponse | Success.set(bool) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobResponse | Success.set(bool) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | ParseWegmansDataModel | Test.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | ParseWegmansDataModel | Test.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | BaseJob | UpdateJobStatus(long, string, int) : void | 92 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunPushAllJobModel | Username.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | Username.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | Username.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunPushAllJobModel | Username.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | Username.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | Username.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | JobInvoker | ValidateNoConflict() : bool | 91 | 1 |  | 0 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | BaseJob | ValidateParameters() : bool | 100 | 1 |  | 0 | 0
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | ParseWegmansData | ValidateParameters() : bool | 91 | 1 |  | 0 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | BaseJob | ValidateParameters() : bool | 100 | 1 |  | 0 | 0
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | ParseWegmansData | ValidateParameters() : bool | 91 | 1 |  | 0 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine | WebApiApplication | WebApiApplication() | 100 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine | WebApiApplication | WebApiApplication() | 100 | 1 |  | 1 | 1
Member | Simpply.Global (Debug) | Simpply.Global | Constants.ControllerAction.Account | Account() | 100 | 1 |  | 0 | 1
Member | Simpply.Global (Debug) | Simpply.Global | Constants.ControllerAction.Account | Account() | 100 | 1 |  | 0 | 1
Member | Simpply.Global (Debug) | Simpply.Global | Constants | Constants() | 100 | 1 |  | 0 | 1
Member | Simpply.Global (Debug) | Simpply.Global | Constants | Constants() | 100 | 1 |  | 0 | 1
Member | Simpply.Global (Debug) | Simpply.Global | Constants.Controller | Controller() | 100 | 1 |  | 0 | 1
Member | Simpply.Global (Debug) | Simpply.Global | Constants.Controller | Controller() | 100 | 1 |  | 0 | 1
Member | Simpply.Global (Debug) | Simpply.Global | Constants.ControllerAction | ControllerAction() | 100 | 1 |  | 0 | 1
Member | Simpply.Global (Debug) | Simpply.Global | Constants.ControllerAction | ControllerAction() | 100 | 1 |  | 0 | 1
Member | Simpply.Global (Debug) | Simpply.Global | Constants.ControllerAction.Item | Item() | 100 | 1 |  | 0 | 1
Member | Simpply.Global (Debug) | Simpply.Global | Constants.ControllerAction.Item | Item() | 100 | 1 |  | 0 | 1
Member | Simpply.Global (Debug) | Simpply.Global | Constants.ViewPages.ItemDetails | ItemDetails() | 100 | 1 |  | 0 | 1
Member | Simpply.Global (Debug) | Simpply.Global | Constants.ControllerAction.Planogram | Planogram() | 100 | 1 |  | 0 | 1
Member | Simpply.Global (Debug) | Simpply.Global | Constants.ControllerAction.Planogram | Planogram() | 100 | 1 |  | 0 | 1
Member | Simpply.Global (Debug) | Simpply.Global | Constants.ControllerAction.Season | Season() | 100 | 1 |  | 0 | 1
Member | Simpply.Global (Debug) | Simpply.Global | Constants.ControllerAction.Season | Season() | 100 | 1 |  | 0 | 1
Member | Simpply.Global (Debug) | Simpply.Global | Constants.ViewPages | ViewPages() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ItemProviderTest | SaveDistribution() : void | 46 | 13 |  | 14 | 26
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | AccountControllerTest | SaveColumnPreferences() : void | 55 | 5 |  | 23 | 12
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | AccountControllerTest | SaveColumnPreferences() : void | 55 | 5 |  | 23 | 12
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ItemProviderTest | GetDetailsReturnsRelatedDistributions() : void | 68 | 3 |  | 10 | 5
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | PlanogramProviderTest | GetResultsAreInOrder() : void | 65 | 3 |  | 9 | 7
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | PlanogramProviderTest | GetResultsAreInOrder() : void | 65 | 3 |  | 9 | 7
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | PlanogramProviderTest | GetReturnsOnlyActivePlanograms() : void | 65 | 3 |  | 9 | 7
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | PlanogramProviderTest | GetReturnsOnlyActivePlanograms() : void | 65 | 3 |  | 9 | 7
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | ItemControllerTest | ItemDetail() : void | 66 | 3 |  | 16 | 5
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | ItemControllerTest | ItemDetail() : void | 65 | 3 |  | 17 | 5
Member | Simpply.Tests (Debug) | Simpply.Tests.ViewModels | ItemModelsTest | ItemDetailModelHasCorrectAggregateGrid() : void | 60 | 3 |  | 11 | 10
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | ItemControllerTest | ItemExplorer() : void | 59 | 3 |  | 20 | 8
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | ItemControllerTest | ItemExplorer() : void | 59 | 3 |  | 20 | 8
Member | Simpply.Tests (Debug) | Simpply.Tests.Jobs | RunSetupJobTest | ValidateParametersTest() : void | 57 | 3 |  | 6 | 15
Member | Simpply.Tests (Debug) | Simpply.Tests.Algorithms | PushAllAlgorithmTest | ExecutePushAllDistributionTest() : void | 62 | 2 |  | 9 | 8
Member | Simpply.Tests (Debug) | Simpply.Tests.Algorithms | SetupAlgorithmTest | ExecuteSetupDistributionTest() : void | 62 | 2 |  | 9 | 8
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ItemProviderTest | GetDetailsReturnsRelatedSalesInformation() : void | 69 | 2 |  | 10 | 5
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | AccountControllerTest | AccountControllerTest() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | AccountControllerTest | AccountControllerTest() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | BaseProviderTest | BaseProviderTest() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | BaseProviderTest | BaseProviderTest() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | BreadcrumbControllerTest | BreadcrumbControllerTest() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ColumnPreferenceProviderTest | ColumnPreferenceProviderTest() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ColumnPreferenceProviderTest | ColumnPreferenceProviderTest() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ColumnPreferenceProviderTest | Get() : void | 82 | 1 |  | 6 | 2
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ColumnPreferenceProviderTest | Get() : void | 82 | 1 |  | 6 | 2
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | BreadcrumbControllerTest | GetBreadcrumbsTest() : void | 100 | 1 |  | 1 | 0
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ItemProviderTest | GetDetailsReturnsANonNullItem() : void | 74 | 1 |  | 5 | 4
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ItemProviderTest | GetDetailsReturnsRelatedStores() : void | 73 | 1 |  | 7 | 4
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ItemProviderTest | GetItem() : void | 100 | 1 |  | 1 | 0
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ItemProviderTest | GetItems() : void | 71 | 1 |  | 7 | 5
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ItemProviderTest | GetItems() : void | 71 | 1 |  | 7 | 5
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | PlanogramProviderTest | GetResultIsNotNull() : void | 69 | 1 |  | 7 | 6
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | PlanogramProviderTest | GetResultIsNotNull() : void | 69 | 1 |  | 7 | 6
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | SalesInformationProviderTest | GetSale() : void | 100 | 1 |  | 1 | 0
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | SalesInformationProviderTest | GetSales() : void | 100 | 1 |  | 1 | 0
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | StoreProviderTest | GetStore() : void | 100 | 1 |  | 1 | 0
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | StoreProviderTest | GetStores() : void | 100 | 1 |  | 1 | 0
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | PlanogramControllerTest | IndexGetsActivePlanogramsOnly() : void | 66 | 1 |  | 8 | 6
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | PlanogramControllerTest | IndexGetsActivePlanogramsOnly() : void | 66 | 1 |  | 8 | 6
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | PlanogramControllerTest | IndexGetsAllPlanograms() : void | 66 | 1 |  | 8 | 6
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | PlanogramControllerTest | IndexGetsAllPlanograms() : void | 66 | 1 |  | 8 | 6
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | ItemControllerTest | ItemControllerTest() | 69 | 1 |  | 5 | 3
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | ItemControllerTest | ItemControllerTest() | 69 | 1 |  | 5 | 3
Member | Simpply.Tests (Debug) | Simpply.Tests.ViewModels | ItemModelsTest | ItemDetailModelHasCorrectDistributionGrid() : void | 71 | 1 |  | 9 | 4
Member | Simpply.Tests (Debug) | Simpply.Tests.ViewModels | ItemModelsTest | ItemDetailModelHasCorrectItemName() : void | 75 | 1 |  | 5 | 3
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | ItemControllerTest | ItemExplorerFiltersToCorrectPlanogram() : void | 63 | 1 |  | 11 | 7
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | ItemControllerTest | ItemExplorerFiltersToCorrectPlanogram() : void | 63 | 1 |  | 11 | 7
Member | Simpply.Tests (Debug) | Simpply.Tests.ViewModels | ItemModelsTest | ItemModelsTest() | 66 | 1 |  | 3 | 4
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ItemProviderTest | ItemProviderTest() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ItemProviderTest | ItemProviderTest() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | PlanogramControllerTest | PlanogramControllerTest() | 76 | 1 |  | 3 | 2
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | PlanogramControllerTest | PlanogramControllerTest() | 76 | 1 |  | 3 | 2
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | PlanogramProviderTest | PlanogramProviderTest() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | PlanogramProviderTest | PlanogramProviderTest() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Algorithms | PushAllAlgorithmTest | PushAllAlgorithmTest() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Jobs | RunSetupJobTest | RunSetupJobTest() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | SalesInformationProviderTest | SalesInformationProviderTest() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ColumnPreferenceProviderTest | Save() : void | 75 | 1 |  | 4 | 2
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ColumnPreferenceProviderTest | Save() : void | 75 | 1 |  | 4 | 2
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ItemProviderTest | SaveItem() : void | 100 | 1 |  | 1 | 0
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | ItemControllerTest | SaveItemDistributionCallsProvidersCorrectly() : void | 72 | 1 |  | 7 | 3
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ItemProviderTest | SaveItems() : void | 100 | 1 |  | 1 | 0
Member | Simpply.Tests (Debug) | Simpply.Tests.Algorithms | SetupAlgorithmTest | SetupAlgorithmTest() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | StoreProviderTest | StoreProviderTest() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | AccountControllerTest | TestInit() : void | 92 | 1 |  | 3 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | ItemControllerTest | TestInit() : void | 67 | 1 |  | 8 | 6
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | PlanogramControllerTest | TestInit() : void | 77 | 1 |  | 5 | 3
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | BaseProviderTest | TestInit() : void | 94 | 1 |  | 3 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ColumnPreferenceProviderTest | TestInit() : void | 94 | 1 |  | 3 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ItemProviderTest | TestInit() : void | 94 | 1 |  | 3 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | PlanogramProviderTest | TestInit() : void | 94 | 1 |  | 3 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | SalesInformationProviderTest | TestInit() : void | 94 | 1 |  | 3 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | StoreProviderTest | TestInit() : void | 94 | 1 |  | 3 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | AccountControllerTest | TestInit() : void | 92 | 1 |  | 3 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | BaseProviderTest | TestInit() : void | 94 | 1 |  | 3 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ColumnPreferenceProviderTest | TestInit() : void | 94 | 1 |  | 3 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | ItemControllerTest | TestInit() : void | 77 | 1 |  | 5 | 3
Member | Simpply.Tests (Debug) | Simpply.Tests.ViewModels | ItemModelsTest | TestInit() : void | 75 | 1 |  | 6 | 2
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ItemProviderTest | TestInit() : void | 94 | 1 |  | 3 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | PlanogramControllerTest | TestInit() : void | 77 | 1 |  | 5 | 3
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | PlanogramProviderTest | TestInit() : void | 94 | 1 |  | 3 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Algorithms | PushAllAlgorithmTest | TestInit() : void | 47 | 1 |  | 8 | 33
Member | Simpply.Tests (Debug) | Simpply.Tests.Jobs | RunSetupJobTest | TestInit() : void | 70 | 1 |  | 1 | 6
Member | Simpply.Tests (Debug) | Simpply.Tests.Algorithms | SetupAlgorithmTest | TestInit() : void | 47 | 1 |  | 9 | 31
Member | Simpply.Util (Debug) | Simpply.Util.Extensions | CollectionExtensions | IsEmpty<T>(this ICollection<T>) : bool | 84 | 2 |  | 2 | 2
Member | Simpply.Util (Debug) | Simpply.Util.Extensions | CollectionExtensions | IsEmpty<T>(this ICollection<T>) : bool | 84 | 2 |  | 2 | 2
Member | Simpply.Util (Debug) | Simpply.Util.Extensions | StringExtensions | IsNullOrWhiteSpace(this string) : bool | 87 | 1 |  | 1 | 2
Member | Simpply.Util (Debug) | Simpply.Util.Extensions | StringExtensions | IsNullOrWhiteSpace(this string) : bool | 87 | 1 |  | 1 | 2

## Code Metrics Iteration 4
Scope | Project | Namespace | Type | Member | Maintainability Index | Cyclomatic Complexity | Depth of Inheritance | Class Coupling | Lines of Code | Web | Engine | Access
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | ItemDetailModel(Item) | 33 | 31 |  | 19 | 40 | 1.937888199 | 1.417721519 | 1.744680851
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ColumnPreferenceModel(string, string, string, List<Column>, List<ColumnPreference>) | 32 | 25 |  | 17 | 77
Member | Simpply (Debug) | Simpply.Models | SeasonExplorerModel | SeasonExplorerModel(List<SeasonInfo>, string, bool, bool, List<ColumnPreference>) | 33 | 20 |  | 15 | 59
Member | Simpply (Debug) | Simpply.Models.POG | PlanogramExplorerModel | PlanogramExplorerModel(List<Planogram>, string, bool, bool, List<ColumnPreference>, int?) | 36 | 16 |  | 16 | 48
Member | Simpply (Debug) | Simpply.Models | BreadcrumbTrailModel | AdjustBreadcrumbsTrail(string, string, string) : void | 48 | 11 |  | 6 | 28
Member | Simpply (Debug) | Simpply.Controllers | ItemController | SaveDistribution(List<DistributionModel>, int, int, bool) : ActionResult | 54 | 9 |  | 9 | 14
Member | Simpply (Debug) | Simpply.Models | ItemExplorerModel | ItemExplorerModel(List<Item>, string, int?, string, bool, List<ColumnPreference>) | 44 | 9 |  | 12 | 31
Member | Simpply (Debug) | Simpply.Helpers | WebHelper | getParamId(string) : int | 64 | 5 |  | 0 | 7
Member | Simpply (Debug) | Simpply.Helpers | WebHelper | GenerateActionUrl(string, string, Dictionary<string, string>) : string | 63 | 5 |  | 4 | 8
Member | Simpply (Debug) | Simpply.Models | ItemExplorerModel | CreateHeaderCell(string, string, int?, string, string, bool) : GridCellModel | 63 | 5 |  | 4 | 7
Member | Simpply (Debug) | Simpply.Controllers | AccountController | SaveColumnPreferences(ColumnPreferenceModel) : ActionResult | 55 | 4 |  | 9 | 12
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | GetColumnId(string) : long? | 65 | 4 |  | 2 | 8
Member | Simpply (Debug) | Simpply.Controllers | SeasonController | SeasonExplorer(bool, string, bool) : ActionResult | 63 | 3 |  | 17 | 7
Member | Simpply (Debug) | Simpply.Controllers | PlanogramController | PlanogramExplorer(int?, bool, string, bool) : ActionResult | 63 | 3 |  | 19 | 7
Member | Simpply (Debug) | Simpply.Controllers | ItemController | ItemExplorer(string, int?, string, bool) : ActionResult | 63 | 3 |  | 18 | 7
Member | Simpply (Debug) | Simpply.Controllers | ItemController | ItemDetail(long) : ActionResult | 62 | 3 |  | 14 | 8
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | GetColumnName(string) : string | 67 | 3 |  | 1 | 7
Member | Simpply (Debug) | Simpply.Models.POG | PlanogramExplorerModel | FormatActionUrl(string, string, bool, bool, int?) : string | 67 | 3 |  | 2 | 6
Member | Simpply (Debug) | Simpply.Controllers | ItemController | Search(string) : ActionResult | 64 | 2 |  | 7 | 8
Member | Simpply (Debug) | Simpply.Helpers | WebHelper | GetControllerActionParameters(string) : string | 72 | 2 |  | 0 | 5
Member | Simpply (Debug) | Simpply.Controllers | BreadcrumbController | GetBreadCrumbs() : ActionResult | 60 | 2 |  | 7 | 11
Member | Simpply (Debug) | Simpply.Helpers | WebHelper | GenerateActionUrl(string, string, string) : string | 73 | 2 |  | 1 | 4
Member | Simpply (Debug) | Simpply.Models | SeasonExplorerModel | FormatActionUrl(string, string, bool, bool) : string | 73 | 2 |  | 1 | 4
Member | Simpply (Debug) | Simpply.Models | SeasonExplorerModel | CreateHeaderCell(string, string, string, bool, bool) : GridCellModel | 78 | 2 |  | 1 | 2
Member | Simpply (Debug) | Simpply.Models.POG | PlanogramExplorerModel | CreateHeaderCell(string, string, string, bool, bool, int?) : GridCellModel | 78 | 2 |  | 2 | 2
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | WarehouseBalanceOnHand.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | WarehouseBalanceOnHand.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | BreadcrumbModel | Value.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | FormInput | Value.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | Value.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | BreadcrumbModel | Value.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | FormInput | Value.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | Value.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | Type.set(GridCellType) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | Type.get() : GridCellType | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | tableCondensed.set(bool) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | tableCondensed.get() : bool | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | Table.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | Table.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Controllers | StoreController | StoreController() | 100 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ShownColumnsList.set(List<SelectListItem>) : void | 95 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ShownColumnsList.get() : List<SelectListItem> | 98 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ShownColumnsDefault.set(List<SelectListItem>) : void | 95 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ShownColumnsDefault.get() : List<SelectListItem> | 98 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ShownColumns.set(List<string>) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ShownColumns.get() : List<string> | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | BreadcrumbTrailModel | SetToDefault() : void | 69 | 1 |  | 3 | 4
Member | Simpply (Debug) | Simpply.Controllers | SeasonController | SeasonController(ISeasonProvider, IColumnPreferenceProvider) | 81 | 1 |  | 3 | 3
Member | Simpply (Debug) | Simpply.Models | GridModel | Rows.set(List<GridRowModel>) : void | 95 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | Rows.get() : List<GridRowModel> | 98 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply | RouteConfig | RouteConfig() | 100 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Controllers | BaseController | Root() : ActionResult | 86 | 1 |  | 2 | 2
Member | Simpply (Debug) | Simpply | RouteConfig | RegisterRoutes(RouteCollection) : void | 82 | 1 |  | 3 | 2
Member | Simpply (Debug) | Simpply | FilterConfig | RegisterGlobalFilters(GlobalFilterCollection) : void | 94 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.App_Start | AutofacConfig | RegisterComponents() : void | 70 | 1 |  | 10 | 5
Member | Simpply (Debug) | Simpply | BundleConfig | RegisterBundles(BundleCollection) : void | 64 | 1 |  | 4 | 6
Member | Simpply (Debug) | Simpply | AuthConfig | RegisterAuth() : void | 100 | 1 |  | 0 | 0
Member | Simpply (Debug) | Simpply | WebApiConfig | Register(HttpConfiguration) : void | 89 | 1 |  | 4 | 1
Member | Simpply (Debug) | Simpply.Controllers | PlanogramController | PlanogramController(IPlanogramProvider, IColumnPreferenceProvider) | 81 | 1 |  | 3 | 3
Member | Simpply (Debug) | Simpply.Models | Column | Name.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | FormInput | Name.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | Name.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | Column | Name.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | FormInput | Name.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | Name.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply | MvcApplication | MvcApplication() | 100 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | ModelRow.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | ModelRow.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | ModelName.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | ModelName.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | ModelAttribute.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | ModelAttribute.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | LastModifiedDate.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | LastModifiedDate.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | LastModifiedBy.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | LastModifiedBy.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Controllers | BaseController | JsonActionResult(JsonReturnType, string, string, string, object) : ActionResult | 68 | 1 |  | 5 | 6
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | ItemFinalized.set(bool) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | ItemFinalized.get() : bool | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Controllers | ItemController | ItemController(IItemProvider, IStoreProvider, ISalesInformationProvider, IColumnPreferenceProvider) | 71 | 1 |  | 6 | 6
Member | Simpply (Debug) | Simpply.Controllers | ItemController | ItemController() | 90 | 1 |  | 4 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | IsSortedDescending.set(bool) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | IsSortedDescending.get() : bool | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | IsSorted.set(bool) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | IsSorted.get() : bool | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridRowModel | IsHeader.set(bool) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridRowModel | IsHeader.get() : bool | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | SeasonExplorerModel | InactiveSeasonURL.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | SeasonExplorerModel | InactiveSeasonURL.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models.POG | PlanogramExplorerModel | InactivePlanogramURL.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models.POG | PlanogramExplorerModel | InactivePlanogramURL.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | HiddenColumnsList.set(List<SelectListItem>) : void | 95 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | HiddenColumnsList.get() : List<SelectListItem> | 98 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | HiddenColumns.set(List<string>) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | HiddenColumns.get() : List<string> | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | Header.set(GridRowModel) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | Header.get() : GridRowModel | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | GridRowModel | GridRowModel() | 87 | 1 |  | 2 | 2
Member | Simpply (Debug) | Simpply.Models | GridModel | GridModel() | 72 | 1 |  | 3 | 5
Member | Simpply (Debug) | Simpply.Models | GridCellModel | GridCellModel() | 78 | 1 |  | 0 | 4
Member | Simpply (Debug) | Simpply.Models | ItemExplorerModel | Grid.set(GridModel) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | SeasonExplorerModel | Grid.set(GridModel) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models.POG | PlanogramExplorerModel | Grid.set(GridModel) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ItemExplorerModel | Grid.get() : GridModel | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | SeasonExplorerModel | Grid.get() : GridModel | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models.POG | PlanogramExplorerModel | Grid.get() : GridModel | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Helpers | WebHelper | GetControllerName(string) : string | 78 | 1 |  | 0 | 3
Member | Simpply (Debug) | Simpply.Helpers | WebHelper | GetControllerActionName(string) : string | 78 | 1 |  | 0 | 3
Member | Simpply (Debug) | Simpply.Models | GridModel | FormMethod.set(FormMethod) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | FormMethod.get() : FormMethod | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | FormInput | FormInput() | 100 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | FormId.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | FormId.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | FormHiddenInputs.set(List<FormInput>) : void | 95 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | FormHiddenInputs.get() : List<FormInput> | 98 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | FormController.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | FormController.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | FormAction.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | FormAction.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply | FilterConfig | FilterConfig() | 100 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | Distribution.set(GridModel) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | Distribution.get() : GridModel | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | Column | DisplayName.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | Column | DisplayName.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | CssClasses.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridRowModel | CssClasses.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | CssClasses.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridRowModel | CssClasses.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ControllerName.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ControllerName.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ControllerAction.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ControllerAction.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Controllers | StoreController | CompareTostore() : ActionResult | 89 | 1 |  | 2 | 2
Member | Simpply (Debug) | Simpply.Controllers | StoreController | CompareToMultiplestores() : ActionResult | 89 | 1 |  | 2 | 2
Member | Simpply (Debug) | Simpply.Models | ItemExplorerModel | ColumnPreferences.set(ColumnPreferenceModel) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | SeasonExplorerModel | ColumnPreferences.set(ColumnPreferenceModel) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models.POG | PlanogramExplorerModel | ColumnPreferences.set(ColumnPreferenceModel) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ItemExplorerModel | ColumnPreferences.get() : ColumnPreferenceModel | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | SeasonExplorerModel | ColumnPreferences.get() : ColumnPreferenceModel | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models.POG | PlanogramExplorerModel | ColumnPreferences.get() : ColumnPreferenceModel | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ColumnPreferenceModel() | 71 | 1 |  | 2 | 6
Member | Simpply (Debug) | Simpply.Models | Column | Column() | 100 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridRowModel | Cells.set(List<GridCellModel>) : void | 95 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | GridRowModel | Cells.get() : List<GridCellModel> | 98 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply | BundleConfig | BundleConfig() | 100 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | BreadcrumbTrailModel | BreadcrumbTrailModel() | 65 | 1 |  | 3 | 6
Member | Simpply (Debug) | Simpply.Models | BreadcrumbModel | BreadcrumbModel() | 100 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Controllers | BreadcrumbController | BreadcrumbController() | 100 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Controllers | BaseController | BaseController() | 100 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply | MvcApplication | Application_Start() : void | 69 | 1 |  | 11 | 7
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | Aggregate.set(GridModel) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | Aggregate.get() : GridModel | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | SeasonExplorerModel | ActiveOnly.set(bool) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models.POG | PlanogramExplorerModel | ActiveOnly.set(bool) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | SeasonExplorerModel | ActiveOnly.get() : bool | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models.POG | PlanogramExplorerModel | ActiveOnly.get() : bool | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | BreadcrumbModel | ActionUrl.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | ActionUrl.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | BreadcrumbModel | ActionUrl.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | ActionUrl.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Controllers | AccountController | AccountController(IColumnPreferenceProvider) | 87 | 1 |  | 2 | 2
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | UnitsSold.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Shared | AggregateItemData | UnitsSold.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | UnitsSold.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Shared | AggregateItemData | UnitsSold.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Shared | AggregateItemData | UnitsShrunk.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Shared | AggregateItemData | UnitsShrunk.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | UnitsReceived.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Shared | AggregateItemData | UnitsReceived.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | UnitsReceived.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Shared | AggregateItemData | UnitsReceived.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Distribution | Type.set(DistributionType) : void | 95 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Distribution | Type.get() : DistributionType | 98 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Account | ColumnPreference | Table.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Account | ColumnPreference | Table.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Item | Stores.set(List<Store>) : void | 95 | 1 |  | 2 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Item | Stores.get() : List<Store> | 98 | 1 |  | 2 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | StoreId.set(long) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | DistributionModel | StoreId.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | StoreId.get() : long | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | DistributionModel | StoreId.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Store | Store() | 100 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SeasonInfo | StartDate.set(DateTime) : void | 95 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data.POG | Planogram | StartDate.set(DateTime) : void | 95 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SeasonInfo | StartDate.get() : DateTime | 98 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data.POG | Planogram | StartDate.get() : DateTime | 98 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Account | ColumnPreference | ShowColumn.set(bool) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Account | ColumnPreference | ShowColumn.get() : bool | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | ShelfSpace.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | ShelfSpace.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | SellThrough.set(double) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Shared | AggregateItemData | SellThrough.set(decimal) : void | 95 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | SellThrough.get() : double | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Shared | AggregateItemData | SellThrough.get() : decimal | 98 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Store | Segmentation.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Store | Segmentation.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SeasonInfo | SeasonInfo() | 100 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | SalesInformation() | 100 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Distribution | SalesId.set(long) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | DistributionModel | SalesId.set(long) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Distribution | SalesId.get() : long | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | DistributionModel | SalesId.get() : long | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Store | Sales.set(SalesInformation) : void | 95 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Store | Sales.get() : SalesInformation | 98 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Job | ProgressPercent.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Job | ProgressPercent.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Job | Progress.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Job | Progress.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.POG | Planogram | Planogram() | 100 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | PercentageOfTotal.set(double) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | PercentageOfTotal.get() : double | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Account | ColumnPreference | Order.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Account | ColumnPreference | Order.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Item | Name.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Job | Name.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SeasonInfo | Name.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Store | Name.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.POG | Planogram | Name.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Item | Name.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Job | Name.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SeasonInfo | Name.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Store | Name.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.POG | Planogram | Name.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Distribution | ModifiedOn.set(DateTime?) : void | 95 | 1 |  | 2 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Distribution | ModifiedOn.get() : DateTime? | 98 | 1 |  | 2 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Distribution | ModifiedBy.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Distribution | ModifiedBy.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | LastYearsSales.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | LastYearsSales.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Job | Job() | 100 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | ItemId.set(long) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | ItemId.get() : long | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Distribution | ItemAmount.set(long) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Distribution | ItemAmount.get() : long | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Item | Item() | 100 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Distribution | Id.set(long) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | DistributionModel | Id.set(long) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Example | Id.set(long) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Item | Id.set(long) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Job | Id.set(long) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | Id.set(long) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Store | Id.set(long) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Account | ColumnPreference | Id.set(long?) : void | 95 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SeasonInfo | Id.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.POG | Planogram | Id.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Account | ColumnPreference | Id.get() : long? | 98 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Distribution | Id.get() : long | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | DistributionModel | Id.get() : long | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Example | Id.get() : long | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Item | Id.get() : long | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Job | Id.get() : long | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | Id.get() : long | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Store | Id.get() : long | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SeasonInfo | Id.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.POG | Planogram | Id.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Example | Example() | 100 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SeasonInfo | EndDate.set(DateTime) : void | 95 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data.POG | Planogram | EndDate.set(DateTime) : void | 95 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SeasonInfo | EndDate.get() : DateTime | 98 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data.POG | Planogram | EndDate.get() : DateTime | 98 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Store | Distributions.set(List<Distribution>) : void | 95 | 1 |  | 2 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Store | Distributions.get() : List<Distribution> | 98 | 1 |  | 2 | 1
Member | Simpply.Data (Debug) | Simpply.Data | DistributionModel | DistributionModel() | 100 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Distribution | Distribution() | 100 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Item | Description.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Item | Description.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Distribution | CreatedOn.set(DateTime) : void | 95 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Distribution | CreatedOn.get() : DateTime | 98 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Account | ColumnPreference | ControllerAction.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Account | ColumnPreference | ControllerAction.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Account | ColumnPreference | Controller.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Account | ColumnPreference | Controller.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Account | ColumnPreference | ColumnPreference() | 100 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Account | ColumnPreference | Column.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Account | ColumnPreference | Column.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | CalculatedInventory.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | CalculatedInventory.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Item | BalanceOnHand.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SeasonInfo | BalanceOnHand.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.POG | Planogram | BalanceOnHand.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Item | BalanceOnHand.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SeasonInfo | BalanceOnHand.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.POG | Planogram | BalanceOnHand.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | DistributionModel | Amount.set(long) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | DistributionModel | Amount.get() : long | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Shared | AggregateItemData | AggregateItemData() | 100 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SeasonInfo | AggregateDataSeasonToDate.set(AggregateItemData) : void | 95 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data.POG | Planogram | AggregateDataSeasonToDate.set(AggregateItemData) : void | 95 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SeasonInfo | AggregateDataSeasonToDate.get() : AggregateItemData | 98 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data.POG | Planogram | AggregateDataSeasonToDate.get() : AggregateItemData | 98 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SeasonInfo | AggregateData7Days.set(AggregateItemData) : void | 95 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SeasonInfo | AggregateData7Days.get() : AggregateItemData | 98 | 1 |  | 1 | 1
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ItemProvider | GetDetails(long) : Item | 46 | 8 |  | 18 | 29
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ItemProvider | SaveDistribution(List<DistributionModel>, int, int, bool, string) : void | 52 | 5 |  | 16 | 15
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ItemProvider | SaveMultiple(List<Distribution>) : void | 52 | 4 |  | 16 | 15
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ColumnPreferenceProvider | Save(List<ColumnPreference>) : void | 52 | 4 |  | 15 | 15
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | SeasonProvider | Get(bool, string, bool) : List<SeasonInfo> | 60 | 4 |  | 13 | 10
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | PlanogramProvider | Get(bool, int?, string, bool) : List<Planogram> | 60 | 4 |  | 13 | 10
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | SalesInformationProvider | Get(long, long) : SalesInformation | 70 | 3 |  | 5 | 5
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | JobProvider | UpdateProgress(long, string, int) : void | 72 | 2 |  | 7 | 4
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ExampleProvider | SelectExample(int) : Example | 70 | 2 |  | 9 | 5
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | JobProvider | Insert(string) : long | 69 | 2 |  | 8 | 5
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | SeasonProvider | GetSeasonName(int) : string | 66 | 2 |  | 9 | 7
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | PlanogramProvider | GetPlanogramName(int) : string | 66 | 2 |  | 9 | 7
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ItemProvider | GetItemName(int) : string | 66 | 2 |  | 9 | 7
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ItemProvider | GetIds() : List<long> | 69 | 2 |  | 9 | 5
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ColumnPreferenceProvider | Get(string, string, string) : List<ColumnPreference> | 66 | 2 |  | 10 | 7
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | StoreProvider | Get(long) : Store | 71 | 2 |  | 5 | 5
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ItemProvider | Get(long?, string, int?, string, bool?) : List<Item> | 69 | 2 |  | 10 | 5
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IJobProvider | UpdateProgress(long, string, int) : void | 100 | 1 |  | 0 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | StoreProvider | StoreProvider() | 76 | 1 |  | 3 | 2
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | SeasonProvider | SeasonProvider() | 100 | 1 |  | 1 | 1
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IItemProvider | SaveDistribution(List<DistributionModel>, int, int, bool, string) : void | 100 | 1 |  | 2 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IColumnPreferenceProvider | Save(List<ColumnPreference>) : void | 100 | 1 |  | 2 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | SalesInformationProvider | SalesInformationProvider() | 68 | 1 |  | 3 | 2
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | PlanogramProvider | PlanogramProvider() | 100 | 1 |  | 1 | 1
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access | AccessModule | Load(ContainerBuilder) : void | 63 | 1 |  | 18 | 7
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | JobProvider | JobProvider() | 100 | 1 |  | 1 | 1
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ItemProvider | ItemProvider() | 100 | 1 |  | 1 | 1
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IJobProvider | Insert(string) : long | 100 | 1 |  | 0 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IItemProvider | GetDetails(long) : Item | 100 | 1 |  | 1 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IColumnPreferenceProvider | Get(string, string, string) : List<ColumnPreference> | 100 | 1 |  | 2 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IStoreProvider | Get(long) : Store | 100 | 1 |  | 1 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IJobProvider | Get(long) : Job | 100 | 1 |  | 1 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | JobProvider | Get(long) : Job | 91 | 1 |  | 1 | 2
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IItemProvider | Get(long?, string, int?, string, bool?) : List<Item> | 100 | 1 |  | 3 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | ISalesInformationProvider | Get(long, long) : SalesInformation | 100 | 1 |  | 1 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | ISeasonProvider | Get(bool, string, bool) : List<SeasonInfo> | 100 | 1 |  | 2 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IPlanogramProvider | Get(bool, int?, string, bool) : List<Planogram> | 100 | 1 |  | 3 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IStoreProvider | Get() : List<Store> | 100 | 1 |  | 2 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | StoreProvider | Get() : List<Store> | 91 | 1 |  | 2 | 2
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | ISalesInformationProvider | Get() : List<SalesInformation> | 100 | 1 |  | 2 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | SalesInformationProvider | Get() : List<SalesInformation> | 91 | 1 |  | 2 | 2
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ExampleProvider | ExampleProvider() | 100 | 1 |  | 1 | 1
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | BaseProvider | connectionString.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | BaseProvider | connectionString.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ColumnPreferenceProvider | ColumnPreferenceProvider() | 100 | 1 |  | 1 | 1
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | BaseProvider | BaseProvider() | 83 | 1 |  | 3 | 2
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access | AccessModule | AccessModule() | 100 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | JobInvoker | ScheduleJob(BaseJob) : JobResponse | 45 | 8 |  | 10 | 34
Member | Simpply.Engine (Debug) | Simpply.Engine.Controllers | JobsController | Post(JobRequest) : object | 54 | 6 |  | 13 | 17
Member | Simpply.Engine (Debug) | Simpply.Engine.Algorithms | PushAllAlgorithm | Execute(Item, BaseJobModel) : List<Distribution> | 51 | 6 |  | 13 | 19
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunSetupJob | ValidateParameters() : bool | 61 | 5 |  | 5 | 11
Member | Simpply.Engine (Debug) | Simpply.Engine.Algorithms | SetupAlgorithm | Execute(Item, BaseJobModel) : List<Distribution> | 48 | 5 |  | 12 | 24
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | JobInvoker | GetInstance() : JobInvoker | 67 | 4 |  | 1 | 8
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunPushAllJob | ValidateParameters() : bool | 67 | 3 |  | 4 | 7
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunPushAllJob | Execute() : bool | 66 | 2 |  | 8 | 7
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunSetupJob | Execute() : bool | 66 | 2 |  | 8 | 7
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | BaseJob | BaseJob(string) | 73 | 2 |  | 1 | 5
Member | Simpply.Engine (Debug) | Simpply.Engine | WebApiApplication | WebApiApplication() | 100 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | BaseJob | ValidateParameters() : bool | 100 | 1 |  | 0 | 0
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | ParseWegmansData | ValidateParameters() : bool | 91 | 1 |  | 0 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | JobInvoker | ValidateNoConflict() : bool | 91 | 1 |  | 0 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunPushAllJobModel | Username.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | Username.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunPushAllJobModel | Username.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | Username.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | ParseWegmansDataModel | Test.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | ParseWegmansDataModel | Test.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobResponse | Success.set(bool) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobResponse | Success.get() : bool | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | SetupDistributionPercent.set(double) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | SetupDistributionPercent.get() : double | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Algorithms | SetupAlgorithm | SetupAlgorithm() | 100 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunPushAllJobModel | SellthroughPercentTrigger.set(double) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunPushAllJobModel | SellthroughPercentTrigger.get() : double | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | RunSetupJobModel() | 100 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunSetupJob | RunSetupJob(string) | 72 | 1 |  | 5 | 4
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunPushAllJobModel | RunPushAllJobModel() | 100 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunPushAllJob | RunPushAllJob(string) | 79 | 1 |  | 4 | 3
Member | Simpply.Engine (Debug) | Simpply.Engine | RouteConfig | RouteConfig() | 100 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine | RouteConfig | RegisterRoutes(RouteCollection) : void | 82 | 1 |  | 4 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine | FilterConfig | RegisterGlobalFilters(GlobalFilterCollection) : void | 94 | 1 |  | 2 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine | BundleConfig | RegisterBundles(BundleCollection) : void | 100 | 1 |  | 1 | 0
Member | Simpply.Engine (Debug) | Simpply.Engine | WebApiConfig | Register(HttpConfiguration) : void | 82 | 1 |  | 5 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | ParseWegmansData | ReadWegmansData() : void | 100 | 1 |  | 0 | 0
Member | Simpply.Engine (Debug) | Simpply.Engine.Algorithms | PushAllAlgorithm | PushAllAlgorithm() | 100 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | ParseWegmansDataModel | ParseWegmansDataModel() | 100 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | ParseWegmansData | ParseWegmansData(string) | 84 | 1 |  | 3 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobResponse | Message.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobResponse | Message.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Controllers | JobsController | JobsController() | 100 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobResponse | JobResponse(bool, int, string, long) | 74 | 1 |  | 0 | 5
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobRequest | JobRequest() | 82 | 1 |  | 0 | 3
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | JobInvoker | JobInvoker() | 76 | 1 |  | 5 | 4
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | JobInvoker | JobInvoker() | 82 | 1 |  | 4 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobResponse | JobId.set(long) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobResponse | JobId.get() : long | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobRequest | Job.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobRequest | Job.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Controllers | HomeController | Index() : ActionResult | 89 | 1 |  | 2 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunPushAllJobModel | Ids.set(List<long>) : void | 95 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | Ids.set(List<long>) : void | 95 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunPushAllJobModel | Ids.get() : List<long> | 98 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | Ids.get() : List<long> | 98 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Controllers | HomeController | HomeController() | 100 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | BaseJob | GetValidParameters() : string | 100 | 1 |  | 0 | 0
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | ParseWegmansData | GetValidParameters() : string | 98 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunPushAllJob | GetValidParameters() : string | 91 | 1 |  | 0 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunSetupJob | GetValidParameters() : string | 91 | 1 |  | 0 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | BaseJob | GetName() : string | 100 | 1 |  | 0 | 0
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | ParseWegmansData | GetName() : string | 91 | 1 |  | 0 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunPushAllJob | GetName() : string | 91 | 1 |  | 0 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunSetupJob | GetName() : string | 91 | 1 |  | 0 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Controllers | JobsController | Get() : string | 91 | 1 |  | 1 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine | FilterConfig | FilterConfig() | 100 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Algorithms | BaseAlgorithm | Execute(Item, BaseJobModel) : List<Distribution> | 100 | 1 |  | 4 | 0
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | BaseJob | Execute() : bool | 100 | 1 |  | 0 | 0
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | ParseWegmansData | Execute() : bool | 86 | 1 |  | 1 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobResponse | ErrorCode.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobResponse | ErrorCode.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | DistributionPercentBySegment.set(Dictionary<string, double>) : void | 95 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | DistributionPercentBySegment.get() : Dictionary<string, double> | 98 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobRequest | Data.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobRequest | Data.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine | BundleConfig | BundleConfig() | 100 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | BaseJob | BaseJob() | 87 | 1 |  | 0 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine | WebApiApplication | Application_Start() : void | 73 | 1 |  | 9 | 5
Member | Simpply.Global (Debug) | Simpply.Global | Constants.ControllerAction.Season | Season() | 100 | 1 |  | 0 | 1
Member | Simpply.Global (Debug) | Simpply.Global | Constants.ControllerAction.Planogram | Planogram() | 100 | 1 |  | 0 | 1
Member | Simpply.Global (Debug) | Simpply.Global | Constants.ControllerAction.Item | Item() | 100 | 1 |  | 0 | 1
Member | Simpply.Global (Debug) | Simpply.Global | Constants.ControllerAction | ControllerAction() | 100 | 1 |  | 0 | 1
Member | Simpply.Global (Debug) | Simpply.Global | Constants.Controller | Controller() | 100 | 1 |  | 0 | 1
Member | Simpply.Global (Debug) | Simpply.Global | Constants | Constants() | 100 | 1 |  | 0 | 1
Member | Simpply.Global (Debug) | Simpply.Global | Constants.ControllerAction.Account | Account() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ItemProviderTest | SaveDistribution() : void | 46 | 13 |  | 13 | 26
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | AccountControllerTest | SaveColumnPreferences() : void | 55 | 5 |  | 23 | 12
Member | Simpply.Tests (Debug) | Simpply.Tests.Jobs | RunSetupJobTest | ValidateParametersTest() : void | 57 | 3 |  | 6 | 15
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | ItemControllerTest | ItemExplorer() : void | 59 | 3 |  | 20 | 8
Member | Simpply.Tests (Debug) | Simpply.Tests.ViewModels | ItemModelsTest | ItemDetailModelHasCorrectAggregateGrid() : void | 61 | 3 |  | 10 | 10
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | ItemControllerTest | ItemDetail() : void | 66 | 3 |  | 16 | 5
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | PlanogramProviderTest | GetReturnsOnlyActivePlanograms() : void | 65 | 3 |  | 9 | 7
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | PlanogramProviderTest | GetResultsAreInOrder() : void | 65 | 3 |  | 9 | 7
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ItemProviderTest | GetDetailsReturnsRelatedDistributions() : void | 69 | 3 |  | 9 | 5
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ItemProviderTest | GetDetailsReturnsRelatedSalesInformation() : void | 69 | 2 |  | 9 | 5
Member | Simpply.Tests (Debug) | Simpply.Tests.Algorithms | SetupAlgorithmTest | ExecuteSetupDistributionTest() : void | 62 | 2 |  | 9 | 8
Member | Simpply.Tests (Debug) | Simpply.Tests.Algorithms | PushAllAlgorithmTest | ExecutePushAllDistributionTest() : void | 62 | 2 |  | 9 | 8
Member | Simpply.Tests (Debug) | Simpply.Tests.Algorithms | PushAllAlgorithmTest | TestInit() : void | 47 | 1 |  | 8 | 33
Member | Simpply.Tests (Debug) | Simpply.Tests.Algorithms | SetupAlgorithmTest | TestInit() : void | 48 | 1 |  | 9 | 29
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | AccountControllerTest | TestInit() : void | 92 | 1 |  | 3 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | ItemControllerTest | TestInit() : void | 70 | 1 |  | 7 | 5
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | PlanogramControllerTest | TestInit() : void | 77 | 1 |  | 5 | 3
Member | Simpply.Tests (Debug) | Simpply.Tests.Jobs | RunSetupJobTest | TestInit() : void | 70 | 1 |  | 1 | 6
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | BaseProviderTest | TestInit() : void | 94 | 1 |  | 3 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ColumnPreferenceProviderTest | TestInit() : void | 94 | 1 |  | 3 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ItemProviderTest | TestInit() : void | 94 | 1 |  | 3 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | PlanogramProviderTest | TestInit() : void | 94 | 1 |  | 3 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | SalesInformationProviderTest | TestInit() : void | 94 | 1 |  | 3 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | StoreProviderTest | TestInit() : void | 94 | 1 |  | 3 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.ViewModels | ItemModelsTest | TestInit() : void | 75 | 1 |  | 6 | 2
Member | Simpply.Tests (Debug) | Simpply.Tests.Algorithms | PushAllAlgorithmTest | TestInit() : void | 47 | 1 |  | 8 | 33
Member | Simpply.Tests (Debug) | Simpply.Tests.Algorithms | SetupAlgorithmTest | TestInit() : void | 47 | 1 |  | 9 | 31
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | AccountControllerTest | TestInit() : void | 92 | 1 |  | 3 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | ItemControllerTest | TestInit() : void | 77 | 1 |  | 5 | 3
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | PlanogramControllerTest | TestInit() : void | 77 | 1 |  | 5 | 3
Member | Simpply.Tests (Debug) | Simpply.Tests.Jobs | RunSetupJobTest | TestInit() : void | 70 | 1 |  | 1 | 6
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | BaseProviderTest | TestInit() : void | 94 | 1 |  | 3 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ColumnPreferenceProviderTest | TestInit() : void | 94 | 1 |  | 3 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ItemProviderTest | TestInit() : void | 94 | 1 |  | 3 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | PlanogramProviderTest | TestInit() : void | 94 | 1 |  | 3 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.ViewModels | ItemModelsTest | TestInit() : void | 75 | 1 |  | 6 | 2
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | StoreProviderTest | StoreProviderTest() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Algorithms | SetupAlgorithmTest | SetupAlgorithmTest() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Algorithms | SetupAlgorithmTest | SetupAlgorithmTest() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | ItemControllerTest | SaveItemDistributionCallsProvidersCorrectly() : void | 72 | 1 |  | 7 | 3
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | ItemControllerTest | SaveItemDistributionCallsProvidersCorrectly() : void | 72 | 1 |  | 7 | 3
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ColumnPreferenceProviderTest | Save() : void | 75 | 1 |  | 4 | 2
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ColumnPreferenceProviderTest | Save() : void | 75 | 1 |  | 4 | 2
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | SalesInformationProviderTest | SalesInformationProviderTest() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Jobs | RunSetupJobTest | RunSetupJobTest() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Jobs | RunSetupJobTest | RunSetupJobTest() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Algorithms | PushAllAlgorithmTest | PushAllAlgorithmTest() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Algorithms | PushAllAlgorithmTest | PushAllAlgorithmTest() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | PlanogramProviderTest | PlanogramProviderTest() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | PlanogramProviderTest | PlanogramProviderTest() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | PlanogramControllerTest | PlanogramControllerTest() | 76 | 1 |  | 3 | 2
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | PlanogramControllerTest | PlanogramControllerTest() | 76 | 1 |  | 3 | 2
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ItemProviderTest | ItemProviderTest() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ItemProviderTest | ItemProviderTest() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.ViewModels | ItemModelsTest | ItemModelsTest() | 66 | 1 |  | 3 | 4
Member | Simpply.Tests (Debug) | Simpply.Tests.ViewModels | ItemModelsTest | ItemModelsTest() | 66 | 1 |  | 3 | 4
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | ItemControllerTest | ItemExplorerFiltersToCorrectPlanogram() : void | 63 | 1 |  | 11 | 7
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | ItemControllerTest | ItemExplorerFiltersToCorrectPlanogram() : void | 63 | 1 |  | 11 | 7
Member | Simpply.Tests (Debug) | Simpply.Tests.ViewModels | ItemModelsTest | ItemDetailModelHasCorrectItemName() : void | 77 | 1 |  | 4 | 3
Member | Simpply.Tests (Debug) | Simpply.Tests.ViewModels | ItemModelsTest | ItemDetailModelHasCorrectItemName() : void | 75 | 1 |  | 5 | 3
Member | Simpply.Tests (Debug) | Simpply.Tests.ViewModels | ItemModelsTest | ItemDetailModelHasCorrectDistributionGrid() : void | 73 | 1 |  | 8 | 4
Member | Simpply.Tests (Debug) | Simpply.Tests.ViewModels | ItemModelsTest | ItemDetailModelHasCorrectDistributionGrid() : void | 71 | 1 |  | 9 | 4
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | ItemControllerTest | ItemControllerTest() | 69 | 1 |  | 5 | 3
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | ItemControllerTest | ItemControllerTest() | 69 | 1 |  | 5 | 3
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | PlanogramControllerTest | IndexGetsAllPlanograms() : void | 66 | 1 |  | 8 | 6
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | PlanogramControllerTest | IndexGetsAllPlanograms() : void | 66 | 1 |  | 8 | 6
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | PlanogramControllerTest | IndexGetsActivePlanogramsOnly() : void | 66 | 1 |  | 8 | 6
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | PlanogramControllerTest | IndexGetsActivePlanogramsOnly() : void | 66 | 1 |  | 8 | 6
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | StoreProviderTest | GetStores() : void | 100 | 1 |  | 1 | 0
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | StoreProviderTest | GetStore() : void | 100 | 1 |  | 1 | 0
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | SalesInformationProviderTest | GetSales() : void | 100 | 1 |  | 1 | 0
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | SalesInformationProviderTest | GetSale() : void | 100 | 1 |  | 1 | 0
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | PlanogramProviderTest | GetResultIsNotNull() : void | 69 | 1 |  | 7 | 6
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | PlanogramProviderTest | GetResultIsNotNull() : void | 69 | 1 |  | 7 | 6
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ItemProviderTest | GetItems() : void | 71 | 1 |  | 7 | 5
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ItemProviderTest | GetItems() : void | 71 | 1 |  | 7 | 5
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ItemProviderTest | GetDetailsReturnsRelatedStores() : void | 74 | 1 |  | 6 | 4
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ItemProviderTest | GetDetailsReturnsRelatedStores() : void | 73 | 1 |  | 7 | 4
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ItemProviderTest | GetDetailsReturnsANonNullItem() : void | 75 | 1 |  | 4 | 4
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ItemProviderTest | GetDetailsReturnsANonNullItem() : void | 74 | 1 |  | 5 | 4
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | BreadcrumbControllerTest | GetBreadcrumbsTest() : void | 100 | 1 |  | 1 | 0
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | BreadcrumbControllerTest | GetBreadcrumbsTest() : void | 100 | 1 |  | 1 | 0
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ColumnPreferenceProviderTest | Get() : void | 82 | 1 |  | 6 | 2
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ColumnPreferenceProviderTest | Get() : void | 82 | 1 |  | 6 | 2
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ColumnPreferenceProviderTest | ColumnPreferenceProviderTest() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ColumnPreferenceProviderTest | ColumnPreferenceProviderTest() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | BreadcrumbControllerTest | BreadcrumbControllerTest() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | BreadcrumbControllerTest | BreadcrumbControllerTest() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | BaseProviderTest | BaseProviderTest() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | BaseProviderTest | BaseProviderTest() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | AccountControllerTest | AccountControllerTest() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | AccountControllerTest | AccountControllerTest() | 100 | 1 |  | 0 | 1
Member | Simpply.Util (Debug) | Simpply.Util.Extensions | CollectionExtensions | IsEmpty<T>(this ICollection<T>) : bool | 84 | 2 |  | 2 | 2
Member | Simpply.Util (Debug) | Simpply.Util.Extensions | CollectionExtensions | IsEmpty<T>(this ICollection<T>) : bool | 84 | 2 |  | 2 | 2
Member | Simpply.Util (Debug) | Simpply.Util.Extensions | StringExtensions | IsNullOrWhiteSpace(this string) : bool | 87 | 1 |  | 1 | 2
Member | Simpply.Util (Debug) | Simpply.Util.Extensions | StringExtensions | IsNullOrWhiteSpace(this string) : bool | 87 | 1 |  | 1 | 2

## Code Metrics Iteration 5
Scope | Project | Namespace | Type | Member | Maintainability Index | Cyclomatic Complexity | Depth of Inheritance | Class Coupling | Lines of Code | Web | Engine | Access
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | ItemDetailModel(Item) | 33 | 32 |  | 19 | 42 | 1.955307263 | 1.520408163 | 1.826923077
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ColumnPreferenceModel(string, string, string, List<Column>, List<ColumnPreference>) | 32 | 25 |  | 17 | 77
Member | Simpply (Debug) | Simpply.Models | SeasonExplorerModel | SeasonExplorerModel(List<SeasonInfo>, string, bool, bool, List<ColumnPreference>) | 36 | 20 |  | 15 | 46
Member | Simpply (Debug) | Simpply.Models | ItemExplorerModel | ItemExplorerModel(List<Item>, string, int?, string, bool, List<ColumnPreference>) | 39 | 20 |  | 12 | 36
Member | Simpply (Debug) | Simpply.Models.POG | PlanogramExplorerModel | PlanogramExplorerModel(List<Planogram>, string, bool, bool, List<ColumnPreference>, int?) | 39 | 16 |  | 16 | 39
Member | Simpply (Debug) | Simpply.Models | BreadcrumbTrailModel | AdjustBreadcrumbsTrail(string, string, string) : void | 48 | 11 |  | 6 | 27
Member | Simpply (Debug) | Simpply.Controllers | ItemController | SaveDistribution(List<DistributionModel>, int, int, bool) : ActionResult | 54 | 9 |  | 9 | 14
Member | Simpply (Debug) | Simpply.Controllers | ItemController | FinalizeItems(List<int>, DistributionType) : ActionResult | 55 | 6 |  | 9 | 16
Member | Simpply (Debug) | Simpply.Helpers | WebHelper | getParamId(string) : int | 63 | 5 |  | 0 | 8
Member | Simpply (Debug) | Simpply.Helpers | WebHelper | GenerateActionUrl(string, string, Dictionary<string, string>) : string | 63 | 5 |  | 4 | 8
Member | Simpply (Debug) | Simpply.Models | ItemExplorerModel | CreateHeaderCell(string, string, int?, string, string, bool) : GridCellModel | 63 | 5 |  | 4 | 7
Member | Simpply (Debug) | Simpply.Controllers | ItemController | SetPreviousNext(ItemDetailModel, long, int?, string, bool) : ItemDetailModel | 55 | 4 |  | 7 | 16
Member | Simpply (Debug) | Simpply.Controllers | AccountController | SaveColumnPreferences(ColumnPreferenceModel) : ActionResult | 55 | 4 |  | 9 | 12
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | GetColumnId(string) : long? | 65 | 4 |  | 2 | 8
Member | Simpply (Debug) | Simpply.Controllers | SeasonController | SeasonExplorer(bool, string, bool) : ActionResult | 63 | 3 |  | 17 | 7
Member | Simpply (Debug) | Simpply.Controllers | PlanogramController | PlanogramExplorer(int?, bool, string, bool) : ActionResult | 63 | 3 |  | 19 | 7
Member | Simpply (Debug) | Simpply.Controllers | ItemController | ItemExplorer(string, int?, string, bool) : ActionResult | 63 | 3 |  | 18 | 7
Member | Simpply (Debug) | Simpply.Controllers | ItemController | ItemDetail(long, int?, string, bool) : ActionResult | 58 | 3 |  | 15 | 12
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | GetColumnName(string) : string | 67 | 3 |  | 1 | 7
Member | Simpply (Debug) | Simpply.Models.POG | PlanogramExplorerModel | FormatActionUrl(string, string, bool, bool, int?) : string | 67 | 3 |  | 2 | 6
Member | Simpply (Debug) | Simpply.Controllers | ItemController | Search(string) : ActionResult | 64 | 2 |  | 7 | 8
Member | Simpply (Debug) | Simpply.Helpers | WebHelper | GetControllerActionParameters(string) : string | 72 | 2 |  | 0 | 5
Member | Simpply (Debug) | Simpply.Controllers | BreadcrumbController | GetBreadCrumbs() : ActionResult | 60 | 2 |  | 7 | 11
Member | Simpply (Debug) | Simpply.Helpers | WebHelper | GenerateActionUrl(string, string, string) : string | 73 | 2 |  | 1 | 4
Member | Simpply (Debug) | Simpply.Models | SeasonExplorerModel | FormatActionUrl(string, string, bool, bool) : string | 73 | 2 |  | 1 | 4
Member | Simpply (Debug) | Simpply.Models | SeasonExplorerModel | CreateHeaderCell(string, string, string, bool, bool) : GridCellModel | 78 | 2 |  | 1 | 2
Member | Simpply (Debug) | Simpply.Models.POG | PlanogramExplorerModel | CreateHeaderCell(string, string, string, bool, bool, int?) : GridCellModel | 78 | 2 |  | 2 | 2
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | WarehouseBalanceOnHand.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | WarehouseBalanceOnHand.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | BreadcrumbModel | Value.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | FormInput | Value.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | Value.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | BreadcrumbModel | Value.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | FormInput | Value.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | Value.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | Type.set(GridCellType) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | Type.get() : GridCellType | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | tableCondensed.set(bool) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | tableCondensed.get() : bool | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | Table.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | Table.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Controllers | StoreController | StoreController() | 100 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | sortDescending.set(bool) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | sortDescending.get() : bool | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | sortColumn.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | sortColumn.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ShownColumnsList.set(List<SelectListItem>) : void | 95 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ShownColumnsList.get() : List<SelectListItem> | 98 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ShownColumnsDefault.set(List<SelectListItem>) : void | 95 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ShownColumnsDefault.get() : List<SelectListItem> | 98 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ShownColumns.set(List<string>) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ShownColumns.get() : List<string> | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | BreadcrumbTrailModel | SetToDefault() : void | 69 | 1 |  | 3 | 4
Member | Simpply (Debug) | Simpply.Controllers | SeasonController | SeasonController(ISeasonProvider, IColumnPreferenceProvider) | 81 | 1 |  | 3 | 3
Member | Simpply (Debug) | Simpply.Models | GridModel | Rows.set(List<GridRowModel>) : void | 95 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | Rows.get() : List<GridRowModel> | 98 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply | RouteConfig | RouteConfig() | 100 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Controllers | BaseController | Root() : ActionResult | 86 | 1 |  | 2 | 2
Member | Simpply (Debug) | Simpply | RouteConfig | RegisterRoutes(RouteCollection) : void | 82 | 1 |  | 3 | 2
Member | Simpply (Debug) | Simpply | FilterConfig | RegisterGlobalFilters(GlobalFilterCollection) : void | 94 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.App_Start | AutofacConfig | RegisterComponents() : void | 70 | 1 |  | 10 | 5
Member | Simpply (Debug) | Simpply | BundleConfig | RegisterBundles(BundleCollection) : void | 64 | 1 |  | 4 | 6
Member | Simpply (Debug) | Simpply | AuthConfig | RegisterAuth() : void | 100 | 1 |  | 0 | 0
Member | Simpply (Debug) | Simpply | WebApiConfig | Register(HttpConfiguration) : void | 89 | 1 |  | 4 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | PreviousId.set(long) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | PreviousId.get() : long | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | planogramId.set(int?) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | planogramId.get() : int? | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Controllers | PlanogramController | PlanogramController(IPlanogramProvider, IColumnPreferenceProvider) | 81 | 1 |  | 3 | 3
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | NextId.set(long) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | NextId.get() : long | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | Column | Name.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | FormInput | Name.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | Name.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | Column | Name.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | FormInput | Name.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | Name.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply | MvcApplication | MvcApplication() | 100 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | ModelRow.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | ModelRow.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | ModelName.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | ModelName.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | ModelAttribute.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | ModelAttribute.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | LastModifiedDate.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | LastModifiedDate.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | LastModifiedBy.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | LastModifiedBy.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Controllers | BaseController | JsonActionResult(JsonReturnType, string, string, string, object) : ActionResult | 68 | 1 |  | 5 | 6
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | ItemFinalized.set(bool) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | ItemFinalized.get() : bool | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Controllers | ItemController | ItemController(IItemProvider, IStoreProvider, ISalesInformationProvider, IColumnPreferenceProvider) | 71 | 1 |  | 6 | 6
Member | Simpply (Debug) | Simpply.Controllers | ItemController | ItemController() | 90 | 1 |  | 4 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | IsSortedDescending.set(bool) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | IsSortedDescending.get() : bool | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | IsSorted.set(bool) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | IsSorted.get() : bool | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridRowModel | IsHeader.set(bool) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridRowModel | IsHeader.get() : bool | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemExplorerModel | IsFilteredToPlanogram.set(bool) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemExplorerModel | IsFilteredToPlanogram.get() : bool | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | SeasonExplorerModel | InactiveSeasonURL.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | SeasonExplorerModel | InactiveSeasonURL.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models.POG | PlanogramExplorerModel | InactivePlanogramURL.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models.POG | PlanogramExplorerModel | InactivePlanogramURL.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | Id.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | Id.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | HiddenColumnsList.set(List<SelectListItem>) : void | 95 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | HiddenColumnsList.get() : List<SelectListItem> | 98 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | HiddenColumns.set(List<string>) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | HiddenColumns.get() : List<string> | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | Header.set(GridRowModel) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | Header.get() : GridRowModel | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | GridRowModel | GridRowModel() | 87 | 1 |  | 2 | 2
Member | Simpply (Debug) | Simpply.Models | GridModel | GridModel() | 72 | 1 |  | 3 | 5
Member | Simpply (Debug) | Simpply.Models | GridCellModel | GridCellModel() | 78 | 1 |  | 0 | 4
Member | Simpply (Debug) | Simpply.Models | ItemExplorerModel | Grid.set(GridModel) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | SeasonExplorerModel | Grid.set(GridModel) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models.POG | PlanogramExplorerModel | Grid.set(GridModel) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ItemExplorerModel | Grid.get() : GridModel | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | SeasonExplorerModel | Grid.get() : GridModel | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models.POG | PlanogramExplorerModel | Grid.get() : GridModel | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Helpers | WebHelper | GetControllerName(string) : string | 78 | 1 |  | 0 | 3
Member | Simpply (Debug) | Simpply.Helpers | WebHelper | GetControllerActionName(string) : string | 78 | 1 |  | 0 | 3
Member | Simpply (Debug) | Simpply.Models | GridModel | FormMethod.set(FormMethod) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | FormMethod.get() : FormMethod | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | FormInput | FormInput() | 100 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | FormId.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | FormId.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | FormHiddenInputs.set(List<FormInput>) : void | 95 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | FormHiddenInputs.get() : List<FormInput> | 98 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | FormController.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | FormController.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | FormAction.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | FormAction.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply | FilterConfig | FilterConfig() | 100 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | Distribution.set(GridModel) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | Distribution.get() : GridModel | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | Column | DisplayName.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | Column | DisplayName.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | CssClasses.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridRowModel | CssClasses.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | CssClasses.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridRowModel | CssClasses.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ControllerName.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ControllerName.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ControllerAction.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ControllerAction.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Controllers | StoreController | CompareTostore() : ActionResult | 89 | 1 |  | 2 | 2
Member | Simpply (Debug) | Simpply.Controllers | StoreController | CompareToMultiplestores() : ActionResult | 89 | 1 |  | 2 | 2
Member | Simpply (Debug) | Simpply.Models | ItemExplorerModel | ColumnPreferences.set(ColumnPreferenceModel) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | SeasonExplorerModel | ColumnPreferences.set(ColumnPreferenceModel) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models.POG | PlanogramExplorerModel | ColumnPreferences.set(ColumnPreferenceModel) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ItemExplorerModel | ColumnPreferences.get() : ColumnPreferenceModel | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | SeasonExplorerModel | ColumnPreferences.get() : ColumnPreferenceModel | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models.POG | PlanogramExplorerModel | ColumnPreferences.get() : ColumnPreferenceModel | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ColumnPreferenceModel() | 71 | 1 |  | 2 | 6
Member | Simpply (Debug) | Simpply.Models | Column | Column() | 100 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridRowModel | Cells.set(List<GridCellModel>) : void | 95 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | GridRowModel | Cells.get() : List<GridCellModel> | 98 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply | BundleConfig | BundleConfig() | 100 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | BreadcrumbTrailModel | BreadcrumbTrailModel() | 65 | 1 |  | 3 | 6
Member | Simpply (Debug) | Simpply.Models | BreadcrumbModel | BreadcrumbModel() | 100 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Controllers | BreadcrumbController | BreadcrumbController() | 100 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Controllers | BaseController | BaseController() | 100 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply | MvcApplication | Application_Start() : void | 69 | 1 |  | 11 | 7
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | Aggregate.set(GridModel) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | Aggregate.get() : GridModel | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | SeasonExplorerModel | ActiveOnly.set(bool) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models.POG | PlanogramExplorerModel | ActiveOnly.set(bool) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | SeasonExplorerModel | ActiveOnly.get() : bool | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models.POG | PlanogramExplorerModel | ActiveOnly.get() : bool | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | BreadcrumbModel | ActionUrl.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | ActionUrl.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridRowModel | ActionUrl.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | BreadcrumbModel | ActionUrl.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | ActionUrl.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridRowModel | ActionUrl.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Controllers | AccountController | AccountController(IColumnPreferenceProvider) | 87 | 1 |  | 2 | 2
Member | Simpply.Data (Debug) | Simpply.Data | WeeklyPurchase | Year.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | WeeklyPurchase | Year.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | WeeklyPurchase | WeeklyPurchase() | 100 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | WeeklyPurchase | Week.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | WeeklyPurchase | Week.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | UnitsSold.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Shared | AggregateItemData | UnitsSold.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | UnitsSold.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Shared | AggregateItemData | UnitsSold.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Shared | AggregateItemData | UnitsShrunk.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Shared | AggregateItemData | UnitsShrunk.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | UnitsReceived.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Shared | AggregateItemData | UnitsReceived.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | UnitsReceived.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Shared | AggregateItemData | UnitsReceived.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Distribution | Type.set(DistributionType) : void | 95 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Distribution | Type.get() : DistributionType | 98 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Account | ColumnPreference | Table.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Account | ColumnPreference | Table.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Item | Stores.set(List<Store>) : void | 95 | 1 |  | 2 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Item | Stores.get() : List<Store> | 98 | 1 |  | 2 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | StoreId.set(long) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | DistributionModel | StoreId.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | StoreId.get() : long | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | DistributionModel | StoreId.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Store | Store() | 100 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Item | Status.set(ItemStatus) : void | 95 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Item | Status.get() : ItemStatus | 98 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SeasonInfo | StartDate.set(DateTime) : void | 95 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data.POG | Planogram | StartDate.set(DateTime) : void | 95 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SeasonInfo | StartDate.get() : DateTime | 98 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data.POG | Planogram | StartDate.get() : DateTime | 98 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Account | ColumnPreference | ShowColumn.set(bool) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Account | ColumnPreference | ShowColumn.get() : bool | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | ShelfSpace.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | ShelfSpace.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | SellThrough.set(double) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Shared | AggregateItemData | SellThrough.set(decimal) : void | 95 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | SellThrough.get() : double | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Shared | AggregateItemData | SellThrough.get() : decimal | 98 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Store | Segmentation.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Store | Segmentation.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SeasonInfo | SeasonInfo() | 100 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | SalesInformation() | 100 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Distribution | SalesId.set(long) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | DistributionModel | SalesId.set(long) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | WeeklyPurchase | SalesId.set(long) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Distribution | SalesId.get() : long | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | DistributionModel | SalesId.get() : long | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | WeeklyPurchase | SalesId.get() : long | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Store | Sales.set(SalesInformation) : void | 95 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Store | Sales.get() : SalesInformation | 98 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data | WeeklyPurchase | Purchases.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | WeeklyPurchase | Purchases.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Job | ProgressPercent.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Job | ProgressPercent.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Job | Progress.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Job | Progress.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.POG | Planogram | Planogram() | 100 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | PercentageOfTotal.set(double) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | PercentageOfTotal.get() : double | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Account | ColumnPreference | Order.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Account | ColumnPreference | Order.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Item | Name.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Job | Name.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SeasonInfo | Name.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Store | Name.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.POG | Planogram | Name.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Item | Name.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Job | Name.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SeasonInfo | Name.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Store | Name.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.POG | Planogram | Name.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Distribution | ModifiedOn.set(DateTime?) : void | 95 | 1 |  | 2 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Distribution | ModifiedOn.get() : DateTime? | 98 | 1 |  | 2 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Distribution | ModifiedBy.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Distribution | ModifiedBy.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | LastYearsSales.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | LastYearsSales.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Job | Job() | 100 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | ItemId.set(long) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | ItemId.get() : long | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Distribution | ItemAmount.set(long) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Distribution | ItemAmount.get() : long | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Item | Item() | 100 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Distribution | Id.set(long) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | DistributionModel | Id.set(long) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Example | Id.set(long) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Job | Id.set(long) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | Id.set(long) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Store | Id.set(long) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | WeeklyPurchase | Id.set(long) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Account | ColumnPreference | Id.set(long?) : void | 95 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Item | Id.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SeasonInfo | Id.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.POG | Planogram | Id.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Account | ColumnPreference | Id.get() : long? | 98 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Distribution | Id.get() : long | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | DistributionModel | Id.get() : long | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Example | Id.get() : long | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Job | Id.get() : long | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | Id.get() : long | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Store | Id.get() : long | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | WeeklyPurchase | Id.get() : long | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Item | Id.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SeasonInfo | Id.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.POG | Planogram | Id.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Example | Example() | 100 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SeasonInfo | EndDate.set(DateTime) : void | 95 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data.POG | Planogram | EndDate.set(DateTime) : void | 95 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SeasonInfo | EndDate.get() : DateTime | 98 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data.POG | Planogram | EndDate.get() : DateTime | 98 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Store | Distributions.set(List<Distribution>) : void | 95 | 1 |  | 2 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Store | Distributions.get() : List<Distribution> | 98 | 1 |  | 2 | 1
Member | Simpply.Data (Debug) | Simpply.Data | DistributionModel | DistributionModel() | 100 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Distribution | Distribution() | 100 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Item | Description.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Item | Description.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Distribution | CreatedOn.set(DateTime) : void | 95 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Distribution | CreatedOn.get() : DateTime | 98 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Account | ColumnPreference | ControllerAction.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Account | ColumnPreference | ControllerAction.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Account | ColumnPreference | Controller.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Account | ColumnPreference | Controller.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Account | ColumnPreference | ColumnPreference() | 100 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Account | ColumnPreference | Column.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Account | ColumnPreference | Column.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | CalculatedInventory.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | CalculatedInventory.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Item | BalanceOnHand.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SeasonInfo | BalanceOnHand.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.POG | Planogram | BalanceOnHand.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Item | BalanceOnHand.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SeasonInfo | BalanceOnHand.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.POG | Planogram | BalanceOnHand.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | DistributionModel | Amount.set(long) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | DistributionModel | Amount.get() : long | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Shared | AggregateItemData | AggregateItemData() | 100 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SeasonInfo | AggregateDataSeasonToDate.set(AggregateItemData) : void | 95 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data.POG | Planogram | AggregateDataSeasonToDate.set(AggregateItemData) : void | 95 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SeasonInfo | AggregateDataSeasonToDate.get() : AggregateItemData | 98 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data.POG | Planogram | AggregateDataSeasonToDate.get() : AggregateItemData | 98 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SeasonInfo | AggregateData7Days.set(AggregateItemData) : void | 95 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SeasonInfo | AggregateData7Days.get() : AggregateItemData | 98 | 1 |  | 1 | 1
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ItemProvider | GetDetails(long) : Item | 45 | 10 |  | 18 | 32
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ItemProvider | SaveDistribution(List<DistributionModel>, int, int, bool, string) : void | 52 | 5 |  | 16 | 15
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ItemProvider | SaveMultiple(List<Distribution>) : void | 52 | 4 |  | 16 | 15
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ColumnPreferenceProvider | Save(List<ColumnPreference>) : void | 52 | 4 |  | 15 | 15
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | SeasonProvider | Get(bool, string, bool) : List<SeasonInfo> | 60 | 4 |  | 13 | 10
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | PlanogramProvider | Get(bool, int?, string, bool) : List<Planogram> | 60 | 4 |  | 13 | 10
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ItemProvider | FinalizeItems(List<int>, DistributionType, string) : void | 50 | 4 |  | 14 | 21
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ItemProvider | GetSalesHistory(List<long>, int?, int?, int?, int?) : List<WeeklyPurchase> | 60 | 3 |  | 15 | 9
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | SalesInformationProvider | Get(long, long) : SalesInformation | 70 | 3 |  | 5 | 5
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | JobProvider | UpdateProgress(long, string, int) : void | 72 | 2 |  | 7 | 4
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ExampleProvider | SelectExample(int) : Example | 70 | 2 |  | 9 | 5
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | JobProvider | Insert(string) : long | 69 | 2 |  | 8 | 5
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | SeasonProvider | GetSeasonName(int) : string | 66 | 2 |  | 9 | 7
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | PlanogramProvider | GetPlanogramName(int) : string | 66 | 2 |  | 9 | 7
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ItemProvider | GetItemName(int) : string | 66 | 2 |  | 9 | 7
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ItemProvider | GetIds() : List<long> | 69 | 2 |  | 9 | 5
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ColumnPreferenceProvider | Get(string, string, string) : List<ColumnPreference> | 66 | 2 |  | 10 | 7
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | StoreProvider | Get(long) : Store | 71 | 2 |  | 5 | 5
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | JobProvider | Get(long) : Job | 69 | 2 |  | 9 | 5
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ItemProvider | Get(long?, string, int?, string, bool?) : List<Item> | 69 | 2 |  | 10 | 5
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IJobProvider | UpdateProgress(long, string, int) : void | 100 | 1 |  | 0 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | StoreProvider | StoreProvider() | 76 | 1 |  | 3 | 2
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | SeasonProvider | SeasonProvider() | 100 | 1 |  | 1 | 1
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IItemProvider | SaveMultiple(List<Distribution>) : void | 100 | 1 |  | 2 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IItemProvider | SaveDistribution(List<DistributionModel>, int, int, bool, string) : void | 100 | 1 |  | 2 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IColumnPreferenceProvider | Save(List<ColumnPreference>) : void | 100 | 1 |  | 2 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | SalesInformationProvider | SalesInformationProvider() | 68 | 1 |  | 3 | 2
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | PlanogramProvider | PlanogramProvider() | 100 | 1 |  | 1 | 1
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access | AccessModule | Load(ContainerBuilder) : void | 63 | 1 |  | 18 | 7
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | JobProvider | JobProvider() | 100 | 1 |  | 1 | 1
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ItemProvider | ItemProvider() | 100 | 1 |  | 1 | 1
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IJobProvider | Insert(string) : long | 100 | 1 |  | 0 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IItemProvider | GetSalesHistory(List<long>, int?, int?, int?, int?) : List<WeeklyPurchase> | 100 | 1 |  | 3 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IItemProvider | GetDetails(long) : Item | 100 | 1 |  | 1 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IColumnPreferenceProvider | Get(string, string, string) : List<ColumnPreference> | 100 | 1 |  | 2 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IStoreProvider | Get(long) : Store | 100 | 1 |  | 1 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IJobProvider | Get(long) : Job | 100 | 1 |  | 1 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IItemProvider | Get(long?, string, int?, string, bool?) : List<Item> | 100 | 1 |  | 3 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | ISalesInformationProvider | Get(long, long) : SalesInformation | 100 | 1 |  | 1 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | ISeasonProvider | Get(bool, string, bool) : List<SeasonInfo> | 100 | 1 |  | 2 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IPlanogramProvider | Get(bool, int?, string, bool) : List<Planogram> | 100 | 1 |  | 3 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IStoreProvider | Get() : List<Store> | 100 | 1 |  | 2 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | StoreProvider | Get() : List<Store> | 91 | 1 |  | 2 | 2
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | ISalesInformationProvider | Get() : List<SalesInformation> | 100 | 1 |  | 2 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | SalesInformationProvider | Get() : List<SalesInformation> | 91 | 1 |  | 2 | 2
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IItemProvider | FinalizeItems(List<int>, DistributionType, string) : void | 100 | 1 |  | 2 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ExampleProvider | ExampleProvider() | 100 | 1 |  | 1 | 1
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | BaseProvider | connectionString.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | BaseProvider | connectionString.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ColumnPreferenceProvider | ColumnPreferenceProvider() | 100 | 1 |  | 1 | 1
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | BaseProvider | BaseProvider() | 83 | 1 |  | 3 | 2
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access | AccessModule | AccessModule() | 100 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | JobInvoker | ScheduleJob(BaseJob) : JobResponse | 45 | 8 |  | 10 | 34
Member | Simpply.Engine (Debug) | Simpply.Engine.Controllers | JobsController | Post(JobRequest) : object | 54 | 6 |  | 13 | 17
Member | Simpply.Engine (Debug) | Simpply.Engine.Algorithms | PushAllAlgorithm | Execute(Item, BaseJobModel) : List<Distribution> | 51 | 6 |  | 13 | 19
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunSetupJob | ValidateParameters() : bool | 58 | 5 |  | 5 | 13
Member | Simpply.Engine (Debug) | Simpply.Engine.Algorithms | SetupAlgorithm | Execute(Item, BaseJobModel) : List<Distribution> | 48 | 5 |  | 12 | 24
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunPushAllJob | ValidateParameters() : bool | 64 | 4 |  | 4 | 9
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunSellthroughJob | ValidateParameters() : bool | 60 | 4 |  | 5 | 11
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | JobInvoker | GetInstance() : JobInvoker | 67 | 4 |  | 1 | 8
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | ParseWegmansData | Execute(long) : bool | 55 | 4 |  | 11 | 16
Member | Simpply.Engine (Debug) | Simpply.Engine.Algorithms | SellthroughAlgorithm | Execute(Item, BaseJobModel) : List<Distribution> | 53 | 4 |  | 11 | 17
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunPushAllJob | Execute(long) : bool | 56 | 3 |  | 8 | 13
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunSellthroughJob | Execute(long) : bool | 51 | 3 |  | 13 | 18
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunSetupJob | Execute(long) : bool | 56 | 3 |  | 8 | 13
Member | Simpply.Engine (Debug) | Simpply.Engine.Algorithms | SellthroughAlgorithm | ComputeForecast(long, List<WeeklyPurchase>) : int | 68 | 3 |  | 4 | 6
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunSellthroughJob | MergeDictionaryWithDefault(Dictionary<string, double>, Dictionary<string, double>) : Dictionary<string, double> | 70 | 2 |  | 4 | 5
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunSetupJob | MergeDictionaryWithDefault(Dictionary<string, double>, Dictionary<string, double>) : Dictionary<string, double> | 70 | 2 |  | 4 | 5
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | BaseJob | BaseJob(string, JobProvider) | 71 | 2 |  | 2 | 6
Member | Simpply.Engine (Debug) | Simpply.Engine | WebApiApplication | WebApiApplication() | 100 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | BaseJob | ValidateParameters() : bool | 100 | 1 |  | 0 | 0
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | ParseWegmansData | ValidateParameters() : bool | 91 | 1 |  | 0 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | JobInvoker | ValidateNoConflict() : bool | 91 | 1 |  | 0 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunPushAllJobModel | Username.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | Username.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | Username.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunPushAllJobModel | Username.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | Username.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | Username.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | BaseJob | UpdateJobStatus(long, string, int) : void | 92 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobResponse | Success.set(bool) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobResponse | Success.get() : bool | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | SetupDistributionPercent.set(double) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | SetupDistributionPercent.get() : double | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Algorithms | SetupAlgorithm | SetupAlgorithm() | 100 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunPushAllJobModel | SellthroughPercentTrigger.set(double) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | SellthroughPercentTrigger.set(double) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunPushAllJobModel | SellthroughPercentTrigger.get() : double | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | SellthroughPercentTrigger.get() : double | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Algorithms | SellthroughAlgorithm | SellthroughAlgorithm() | 100 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | RunSetupJobModel() | 100 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunSetupJob | RunSetupJob(string) | 72 | 1 |  | 5 | 4
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | RunSellthroughJobModel() | 100 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunSellthroughJob | RunSellthroughJob(string) | 72 | 1 |  | 5 | 4
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunPushAllJobModel | RunPushAllJobModel() | 100 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunPushAllJob | RunPushAllJob(string) | 79 | 1 |  | 4 | 3
Member | Simpply.Engine (Debug) | Simpply.Engine | RouteConfig | RouteConfig() | 100 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine | RouteConfig | RegisterRoutes(RouteCollection) : void | 82 | 1 |  | 4 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine | FilterConfig | RegisterGlobalFilters(GlobalFilterCollection) : void | 94 | 1 |  | 2 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine | BundleConfig | RegisterBundles(BundleCollection) : void | 100 | 1 |  | 1 | 0
Member | Simpply.Engine (Debug) | Simpply.Engine | WebApiConfig | Register(HttpConfiguration) : void | 75 | 1 |  | 9 | 3
Member | Simpply.Engine (Debug) | Simpply.Engine.Algorithms | PushAllAlgorithm | PushAllAlgorithm() | 100 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | ParseWegmansData | ParseWegmansData(string) | 98 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobResponse | Message.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobResponse | Message.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Controllers | JobsController | JobsController() | 100 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobResponse | JobResponse(bool, int, string, long) | 74 | 1 |  | 0 | 5
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobRequest | JobRequest() | 82 | 1 |  | 0 | 3
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | JobInvoker | JobInvoker() | 76 | 1 |  | 5 | 4
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | JobInvoker | JobInvoker() | 82 | 1 |  | 4 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobResponse | JobId.set(long) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobResponse | JobId.get() : long | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobRequest | Job.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobRequest | Job.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Controllers | HomeController | Index() : ActionResult | 89 | 1 |  | 2 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunPushAllJobModel | Ids.set(List<long>) : void | 95 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | Ids.set(List<long>) : void | 95 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | Ids.set(List<long>) : void | 95 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunPushAllJobModel | Ids.get() : List<long> | 98 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | Ids.get() : List<long> | 98 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | Ids.get() : List<long> | 98 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Controllers | HomeController | HomeController() | 100 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | History.set(List<WeeklyPurchase>) : void | 95 | 1 |  | 2 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | History.get() : List<WeeklyPurchase> | 98 | 1 |  | 2 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | BaseJob | GetValidParameters() : string | 100 | 1 |  | 0 | 0
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | ParseWegmansData | GetValidParameters() : string | 91 | 1 |  | 0 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunPushAllJob | GetValidParameters() : string | 91 | 1 |  | 0 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunSellthroughJob | GetValidParameters() : string | 91 | 1 |  | 0 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunSetupJob | GetValidParameters() : string | 91 | 1 |  | 0 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | BaseJob | GetName() : string | 100 | 1 |  | 0 | 0
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | ParseWegmansData | GetName() : string | 91 | 1 |  | 0 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunPushAllJob | GetName() : string | 91 | 1 |  | 0 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunSellthroughJob | GetName() : string | 91 | 1 |  | 0 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunSetupJob | GetName() : string | 91 | 1 |  | 0 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Controllers | JobsController | Get(long) : string | 79 | 1 |  | 3 | 3
Member | Simpply.Engine (Debug) | Simpply.Engine | FilterConfig | FilterConfig() | 100 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | BaseJob | Execute(long) : bool | 100 | 1 |  | 0 | 0
Member | Simpply.Engine (Debug) | Simpply.Engine.Algorithms | BaseAlgorithm | Execute(Item, BaseJobModel) : List<Distribution> | 100 | 1 |  | 4 | 0
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobResponse | ErrorCode.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobResponse | ErrorCode.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | DistributionPercentBySegment.set(Dictionary<string, double>) : void | 95 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | DistributionPercentBySegment.set(Dictionary<string, double>) : void | 95 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | DistributionPercentBySegment.get() : Dictionary<string, double> | 98 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | DistributionPercentBySegment.get() : Dictionary<string, double> | 98 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobRequest | Data.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobRequest | Data.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine | BundleConfig | BundleConfig() | 100 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | BaseJob | BaseJob(string) | 94 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | BaseJob | BaseJob() | 80 | 1 |  | 1 | 3
Member | Simpply.Engine (Debug) | Simpply.Engine | WebApiApplication | Application_Start() : void | 73 | 1 |  | 9 | 5
Member | Simpply.Global (Debug) | Simpply.Global | Constants.ControllerAction.Season | Season() | 100 | 1 |  | 0 | 1
Member | Simpply.Global (Debug) | Simpply.Global | Constants.ControllerAction.Planogram | Planogram() | 100 | 1 |  | 0 | 1
Member | Simpply.Global (Debug) | Simpply.Global | Constants.ControllerAction.Item | Item() | 100 | 1 |  | 0 | 1
Member | Simpply.Global (Debug) | Simpply.Global | Constants.ControllerAction | ControllerAction() | 100 | 1 |  | 0 | 1
Member | Simpply.Global (Debug) | Simpply.Global | Constants.Controller | Controller() | 100 | 1 |  | 0 | 1
Member | Simpply.Global (Debug) | Simpply.Global | Constants | Constants() | 100 | 1 |  | 0 | 1
Member | Simpply.Global (Debug) | Simpply.Global | Constants.ControllerAction.Account | Account() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ItemProviderTest | SaveDistribution() : void | 46 | 13 |  | 13 | 26
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | AccountControllerTest | SaveColumnPreferences() : void | 55 | 5 |  | 23 | 12
Member | Simpply.Tests (Debug) | Simpply.Tests.Jobs | RunSetupJobTest | ValidateParametersTest() : void | 57 | 3 |  | 6 | 15
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | ItemControllerTest | ItemExplorer() : void | 59 | 3 |  | 20 | 8
Member | Simpply.Tests (Debug) | Simpply.Tests.ViewModels | ItemModelsTest | ItemDetailModelHasCorrectAggregateGrid() : void | 61 | 3 |  | 10 | 10
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | ItemControllerTest | ItemDetail() : void | 66 | 3 |  | 17 | 5
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | PlanogramProviderTest | GetReturnsOnlyActivePlanograms() : void | 65 | 3 |  | 9 | 7
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | PlanogramProviderTest | GetResultsAreInOrder() : void | 65 | 3 |  | 9 | 7
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ItemProviderTest | GetDetailsReturnsRelatedDistributions() : void | 69 | 3 |  | 9 | 5
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ItemProviderTest | GetDetailsReturnsRelatedSalesInformation() : void | 69 | 2 |  | 9 | 5
Member | Simpply.Tests (Debug) | Simpply.Tests.Algorithms | SetupAlgorithmTest | ExecuteSetupDistributionTest() : void | 62 | 2 |  | 9 | 8
Member | Simpply.Tests (Debug) | Simpply.Tests.Algorithms | PushAllAlgorithmTest | ExecutePushAllDistributionTest() : void | 62 | 2 |  | 9 | 8
Member | Simpply.Tests (Debug) | Simpply.Tests.Algorithms | PushAllAlgorithmTest | TestInit() : void | 47 | 1 |  | 8 | 33
Member | Simpply.Tests (Debug) | Simpply.Tests.Algorithms | SetupAlgorithmTest | TestInit() : void | 48 | 1 |  | 9 | 29
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | AccountControllerTest | TestInit() : void | 92 | 1 |  | 3 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | ItemControllerTest | TestInit() : void | 70 | 1 |  | 7 | 5
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | PlanogramControllerTest | TestInit() : void | 77 | 1 |  | 5 | 3
Member | Simpply.Tests (Debug) | Simpply.Tests.Jobs | RunSetupJobTest | TestInit() : void | 70 | 1 |  | 1 | 6
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | BaseProviderTest | TestInit() : void | 94 | 1 |  | 3 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ColumnPreferenceProviderTest | TestInit() : void | 94 | 1 |  | 3 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ItemProviderTest | TestInit() : void | 94 | 1 |  | 3 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | PlanogramProviderTest | TestInit() : void | 94 | 1 |  | 3 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | SalesInformationProviderTest | TestInit() : void | 94 | 1 |  | 3 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | StoreProviderTest | TestInit() : void | 94 | 1 |  | 3 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.ViewModels | ItemModelsTest | TestInit() : void | 75 | 1 |  | 6 | 2
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | StoreProviderTest | StoreProviderTest() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Algorithms | SetupAlgorithmTest | SetupAlgorithmTest() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | ItemControllerTest | SaveItemDistributionCallsProvidersCorrectly() : void | 72 | 1 |  | 7 | 3
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ColumnPreferenceProviderTest | Save() : void | 75 | 1 |  | 4 | 2
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | SalesInformationProviderTest | SalesInformationProviderTest() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Jobs | RunSetupJobTest | RunSetupJobTest() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Algorithms | PushAllAlgorithmTest | PushAllAlgorithmTest() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | PlanogramProviderTest | PlanogramProviderTest() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | PlanogramControllerTest | PlanogramControllerTest() | 76 | 1 |  | 3 | 2
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ItemProviderTest | ItemProviderTest() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.ViewModels | ItemModelsTest | ItemModelsTest() | 66 | 1 |  | 3 | 4
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | ItemControllerTest | ItemExplorerFiltersToCorrectPlanogram() : void | 63 | 1 |  | 11 | 7
Member | Simpply.Tests (Debug) | Simpply.Tests.ViewModels | ItemModelsTest | ItemDetailModelHasCorrectItemName() : void | 77 | 1 |  | 4 | 3
Member | Simpply.Tests (Debug) | Simpply.Tests.ViewModels | ItemModelsTest | ItemDetailModelHasCorrectDistributionGrid() : void | 73 | 1 |  | 8 | 4
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | ItemControllerTest | ItemControllerTest() | 69 | 1 |  | 5 | 3
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | PlanogramControllerTest | IndexGetsAllPlanograms() : void | 66 | 1 |  | 8 | 6
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | PlanogramControllerTest | IndexGetsActivePlanogramsOnly() : void | 66 | 1 |  | 8 | 6
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | StoreProviderTest | GetStores() : void | 100 | 1 |  | 1 | 0
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | StoreProviderTest | GetStore() : void | 100 | 1 |  | 1 | 0
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | SalesInformationProviderTest | GetSales() : void | 100 | 1 |  | 1 | 0
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | SalesInformationProviderTest | GetSale() : void | 100 | 1 |  | 1 | 0
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | PlanogramProviderTest | GetResultIsNotNull() : void | 69 | 1 |  | 7 | 6
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ItemProviderTest | GetItems() : void | 71 | 1 |  | 7 | 5
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ItemProviderTest | GetDetailsReturnsRelatedStores() : void | 74 | 1 |  | 6 | 4
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ItemProviderTest | GetDetailsReturnsANonNullItem() : void | 75 | 1 |  | 4 | 4
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | BreadcrumbControllerTest | GetBreadcrumbsTest() : void | 100 | 1 |  | 1 | 0
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ColumnPreferenceProviderTest | Get() : void | 82 | 1 |  | 6 | 2
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ColumnPreferenceProviderTest | ColumnPreferenceProviderTest() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | BreadcrumbControllerTest | BreadcrumbControllerTest() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | BaseProviderTest | BaseProviderTest() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | AccountControllerTest | AccountControllerTest() | 100 | 1 |  | 0 | 1
Member | Simpply.Util (Debug) | Simpply.Util.Extensions | CollectionExtensions | IsEmpty<T>(this ICollection<T>) : bool | 84 | 2 |  | 2 | 2
Member | Simpply.Util (Debug) | Simpply.Util.Extensions | StringExtensions | IsNullOrWhiteSpace(this string) : bool | 87 | 1 |  | 1 | 2

## Code Metrics Iteration 6
Scope | Project | Namespace | Type | Member | Maintainability Index | Cyclomatic Complexity | Depth of Inheritance | Class Coupling | Lines of Code | Web | Engine | Access
Member | Simpply (Debug) | Simpply.Models | ItemExplorerModel | ItemExplorerModel(List<Item>, string, int?, string, bool, List<ColumnPreference>) | 31 | 34 |  | 13 | 60 | 1.912663755 | 1.695067265 | 1.807017544
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | ItemDetailModel(Item, string, int?, string, bool, string, bool, ChartModel) | 29 | 31 |  | 18 | 57
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ColumnPreferenceModel(string, string, string, List<Column>, List<ColumnPreference>) | 32 | 25 |  | 17 | 77
Member | Simpply (Debug) | Simpply.Models | SeasonExplorerModel | SeasonExplorerModel(List<SeasonInfo>, string, bool, bool, List<ColumnPreference>) | 36 | 20 |  | 15 | 46
Member | Simpply (Debug) | Simpply.Models.POG | PlanogramExplorerModel | PlanogramExplorerModel(List<Planogram>, string, bool, bool, List<ColumnPreference>, int?) | 37 | 20 |  | 17 | 42
Member | Simpply (Debug) | Simpply.Controllers | ItemController | BuildSalesHistoryChartModel(long, List<WeeklyPurchase>, string, string, string, string) : ChartModel | 48 | 13 |  | 12 | 21
Member | Simpply (Debug) | Simpply.Models | BreadcrumbTrailModel | AdjustBreadcrumbsTrail(string, string, string) : void | 48 | 11 |  | 6 | 27
Member | Simpply (Debug) | Simpply.Controllers | ItemController | SaveDistribution(List<DistributionModel>, int, int, bool) : ActionResult | 54 | 9 |  | 9 | 14
Member | Simpply (Debug) | Simpply.Controllers | ItemController | ItemDetail(long, int?, string, bool, string, bool) : ActionResult | 51 | 6 |  | 19 | 19
Member | Simpply (Debug) | Simpply.Controllers | ItemController | FinalizeItems(List<int>, DistributionType) : ActionResult | 55 | 6 |  | 9 | 16
Member | Simpply (Debug) | Simpply.Helpers | WebHelper | getParamId(string) : int | 63 | 5 |  | 0 | 8
Member | Simpply (Debug) | Simpply.Helpers | WebHelper | GenerateActionUrl(string, string, Dictionary<string, string>) : string | 63 | 5 |  | 4 | 8
Member | Simpply (Debug) | Simpply.Models | ItemExplorerModel | CreateHeaderCell(string, string, int?, string, string, bool) : GridCellModel | 63 | 5 |  | 4 | 7
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | CreateDetailHeaderCell(string, int, string, int?, string, bool, string, string, bool) : GridCellModel | 60 | 5 |  | 4 | 9
Member | Simpply (Debug) | Simpply.Controllers | ItemController | SetPreviousNext(ItemDetailModel, long, int?, string, bool) : ItemDetailModel | 54 | 4 |  | 7 | 18
Member | Simpply (Debug) | Simpply.Controllers | AccountController | SaveColumnPreferences(ColumnPreferenceModel) : ActionResult | 55 | 4 |  | 9 | 12
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | GetColumnId(string) : long? | 65 | 4 |  | 2 | 8
Member | Simpply (Debug) | Simpply.Controllers | SeasonController | SeasonExplorer(bool, string, bool) : ActionResult | 63 | 3 |  | 17 | 7
Member | Simpply (Debug) | Simpply.Controllers | ItemController | SalesHistoryChart(long, string) : ActionResult | 67 | 3 |  | 6 | 6
Member | Simpply (Debug) | Simpply.Controllers | PlanogramController | PlanogramExplorer(int?, bool, string, bool) : ActionResult | 63 | 3 |  | 19 | 7
Member | Simpply (Debug) | Simpply.Controllers | ItemController | ItemExplorer(string, int?, string, bool) : ActionResult | 63 | 3 |  | 18 | 7
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | GetColumnName(string) : string | 67 | 3 |  | 1 | 7
Member | Simpply (Debug) | Simpply.Models.POG | PlanogramExplorerModel | FormatActionUrl(string, string, bool, bool, int?) : string | 67 | 3 |  | 2 | 6
Member | Simpply (Debug) | Simpply.Controllers | ItemController | Search(string) : ActionResult | 64 | 2 |  | 7 | 8
Member | Simpply (Debug) | Simpply.Helpers | WebHelper | GetControllerActionParameters(string) : string | 72 | 2 |  | 0 | 5
Member | Simpply (Debug) | Simpply.Controllers | BreadcrumbController | GetBreadCrumbs() : ActionResult | 60 | 2 |  | 7 | 11
Member | Simpply (Debug) | Simpply.Helpers | WebHelper | GenerateActionUrl(string, string, string) : string | 73 | 2 |  | 1 | 4
Member | Simpply (Debug) | Simpply.Models | SeasonExplorerModel | FormatActionUrl(string, string, bool, bool) : string | 73 | 2 |  | 1 | 4
Member | Simpply (Debug) | Simpply.Models | SeasonExplorerModel | CreateHeaderCell(string, string, string, bool, bool) : GridCellModel | 78 | 2 |  | 1 | 2
Member | Simpply (Debug) | Simpply.Models.POG | PlanogramExplorerModel | CreateHeaderCell(string, string, string, bool, bool, int?) : GridCellModel | 78 | 2 |  | 2 | 2
Member | Simpply (Debug) | Simpply.Models | ChartModel | YAxisLabel.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ChartModel | YAxisLabel.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ChartModel | XAxisLabel.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ChartModel | XAxisLabel.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ChartModel | Width.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ChartModel | Width.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | WarehouseBalanceOnOrder.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | WarehouseBalanceOnOrder.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | WarehouseBalanceOnHand.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | WarehouseBalanceOnHand.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ChartSeries | Values.set(List<ChartValue>) : void | 95 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | ChartSeries | Values.get() : List<ChartValue> | 98 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | BreadcrumbModel | Value.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | FormInput | Value.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | Value.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ChartValue | Value.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | BreadcrumbModel | Value.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | FormInput | Value.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | Value.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ChartValue | Value.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | Type.set(GridCellType) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ChartModel | Type.set(ChartType) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | Type.get() : GridCellType | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ChartModel | Type.get() : ChartType | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | TotalItems.set(long) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | TotalItems.get() : long | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ChartModel | Title.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ChartModel | Title.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | tableCondensed.set(bool) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | tableCondensed.get() : bool | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | Table.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | Table.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Controllers | StoreController | StoreController() | 100 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Controllers | ItemController | StandInItem(List<int>) : ActionResult | 83 | 1 |  | 4 | 2
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | SortDetailsDescending.set(bool) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | SortDetailsDescending.get() : bool | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | sortDescending.set(bool) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | sortDescending.get() : bool | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | sortColumn.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | sortColumn.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ShownColumnsList.set(List<SelectListItem>) : void | 95 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ShownColumnsList.get() : List<SelectListItem> | 98 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ShownColumnsDefault.set(List<SelectListItem>) : void | 95 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ShownColumnsDefault.get() : List<SelectListItem> | 98 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ShownColumns.set(List<string>) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ShownColumns.get() : List<string> | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | BreadcrumbTrailModel | SetToDefault() : void | 69 | 1 |  | 3 | 4
Member | Simpply (Debug) | Simpply.Models | ChartModel | Series.set(List<ChartSeries>) : void | 95 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | ChartModel | Series.get() : List<ChartSeries> | 98 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Controllers | SeasonController | SeasonController(ISeasonProvider, IColumnPreferenceProvider) | 81 | 1 |  | 3 | 3
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | SalesHistoryChart.set(ChartModel) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | SalesHistoryChart.get() : ChartModel | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | Rows.set(List<GridRowModel>) : void | 95 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | Rows.get() : List<GridRowModel> | 98 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply | RouteConfig | RouteConfig() | 100 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Controllers | BaseController | Root() : ActionResult | 86 | 1 |  | 2 | 2
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | ReplenishmentLevel.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | ReplenishmentLevel.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | ReplenishmentDescription.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | ReplenishmentDescription.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply | RouteConfig | RegisterRoutes(RouteCollection) : void | 82 | 1 |  | 3 | 2
Member | Simpply (Debug) | Simpply | FilterConfig | RegisterGlobalFilters(GlobalFilterCollection) : void | 94 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.App_Start | AutofacConfig | RegisterComponents() : void | 70 | 1 |  | 10 | 5
Member | Simpply (Debug) | Simpply | BundleConfig | RegisterBundles(BundleCollection) : void | 64 | 1 |  | 4 | 6
Member | Simpply (Debug) | Simpply | AuthConfig | RegisterAuth() : void | 100 | 1 |  | 0 | 0
Member | Simpply (Debug) | Simpply | WebApiConfig | Register(HttpConfiguration) : void | 89 | 1 |  | 4 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | PreviousId.set(long) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | PreviousId.get() : long | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | planogramId.set(int?) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | planogramId.get() : int? | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Controllers | PlanogramController | PlanogramController(IPlanogramProvider, IColumnPreferenceProvider) | 81 | 1 |  | 3 | 3
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | NumberOfTotal.set(long) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | NumberOfTotal.get() : long | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | NextId.set(long) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | NextId.get() : long | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ChartSeries | Name.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | Column | Name.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | FormInput | Name.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | Name.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ChartSeries | Name.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | Column | Name.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | FormInput | Name.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | Name.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply | MvcApplication | MvcApplication() | 100 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | ModelRow.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | ModelRow.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | ModelName.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | ModelName.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | ModelAttribute.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | ModelAttribute.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | LastModifiedDate.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | LastModifiedDate.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | LastModifiedBy.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | LastModifiedBy.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Controllers | BaseController | JsonActionResult(JsonReturnType, string, string, string, object) : ActionResult | 68 | 1 |  | 5 | 6
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | ItemFinalized.set(bool) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | ItemFinalized.get() : bool | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Controllers | ItemController | ItemController(IItemProvider, IStoreProvider, ISalesInformationProvider, IColumnPreferenceProvider) | 71 | 1 |  | 6 | 6
Member | Simpply (Debug) | Simpply.Controllers | ItemController | ItemController() | 90 | 1 |  | 4 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | IsSortedDescending.set(bool) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | IsSortedDescending.get() : bool | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | IsSorted.set(bool) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | IsSorted.get() : bool | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridRowModel | IsHeader.set(bool) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridRowModel | IsHeader.get() : bool | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemExplorerModel | IsFilteredToPlanogram.set(bool) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemExplorerModel | IsFilteredToPlanogram.get() : bool | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | SeasonExplorerModel | InactiveSeasonURL.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | SeasonExplorerModel | InactiveSeasonURL.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models.POG | PlanogramExplorerModel | InactivePlanogramURL.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models.POG | PlanogramExplorerModel | InactivePlanogramURL.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ChartModel | Id.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | Id.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ChartModel | Id.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | Id.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | HiddenColumnsList.set(List<SelectListItem>) : void | 95 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | HiddenColumnsList.get() : List<SelectListItem> | 98 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | HiddenColumns.set(List<string>) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | HiddenColumns.get() : List<string> | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ChartModel | Height.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ChartModel | Height.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | Header.set(GridRowModel) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | Header.get() : GridRowModel | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | GridRowModel | GridRowModel() | 87 | 1 |  | 2 | 2
Member | Simpply (Debug) | Simpply.Models | GridModel | GridModel() | 72 | 1 |  | 3 | 5
Member | Simpply (Debug) | Simpply.Models | GridCellModel | GridCellModel() | 78 | 1 |  | 0 | 4
Member | Simpply (Debug) | Simpply.Models | ItemExplorerModel | Grid.set(GridModel) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | SeasonExplorerModel | Grid.set(GridModel) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models.POG | PlanogramExplorerModel | Grid.set(GridModel) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ItemExplorerModel | Grid.get() : GridModel | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | SeasonExplorerModel | Grid.get() : GridModel | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models.POG | PlanogramExplorerModel | Grid.get() : GridModel | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Helpers | WebHelper | GetControllerName(string) : string | 78 | 1 |  | 0 | 3
Member | Simpply (Debug) | Simpply.Helpers | WebHelper | GetControllerActionName(string) : string | 78 | 1 |  | 0 | 3
Member | Simpply (Debug) | Simpply.Models | GridModel | FormMethod.set(FormMethod) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | FormMethod.get() : FormMethod | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | FormInput | FormInput() | 100 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | FormId.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | FormId.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | FormHiddenInputs.set(List<FormInput>) : void | 95 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | FormHiddenInputs.get() : List<FormInput> | 98 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | FormController.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | FormController.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | FormAction.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | FormAction.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply | FilterConfig | FilterConfig() | 100 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | Distribution.set(GridModel) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | Distribution.get() : GridModel | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | Column | DisplayName.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | Column | DisplayName.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | CurrentlySortedDetailsColumn.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | CurrentlySortedDetailsColumn.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | CssClasses.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridRowModel | CssClasses.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | CssClasses.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridRowModel | CssClasses.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ControllerName.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ControllerName.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ControllerAction.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ControllerAction.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Controllers | StoreController | CompareTostore() : ActionResult | 89 | 1 |  | 2 | 2
Member | Simpply (Debug) | Simpply.Controllers | StoreController | CompareToMultiplestores() : ActionResult | 89 | 1 |  | 2 | 2
Member | Simpply (Debug) | Simpply.Models | ItemExplorerModel | ColumnPreferences.set(ColumnPreferenceModel) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | SeasonExplorerModel | ColumnPreferences.set(ColumnPreferenceModel) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models.POG | PlanogramExplorerModel | ColumnPreferences.set(ColumnPreferenceModel) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ItemExplorerModel | ColumnPreferences.get() : ColumnPreferenceModel | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | SeasonExplorerModel | ColumnPreferences.get() : ColumnPreferenceModel | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models.POG | PlanogramExplorerModel | ColumnPreferences.get() : ColumnPreferenceModel | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ColumnPreferenceModel() | 71 | 1 |  | 2 | 6
Member | Simpply (Debug) | Simpply.Models | Column | Column() | 100 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ChartValue | ChartValue() | 100 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ChartSeries | ChartSeries(string, int) | 80 | 1 |  | 2 | 3
Member | Simpply (Debug) | Simpply.Models | ChartSeries | ChartSeries() | 87 | 1 |  | 2 | 2
Member | Simpply (Debug) | Simpply.Models | ChartModel | ChartModel() | 74 | 1 |  | 2 | 5
Member | Simpply (Debug) | Simpply.Models | GridRowModel | Cells.set(List<GridCellModel>) : void | 95 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | GridRowModel | Cells.get() : List<GridCellModel> | 98 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | ChartValue | Category.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ChartValue | Category.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply | BundleConfig | BundleConfig() | 100 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | BreadcrumbTrailModel | BreadcrumbTrailModel() | 65 | 1 |  | 3 | 6
Member | Simpply (Debug) | Simpply.Models | BreadcrumbModel | BreadcrumbModel() | 100 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Controllers | BreadcrumbController | BreadcrumbController() | 100 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Controllers | BaseController | BaseController() | 100 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply | MvcApplication | Application_Start() : void | 69 | 1 |  | 11 | 7
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | Aggregate.set(GridModel) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | Aggregate.get() : GridModel | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | SeasonExplorerModel | ActiveOnly.set(bool) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models.POG | PlanogramExplorerModel | ActiveOnly.set(bool) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | SeasonExplorerModel | ActiveOnly.get() : bool | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models.POG | PlanogramExplorerModel | ActiveOnly.get() : bool | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | BreadcrumbModel | ActionUrl.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ChartModel | ActionUrl.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | ActionUrl.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridRowModel | ActionUrl.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | BreadcrumbModel | ActionUrl.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ChartModel | ActionUrl.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | ActionUrl.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridRowModel | ActionUrl.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Controllers | AccountController | AccountController(IColumnPreferenceProvider) | 87 | 1 |  | 2 | 2
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ItemProvider | GetDetails(long, string, bool?) : Item | 45 | 10 |  | 18 | 32
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ItemProvider | SaveDistribution(List<DistributionModel>, int, int, bool, string) : void | 52 | 5 |  | 16 | 15
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ItemProvider | SaveMultiple(List<Distribution>) : void | 52 | 4 |  | 16 | 15
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ColumnPreferenceProvider | Save(List<ColumnPreference>) : void | 52 | 4 |  | 15 | 15
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | SeasonProvider | Get(bool, string, bool) : List<SeasonInfo> | 60 | 4 |  | 13 | 10
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | PlanogramProvider | Get(bool, int?, string, bool) : List<Planogram> | 60 | 4 |  | 13 | 10
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ItemProvider | FinalizeItems(List<int>, DistributionType, string) : void | 50 | 4 |  | 14 | 21
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ItemProvider | GetSalesHistory(List<long>, int?, int?, int?, int?) : List<WeeklyPurchase> | 60 | 3 |  | 15 | 9
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | SalesInformationProvider | Get(long, long) : SalesInformation | 70 | 3 |  | 5 | 5
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | JobProvider | UpdateProgress(long, string, int) : void | 72 | 2 |  | 7 | 4
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ExampleProvider | SelectExample(int) : Example | 70 | 2 |  | 9 | 5
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | JobProvider | Insert(string) : long | 69 | 2 |  | 8 | 5
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ItemProvider | GetStandInItem(int) : string | 66 | 2 |  | 9 | 7
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | SeasonProvider | GetSeasonName(int) : string | 66 | 2 |  | 9 | 7
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ItemProvider | GetSalesHistoryForChart(long) : List<WeeklyPurchase> | 69 | 2 |  | 10 | 5
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | PlanogramProvider | GetPlanogramName(int) : string | 66 | 2 |  | 9 | 7
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ItemProvider | GetItemsDetails(long, string, bool?) : List<Item> | 69 | 2 |  | 10 | 5
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ItemProvider | GetItemName(int) : string | 66 | 2 |  | 9 | 7
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ItemProvider | GetIds() : List<long> | 69 | 2 |  | 9 | 5
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ColumnPreferenceProvider | Get(string, string, string) : List<ColumnPreference> | 66 | 2 |  | 10 | 7
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | StoreProvider | Get(long) : Store | 71 | 2 |  | 5 | 5
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | JobProvider | Get(long) : Job | 69 | 2 |  | 9 | 5
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ItemProvider | Get(long?, string, int?, string, bool?) : List<Item> | 69 | 2 |  | 10 | 5
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IJobProvider | UpdateProgress(long, string, int) : void | 100 | 1 |  | 0 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | StoreProvider | StoreProvider() | 76 | 1 |  | 3 | 2
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | SeasonProvider | SeasonProvider() | 100 | 1 |  | 1 | 1
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IItemProvider | SaveMultiple(List<Distribution>) : void | 100 | 1 |  | 2 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IItemProvider | SaveDistribution(List<DistributionModel>, int, int, bool, string) : void | 100 | 1 |  | 2 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IColumnPreferenceProvider | Save(List<ColumnPreference>) : void | 100 | 1 |  | 2 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | SalesInformationProvider | SalesInformationProvider() | 68 | 1 |  | 3 | 2
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | PlanogramProvider | PlanogramProvider() | 100 | 1 |  | 1 | 1
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access | AccessModule | Load(ContainerBuilder) : void | 63 | 1 |  | 18 | 7
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | JobProvider | JobProvider() | 100 | 1 |  | 1 | 1
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ItemProvider | ItemProvider() | 100 | 1 |  | 1 | 1
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IJobProvider | Insert(string) : long | 100 | 1 |  | 0 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IItemProvider | GetSalesHistoryForChart(long) : List<WeeklyPurchase> | 100 | 1 |  | 2 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IItemProvider | GetSalesHistory(List<long>, int?, int?, int?, int?) : List<WeeklyPurchase> | 100 | 1 |  | 3 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IItemProvider | GetItemsDetails(long, string, bool?) : List<Item> | 100 | 1 |  | 3 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IItemProvider | GetDetails(long, string, bool?) : Item | 100 | 1 |  | 2 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IColumnPreferenceProvider | Get(string, string, string) : List<ColumnPreference> | 100 | 1 |  | 2 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IStoreProvider | Get(long) : Store | 100 | 1 |  | 1 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IJobProvider | Get(long) : Job | 100 | 1 |  | 1 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IItemProvider | Get(long?, string, int?, string, bool?) : List<Item> | 100 | 1 |  | 3 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | ISalesInformationProvider | Get(long, long) : SalesInformation | 100 | 1 |  | 1 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | ISeasonProvider | Get(bool, string, bool) : List<SeasonInfo> | 100 | 1 |  | 2 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IPlanogramProvider | Get(bool, int?, string, bool) : List<Planogram> | 100 | 1 |  | 3 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IStoreProvider | Get() : List<Store> | 100 | 1 |  | 2 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | StoreProvider | Get() : List<Store> | 91 | 1 |  | 2 | 2
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | ISalesInformationProvider | Get() : List<SalesInformation> | 100 | 1 |  | 2 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | SalesInformationProvider | Get() : List<SalesInformation> | 91 | 1 |  | 2 | 2
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IItemProvider | FinalizeItems(List<int>, DistributionType, string) : void | 100 | 1 |  | 2 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ExampleProvider | ExampleProvider() | 100 | 1 |  | 1 | 1
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | BaseProvider | connectionString.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | BaseProvider | connectionString.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ColumnPreferenceProvider | ColumnPreferenceProvider() | 100 | 1 |  | 1 | 1
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | BaseProvider | BaseProvider() | 83 | 1 |  | 3 | 2
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access | AccessModule | AccessModule() | 100 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Algorithms | PushAllAlgorithm | Execute(Item, BaseJobModel) : List<Distribution> | 44 | 12 |  | 14 | 32
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | JobInvoker | ScheduleJob(BaseJob) : JobResponse | 41 | 10 |  | 11 | 45
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | JobInvoker | ValidateNoConflict(BaseJob) : bool | 52 | 9 |  | 7 | 20
Member | Simpply.Engine (Debug) | Simpply.Engine.Algorithms | SetupAlgorithm | Execute(Item, BaseJobModel) : List<Distribution> | 42 | 9 |  | 13 | 37
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | JobInvoker | ScheduleJob(BaseJob) : JobResponse | 45 | 8 |  | 10 | 34
Member | Simpply.Engine (Debug) | Simpply.Engine.Algorithms | PushAllAlgorithm | Execute(Item, BaseJobModel) : List<Distribution> | 47 | 8 |  | 14 | 26
Member | Simpply.Engine (Debug) | Simpply.Engine.Algorithms | SellthroughAlgorithm | Execute(Item, BaseJobModel) : List<Distribution> | 48 | 8 |  | 11 | 26
Member | Simpply.Engine (Debug) | Simpply.Engine.Algorithms | SellthroughAlgorithm | Execute(Item, BaseJobModel) : List<Distribution> | 47 | 8 |  | 12 | 27
Member | Simpply.Engine (Debug) | Simpply.Engine.Algorithms | SetupAlgorithm | Execute(Item, BaseJobModel) : List<Distribution> | 49 | 8 |  | 16 | 21
Member | Simpply.Engine (Debug) | Simpply.Engine.Algorithms | SetupAlgorithm | DistributeProductToSegment(Dictionary<long, Distribution>, Item, string, long, DateTime, string) : void | 48 | 8 |  | 15 | 25
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunSellthroughJob | ValidateParameters() : bool | 56 | 7 |  | 4 | 15
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunSetupJob | ValidateParameters() : bool | 57 | 7 |  | 5 | 13
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunSellthroughJob | ValidateParameters() : bool | 56 | 7 |  | 4 | 15
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunSetupJob | ValidateParameters() : bool | 57 | 7 |  | 5 | 13
Member | Simpply.Engine (Debug) | Simpply.Engine.Controllers | JobsController | Post(JobRequest) : object | 54 | 6 |  | 13 | 17
Member | Simpply.Engine (Debug) | Simpply.Engine.Controllers | JobsController | Post(JobRequest) : object | 52 | 6 |  | 15 | 20
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunPushAllJob | ValidateParameters() : bool | 64 | 4 |  | 4 | 9
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunPushAllJob | ValidateParameters() : bool | 64 | 4 |  | 4 | 9
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | JobInvoker | GetInstance() : JobInvoker | 67 | 4 |  | 1 | 8
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | JobInvoker | GetInstance() : JobInvoker | 67 | 4 |  | 1 | 8
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | ParseWegmansData | Execute(long) : bool | 55 | 4 |  | 11 | 16
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | ParseWegmansData | Execute(long) : bool | 52 | 4 |  | 13 | 19
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunPushAllJob | Execute(long) : bool | 56 | 3 |  | 9 | 13
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunSellthroughJob | Execute(long) : bool | 51 | 3 |  | 13 | 18
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunSetupJob | Execute(long) : bool | 56 | 3 |  | 9 | 13
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunPushAllJob | Execute(long) : bool | 56 | 3 |  | 9 | 13
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunSellthroughJob | Execute(long) : bool | 51 | 3 |  | 13 | 18
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunSetupJob | Execute(long) : bool | 56 | 3 |  | 9 | 13
Member | Simpply.Engine (Debug) | Simpply.Engine.Algorithms | BaseAlgorithm | ConvertWarehouseToStore(long, int, int) : long | 76 | 3 |  | 0 | 4
Member | Simpply.Engine (Debug) | Simpply.Engine.Algorithms | BaseAlgorithm | ConvertStoreToWarehouse(long, int, int) : long | 68 | 3 |  | 0 | 7
Member | Simpply.Engine (Debug) | Simpply.Engine.Algorithms | BaseAlgorithm | ConvertStoreToWarehouse(long, int, int) : long | 76 | 3 |  | 0 | 4
Member | Simpply.Engine (Debug) | Simpply.Engine.Algorithms | SellthroughAlgorithm | ComputeForecast(long, List<WeeklyPurchase>) : int | 68 | 3 |  | 4 | 6
Member | Simpply.Engine (Debug) | Simpply.Engine.Algorithms | SellthroughAlgorithm | ComputeForecast(long, List<WeeklyPurchase>) : int | 68 | 3 |  | 4 | 6
Member | Simpply.Engine (Debug) | Simpply.Engine.Algorithms | BaseAlgorithm | ConvertWarehouseToStore(long, int, int) : long | 77 | 2 |  | 0 | 4
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | BaseJob | BaseJob(string, JobProvider) | 71 | 2 |  | 2 | 6
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | BaseJob | BaseJob(string, JobProvider) | 71 | 2 |  | 2 | 6
Member | Simpply.Engine (Debug) | Simpply.Engine | WebApiApplication | WebApiApplication() | 100 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine | WebApiApplication | WebApiApplication() | 100 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | BaseJob | ValidateParameters() : bool | 100 | 1 |  | 0 | 0
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | ParseWegmansData | ValidateParameters() : bool | 91 | 1 |  | 0 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | BaseJob | ValidateParameters() : bool | 100 | 1 |  | 0 | 0
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | ParseWegmansData | ValidateParameters() : bool | 91 | 1 |  | 0 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | JobInvoker | ValidateNoConflict() : bool | 91 | 1 |  | 0 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunPushAllJobModel | Username.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | Username.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | Username.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunPushAllJobModel | Username.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | Username.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | Username.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunPushAllJobModel | Username.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | Username.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | Username.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunPushAllJobModel | Username.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | Username.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | Username.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | BaseJob | UpdateJobStatus(long, string, int) : void | 92 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | BaseJob | UpdateJobStatus(long, string, int) : void | 92 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobResponse | Success.set(bool) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobResponse | Success.set(bool) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobResponse | Success.get() : bool | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobResponse | Success.get() : bool | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | SetupDistributionPercent.set(double) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | SetupDistributionPercent.set(double) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | SetupDistributionPercent.get() : double | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | SetupDistributionPercent.get() : double | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Algorithms | SetupAlgorithm | SetupAlgorithm() | 100 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Algorithms | SetupAlgorithm | SetupAlgorithm() | 100 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunPushAllJobModel | SellthroughPercentTrigger.set(double) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | SellthroughPercentTrigger.set(double) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunPushAllJobModel | SellthroughPercentTrigger.set(double) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | SellthroughPercentTrigger.set(double) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunPushAllJobModel | SellthroughPercentTrigger.get() : double | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | SellthroughPercentTrigger.get() : double | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunPushAllJobModel | SellthroughPercentTrigger.get() : double | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | SellthroughPercentTrigger.get() : double | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Algorithms | SellthroughAlgorithm | SellthroughAlgorithm() | 100 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Algorithms | SellthroughAlgorithm | SellthroughAlgorithm() | 100 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | SegmentCDistributionPercent.set(double) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | SegmentCDistributionPercent.set(double) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | SegmentCDistributionPercent.set(double) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | SegmentCDistributionPercent.set(double) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | SegmentCDistributionPercent.get() : double | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | SegmentCDistributionPercent.get() : double | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | SegmentCDistributionPercent.get() : double | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | SegmentCDistributionPercent.get() : double | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | SegmentBDistributionPercent.set(double) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | SegmentBDistributionPercent.set(double) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | SegmentBDistributionPercent.set(double) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | SegmentBDistributionPercent.set(double) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | SegmentBDistributionPercent.get() : double | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | SegmentBDistributionPercent.get() : double | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | SegmentBDistributionPercent.get() : double | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | SegmentBDistributionPercent.get() : double | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | SegmentationPercents.set(Dictionary<string, double>) : void | 95 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | SegmentationPercents.set(Dictionary<string, double>) : void | 95 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | SegmentationPercents.get() : Dictionary<string, double> | 98 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | SegmentationPercents.get() : Dictionary<string, double> | 98 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | SegmentADistributionPercent.set(double) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | SegmentADistributionPercent.set(double) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | SegmentADistributionPercent.set(double) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | SegmentADistributionPercent.set(double) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | SegmentADistributionPercent.get() : double | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | SegmentADistributionPercent.get() : double | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | SegmentADistributionPercent.get() : double | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | SegmentADistributionPercent.get() : double | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | RunSetupJobModel() | 100 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | RunSetupJobModel() | 100 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunSetupJob | RunSetupJob(string) | 79 | 1 |  | 4 | 3
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunSetupJob | RunSetupJob(string) | 79 | 1 |  | 4 | 3
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | RunSellthroughJobModel() | 100 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | RunSellthroughJobModel() | 100 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunSellthroughJob | RunSellthroughJob(string) | 79 | 1 |  | 4 | 3
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunSellthroughJob | RunSellthroughJob(string) | 79 | 1 |  | 4 | 3
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunPushAllJobModel | RunPushAllJobModel() | 100 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunPushAllJobModel | RunPushAllJobModel() | 100 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunPushAllJob | RunPushAllJob(string) | 79 | 1 |  | 4 | 3
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunPushAllJob | RunPushAllJob(string) | 79 | 1 |  | 4 | 3
Member | Simpply.Engine (Debug) | Simpply.Engine | RouteConfig | RouteConfig() | 100 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine | RouteConfig | RouteConfig() | 100 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine | RouteConfig | RegisterRoutes(RouteCollection) : void | 82 | 1 |  | 4 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine | RouteConfig | RegisterRoutes(RouteCollection) : void | 82 | 1 |  | 4 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine | FilterConfig | RegisterGlobalFilters(GlobalFilterCollection) : void | 94 | 1 |  | 2 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine | FilterConfig | RegisterGlobalFilters(GlobalFilterCollection) : void | 94 | 1 |  | 2 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine | BundleConfig | RegisterBundles(BundleCollection) : void | 100 | 1 |  | 1 | 0
Member | Simpply.Engine (Debug) | Simpply.Engine | BundleConfig | RegisterBundles(BundleCollection) : void | 100 | 1 |  | 1 | 0
Member | Simpply.Engine (Debug) | Simpply.Engine | WebApiConfig | Register(HttpConfiguration) : void | 75 | 1 |  | 9 | 3
Member | Simpply.Engine (Debug) | Simpply.Engine | WebApiConfig | Register(HttpConfiguration) : void | 75 | 1 |  | 9 | 3
Member | Simpply.Engine (Debug) | Simpply.Engine.Algorithms | PushAllAlgorithm | PushAllAlgorithm() | 100 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Algorithms | PushAllAlgorithm | PushAllAlgorithm() | 100 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | ParseWegmansData | ParseWegmansData(string) | 98 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | ParseWegmansData | ParseWegmansData(string) | 87 | 1 |  | 2 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | ParseWegmansData | ParseWegmansData() | 90 | 1 |  | 4 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobResponse | Message.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobResponse | Message.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobResponse | Message.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobResponse | Message.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Controllers | JobsController | JobsController() | 100 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Controllers | JobsController | JobsController() | 100 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Controllers | JobsController | JobsController() | 90 | 1 |  | 4 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobResponse | JobResponse(bool, int, string, long) | 74 | 1 |  | 0 | 5
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobResponse | JobResponse(bool, int, string, long) | 74 | 1 |  | 0 | 5
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobRequest | JobRequest() | 82 | 1 |  | 0 | 3
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobRequest | JobRequest() | 82 | 1 |  | 0 | 3
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | JobInvoker | JobInvoker() | 76 | 1 |  | 5 | 4
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | JobInvoker | JobInvoker() | 82 | 1 |  | 4 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | JobInvoker | JobInvoker() | 76 | 1 |  | 5 | 4
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | JobInvoker | JobInvoker() | 77 | 1 |  | 4 | 3
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobResponse | JobId.set(long) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobResponse | JobId.set(long) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobResponse | JobId.get() : long | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobResponse | JobId.get() : long | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobRequest | Job.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobRequest | Job.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobRequest | Job.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobRequest | Job.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Controllers | HomeController | Index() : ActionResult | 89 | 1 |  | 2 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Controllers | HomeController | Index() : ActionResult | 89 | 1 |  | 2 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunPushAllJobModel | Ids.set(List<long>) : void | 95 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | Ids.set(List<long>) : void | 95 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | Ids.set(List<long>) : void | 95 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunPushAllJobModel | Ids.set(List<long>) : void | 95 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | Ids.set(List<long>) : void | 95 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | Ids.set(List<long>) : void | 95 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunPushAllJobModel | Ids.get() : List<long> | 98 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | Ids.get() : List<long> | 98 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | Ids.get() : List<long> | 98 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunPushAllJobModel | Ids.get() : List<long> | 98 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | Ids.get() : List<long> | 98 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | Ids.get() : List<long> | 98 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Controllers | HomeController | HomeController() | 100 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Controllers | HomeController | HomeController() | 100 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | History.set(List<WeeklyPurchase>) : void | 95 | 1 |  | 2 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | History.set(List<WeeklyPurchase>) : void | 95 | 1 |  | 2 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | History.get() : List<WeeklyPurchase> | 98 | 1 |  | 2 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | History.get() : List<WeeklyPurchase> | 98 | 1 |  | 2 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | BaseJob | GetValidParameters() : string | 100 | 1 |  | 0 | 0
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | ParseWegmansData | GetValidParameters() : string | 91 | 1 |  | 0 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunPushAllJob | GetValidParameters() : string | 91 | 1 |  | 0 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunSellthroughJob | GetValidParameters() : string | 91 | 1 |  | 0 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunSetupJob | GetValidParameters() : string | 91 | 1 |  | 0 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | BaseJob | GetValidParameters() : string | 100 | 1 |  | 0 | 0
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | ParseWegmansData | GetValidParameters() : string | 91 | 1 |  | 0 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunPushAllJob | GetValidParameters() : string | 91 | 1 |  | 0 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunSellthroughJob | GetValidParameters() : string | 91 | 1 |  | 0 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunSetupJob | GetValidParameters() : string | 91 | 1 |  | 0 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | BaseJob | GetName() : string | 100 | 1 |  | 0 | 0
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | ParseWegmansData | GetName() : string | 91 | 1 |  | 0 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunPushAllJob | GetName() : string | 91 | 1 |  | 0 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunSellthroughJob | GetName() : string | 91 | 1 |  | 0 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunSetupJob | GetName() : string | 91 | 1 |  | 0 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | BaseJob | GetName() : string | 100 | 1 |  | 0 | 0
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | ParseWegmansData | GetName() : string | 91 | 1 |  | 0 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunPushAllJob | GetName() : string | 91 | 1 |  | 0 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunSellthroughJob | GetName() : string | 91 | 1 |  | 0 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunSetupJob | GetName() : string | 91 | 1 |  | 0 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | BaseJob | GetItemIdParameter() : List<long> | 100 | 1 |  | 1 | 0
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | ParseWegmansData | GetItemIdParameter() : List<long> | 89 | 1 |  | 1 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunPushAllJob | GetItemIdParameter() : List<long> | 87 | 1 |  | 2 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunSellthroughJob | GetItemIdParameter() : List<long> | 87 | 1 |  | 2 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunSetupJob | GetItemIdParameter() : List<long> | 87 | 1 |  | 2 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Controllers | JobsController | Get(long) : string | 79 | 1 |  | 3 | 3
Member | Simpply.Engine (Debug) | Simpply.Engine.Controllers | JobsController | Get(long) : string | 79 | 1 |  | 3 | 3
Member | Simpply.Engine (Debug) | Simpply.Engine | FilterConfig | FilterConfig() | 100 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine | FilterConfig | FilterConfig() | 100 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | BaseJob | Execute(long) : bool | 100 | 1 |  | 0 | 0
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | BaseJob | Execute(long) : bool | 100 | 1 |  | 0 | 0
Member | Simpply.Engine (Debug) | Simpply.Engine.Algorithms | BaseAlgorithm | Execute(Item, BaseJobModel) : List<Distribution> | 100 | 1 |  | 4 | 0
Member | Simpply.Engine (Debug) | Simpply.Engine.Algorithms | BaseAlgorithm | Execute(Item, BaseJobModel) : List<Distribution> | 100 | 1 |  | 4 | 0
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobResponse | ErrorCode.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobResponse | ErrorCode.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobResponse | ErrorCode.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobResponse | ErrorCode.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobRequest | Data.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobRequest | Data.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobRequest | Data.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobRequest | Data.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine | BundleConfig | BundleConfig() | 100 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine | BundleConfig | BundleConfig() | 100 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | BaseJob | BaseJob(string) | 94 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | BaseJob | BaseJob(string) | 94 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | BaseJob | BaseJob() | 80 | 1 |  | 1 | 3
Member | Simpply.Engine (Debug) | Simpply.Engine.Algorithms | BaseAlgorithm | BaseAlgorithm() | 94 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine | WebApiApplication | Application_Start() : void | 73 | 1 |  | 9 | 5
Member | Simpply.Global (Debug) | Simpply.Global | Constants.ViewPages | ViewPages() | 100 | 1 |  | 0 | 1
Member | Simpply.Global (Debug) | Simpply.Global | Constants.ControllerAction.Season | Season() | 100 | 1 |  | 0 | 1
Member | Simpply.Global (Debug) | Simpply.Global | Constants.ControllerAction.Planogram | Planogram() | 100 | 1 |  | 0 | 1
Member | Simpply.Global (Debug) | Simpply.Global | Constants.ViewPages.ItemDetails | ItemDetails() | 100 | 1 |  | 0 | 1
Member | Simpply.Global (Debug) | Simpply.Global | Constants.ControllerAction.Item | Item() | 100 | 1 |  | 0 | 1
Member | Simpply.Global (Debug) | Simpply.Global | Constants.ControllerAction | ControllerAction() | 100 | 1 |  | 0 | 1
Member | Simpply.Global (Debug) | Simpply.Global | Constants.Controller | Controller() | 100 | 1 |  | 0 | 1
Member | Simpply.Global (Debug) | Simpply.Global | Constants | Constants() | 100 | 1 |  | 0 | 1
Member | Simpply.Global (Debug) | Simpply.Global | Constants.ControllerAction.Account | Account() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ItemProviderTest | SaveDistribution() : void | 46 | 13 |  | 14 | 26
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | AccountControllerTest | SaveColumnPreferences() : void | 55 | 5 |  | 23 | 12
Member | Simpply.Tests (Debug) | Simpply.Tests.Jobs | RunSetupJobTest | ValidateParametersTest() : void | 57 | 3 |  | 6 | 15
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | ItemControllerTest | ItemExplorer() : void | 59 | 3 |  | 20 | 8
Member | Simpply.Tests (Debug) | Simpply.Tests.ViewModels | ItemModelsTest | ItemDetailModelHasCorrectAggregateGrid() : void | 60 | 3 |  | 11 | 10
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | ItemControllerTest | ItemDetail() : void | 65 | 3 |  | 17 | 5
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | PlanogramProviderTest | GetReturnsOnlyActivePlanograms() : void | 65 | 3 |  | 9 | 7
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | PlanogramProviderTest | GetResultsAreInOrder() : void | 65 | 3 |  | 9 | 7
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ItemProviderTest | GetDetailsReturnsRelatedDistributions() : void | 68 | 3 |  | 10 | 5
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ItemProviderTest | GetDetailsReturnsRelatedSalesInformation() : void | 69 | 2 |  | 10 | 5
Member | Simpply.Tests (Debug) | Simpply.Tests.Algorithms | SetupAlgorithmTest | ExecuteSetupDistributionTest() : void | 62 | 2 |  | 9 | 8
Member | Simpply.Tests (Debug) | Simpply.Tests.Algorithms | PushAllAlgorithmTest | ExecutePushAllDistributionTest() : void | 62 | 2 |  | 9 | 8
Member | Simpply.Tests (Debug) | Simpply.Tests.Algorithms | PushAllAlgorithmTest | TestInit() : void | 47 | 1 |  | 8 | 33
Member | Simpply.Tests (Debug) | Simpply.Tests.Algorithms | SetupAlgorithmTest | TestInit() : void | 47 | 1 |  | 9 | 31
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | AccountControllerTest | TestInit() : void | 92 | 1 |  | 3 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | ItemControllerTest | TestInit() : void | 77 | 1 |  | 5 | 3
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | PlanogramControllerTest | TestInit() : void | 77 | 1 |  | 5 | 3
Member | Simpply.Tests (Debug) | Simpply.Tests.Jobs | RunSetupJobTest | TestInit() : void | 70 | 1 |  | 1 | 6
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | BaseProviderTest | TestInit() : void | 94 | 1 |  | 3 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ColumnPreferenceProviderTest | TestInit() : void | 94 | 1 |  | 3 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ItemProviderTest | TestInit() : void | 94 | 1 |  | 3 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | PlanogramProviderTest | TestInit() : void | 94 | 1 |  | 3 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.ViewModels | ItemModelsTest | TestInit() : void | 75 | 1 |  | 6 | 2
Member | Simpply.Tests (Debug) | Simpply.Tests.Algorithms | SetupAlgorithmTest | SetupAlgorithmTest() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | ItemControllerTest | SaveItemDistributionCallsProvidersCorrectly() : void | 72 | 1 |  | 7 | 3
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ColumnPreferenceProviderTest | Save() : void | 75 | 1 |  | 4 | 2
Member | Simpply.Tests (Debug) | Simpply.Tests.Jobs | RunSetupJobTest | RunSetupJobTest() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Algorithms | PushAllAlgorithmTest | PushAllAlgorithmTest() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | PlanogramProviderTest | PlanogramProviderTest() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | PlanogramControllerTest | PlanogramControllerTest() | 76 | 1 |  | 3 | 2
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ItemProviderTest | ItemProviderTest() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.ViewModels | ItemModelsTest | ItemModelsTest() | 66 | 1 |  | 3 | 4
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | ItemControllerTest | ItemExplorerFiltersToCorrectPlanogram() : void | 63 | 1 |  | 11 | 7
Member | Simpply.Tests (Debug) | Simpply.Tests.ViewModels | ItemModelsTest | ItemDetailModelHasCorrectItemName() : void | 75 | 1 |  | 5 | 3
Member | Simpply.Tests (Debug) | Simpply.Tests.ViewModels | ItemModelsTest | ItemDetailModelHasCorrectDistributionGrid() : void | 71 | 1 |  | 9 | 4
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | ItemControllerTest | ItemControllerTest() | 69 | 1 |  | 5 | 3
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | PlanogramControllerTest | IndexGetsAllPlanograms() : void | 66 | 1 |  | 8 | 6
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | PlanogramControllerTest | IndexGetsActivePlanogramsOnly() : void | 66 | 1 |  | 8 | 6
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | PlanogramProviderTest | GetResultIsNotNull() : void | 69 | 1 |  | 7 | 6
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ItemProviderTest | GetItems() : void | 71 | 1 |  | 7 | 5
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ItemProviderTest | GetDetailsReturnsRelatedStores() : void | 73 | 1 |  | 7 | 4
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ItemProviderTest | GetDetailsReturnsANonNullItem() : void | 74 | 1 |  | 5 | 4
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | BreadcrumbControllerTest | GetBreadcrumbsTest() : void | 100 | 1 |  | 1 | 0
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ColumnPreferenceProviderTest | Get() : void | 82 | 1 |  | 6 | 2
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ColumnPreferenceProviderTest | ColumnPreferenceProviderTest() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | BreadcrumbControllerTest | BreadcrumbControllerTest() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | BaseProviderTest | BaseProviderTest() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | AccountControllerTest | AccountControllerTest() | 100 | 1 |  | 0 | 1
Member | Simpply.Util (Debug) | Simpply.Util.Extensions | CollectionExtensions | IsEmpty<T>(this ICollection<T>) : bool | 84 | 2 |  | 2 | 2
Member | Simpply.Util (Debug) | Simpply.Util.Extensions | StringExtensions | IsNullOrWhiteSpace(this string) : bool | 87 | 1 |  | 1 | 2

## Code Metrics Iteration 7
Scope | Project | Namespace | Type | Member | Maintainability Index | Cyclomatic Complexity | Depth of Inheritance | Class Coupling | Lines of Code | Web | Engine | Access
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | ItemDetailModel(Item, string, int?, string, bool, string, bool, ChartModel, List<ColumnPreference>) | 21 | 48 |  | 22 | 103 | 1.9 | 1.35078534 | 1.789473684
Member | Simpply (Debug) | Simpply.Models | ItemExplorerModel | ItemExplorerModel(List<Item>, string, int?, string, bool, List<ColumnPreference>) | 30 | 34 |  | 13 | 61
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ColumnPreferenceModel(string, string, string, List<Column>, List<ColumnPreference>) | 32 | 25 |  | 17 | 77
Member | Simpply (Debug) | Simpply.Models | SeasonExplorerModel | SeasonExplorerModel(List<SeasonInfo>, string, bool, bool, List<ColumnPreference>) | 36 | 20 |  | 15 | 46
Member | Simpply (Debug) | Simpply.Models.POG | PlanogramExplorerModel | PlanogramExplorerModel(List<Planogram>, string, bool, bool, List<ColumnPreference>, int?) | 37 | 20 |  | 17 | 42
Member | Simpply (Debug) | Simpply.Controllers | ItemController | BuildSalesHistoryChartModel(long, List<WeeklyPurchase>, string, string, string, string) : ChartModel | 48 | 13 |  | 12 | 21
Member | Simpply (Debug) | Simpply.Models | BreadcrumbTrailModel | AdjustBreadcrumbsTrail(string, string, string) : void | 48 | 11 |  | 6 | 27
Member | Simpply (Debug) | Simpply.Controllers | ItemController | FinalizeItems(string, DistributionType, FinalizedDistributionType, int, int) : ActionResult | 48 | 9 |  | 14 | 26
Member | Simpply (Debug) | Simpply.Controllers | ItemController | SaveDistribution(List<DistributionModel>, int, int) : ActionResult | 55 | 8 |  | 9 | 13
Member | Simpply (Debug) | Simpply.Helpers | WebHelper | ToAbsoluteUrl(this string) : string | 57 | 6 |  | 5 | 12
Member | Simpply (Debug) | Simpply.Controllers | ItemController | ItemDetail(long, int?, string, bool, string, bool) : ActionResult | 50 | 6 |  | 21 | 20
Member | Simpply (Debug) | Simpply.Helpers | WebHelper | getParamId(string) : int | 63 | 5 |  | 0 | 8
Member | Simpply (Debug) | Simpply.Helpers | WebHelper | GenerateActionUrl(string, string, Dictionary<string, string>) : string | 63 | 5 |  | 4 | 8
Member | Simpply (Debug) | Simpply.Models | ItemExplorerModel | CreateHeaderCell(string, string, int?, string, string, bool) : GridCellModel | 63 | 5 |  | 4 | 7
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | CreateDetailHeaderCell(string, int, string, int?, string, bool, string, string, bool) : GridCellModel | 60 | 5 |  | 4 | 9
Member | Simpply (Debug) | Simpply.Controllers | ItemController | SetPreviousNext(ItemDetailModel, long, int?, string, bool) : ItemDetailModel | 54 | 4 |  | 7 | 18
Member | Simpply (Debug) | Simpply.Controllers | AccountController | SaveColumnPreferences(ColumnPreferenceModel) : ActionResult | 55 | 4 |  | 9 | 12
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | GetColumnId(string) : long? | 65 | 4 |  | 2 | 8
Member | Simpply (Debug) | Simpply.Controllers | SeasonController | SeasonExplorer(bool, string, bool) : ActionResult | 63 | 3 |  | 17 | 7
Member | Simpply (Debug) | Simpply.Controllers | ItemController | SalesHistoryChart(long, string) : ActionResult | 67 | 3 |  | 6 | 6
Member | Simpply (Debug) | Simpply.Controllers | PlanogramController | PlanogramExplorer(int?, bool, string, bool) : ActionResult | 63 | 3 |  | 19 | 7
Member | Simpply (Debug) | Simpply.Controllers | ItemController | ItemExplorer(string, int?, string, bool) : ActionResult | 63 | 3 |  | 18 | 7
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | GetColumnName(string) : string | 67 | 3 |  | 1 | 7
Member | Simpply (Debug) | Simpply.Models.POG | PlanogramExplorerModel | FormatActionUrl(string, string, bool, bool, int?) : string | 67 | 3 |  | 2 | 6
Member | Simpply (Debug) | Simpply.Controllers | ItemController | Search(string) : ActionResult | 64 | 2 |  | 7 | 8
Member | Simpply (Debug) | Simpply.Helpers | WebHelper | GetControllerActionParameters(string) : string | 72 | 2 |  | 0 | 5
Member | Simpply (Debug) | Simpply.Controllers | BreadcrumbController | GetBreadCrumbs() : ActionResult | 60 | 2 |  | 7 | 11
Member | Simpply (Debug) | Simpply.Helpers | WebHelper | GetBaseUrl() : string | 71 | 2 |  | 3 | 4
Member | Simpply (Debug) | Simpply.Helpers | WebHelper | GenerateActionUrl(string, string, string) : string | 73 | 2 |  | 1 | 4
Member | Simpply (Debug) | Simpply.Models | SeasonExplorerModel | FormatActionUrl(string, string, bool, bool) : string | 73 | 2 |  | 1 | 4
Member | Simpply (Debug) | Simpply.Models | SeasonExplorerModel | CreateHeaderCell(string, string, string, bool, bool) : GridCellModel | 78 | 2 |  | 1 | 2
Member | Simpply (Debug) | Simpply.Models.POG | PlanogramExplorerModel | CreateHeaderCell(string, string, string, bool, bool, int?) : GridCellModel | 78 | 2 |  | 2 | 2
Member | Simpply (Debug) | Simpply.Models | ChartModel | YAxisLabel.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ChartModel | YAxisLabel.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ChartModel | XAxisLabel.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ChartModel | XAxisLabel.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ChartModel | Width.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ChartModel | Width.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | WarehouseBalanceOnOrder.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | WarehouseBalanceOnOrder.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | WarehouseBalanceOnHand.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | WarehouseBalanceOnHand.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ChartSeries | Values.set(List<ChartValue>) : void | 95 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | ChartSeries | Values.get() : List<ChartValue> | 98 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | BreadcrumbModel | Value.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | FormInput | Value.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | Value.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ChartValue | Value.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | BreadcrumbModel | Value.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | FormInput | Value.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | Value.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ChartValue | Value.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | Type.set(GridCellType) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ChartModel | Type.set(ChartType) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | Type.get() : GridCellType | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ChartModel | Type.get() : ChartType | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | TotalItems.set(long) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | TotalItems.get() : long | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ChartModel | Title.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ChartModel | Title.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | TableId.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | TableId.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | tableCondensed.set(bool) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | tableCondensed.get() : bool | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | Table.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | Table.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Controllers | StoreController | StoreController() | 100 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | StepValue.set(int?) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | StepValue.get() : int? | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Controllers | ItemController | StandInItem(List<int>) : ActionResult | 83 | 1 |  | 4 | 2
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | SortDetailsDescending.set(bool) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | SortDetailsDescending.get() : bool | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | sortDescending.set(bool) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | sortDescending.get() : bool | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | sortColumn.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | sortColumn.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ShownColumnsList.set(List<SelectListItem>) : void | 95 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ShownColumnsList.get() : List<SelectListItem> | 98 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ShownColumnsDefault.set(List<SelectListItem>) : void | 95 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ShownColumnsDefault.get() : List<SelectListItem> | 98 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ShownColumns.set(List<string>) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ShownColumns.get() : List<string> | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | ShipWeek.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | ShipWeek.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | BreadcrumbTrailModel | SetToDefault() : void | 69 | 1 |  | 3 | 4
Member | Simpply (Debug) | Simpply.Models | ChartModel | Series.set(List<ChartSeries>) : void | 95 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | ChartModel | Series.get() : List<ChartSeries> | 98 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Controllers | SeasonController | SeasonController(ISeasonProvider, IColumnPreferenceProvider) | 81 | 1 |  | 3 | 3
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | SalesHistoryChart.set(ChartModel) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | SalesHistoryChart.get() : ChartModel | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | Rows.set(List<GridRowModel>) : void | 95 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | Rows.get() : List<GridRowModel> | 98 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply | RouteConfig | RouteConfig() | 100 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Controllers | BaseController | Root() : ActionResult | 86 | 1 |  | 2 | 2
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | ReplenishmentLevel.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | ReplenishmentLevel.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | ReplenishmentDescription.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | ReplenishmentDescription.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply | RouteConfig | RegisterRoutes(RouteCollection) : void | 82 | 1 |  | 3 | 2
Member | Simpply (Debug) | Simpply | FilterConfig | RegisterGlobalFilters(GlobalFilterCollection) : void | 94 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.App_Start | AutofacConfig | RegisterComponents() : void | 70 | 1 |  | 10 | 5
Member | Simpply (Debug) | Simpply | BundleConfig | RegisterBundles(BundleCollection) : void | 64 | 1 |  | 4 | 6
Member | Simpply (Debug) | Simpply | AuthConfig | RegisterAuth() : void | 100 | 1 |  | 0 | 0
Member | Simpply (Debug) | Simpply | WebApiConfig | Register(HttpConfiguration) : void | 89 | 1 |  | 4 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | PreviousId.set(long) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | PreviousId.get() : long | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | planogramId.set(int?) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | planogramId.get() : int? | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Controllers | PlanogramController | PlanogramController(IPlanogramProvider, IColumnPreferenceProvider) | 81 | 1 |  | 3 | 3
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | PickWeek.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | PickWeek.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | NumberOfTotal.set(long) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | NumberOfTotal.get() : long | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | NextId.set(long) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | NextId.get() : long | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ChartSeries | Name.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | Column | Name.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | FormInput | Name.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | Name.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ChartSeries | Name.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | Column | Name.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | FormInput | Name.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | Name.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply | MvcApplication | MvcApplication() | 100 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | ModelRow.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | ModelRow.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | ModelName.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | ModelName.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | ModelAttribute.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | ModelAttribute.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | MinValue.set(int?) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | MinValue.get() : int? | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | MaxValue.set(int?) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | MaxValue.get() : int? | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | LastModifiedDate.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | LastModifiedDate.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | LastModifiedBy.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | LastModifiedBy.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Controllers | BaseController | JsonActionResult(JsonReturnType, string, string, string, object) : ActionResult | 68 | 1 |  | 5 | 6
Member | Simpply (Debug) | Simpply.Models | FinalizeDistributionModel | ItemIds.set(List<int>) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | FinalizeDistributionModel | ItemIds.get() : List<int> | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | ItemFinalized.set(bool) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | ItemFinalized.get() : bool | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Controllers | ItemController | ItemController(IItemProvider, IStoreProvider, ISalesInformationProvider, IColumnPreferenceProvider) | 71 | 1 |  | 6 | 6
Member | Simpply (Debug) | Simpply.Controllers | ItemController | ItemController() | 90 | 1 |  | 4 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | IsSortedDescending.set(bool) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | IsSortedDescending.get() : bool | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | IsSorted.set(bool) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | IsSorted.get() : bool | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridRowModel | IsHeader.set(bool) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridRowModel | IsHeader.get() : bool | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemExplorerModel | IsFilteredToPlanogram.set(bool) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemExplorerModel | IsFilteredToPlanogram.get() : bool | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | IndexOfStoreSegmentationColumn.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | IndexOfStoreSegmentationColumn.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | IndexOfShipDistributionColumn.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | IndexOfShipDistributionColumn.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | IndexOfAggregateSegmentationColumn.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | IndexOfAggregateSegmentationColumn.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | IndexOfAggregateDistributionColumn.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | IndexOfAggregateDistributionColumn.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | SeasonExplorerModel | InactiveSeasonURL.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | SeasonExplorerModel | InactiveSeasonURL.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models.POG | PlanogramExplorerModel | InactivePlanogramURL.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models.POG | PlanogramExplorerModel | InactivePlanogramURL.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ChartModel | Id.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | Id.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ChartModel | Id.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | Id.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | HiddenColumnsList.set(List<SelectListItem>) : void | 95 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | HiddenColumnsList.get() : List<SelectListItem> | 98 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | HiddenColumns.set(List<string>) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | HiddenColumns.get() : List<string> | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ChartModel | Height.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ChartModel | Height.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | Header.set(GridRowModel) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | Header.get() : GridRowModel | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | GridRowModel | GridRowModel() | 87 | 1 |  | 2 | 2
Member | Simpply (Debug) | Simpply.Models | GridModel | GridModel() | 72 | 1 |  | 3 | 5
Member | Simpply (Debug) | Simpply.Models | GridCellModel | GridCellModel() | 78 | 1 |  | 0 | 4
Member | Simpply (Debug) | Simpply.Models | ItemExplorerModel | Grid.set(GridModel) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | SeasonExplorerModel | Grid.set(GridModel) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models.POG | PlanogramExplorerModel | Grid.set(GridModel) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ItemExplorerModel | Grid.get() : GridModel | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | SeasonExplorerModel | Grid.get() : GridModel | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models.POG | PlanogramExplorerModel | Grid.get() : GridModel | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Helpers | WebHelper | GetControllerName(string) : string | 78 | 1 |  | 0 | 3
Member | Simpply (Debug) | Simpply.Helpers | WebHelper | GetControllerActionName(string) : string | 78 | 1 |  | 0 | 3
Member | Simpply (Debug) | Simpply.Models | GridModel | FormMethod.set(FormMethod) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | FormMethod.get() : FormMethod | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | FormInput | FormInput() | 100 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | FormId.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | FormId.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | FormHiddenInputs.set(List<FormInput>) : void | 95 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | FormHiddenInputs.get() : List<FormInput> | 98 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | FormController.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | FormController.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | FormAction.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | FormAction.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | FinalizeDistributionModel | FinalizeDistributionModel() | 87 | 1 |  | 1 | 2
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | FinalizedDistributionType.set(FinalizedDistributionType) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | FinalizedDistributionType.get() : FinalizedDistributionType | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply | FilterConfig | FilterConfig() | 100 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | FinalizeDistributionModel | DistributionType.set(DistributionType) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | FinalizeDistributionModel | DistributionType.get() : DistributionType | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | Distribution.set(GridModel) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | Distribution.get() : GridModel | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | Column | DisplayName.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | Column | DisplayName.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | CurrentlySortedDetailsColumn.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | CurrentlySortedDetailsColumn.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | CssClasses.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridRowModel | CssClasses.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | CssClasses.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridRowModel | CssClasses.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ControllerName.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ControllerName.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ControllerAction.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ControllerAction.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Controllers | StoreController | CompareTostore() : ActionResult | 89 | 1 |  | 2 | 2
Member | Simpply (Debug) | Simpply.Controllers | StoreController | CompareToMultiplestores() : ActionResult | 89 | 1 |  | 2 | 2
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | ColumnPreferences.set(ColumnPreferenceModel) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ItemExplorerModel | ColumnPreferences.set(ColumnPreferenceModel) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | SeasonExplorerModel | ColumnPreferences.set(ColumnPreferenceModel) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models.POG | PlanogramExplorerModel | ColumnPreferences.set(ColumnPreferenceModel) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | ColumnPreferences.get() : ColumnPreferenceModel | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ItemExplorerModel | ColumnPreferences.get() : ColumnPreferenceModel | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | SeasonExplorerModel | ColumnPreferences.get() : ColumnPreferenceModel | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models.POG | PlanogramExplorerModel | ColumnPreferences.get() : ColumnPreferenceModel | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ColumnPreferenceModel() | 71 | 1 |  | 2 | 6
Member | Simpply (Debug) | Simpply.Models | Column | Column() | 100 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ChartValue | ChartValue() | 100 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ChartSeries | ChartSeries(string, int) | 80 | 1 |  | 2 | 3
Member | Simpply (Debug) | Simpply.Models | ChartSeries | ChartSeries() | 87 | 1 |  | 2 | 2
Member | Simpply (Debug) | Simpply.Models | ChartModel | ChartModel() | 74 | 1 |  | 2 | 5
Member | Simpply (Debug) | Simpply.Models | GridRowModel | Cells.set(List<GridCellModel>) : void | 95 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | GridRowModel | Cells.get() : List<GridCellModel> | 98 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | ChartValue | Category.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ChartValue | Category.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply | BundleConfig | BundleConfig() | 100 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | BreadcrumbTrailModel | BreadcrumbTrailModel() | 65 | 1 |  | 3 | 6
Member | Simpply (Debug) | Simpply.Models | BreadcrumbModel | BreadcrumbModel() | 100 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Controllers | BreadcrumbController | BreadcrumbController() | 100 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Controllers | BaseController | BaseController() | 100 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply | MvcApplication | Application_Start() : void | 69 | 1 |  | 11 | 7
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | Aggregate.set(GridModel) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | Aggregate.get() : GridModel | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | SeasonExplorerModel | ActiveOnly.set(bool) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models.POG | PlanogramExplorerModel | ActiveOnly.set(bool) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | SeasonExplorerModel | ActiveOnly.get() : bool | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models.POG | PlanogramExplorerModel | ActiveOnly.get() : bool | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | BreadcrumbModel | ActionUrl.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ChartModel | ActionUrl.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | ActionUrl.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridRowModel | ActionUrl.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | BreadcrumbModel | ActionUrl.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ChartModel | ActionUrl.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | ActionUrl.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridRowModel | ActionUrl.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Controllers | AccountController | AccountController(IColumnPreferenceProvider) | 87 | 1 |  | 2 | 2
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ItemProvider | GetDetails(long, string, bool?) : Item | 45 | 10 |  | 18 | 32
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ItemProvider | SaveMultiple(List<Distribution>) : void | 52 | 4 |  | 16 | 15
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ItemProvider | SaveDistribution(List<DistributionModel>, int, int, string) : void | 52 | 4 |  | 16 | 15
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ColumnPreferenceProvider | Save(List<ColumnPreference>) : void | 52 | 4 |  | 15 | 15
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | SeasonProvider | Get(bool, string, bool) : List<SeasonInfo> | 60 | 4 |  | 13 | 10
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | PlanogramProvider | Get(bool, int?, string, bool) : List<Planogram> | 60 | 4 |  | 13 | 10
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ItemProvider | FinalizeItems(List<int>, DistributionType, FinalizedDistributionType, int, int, string) : void | 46 | 4 |  | 15 | 30
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ItemProvider | GetSalesHistory(List<long>, int?, int?, int?, int?) : List<WeeklyPurchase> | 60 | 3 |  | 15 | 9
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | SalesInformationProvider | Get(long, long) : SalesInformation | 70 | 3 |  | 5 | 5
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | JobProvider | UpdateProgress(long, string, int) : void | 72 | 2 |  | 7 | 4
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ExampleProvider | SelectExample(int) : Example | 70 | 2 |  | 9 | 5
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | JobProvider | Insert(string) : long | 69 | 2 |  | 8 | 5
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ItemProvider | GetStandInItem(int) : string | 66 | 2 |  | 9 | 7
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | SeasonProvider | GetSeasonName(int) : string | 66 | 2 |  | 9 | 7
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ItemProvider | GetSalesHistoryForChart(long) : List<WeeklyPurchase> | 69 | 2 |  | 10 | 5
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | PlanogramProvider | GetPlanogramName(int) : string | 66 | 2 |  | 9 | 7
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ItemProvider | GetItemsDetails(long?, string, int?, string, bool?) : List<Item> | 69 | 2 |  | 10 | 5
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ItemProvider | GetItemName(int) : string | 66 | 2 |  | 9 | 7
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ItemProvider | GetIds() : List<long> | 69 | 2 |  | 9 | 5
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ColumnPreferenceProvider | Get(string, string, string) : List<ColumnPreference> | 66 | 2 |  | 10 | 7
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | StoreProvider | Get(long) : Store | 71 | 2 |  | 5 | 5
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | JobProvider | Get(long) : Job | 69 | 2 |  | 9 | 5
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ItemProvider | Get(long?, string, int?, string, bool?) : List<Item> | 69 | 2 |  | 10 | 5
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IJobProvider | UpdateProgress(long, string, int) : void | 100 | 1 |  | 0 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | StoreProvider | StoreProvider() | 76 | 1 |  | 3 | 2
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | SeasonProvider | SeasonProvider() | 100 | 1 |  | 1 | 1
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IItemProvider | SaveMultiple(List<Distribution>) : void | 100 | 1 |  | 2 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IItemProvider | SaveDistribution(List<DistributionModel>, int, int, string) : void | 100 | 1 |  | 2 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IColumnPreferenceProvider | Save(List<ColumnPreference>) : void | 100 | 1 |  | 2 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | SalesInformationProvider | SalesInformationProvider() | 68 | 1 |  | 3 | 2
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | PlanogramProvider | PlanogramProvider() | 100 | 1 |  | 1 | 1
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access | AccessModule | Load(ContainerBuilder) : void | 63 | 1 |  | 18 | 7
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | JobProvider | JobProvider() | 100 | 1 |  | 1 | 1
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ItemProvider | ItemProvider() | 100 | 1 |  | 1 | 1
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IJobProvider | Insert(string) : long | 100 | 1 |  | 0 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IItemProvider | GetSalesHistoryForChart(long) : List<WeeklyPurchase> | 100 | 1 |  | 2 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IItemProvider | GetSalesHistory(List<long>, int?, int?, int?, int?) : List<WeeklyPurchase> | 100 | 1 |  | 3 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IItemProvider | GetItemsDetails(long?, string, int?, string, bool?) : List<Item> | 100 | 1 |  | 3 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IItemProvider | GetDetails(long, string, bool?) : Item | 100 | 1 |  | 2 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IColumnPreferenceProvider | Get(string, string, string) : List<ColumnPreference> | 100 | 1 |  | 2 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IStoreProvider | Get(long) : Store | 100 | 1 |  | 1 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IJobProvider | Get(long) : Job | 100 | 1 |  | 1 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IItemProvider | Get(long?, string, int?, string, bool?) : List<Item> | 100 | 1 |  | 3 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | ISalesInformationProvider | Get(long, long) : SalesInformation | 100 | 1 |  | 1 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | ISeasonProvider | Get(bool, string, bool) : List<SeasonInfo> | 100 | 1 |  | 2 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IPlanogramProvider | Get(bool, int?, string, bool) : List<Planogram> | 100 | 1 |  | 3 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IStoreProvider | Get() : List<Store> | 100 | 1 |  | 2 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | StoreProvider | Get() : List<Store> | 91 | 1 |  | 2 | 2
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | ISalesInformationProvider | Get() : List<SalesInformation> | 100 | 1 |  | 2 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | SalesInformationProvider | Get() : List<SalesInformation> | 91 | 1 |  | 2 | 2
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IItemProvider | FinalizeItems(List<int>, DistributionType, FinalizedDistributionType, int, int, string) : void | 100 | 1 |  | 3 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ExampleProvider | ExampleProvider() | 100 | 1 |  | 1 | 1
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | BaseProvider | connectionString.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | BaseProvider | connectionString.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ColumnPreferenceProvider | ColumnPreferenceProvider() | 100 | 1 |  | 1 | 1
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | BaseProvider | BaseProvider() | 83 | 1 |  | 3 | 2
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access | AccessModule | AccessModule() | 100 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Algorithms | SetupAlgorithm | Execute(Item, BaseJobModel) : List<Distribution> | 42 | 9 |  | 13 | 37
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | JobInvoker | ScheduleJob(BaseJob) : JobResponse | 45 | 8 |  | 10 | 34
Member | Simpply.Engine (Debug) | Simpply.Engine.Algorithms | PushAllAlgorithm | Execute(Item, BaseJobModel) : List<Distribution> | 47 | 8 |  | 14 | 26
Member | Simpply.Engine (Debug) | Simpply.Engine.Algorithms | SellthroughAlgorithm | Execute(Item, BaseJobModel) : List<Distribution> | 47 | 8 |  | 12 | 27
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunSellthroughJob | ValidateParameters() : bool | 56 | 7 |  | 4 | 15
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunSetupJob | ValidateParameters() : bool | 57 | 7 |  | 5 | 13
Member | Simpply.Engine (Debug) | Simpply.Engine.Controllers | JobsController | Post(JobRequest) : object | 54 | 6 |  | 13 | 17
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunPushAllJob | ValidateParameters() : bool | 64 | 4 |  | 4 | 9
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | JobInvoker | GetInstance() : JobInvoker | 67 | 4 |  | 1 | 8
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | ParseWegmansData | Execute(long) : bool | 53 | 4 |  | 12 | 18
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunPushAllJob | Execute(long) : bool | 56 | 3 |  | 9 | 13
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunSellthroughJob | Execute(long) : bool | 51 | 3 |  | 13 | 18
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunSetupJob | Execute(long) : bool | 56 | 3 |  | 9 | 13
Member | Simpply.Engine (Debug) | Simpply.Engine.Algorithms | BaseAlgorithm | ConvertStoreToWarehouse(long, int, int) : long | 68 | 3 |  | 0 | 7
Member | Simpply.Engine (Debug) | Simpply.Engine.Algorithms | SellthroughAlgorithm | ComputeForecast(long, List<WeeklyPurchase>) : int | 68 | 3 |  | 4 | 6
Member | Simpply.Engine (Debug) | Simpply.Engine.Algorithms | BaseAlgorithm | ConvertWarehouseToStore(long, int, int) : long | 77 | 2 |  | 0 | 4
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | BaseJob | BaseJob(string, JobProvider) | 71 | 2 |  | 2 | 6
Member | Simpply.Engine (Debug) | Simpply.Engine | WebApiApplication | WebApiApplication() | 100 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | BaseJob | ValidateParameters() : bool | 100 | 1 |  | 0 | 0
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | ParseWegmansData | ValidateParameters() : bool | 91 | 1 |  | 0 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | JobInvoker | ValidateNoConflict() : bool | 91 | 1 |  | 0 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunPushAllJobModel | Username.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | Username.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | Username.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunPushAllJobModel | Username.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | Username.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | Username.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | BaseJob | UpdateJobStatus(long, string, int) : void | 92 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobResponse | Success.set(bool) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobResponse | Success.get() : bool | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | SetupDistributionPercent.set(double) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | SetupDistributionPercent.get() : double | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Algorithms | SetupAlgorithm | SetupAlgorithm() | 100 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunPushAllJobModel | SellthroughPercentTrigger.set(double) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | SellthroughPercentTrigger.set(double) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | SellthroughPercentTrigger.set(double) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunPushAllJobModel | SellthroughPercentTrigger.get() : double | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | SellthroughPercentTrigger.get() : double | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunPushAllJobModel | SellthroughPercentTrigger.get() : double | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | SellthroughPercentTrigger.get() : double | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Algorithms | SellthroughAlgorithm | SellthroughAlgorithm() | 100 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Algorithms | SellthroughAlgorithm | SellthroughAlgorithm() | 100 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | SegmentCDistributionPercent.set(double) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | SegmentCDistributionPercent.set(double) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | SegmentCDistributionPercent.set(double) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | SegmentCDistributionPercent.set(double) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | SegmentCDistributionPercent.get() : double | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | SegmentCDistributionPercent.get() : double | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | SegmentCDistributionPercent.get() : double | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | SegmentCDistributionPercent.get() : double | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | SegmentBDistributionPercent.set(double) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | SegmentBDistributionPercent.set(double) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | SegmentBDistributionPercent.set(double) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | SegmentBDistributionPercent.set(double) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | SegmentBDistributionPercent.get() : double | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | SegmentBDistributionPercent.get() : double | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | SegmentBDistributionPercent.get() : double | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | SegmentBDistributionPercent.get() : double | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | SegmentationPercents.set(Dictionary<string, double>) : void | 95 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | SegmentationPercents.set(Dictionary<string, double>) : void | 95 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | SegmentationPercents.get() : Dictionary<string, double> | 98 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | SegmentationPercents.get() : Dictionary<string, double> | 98 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | SegmentADistributionPercent.set(double) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | SegmentADistributionPercent.set(double) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | SegmentADistributionPercent.set(double) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | SegmentADistributionPercent.set(double) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | SegmentADistributionPercent.get() : double | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | SegmentADistributionPercent.get() : double | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | SegmentADistributionPercent.get() : double | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | SegmentADistributionPercent.get() : double | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | RunSetupJobModel() | 100 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | RunSetupJobModel() | 100 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunSetupJob | RunSetupJob(string) | 79 | 1 |  | 4 | 3
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunSetupJob | RunSetupJob(string) | 79 | 1 |  | 4 | 3
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | RunSellthroughJobModel() | 100 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | RunSellthroughJobModel() | 100 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunSellthroughJob | RunSellthroughJob(string) | 79 | 1 |  | 4 | 3
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunSellthroughJob | RunSellthroughJob(string) | 79 | 1 |  | 4 | 3
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunPushAllJobModel | RunPushAllJobModel() | 100 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunPushAllJobModel | RunPushAllJobModel() | 100 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunPushAllJob | RunPushAllJob(string) | 79 | 1 |  | 4 | 3
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunPushAllJob | RunPushAllJob(string) | 79 | 1 |  | 4 | 3
Member | Simpply.Engine (Debug) | Simpply.Engine | RouteConfig | RouteConfig() | 100 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine | RouteConfig | RouteConfig() | 100 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine | RouteConfig | RegisterRoutes(RouteCollection) : void | 82 | 1 |  | 4 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine | RouteConfig | RegisterRoutes(RouteCollection) : void | 82 | 1 |  | 4 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine | FilterConfig | RegisterGlobalFilters(GlobalFilterCollection) : void | 94 | 1 |  | 2 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine | FilterConfig | RegisterGlobalFilters(GlobalFilterCollection) : void | 94 | 1 |  | 2 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine | BundleConfig | RegisterBundles(BundleCollection) : void | 100 | 1 |  | 1 | 0
Member | Simpply.Engine (Debug) | Simpply.Engine | BundleConfig | RegisterBundles(BundleCollection) : void | 100 | 1 |  | 1 | 0
Member | Simpply.Engine (Debug) | Simpply.Engine | WebApiConfig | Register(HttpConfiguration) : void | 75 | 1 |  | 9 | 3
Member | Simpply.Engine (Debug) | Simpply.Engine | WebApiConfig | Register(HttpConfiguration) : void | 75 | 1 |  | 9 | 3
Member | Simpply.Engine (Debug) | Simpply.Engine.Algorithms | PushAllAlgorithm | PushAllAlgorithm() | 100 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Algorithms | PushAllAlgorithm | PushAllAlgorithm() | 100 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | ParseWegmansData | ParseWegmansData(string) | 98 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | ParseWegmansData | ParseWegmansData(string) | 87 | 1 |  | 2 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | ParseWegmansData | ParseWegmansData() | 90 | 1 |  | 4 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobResponse | Message.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobResponse | Message.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobResponse | Message.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobResponse | Message.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Controllers | JobsController | JobsController() | 100 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Controllers | JobsController | JobsController() | 100 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Controllers | JobsController | JobsController() | 90 | 1 |  | 4 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobResponse | JobResponse(bool, int, string, long) | 74 | 1 |  | 0 | 5
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobResponse | JobResponse(bool, int, string, long) | 74 | 1 |  | 0 | 5
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobRequest | JobRequest() | 82 | 1 |  | 0 | 3
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobRequest | JobRequest() | 82 | 1 |  | 0 | 3
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | JobInvoker | JobInvoker() | 76 | 1 |  | 5 | 4
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | JobInvoker | JobInvoker() | 82 | 1 |  | 4 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | JobInvoker | JobInvoker() | 76 | 1 |  | 5 | 4
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | JobInvoker | JobInvoker() | 77 | 1 |  | 4 | 3
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobResponse | JobId.set(long) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobResponse | JobId.set(long) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobResponse | JobId.get() : long | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobResponse | JobId.get() : long | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobRequest | Job.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobRequest | Job.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobRequest | Job.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobRequest | Job.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Controllers | HomeController | Index() : ActionResult | 89 | 1 |  | 2 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Controllers | HomeController | Index() : ActionResult | 89 | 1 |  | 2 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunPushAllJobModel | Ids.set(List<long>) : void | 95 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | Ids.set(List<long>) : void | 95 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | Ids.set(List<long>) : void | 95 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunPushAllJobModel | Ids.set(List<long>) : void | 95 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | Ids.set(List<long>) : void | 95 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | Ids.set(List<long>) : void | 95 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunPushAllJobModel | Ids.get() : List<long> | 98 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | Ids.get() : List<long> | 98 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | Ids.get() : List<long> | 98 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunPushAllJobModel | Ids.get() : List<long> | 98 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | Ids.get() : List<long> | 98 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | Ids.get() : List<long> | 98 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Controllers | HomeController | HomeController() | 100 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Controllers | HomeController | HomeController() | 100 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | History.set(List<WeeklyPurchase>) : void | 95 | 1 |  | 2 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | History.set(List<WeeklyPurchase>) : void | 95 | 1 |  | 2 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | History.get() : List<WeeklyPurchase> | 98 | 1 |  | 2 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | History.get() : List<WeeklyPurchase> | 98 | 1 |  | 2 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | BaseJob | GetValidParameters() : string | 100 | 1 |  | 0 | 0
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | ParseWegmansData | GetValidParameters() : string | 91 | 1 |  | 0 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunPushAllJob | GetValidParameters() : string | 91 | 1 |  | 0 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunSellthroughJob | GetValidParameters() : string | 91 | 1 |  | 0 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunSetupJob | GetValidParameters() : string | 91 | 1 |  | 0 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | BaseJob | GetValidParameters() : string | 100 | 1 |  | 0 | 0
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | ParseWegmansData | GetValidParameters() : string | 91 | 1 |  | 0 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunPushAllJob | GetValidParameters() : string | 91 | 1 |  | 0 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunSellthroughJob | GetValidParameters() : string | 91 | 1 |  | 0 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunSetupJob | GetValidParameters() : string | 91 | 1 |  | 0 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | BaseJob | GetName() : string | 100 | 1 |  | 0 | 0
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | ParseWegmansData | GetName() : string | 91 | 1 |  | 0 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunPushAllJob | GetName() : string | 91 | 1 |  | 0 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunSellthroughJob | GetName() : string | 91 | 1 |  | 0 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunSetupJob | GetName() : string | 91 | 1 |  | 0 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | BaseJob | GetName() : string | 100 | 1 |  | 0 | 0
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | ParseWegmansData | GetName() : string | 91 | 1 |  | 0 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunPushAllJob | GetName() : string | 91 | 1 |  | 0 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunSellthroughJob | GetName() : string | 91 | 1 |  | 0 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunSetupJob | GetName() : string | 91 | 1 |  | 0 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | BaseJob | GetItemIdParameter() : List<long> | 100 | 1 |  | 1 | 0
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | ParseWegmansData | GetItemIdParameter() : List<long> | 89 | 1 |  | 1 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunPushAllJob | GetItemIdParameter() : List<long> | 87 | 1 |  | 2 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunSellthroughJob | GetItemIdParameter() : List<long> | 87 | 1 |  | 2 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunSetupJob | GetItemIdParameter() : List<long> | 87 | 1 |  | 2 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Controllers | JobsController | Get(long) : string | 79 | 1 |  | 3 | 3
Member | Simpply.Engine (Debug) | Simpply.Engine.Controllers | JobsController | Get(long) : string | 79 | 1 |  | 3 | 3
Member | Simpply.Engine (Debug) | Simpply.Engine | FilterConfig | FilterConfig() | 100 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine | FilterConfig | FilterConfig() | 100 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | BaseJob | Execute(long) : bool | 100 | 1 |  | 0 | 0
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | BaseJob | Execute(long) : bool | 100 | 1 |  | 0 | 0
Member | Simpply.Engine (Debug) | Simpply.Engine.Algorithms | BaseAlgorithm | Execute(Item, BaseJobModel) : List<Distribution> | 100 | 1 |  | 4 | 0
Member | Simpply.Engine (Debug) | Simpply.Engine.Algorithms | BaseAlgorithm | Execute(Item, BaseJobModel) : List<Distribution> | 100 | 1 |  | 4 | 0
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobResponse | ErrorCode.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobResponse | ErrorCode.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobResponse | ErrorCode.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobResponse | ErrorCode.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobRequest | Data.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobRequest | Data.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobRequest | Data.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobRequest | Data.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine | BundleConfig | BundleConfig() | 100 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine | BundleConfig | BundleConfig() | 100 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | BaseJob | BaseJob(string) | 94 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | BaseJob | BaseJob(string) | 94 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | BaseJob | BaseJob() | 80 | 1 |  | 1 | 3
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | BaseJob | BaseJob() | 80 | 1 |  | 1 | 3
Member | Simpply.Engine (Debug) | Simpply.Engine.Algorithms | BaseAlgorithm | BaseAlgorithm() | 100 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Algorithms | BaseAlgorithm | BaseAlgorithm() | 100 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine | WebApiApplication | Application_Start() : void | 73 | 1 |  | 9 | 5
Member | Simpply.Engine (Debug) | Simpply.Engine | WebApiApplication | Application_Start() : void | 73 | 1 |  | 9 | 5
Member | Simpply.Global (Debug) | Simpply.Global | Constants.ViewPages | ViewPages() | 100 | 1 |  | 0 | 1
Member | Simpply.Global (Debug) | Simpply.Global | Constants.ControllerAction.Season | Season() | 100 | 1 |  | 0 | 1
Member | Simpply.Global (Debug) | Simpply.Global | Constants.ControllerAction.Planogram | Planogram() | 100 | 1 |  | 0 | 1
Member | Simpply.Global (Debug) | Simpply.Global | Constants.ViewPages.ItemDetails | ItemDetails() | 100 | 1 |  | 0 | 1
Member | Simpply.Global (Debug) | Simpply.Global | Constants.ControllerAction.Item | Item() | 100 | 1 |  | 0 | 1
Member | Simpply.Global (Debug) | Simpply.Global | Constants.ControllerAction | ControllerAction() | 100 | 1 |  | 0 | 1
Member | Simpply.Global (Debug) | Simpply.Global | Constants.Controller | Controller() | 100 | 1 |  | 0 | 1
Member | Simpply.Global (Debug) | Simpply.Global | Constants | Constants() | 100 | 1 |  | 0 | 1
Member | Simpply.Global (Debug) | Simpply.Global | Constants.ControllerAction.Account | Account() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ItemProviderTest | SaveDistribution() : void | 46 | 13 |  | 14 | 26
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | AccountControllerTest | SaveColumnPreferences() : void | 55 | 5 |  | 23 | 12
Member | Simpply.Tests (Debug) | Simpply.Tests.Jobs | RunSetupJobTest | ValidateParametersTest() : void | 57 | 3 |  | 6 | 15
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | ItemControllerTest | ItemExplorer() : void | 59 | 3 |  | 20 | 8
Member | Simpply.Tests (Debug) | Simpply.Tests.ViewModels | ItemModelsTest | ItemDetailModelHasCorrectAggregateGrid() : void | 60 | 3 |  | 11 | 10
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | ItemControllerTest | ItemDetail() : void | 65 | 3 |  | 17 | 5
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | PlanogramProviderTest | GetReturnsOnlyActivePlanograms() : void | 65 | 3 |  | 9 | 7
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | PlanogramProviderTest | GetResultsAreInOrder() : void | 65 | 3 |  | 9 | 7
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ItemProviderTest | GetDetailsReturnsRelatedDistributions() : void | 68 | 3 |  | 10 | 5
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ItemProviderTest | GetDetailsReturnsRelatedSalesInformation() : void | 69 | 2 |  | 10 | 5
Member | Simpply.Tests (Debug) | Simpply.Tests.Algorithms | SetupAlgorithmTest | ExecuteSetupDistributionTest() : void | 62 | 2 |  | 9 | 8
Member | Simpply.Tests (Debug) | Simpply.Tests.Algorithms | PushAllAlgorithmTest | ExecutePushAllDistributionTest() : void | 62 | 2 |  | 9 | 8
Member | Simpply.Tests (Debug) | Simpply.Tests.Algorithms | PushAllAlgorithmTest | TestInit() : void | 47 | 1 |  | 8 | 33
Member | Simpply.Tests (Debug) | Simpply.Tests.Algorithms | SetupAlgorithmTest | TestInit() : void | 47 | 1 |  | 9 | 31
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | AccountControllerTest | TestInit() : void | 92 | 1 |  | 3 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | ItemControllerTest | TestInit() : void | 77 | 1 |  | 5 | 3
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | PlanogramControllerTest | TestInit() : void | 77 | 1 |  | 5 | 3
Member | Simpply.Tests (Debug) | Simpply.Tests.Jobs | RunSetupJobTest | TestInit() : void | 70 | 1 |  | 1 | 6
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | BaseProviderTest | TestInit() : void | 94 | 1 |  | 3 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ColumnPreferenceProviderTest | TestInit() : void | 94 | 1 |  | 3 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ItemProviderTest | TestInit() : void | 94 | 1 |  | 3 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | PlanogramProviderTest | TestInit() : void | 94 | 1 |  | 3 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.ViewModels | ItemModelsTest | TestInit() : void | 75 | 1 |  | 6 | 2
Member | Simpply.Tests (Debug) | Simpply.Tests.Algorithms | SetupAlgorithmTest | SetupAlgorithmTest() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | ItemControllerTest | SaveItemDistributionCallsProvidersCorrectly() : void | 72 | 1 |  | 7 | 3
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ColumnPreferenceProviderTest | Save() : void | 75 | 1 |  | 4 | 2
Member | Simpply.Tests (Debug) | Simpply.Tests.Jobs | RunSetupJobTest | RunSetupJobTest() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Algorithms | PushAllAlgorithmTest | PushAllAlgorithmTest() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | PlanogramProviderTest | PlanogramProviderTest() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | PlanogramControllerTest | PlanogramControllerTest() | 76 | 1 |  | 3 | 2
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ItemProviderTest | ItemProviderTest() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.ViewModels | ItemModelsTest | ItemModelsTest() | 66 | 1 |  | 3 | 4
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | ItemControllerTest | ItemExplorerFiltersToCorrectPlanogram() : void | 63 | 1 |  | 11 | 7
Member | Simpply.Tests (Debug) | Simpply.Tests.ViewModels | ItemModelsTest | ItemDetailModelHasCorrectItemName() : void | 75 | 1 |  | 5 | 3
Member | Simpply.Tests (Debug) | Simpply.Tests.ViewModels | ItemModelsTest | ItemDetailModelHasCorrectDistributionGrid() : void | 71 | 1 |  | 9 | 4
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | ItemControllerTest | ItemControllerTest() | 69 | 1 |  | 5 | 3
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | PlanogramControllerTest | IndexGetsAllPlanograms() : void | 66 | 1 |  | 8 | 6
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | PlanogramControllerTest | IndexGetsActivePlanogramsOnly() : void | 66 | 1 |  | 8 | 6
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | PlanogramProviderTest | GetResultIsNotNull() : void | 69 | 1 |  | 7 | 6
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ItemProviderTest | GetItems() : void | 71 | 1 |  | 7 | 5
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ItemProviderTest | GetDetailsReturnsRelatedStores() : void | 73 | 1 |  | 7 | 4
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ItemProviderTest | GetDetailsReturnsANonNullItem() : void | 74 | 1 |  | 5 | 4
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | BreadcrumbControllerTest | GetBreadcrumbsTest() : void | 100 | 1 |  | 1 | 0
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ColumnPreferenceProviderTest | Get() : void | 82 | 1 |  | 6 | 2
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ColumnPreferenceProviderTest | ColumnPreferenceProviderTest() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | BreadcrumbControllerTest | BreadcrumbControllerTest() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | BaseProviderTest | BaseProviderTest() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | AccountControllerTest | AccountControllerTest() | 100 | 1 |  | 0 | 1
Member | Simpply.Util (Debug) | Simpply.Util.Extensions | CollectionExtensions | IsEmpty<T>(this ICollection<T>) : bool | 84 | 2 |  | 2 | 2
Member | Simpply.Util (Debug) | Simpply.Util.Extensions | StringExtensions | IsNullOrWhiteSpace(this string) : bool | 87 | 1 |  | 1 | 2

## Code Metrics Iteration 8
Scope | Project | Namespace | Type | Member | Maintainability Index | Cyclomatic Complexity | Depth of Inheritance | Class Coupling | Lines of Code | Web | Engine | Access
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | ItemDetailModel(Item, string, int?, string, bool, string, bool, ChartModel, List<ColumnPreference>) | 19 | 54 |  | 22 | 117 | 1.93385214 | 1.400943396 | 1.911111111
Member | Simpply (Debug) | Simpply.Models | ItemExplorerModel | ItemExplorerModel(List<Item>, string, int?, string, bool, List<ColumnPreference>) | 30 | 34 |  | 14 | 61
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ColumnPreferenceModel(string, string, string, List<Column>, List<ColumnPreference>) | 32 | 25 |  | 17 | 77
Member | Simpply (Debug) | Simpply.Models | SeasonExplorerModel | SeasonExplorerModel(List<SeasonInfo>, string, bool, bool, List<ColumnPreference>) | 36 | 20 |  | 15 | 46
Member | Simpply (Debug) | Simpply.Models.POG | PlanogramExplorerModel | PlanogramExplorerModel(List<Planogram>, string, bool, bool, List<ColumnPreference>, int?) | 37 | 20 |  | 17 | 42
Member | Simpply (Debug) | Simpply.Controllers | ItemController | BuildSalesHistoryChartModel(long, List<WeeklyPurchase>, string, string, string, string) : ChartModel | 48 | 13 |  | 12 | 21
Member | Simpply (Debug) | Simpply.Models | BreadcrumbTrailModel | AdjustBreadcrumbsTrail(string, string, string) : void | 48 | 11 |  | 6 | 27
Member | Simpply (Debug) | Simpply.Controllers | ItemController | FinalizeItems(string, DistributionType, FinalizedDistributionType, int, int) : ActionResult | 48 | 9 |  | 14 | 26
Member | Simpply (Debug) | Simpply.Controllers | ItemController | SaveDistribution(List<DistributionModel>, int, int) : ActionResult | 55 | 8 |  | 9 | 13
Member | Simpply (Debug) | Simpply.Helpers | WebHelper | ToAbsoluteUrl(this string) : string | 57 | 6 |  | 5 | 12
Member | Simpply (Debug) | Simpply.Controllers | ItemController | ItemDetail(long, int?, string, bool, string, bool) : ActionResult | 50 | 6 |  | 22 | 20
Member | Simpply (Debug) | Simpply.Helpers | WebHelper | getParamId(string) : int | 63 | 5 |  | 0 | 8
Member | Simpply (Debug) | Simpply.Helpers | WebHelper | GenerateActionUrl(string, string, Dictionary<string, string>) : string | 63 | 5 |  | 4 | 8
Member | Simpply (Debug) | Simpply.Models | ItemExplorerModel | CreateHeaderCell(string, string, int?, string, string, bool) : GridCellModel | 63 | 5 |  | 4 | 7
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | CreateDetailHeaderCell(string, int, string, int?, string, bool, string, string, bool) : GridCellModel | 60 | 5 |  | 4 | 9
Member | Simpply (Debug) | Simpply.Controllers | ItemController | SetPreviousNext(ItemDetailModel, long, int?, string, bool) : ItemDetailModel | 54 | 4 |  | 7 | 18
Member | Simpply (Debug) | Simpply.Controllers | AccountController | SaveColumnPreferences(ColumnPreferenceModel) : ActionResult | 55 | 4 |  | 9 | 12
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | GetColumnId(string) : long? | 65 | 4 |  | 2 | 8
Member | Simpply (Debug) | Simpply.Controllers | SeasonController | SeasonExplorer(bool, string, bool) : ActionResult | 63 | 3 |  | 17 | 7
Member | Simpply (Debug) | Simpply.Controllers | ItemController | SalesHistoryChart(long, string) : ActionResult | 67 | 3 |  | 6 | 6
Member | Simpply (Debug) | Simpply.Controllers | PlanogramController | PlanogramExplorer(int?, bool, string, bool) : ActionResult | 63 | 3 |  | 19 | 7
Member | Simpply (Debug) | Simpply.Controllers | ItemController | ItemExplorer(string, int?, string, bool) : ActionResult | 63 | 3 |  | 18 | 7
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | GetColumnName(string) : string | 67 | 3 |  | 1 | 7
Member | Simpply (Debug) | Simpply.Models.POG | PlanogramExplorerModel | FormatActionUrl(string, string, bool, bool, int?) : string | 67 | 3 |  | 2 | 6
Member | Simpply (Debug) | Simpply.Controllers | ItemController | Search(string) : ActionResult | 64 | 2 |  | 7 | 8
Member | Simpply (Debug) | Simpply.Helpers | WebHelper | GetControllerActionParameters(string) : string | 72 | 2 |  | 0 | 5
Member | Simpply (Debug) | Simpply.Controllers | BreadcrumbController | GetBreadCrumbs() : ActionResult | 60 | 2 |  | 7 | 11
Member | Simpply (Debug) | Simpply.Helpers | WebHelper | GetBaseUrl() : string | 71 | 2 |  | 3 | 4
Member | Simpply (Debug) | Simpply.Helpers | WebHelper | GenerateActionUrl(string, string, string) : string | 73 | 2 |  | 1 | 4
Member | Simpply (Debug) | Simpply.Models | SeasonExplorerModel | FormatActionUrl(string, string, bool, bool) : string | 73 | 2 |  | 1 | 4
Member | Simpply (Debug) | Simpply.Models | SeasonExplorerModel | CreateHeaderCell(string, string, string, bool, bool) : GridCellModel | 78 | 2 |  | 1 | 2
Member | Simpply (Debug) | Simpply.Models.POG | PlanogramExplorerModel | CreateHeaderCell(string, string, string, bool, bool, int?) : GridCellModel | 78 | 2 |  | 2 | 2
Member | Simpply (Debug) | Simpply.Models | ChartModel | YAxisLabel.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ChartModel | YAxisLabel.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ChartModel | XAxisLabel.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ChartModel | XAxisLabel.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ChartModel | Width.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ChartModel | Width.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | WarehouseBalanceOnOrder.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | WarehouseBalanceOnOrder.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | WarehouseBalanceOnHand.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | WarehouseBalanceOnHand.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ChartSeries | Values.set(List<ChartValue>) : void | 95 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | ChartSeries | Values.get() : List<ChartValue> | 98 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | BreadcrumbModel | Value.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | FormInput | Value.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | Value.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ChartValue | Value.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | BreadcrumbModel | Value.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | FormInput | Value.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | Value.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ChartValue | Value.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | Type.set(GridCellType) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ChartModel | Type.set(ChartType) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | Type.get() : GridCellType | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ChartModel | Type.get() : ChartType | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | TotalItems.set(long) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | TotalItems.get() : long | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ChartModel | Title.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ChartModel | Title.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | TableId.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | TableId.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | tableCondensed.set(bool) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | tableCondensed.get() : bool | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | Table.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | Table.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | StepValue.set(int?) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | StepValue.get() : int? | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Controllers | ItemController | StandInItem(List<int>) : ActionResult | 83 | 1 |  | 4 | 2
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | SortDetailsDescending.set(bool) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | SortDetailsDescending.get() : bool | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | sortDescending.set(bool) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | sortDescending.get() : bool | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | sortColumn.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | sortColumn.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ShownColumnsList.set(List<SelectListItem>) : void | 95 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ShownColumnsList.get() : List<SelectListItem> | 98 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ShownColumnsDefault.set(List<SelectListItem>) : void | 95 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ShownColumnsDefault.get() : List<SelectListItem> | 98 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ShownColumns.set(List<string>) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ShownColumns.get() : List<string> | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | ShipWeek.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | ShipWeek.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | BreadcrumbTrailModel | SetToDefault() : void | 69 | 1 |  | 3 | 4
Member | Simpply (Debug) | Simpply.Models | ChartModel | Series.set(List<ChartSeries>) : void | 95 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | ChartModel | Series.get() : List<ChartSeries> | 98 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Controllers | SeasonController | SeasonController(ISeasonProvider, IColumnPreferenceProvider) | 81 | 1 |  | 3 | 3
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | SalesHistoryChart.set(ChartModel) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | SalesHistoryChart.get() : ChartModel | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | Rows.set(List<GridRowModel>) : void | 95 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | Rows.get() : List<GridRowModel> | 98 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply | RouteConfig | RouteConfig() | 100 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Controllers | BaseController | Root() : ActionResult | 86 | 1 |  | 2 | 2
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | ReplenishmentLevel.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | ReplenishmentLevel.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | ReplenishmentDescription.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | ReplenishmentDescription.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply | RouteConfig | RegisterRoutes(RouteCollection) : void | 82 | 1 |  | 3 | 2
Member | Simpply (Debug) | Simpply | FilterConfig | RegisterGlobalFilters(GlobalFilterCollection) : void | 94 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.App_Start | AutofacConfig | RegisterComponents() : void | 70 | 1 |  | 10 | 5
Member | Simpply (Debug) | Simpply | BundleConfig | RegisterBundles(BundleCollection) : void | 64 | 1 |  | 4 | 6
Member | Simpply (Debug) | Simpply | AuthConfig | RegisterAuth() : void | 100 | 1 |  | 0 | 0
Member | Simpply (Debug) | Simpply | WebApiConfig | Register(HttpConfiguration) : void | 89 | 1 |  | 4 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | PreviousId.set(long) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | PreviousId.get() : long | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | planogramId.set(int?) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | planogramId.get() : int? | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Controllers | PlanogramController | PlanogramController(IPlanogramProvider, IColumnPreferenceProvider) | 81 | 1 |  | 3 | 3
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | PickWeek.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | PickWeek.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | NumberOfTotal.set(long) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | NumberOfTotal.get() : long | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | NextId.set(long) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | NextId.get() : long | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ChartSeries | Name.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | Column | Name.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | FormInput | Name.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | Name.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ChartSeries | Name.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | Column | Name.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | FormInput | Name.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | Name.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply | MvcApplication | MvcApplication() | 100 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | ModelRow.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | ModelRow.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | ModelName.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | ModelName.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | ModelAttribute.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | ModelAttribute.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | MinValue.set(int?) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | MinValue.get() : int? | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | MaxValue.set(int?) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | MaxValue.get() : int? | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | LastModifiedDate.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | LastModifiedDate.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | LastModifiedBy.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | LastModifiedBy.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Controllers | BaseController | JsonActionResult(JsonReturnType, string, string, string, object) : ActionResult | 68 | 1 |  | 5 | 6
Member | Simpply (Debug) | Simpply.Models | FinalizeDistributionModel | ItemIds.set(List<int>) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | FinalizeDistributionModel | ItemIds.get() : List<int> | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | ItemFinalized.set(bool) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | ItemFinalized.get() : bool | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Controllers | ItemController | ItemController(IItemProvider, IColumnPreferenceProvider) | 77 | 1 |  | 4 | 4
Member | Simpply (Debug) | Simpply.Controllers | ItemController | ItemController() | 90 | 1 |  | 4 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | IsSortedDescending.set(bool) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | IsSortedDescending.get() : bool | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | IsSorted.set(bool) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | IsSorted.get() : bool | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridRowModel | IsHeader.set(bool) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridRowModel | IsHeader.get() : bool | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemExplorerModel | IsFilteredToPlanogram.set(bool) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemExplorerModel | IsFilteredToPlanogram.get() : bool | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | IndexOfStoreSegmentationColumn.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | IndexOfStoreSegmentationColumn.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | IndexOfShipDistributionColumn.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | IndexOfShipDistributionColumn.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | IndexOfAggregateSegmentationColumn.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | IndexOfAggregateSegmentationColumn.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | IndexOfAggregateDistributionColumn.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | IndexOfAggregateDistributionColumn.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | SeasonExplorerModel | InactiveSeasonURL.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | SeasonExplorerModel | InactiveSeasonURL.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models.POG | PlanogramExplorerModel | InactivePlanogramURL.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models.POG | PlanogramExplorerModel | InactivePlanogramURL.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ChartModel | Id.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | Id.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ChartModel | Id.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | Id.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | HiddenColumnsList.set(List<SelectListItem>) : void | 95 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | HiddenColumnsList.get() : List<SelectListItem> | 98 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | HiddenColumns.set(List<string>) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | HiddenColumns.get() : List<string> | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ChartModel | Height.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ChartModel | Height.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | Header.set(GridRowModel) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | Header.get() : GridRowModel | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | GridRowModel | GridRowModel() | 87 | 1 |  | 2 | 2
Member | Simpply (Debug) | Simpply.Models | GridModel | GridModel() | 72 | 1 |  | 3 | 5
Member | Simpply (Debug) | Simpply.Models | GridCellModel | GridCellModel() | 78 | 1 |  | 0 | 4
Member | Simpply (Debug) | Simpply.Models | ItemExplorerModel | Grid.set(GridModel) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | SeasonExplorerModel | Grid.set(GridModel) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models.POG | PlanogramExplorerModel | Grid.set(GridModel) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ItemExplorerModel | Grid.get() : GridModel | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | SeasonExplorerModel | Grid.get() : GridModel | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models.POG | PlanogramExplorerModel | Grid.get() : GridModel | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Helpers | WebHelper | GetControllerName(string) : string | 78 | 1 |  | 0 | 3
Member | Simpply (Debug) | Simpply.Helpers | WebHelper | GetControllerActionName(string) : string | 78 | 1 |  | 0 | 3
Member | Simpply (Debug) | Simpply.Models | GridModel | FormMethod.set(FormMethod) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | FormMethod.get() : FormMethod | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | FormInput | FormInput() | 100 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | FormId.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | FormId.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | FormHiddenInputs.set(List<FormInput>) : void | 95 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | FormHiddenInputs.get() : List<FormInput> | 98 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | FormController.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | FormController.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | FormAction.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | FormAction.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | FinalizeDistributionModel | FinalizeDistributionModel() | 87 | 1 |  | 1 | 2
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | FinalizedDistributionType.set(FinalizedDistributionType) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | FinalizedDistributionType.get() : FinalizedDistributionType | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply | FilterConfig | FilterConfig() | 100 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | FinalizeDistributionModel | DistributionType.set(DistributionType) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | FinalizeDistributionModel | DistributionType.get() : DistributionType | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | Distributions.set(GridModel) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | Distributions.get() : GridModel | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | Column | DisplayName.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | Column | DisplayName.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | CurrentlySortedDetailsColumn.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | CurrentlySortedDetailsColumn.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | CssClasses.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridRowModel | CssClasses.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | CssClasses.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridRowModel | CssClasses.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ControllerName.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ControllerName.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ControllerAction.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ControllerAction.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | ColumnPreferences.set(ColumnPreferenceModel) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ItemExplorerModel | ColumnPreferences.set(ColumnPreferenceModel) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | SeasonExplorerModel | ColumnPreferences.set(ColumnPreferenceModel) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models.POG | PlanogramExplorerModel | ColumnPreferences.set(ColumnPreferenceModel) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | ColumnPreferences.get() : ColumnPreferenceModel | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ItemExplorerModel | ColumnPreferences.get() : ColumnPreferenceModel | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | SeasonExplorerModel | ColumnPreferences.get() : ColumnPreferenceModel | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models.POG | PlanogramExplorerModel | ColumnPreferences.get() : ColumnPreferenceModel | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ColumnPreferenceModel() | 71 | 1 |  | 2 | 6
Member | Simpply (Debug) | Simpply.Models | Column | Column() | 100 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ChartValue | ChartValue() | 100 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ChartSeries | ChartSeries(string, int) | 80 | 1 |  | 2 | 3
Member | Simpply (Debug) | Simpply.Models | ChartSeries | ChartSeries() | 87 | 1 |  | 2 | 2
Member | Simpply (Debug) | Simpply.Models | ChartModel | ChartModel() | 74 | 1 |  | 2 | 5
Member | Simpply (Debug) | Simpply.Models | GridRowModel | Cells.set(List<GridCellModel>) : void | 95 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | GridRowModel | Cells.get() : List<GridCellModel> | 98 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | ChartValue | Category.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ChartValue | Category.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply | BundleConfig | BundleConfig() | 100 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | BreadcrumbTrailModel | BreadcrumbTrailModel() | 65 | 1 |  | 3 | 6
Member | Simpply (Debug) | Simpply.Models | BreadcrumbModel | BreadcrumbModel() | 100 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Controllers | BreadcrumbController | BreadcrumbController() | 100 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Controllers | BaseController | BaseController() | 100 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply | MvcApplication | Application_Start() : void | 69 | 1 |  | 11 | 7
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | Aggregate.set(GridModel) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | Aggregate.get() : GridModel | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | SeasonExplorerModel | ActiveOnly.set(bool) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models.POG | PlanogramExplorerModel | ActiveOnly.set(bool) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | SeasonExplorerModel | ActiveOnly.get() : bool | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models.POG | PlanogramExplorerModel | ActiveOnly.get() : bool | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | BreadcrumbModel | ActionUrl.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ChartModel | ActionUrl.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | ActionUrl.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridRowModel | ActionUrl.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | BreadcrumbModel | ActionUrl.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ChartModel | ActionUrl.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | ActionUrl.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridRowModel | ActionUrl.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Controllers | AccountController | AccountController(IColumnPreferenceProvider) | 87 | 1 |  | 2 | 2
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ItemProvider | GetDetails(long, string, bool?) : Item | 45 | 10 |  | 18 | 32
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ItemProvider | SaveMultiple(List<Distribution>) : void | 52 | 4 |  | 16 | 15
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ItemProvider | SaveDistribution(List<DistributionModel>, int, int, string) : void | 52 | 4 |  | 16 | 15
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ColumnPreferenceProvider | Save(List<ColumnPreference>) : void | 52 | 4 |  | 15 | 15
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | SeasonProvider | Get(bool, string, bool) : List<SeasonInfo> | 60 | 4 |  | 13 | 10
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | PlanogramProvider | Get(bool, int?, string, bool) : List<Planogram> | 60 | 4 |  | 13 | 10
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ItemProvider | FinalizeItems(List<int>, DistributionType, FinalizedDistributionType, int, int, string) : void | 46 | 4 |  | 15 | 30
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ItemProvider | GetSalesHistory(List<long>, int?, int?, int?, int?) : List<WeeklyPurchase> | 60 | 3 |  | 15 | 9
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | JobProvider | UpdateProgress(long, string, int) : void | 72 | 2 |  | 7 | 4
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | JobProvider | Insert(string) : long | 69 | 2 |  | 8 | 5
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ItemProvider | GetStandInItem(int) : string | 66 | 2 |  | 9 | 7
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | SeasonProvider | GetSeasonName(int) : string | 66 | 2 |  | 9 | 7
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ItemProvider | GetSalesHistoryForChart(long) : List<WeeklyPurchase> | 69 | 2 |  | 10 | 5
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | PlanogramProvider | GetPlanogramName(int) : string | 66 | 2 |  | 9 | 7
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ItemProvider | GetItemsDetails(long?, string, int?, string, bool?) : List<Item> | 69 | 2 |  | 10 | 5
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ItemProvider | GetItemName(int) : string | 66 | 2 |  | 9 | 7
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ItemProvider | GetIds() : List<long> | 69 | 2 |  | 9 | 5
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ColumnPreferenceProvider | Get(string, string, string) : List<ColumnPreference> | 66 | 2 |  | 10 | 7
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | JobProvider | Get(long) : Job | 69 | 2 |  | 9 | 5
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ItemProvider | Get(long?, string, int?, string, bool?) : List<Item> | 69 | 2 |  | 10 | 5
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IJobProvider | UpdateProgress(long, string, int) : void | 100 | 1 |  | 0 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | SeasonProvider | SeasonProvider() | 100 | 1 |  | 1 | 1
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IItemProvider | SaveMultiple(List<Distribution>) : void | 100 | 1 |  | 2 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IItemProvider | SaveDistribution(List<DistributionModel>, int, int, string) : void | 100 | 1 |  | 2 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IColumnPreferenceProvider | Save(List<ColumnPreference>) : void | 100 | 1 |  | 2 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | PlanogramProvider | PlanogramProvider() | 100 | 1 |  | 1 | 1
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access | AccessModule | Load(ContainerBuilder) : void | 67 | 1 |  | 14 | 5
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | JobProvider | JobProvider() | 100 | 1 |  | 1 | 1
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ItemProvider | ItemProvider() | 100 | 1 |  | 1 | 1
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IJobProvider | Insert(string) : long | 100 | 1 |  | 0 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IItemProvider | GetSalesHistoryForChart(long) : List<WeeklyPurchase> | 100 | 1 |  | 2 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IItemProvider | GetSalesHistory(List<long>, int?, int?, int?, int?) : List<WeeklyPurchase> | 100 | 1 |  | 3 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IItemProvider | GetItemsDetails(long?, string, int?, string, bool?) : List<Item> | 100 | 1 |  | 3 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IItemProvider | GetDetails(long, string, bool?) : Item | 100 | 1 |  | 2 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IColumnPreferenceProvider | Get(string, string, string) : List<ColumnPreference> | 100 | 1 |  | 2 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IJobProvider | Get(long) : Job | 100 | 1 |  | 1 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IItemProvider | Get(long?, string, int?, string, bool?) : List<Item> | 100 | 1 |  | 3 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | ISeasonProvider | Get(bool, string, bool) : List<SeasonInfo> | 100 | 1 |  | 2 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IPlanogramProvider | Get(bool, int?, string, bool) : List<Planogram> | 100 | 1 |  | 3 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IItemProvider | FinalizeItems(List<int>, DistributionType, FinalizedDistributionType, int, int, string) : void | 100 | 1 |  | 3 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | BaseProvider | connectionString.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | BaseProvider | connectionString.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ColumnPreferenceProvider | ColumnPreferenceProvider() | 100 | 1 |  | 1 | 1
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | BaseProvider | BaseProvider() | 83 | 1 |  | 3 | 2
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access | AccessModule | AccessModule() | 100 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Algorithms | PushAllAlgorithm | Execute(Item, BaseJobModel) : List<Distribution> | 44 | 12 |  | 14 | 32
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | JobInvoker | ScheduleJob(BaseJob) : JobResponse | 41 | 10 |  | 11 | 45
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | JobInvoker | ValidateNoConflict(BaseJob) : bool | 52 | 9 |  | 7 | 20
Member | Simpply.Engine (Debug) | Simpply.Engine.Algorithms | SellthroughAlgorithm | Execute(Item, BaseJobModel) : List<Distribution> | 47 | 8 |  | 12 | 27
Member | Simpply.Engine (Debug) | Simpply.Engine.Algorithms | SetupAlgorithm | Execute(Item, BaseJobModel) : List<Distribution> | 49 | 8 |  | 16 | 21
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunSellthroughJob | ValidateParameters() : bool | 56 | 7 |  | 4 | 15
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunSetupJob | ValidateParameters() : bool | 57 | 7 |  | 5 | 13
Member | Simpply.Engine (Debug) | Simpply.Engine.Algorithms | SetupAlgorithm | DistributeProductToSegment(Dictionary<long, Distribution>, Item, string, long, DateTime, string) : void | 51 | 7 |  | 11 | 20
Member | Simpply.Engine (Debug) | Simpply.Engine.Controllers | JobsController | Post(JobRequest) : object | 52 | 6 |  | 15 | 20
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunPushAllJob | ValidateParameters() : bool | 64 | 4 |  | 4 | 9
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | JobInvoker | GetInstance() : JobInvoker | 67 | 4 |  | 1 | 8
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | ParseWegmansData | Execute(long) : bool | 52 | 4 |  | 13 | 19
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunPushAllJob | Execute(long) : bool | 56 | 3 |  | 9 | 13
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunSellthroughJob | Execute(long) : bool | 51 | 3 |  | 13 | 18
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunSetupJob | Execute(long) : bool | 56 | 3 |  | 9 | 13
Member | Simpply.Engine (Debug) | Simpply.Engine.Algorithms | SellthroughAlgorithm | ComputeForecast(long, List<WeeklyPurchase>) : int | 68 | 3 |  | 4 | 6
Member | Simpply.Engine (Debug) | Simpply.Engine.Algorithms | BaseAlgorithm | ConvertWarehouseToStore(long, int, int) : long | 77 | 2 |  | 0 | 4
Member | Simpply.Engine (Debug) | Simpply.Engine.Algorithms | BaseAlgorithm | ConvertStoreToWarehouse(long, int, int) : long | 77 | 2 |  | 0 | 4
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | BaseJob | BaseJob(string, JobProvider) | 71 | 2 |  | 2 | 6
Member | Simpply.Engine (Debug) | Simpply.Engine | WebApiApplication | WebApiApplication() | 100 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine | WebApiApplication | WebApiApplication() | 100 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | BaseJob | ValidateParameters() : bool | 100 | 1 |  | 0 | 0
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | ParseWegmansData | ValidateParameters() : bool | 91 | 1 |  | 0 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | BaseJob | ValidateParameters() : bool | 100 | 1 |  | 0 | 0
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | ParseWegmansData | ValidateParameters() : bool | 91 | 1 |  | 0 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunPushAllJobModel | Username.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | Username.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | Username.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunPushAllJobModel | Username.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | Username.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | Username.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunPushAllJobModel | Username.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | Username.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | Username.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunPushAllJobModel | Username.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | Username.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | Username.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | BaseJob | UpdateJobStatus(long, string, int) : void | 92 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | BaseJob | UpdateJobStatus(long, string, int) : void | 92 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobResponse | Success.set(bool) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobResponse | Success.set(bool) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobResponse | Success.get() : bool | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobResponse | Success.get() : bool | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | SetupDistributionPercent.set(double) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | SetupDistributionPercent.set(double) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | SetupDistributionPercent.get() : double | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | SetupDistributionPercent.get() : double | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Algorithms | SetupAlgorithm | SetupAlgorithm() | 100 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Algorithms | SetupAlgorithm | SetupAlgorithm() | 100 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunPushAllJobModel | SellthroughPercentTrigger.set(double) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | SellthroughPercentTrigger.set(double) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunPushAllJobModel | SellthroughPercentTrigger.set(double) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | SellthroughPercentTrigger.set(double) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunPushAllJobModel | SellthroughPercentTrigger.get() : double | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | SellthroughPercentTrigger.get() : double | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunPushAllJobModel | SellthroughPercentTrigger.get() : double | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | SellthroughPercentTrigger.get() : double | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Algorithms | SellthroughAlgorithm | SellthroughAlgorithm() | 100 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Algorithms | SellthroughAlgorithm | SellthroughAlgorithm() | 100 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | SegmentCDistributionPercent.set(double) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | SegmentCDistributionPercent.set(double) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | SegmentCDistributionPercent.set(double) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | SegmentCDistributionPercent.set(double) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | SegmentCDistributionPercent.get() : double | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | SegmentCDistributionPercent.get() : double | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | SegmentCDistributionPercent.get() : double | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | SegmentCDistributionPercent.get() : double | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | SegmentBDistributionPercent.set(double) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | SegmentBDistributionPercent.set(double) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | SegmentBDistributionPercent.set(double) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | SegmentBDistributionPercent.set(double) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | SegmentBDistributionPercent.get() : double | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | SegmentBDistributionPercent.get() : double | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | SegmentBDistributionPercent.get() : double | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | SegmentBDistributionPercent.get() : double | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | SegmentationPercents.set(Dictionary<string, double>) : void | 95 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | SegmentationPercents.set(Dictionary<string, double>) : void | 95 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | SegmentationPercents.get() : Dictionary<string, double> | 98 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | SegmentationPercents.get() : Dictionary<string, double> | 98 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | SegmentADistributionPercent.set(double) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | SegmentADistributionPercent.set(double) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | SegmentADistributionPercent.set(double) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | SegmentADistributionPercent.set(double) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | SegmentADistributionPercent.get() : double | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | SegmentADistributionPercent.get() : double | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | SegmentADistributionPercent.get() : double | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | SegmentADistributionPercent.get() : double | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | RunSetupJobModel() | 100 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | RunSetupJobModel() | 100 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunSetupJob | RunSetupJob(string) | 79 | 1 |  | 4 | 3
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunSetupJob | RunSetupJob(string) | 79 | 1 |  | 4 | 3
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | RunSellthroughJobModel() | 100 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | RunSellthroughJobModel() | 100 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunSellthroughJob | RunSellthroughJob(string) | 79 | 1 |  | 4 | 3
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunSellthroughJob | RunSellthroughJob(string) | 79 | 1 |  | 4 | 3
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunPushAllJobModel | RunPushAllJobModel() | 100 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunPushAllJobModel | RunPushAllJobModel() | 100 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunPushAllJob | RunPushAllJob(string) | 79 | 1 |  | 4 | 3
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunPushAllJob | RunPushAllJob(string) | 79 | 1 |  | 4 | 3
Member | Simpply.Engine (Debug) | Simpply.Engine | RouteConfig | RouteConfig() | 100 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine | RouteConfig | RouteConfig() | 100 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine | RouteConfig | RegisterRoutes(RouteCollection) : void | 82 | 1 |  | 4 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine | RouteConfig | RegisterRoutes(RouteCollection) : void | 82 | 1 |  | 4 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine | FilterConfig | RegisterGlobalFilters(GlobalFilterCollection) : void | 94 | 1 |  | 2 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine | FilterConfig | RegisterGlobalFilters(GlobalFilterCollection) : void | 94 | 1 |  | 2 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine | BundleConfig | RegisterBundles(BundleCollection) : void | 100 | 1 |  | 1 | 0
Member | Simpply.Engine (Debug) | Simpply.Engine | BundleConfig | RegisterBundles(BundleCollection) : void | 100 | 1 |  | 1 | 0
Member | Simpply.Engine (Debug) | Simpply.Engine | WebApiConfig | Register(HttpConfiguration) : void | 75 | 1 |  | 9 | 3
Member | Simpply.Engine (Debug) | Simpply.Engine | WebApiConfig | Register(HttpConfiguration) : void | 75 | 1 |  | 9 | 3
Member | Simpply.Engine (Debug) | Simpply.Engine.Algorithms | PushAllAlgorithm | PushAllAlgorithm() | 100 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Algorithms | PushAllAlgorithm | PushAllAlgorithm() | 100 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | ParseWegmansData | ParseWegmansData(string) | 87 | 1 |  | 2 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | ParseWegmansData | ParseWegmansData(string) | 87 | 1 |  | 2 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | ParseWegmansData | ParseWegmansData() | 90 | 1 |  | 4 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | ParseWegmansData | ParseWegmansData() | 90 | 1 |  | 4 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobResponse | Message.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobResponse | Message.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobResponse | Message.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobResponse | Message.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Controllers | JobsController | JobsController() | 100 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Controllers | JobsController | JobsController() | 90 | 1 |  | 4 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Controllers | JobsController | JobsController() | 100 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Controllers | JobsController | JobsController() | 90 | 1 |  | 4 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobResponse | JobResponse(bool, int, string, long) | 74 | 1 |  | 0 | 5
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobResponse | JobResponse(bool, int, string, long) | 74 | 1 |  | 0 | 5
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobRequest | JobRequest() | 82 | 1 |  | 0 | 3
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobRequest | JobRequest() | 82 | 1 |  | 0 | 3
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | JobInvoker | JobInvoker() | 76 | 1 |  | 5 | 4
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | JobInvoker | JobInvoker() | 77 | 1 |  | 4 | 3
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | JobInvoker | JobInvoker() | 76 | 1 |  | 5 | 4
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | JobInvoker | JobInvoker() | 77 | 1 |  | 4 | 3
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobResponse | JobId.set(long) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobResponse | JobId.set(long) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobResponse | JobId.get() : long | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobResponse | JobId.get() : long | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobRequest | Job.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobRequest | Job.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobRequest | Job.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobRequest | Job.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Controllers | HomeController | Index() : ActionResult | 89 | 1 |  | 2 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Controllers | HomeController | Index() : ActionResult | 89 | 1 |  | 2 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunPushAllJobModel | Ids.set(List<long>) : void | 95 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | Ids.set(List<long>) : void | 95 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | Ids.set(List<long>) : void | 95 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunPushAllJobModel | Ids.set(List<long>) : void | 95 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | Ids.set(List<long>) : void | 95 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | Ids.set(List<long>) : void | 95 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunPushAllJobModel | Ids.get() : List<long> | 98 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | Ids.get() : List<long> | 98 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | Ids.get() : List<long> | 98 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunPushAllJobModel | Ids.get() : List<long> | 98 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | Ids.get() : List<long> | 98 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSetupJobModel | Ids.get() : List<long> | 98 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Controllers | HomeController | HomeController() | 100 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Controllers | HomeController | HomeController() | 100 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | History.set(List<WeeklyPurchase>) : void | 95 | 1 |  | 2 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | History.set(List<WeeklyPurchase>) : void | 95 | 1 |  | 2 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | History.get() : List<WeeklyPurchase> | 98 | 1 |  | 2 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | RunSellthroughJobModel | History.get() : List<WeeklyPurchase> | 98 | 1 |  | 2 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | BaseJob | GetValidParameters() : string | 100 | 1 |  | 0 | 0
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | ParseWegmansData | GetValidParameters() : string | 91 | 1 |  | 0 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunPushAllJob | GetValidParameters() : string | 91 | 1 |  | 0 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunSellthroughJob | GetValidParameters() : string | 91 | 1 |  | 0 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunSetupJob | GetValidParameters() : string | 91 | 1 |  | 0 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | BaseJob | GetValidParameters() : string | 100 | 1 |  | 0 | 0
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | ParseWegmansData | GetValidParameters() : string | 91 | 1 |  | 0 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunPushAllJob | GetValidParameters() : string | 91 | 1 |  | 0 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunSellthroughJob | GetValidParameters() : string | 91 | 1 |  | 0 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunSetupJob | GetValidParameters() : string | 91 | 1 |  | 0 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | BaseJob | GetName() : string | 100 | 1 |  | 0 | 0
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | ParseWegmansData | GetName() : string | 91 | 1 |  | 0 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunPushAllJob | GetName() : string | 91 | 1 |  | 0 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunSellthroughJob | GetName() : string | 91 | 1 |  | 0 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunSetupJob | GetName() : string | 91 | 1 |  | 0 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | BaseJob | GetName() : string | 100 | 1 |  | 0 | 0
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | ParseWegmansData | GetName() : string | 91 | 1 |  | 0 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunPushAllJob | GetName() : string | 91 | 1 |  | 0 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunSellthroughJob | GetName() : string | 91 | 1 |  | 0 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunSetupJob | GetName() : string | 91 | 1 |  | 0 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | BaseJob | GetItemIdParameter() : List<long> | 100 | 1 |  | 1 | 0
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | ParseWegmansData | GetItemIdParameter() : List<long> | 89 | 1 |  | 1 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunPushAllJob | GetItemIdParameter() : List<long> | 87 | 1 |  | 2 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunSellthroughJob | GetItemIdParameter() : List<long> | 87 | 1 |  | 2 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunSetupJob | GetItemIdParameter() : List<long> | 87 | 1 |  | 2 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | BaseJob | GetItemIdParameter() : List<long> | 100 | 1 |  | 1 | 0
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | ParseWegmansData | GetItemIdParameter() : List<long> | 89 | 1 |  | 1 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunPushAllJob | GetItemIdParameter() : List<long> | 87 | 1 |  | 2 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunSellthroughJob | GetItemIdParameter() : List<long> | 87 | 1 |  | 2 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunSetupJob | GetItemIdParameter() : List<long> | 87 | 1 |  | 2 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Controllers | JobsController | Get(long) : string | 79 | 1 |  | 3 | 3
Member | Simpply.Engine (Debug) | Simpply.Engine.Controllers | JobsController | Get(long) : string | 79 | 1 |  | 3 | 3
Member | Simpply.Engine (Debug) | Simpply.Engine | FilterConfig | FilterConfig() | 100 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine | FilterConfig | FilterConfig() | 100 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | BaseJob | Execute(long) : bool | 100 | 1 |  | 0 | 0
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | BaseJob | Execute(long) : bool | 100 | 1 |  | 0 | 0
Member | Simpply.Engine (Debug) | Simpply.Engine.Algorithms | BaseAlgorithm | Execute(Item, BaseJobModel) : List<Distribution> | 100 | 1 |  | 4 | 0
Member | Simpply.Engine (Debug) | Simpply.Engine.Algorithms | BaseAlgorithm | Execute(Item, BaseJobModel) : List<Distribution> | 100 | 1 |  | 4 | 0
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobResponse | ErrorCode.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobResponse | ErrorCode.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobResponse | ErrorCode.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobResponse | ErrorCode.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobRequest | Data.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobRequest | Data.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobRequest | Data.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobRequest | Data.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine | BundleConfig | BundleConfig() | 100 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine | BundleConfig | BundleConfig() | 100 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | BaseJob | BaseJob(string) | 94 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | BaseJob | BaseJob(string) | 94 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | BaseJob | BaseJob() | 80 | 1 |  | 1 | 3
Member | Simpply.Engine (Debug) | Simpply.Engine.Algorithms | BaseAlgorithm | BaseAlgorithm() | 100 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine | WebApiApplication | Application_Start() : void | 73 | 1 |  | 9 | 5
Member | Simpply.Global (Debug) | Simpply.Global | Constants.ViewPages | ViewPages() | 100 | 1 |  | 0 | 1
Member | Simpply.Global (Debug) | Simpply.Global | Constants.ControllerAction.Season | Season() | 100 | 1 |  | 0 | 1
Member | Simpply.Global (Debug) | Simpply.Global | Constants.ControllerAction.Planogram | Planogram() | 100 | 1 |  | 0 | 1
Member | Simpply.Global (Debug) | Simpply.Global | Constants.ViewPages.ItemDetails | ItemDetails() | 100 | 1 |  | 0 | 1
Member | Simpply.Global (Debug) | Simpply.Global | Constants.ControllerAction.Item | Item() | 100 | 1 |  | 0 | 1
Member | Simpply.Global (Debug) | Simpply.Global | Constants.ControllerAction | ControllerAction() | 100 | 1 |  | 0 | 1
Member | Simpply.Global (Debug) | Simpply.Global | Constants.Controller | Controller() | 100 | 1 |  | 0 | 1
Member | Simpply.Global (Debug) | Simpply.Global | Constants | Constants() | 100 | 1 |  | 0 | 1
Member | Simpply.Global (Debug) | Simpply.Global | Constants.ControllerAction.Account | Account() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ItemProviderTest | SaveDistribution() : void | 46 | 13 |  | 14 | 26
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | AccountControllerTest | SaveColumnPreferences() : void | 55 | 5 |  | 23 | 12
Member | Simpply.Tests (Debug) | Simpply.Tests.Jobs | RunSetupJobTest | ValidateParametersTest() : void | 57 | 3 |  | 6 | 15
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | ItemControllerTest | ItemExplorer() : void | 59 | 3 |  | 20 | 8
Member | Simpply.Tests (Debug) | Simpply.Tests.ViewModels | ItemModelsTest | ItemDetailModelHasCorrectAggregateGrid() : void | 60 | 3 |  | 11 | 10
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | ItemControllerTest | ItemDetail() : void | 65 | 3 |  | 17 | 5
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | PlanogramProviderTest | GetReturnsOnlyActivePlanograms() : void | 65 | 3 |  | 9 | 7
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | PlanogramProviderTest | GetResultsAreInOrder() : void | 65 | 3 |  | 9 | 7
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ItemProviderTest | GetDetailsReturnsRelatedDistributions() : void | 68 | 3 |  | 10 | 5
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ItemProviderTest | GetDetailsReturnsRelatedSalesInformation() : void | 69 | 2 |  | 10 | 5
Member | Simpply.Tests (Debug) | Simpply.Tests.Algorithms | SetupAlgorithmTest | ExecuteSetupDistributionTest() : void | 62 | 2 |  | 9 | 8
Member | Simpply.Tests (Debug) | Simpply.Tests.Algorithms | PushAllAlgorithmTest | ExecutePushAllDistributionTest() : void | 62 | 2 |  | 9 | 8
Member | Simpply.Tests (Debug) | Simpply.Tests.Algorithms | PushAllAlgorithmTest | TestInit() : void | 47 | 1 |  | 8 | 33
Member | Simpply.Tests (Debug) | Simpply.Tests.Algorithms | SetupAlgorithmTest | TestInit() : void | 47 | 1 |  | 9 | 31
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | AccountControllerTest | TestInit() : void | 92 | 1 |  | 3 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | ItemControllerTest | TestInit() : void | 77 | 1 |  | 5 | 3
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | PlanogramControllerTest | TestInit() : void | 77 | 1 |  | 5 | 3
Member | Simpply.Tests (Debug) | Simpply.Tests.Jobs | RunSetupJobTest | TestInit() : void | 70 | 1 |  | 1 | 6
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | BaseProviderTest | TestInit() : void | 94 | 1 |  | 3 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ColumnPreferenceProviderTest | TestInit() : void | 94 | 1 |  | 3 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ItemProviderTest | TestInit() : void | 94 | 1 |  | 3 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | PlanogramProviderTest | TestInit() : void | 94 | 1 |  | 3 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.ViewModels | ItemModelsTest | TestInit() : void | 75 | 1 |  | 6 | 2
Member | Simpply.Tests (Debug) | Simpply.Tests.Algorithms | SetupAlgorithmTest | SetupAlgorithmTest() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | ItemControllerTest | SaveItemDistributionCallsProvidersCorrectly() : void | 72 | 1 |  | 7 | 3
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ColumnPreferenceProviderTest | Save() : void | 75 | 1 |  | 4 | 2
Member | Simpply.Tests (Debug) | Simpply.Tests.Jobs | RunSetupJobTest | RunSetupJobTest() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Algorithms | PushAllAlgorithmTest | PushAllAlgorithmTest() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | PlanogramProviderTest | PlanogramProviderTest() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | PlanogramControllerTest | PlanogramControllerTest() | 76 | 1 |  | 3 | 2
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ItemProviderTest | ItemProviderTest() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.ViewModels | ItemModelsTest | ItemModelsTest() | 66 | 1 |  | 3 | 4
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | ItemControllerTest | ItemExplorerFiltersToCorrectPlanogram() : void | 63 | 1 |  | 11 | 7
Member | Simpply.Tests (Debug) | Simpply.Tests.ViewModels | ItemModelsTest | ItemDetailModelHasCorrectItemName() : void | 75 | 1 |  | 5 | 3
Member | Simpply.Tests (Debug) | Simpply.Tests.ViewModels | ItemModelsTest | ItemDetailModelHasCorrectDistributionGrid() : void | 71 | 1 |  | 9 | 4
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | ItemControllerTest | ItemControllerTest() | 69 | 1 |  | 5 | 3
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | PlanogramControllerTest | IndexGetsAllPlanograms() : void | 66 | 1 |  | 8 | 6
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | PlanogramControllerTest | IndexGetsActivePlanogramsOnly() : void | 66 | 1 |  | 8 | 6
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | PlanogramProviderTest | GetResultIsNotNull() : void | 69 | 1 |  | 7 | 6
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ItemProviderTest | GetItems() : void | 71 | 1 |  | 7 | 5
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ItemProviderTest | GetDetailsReturnsRelatedStores() : void | 73 | 1 |  | 7 | 4
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ItemProviderTest | GetDetailsReturnsANonNullItem() : void | 74 | 1 |  | 5 | 4
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | BreadcrumbControllerTest | GetBreadcrumbsTest() : void | 100 | 1 |  | 1 | 0
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ColumnPreferenceProviderTest | Get() : void | 82 | 1 |  | 6 | 2
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ColumnPreferenceProviderTest | ColumnPreferenceProviderTest() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | BreadcrumbControllerTest | BreadcrumbControllerTest() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | BaseProviderTest | BaseProviderTest() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | AccountControllerTest | AccountControllerTest() | 100 | 1 |  | 0 | 1
Member | Simpply.Util (Debug) | Simpply.Util.Extensions | CollectionExtensions | IsEmpty<T>(this ICollection<T>) : bool | 84 | 2 |  | 2 | 2
Member | Simpply.Util (Debug) | Simpply.Util.Extensions | StringExtensions | IsNullOrWhiteSpace(this string) : bool | 87 | 1 |  | 1 | 2