## Sheet1
ID | Title | Status | Category | Description | Mitigation Approach | Probability | Loss (Weeks) | Exposure | First Indicator | Status (timestamp - action taken)
1 | Catastrophic Repository Failure |  | Act of God | Everything is just gone | Each developer has a local copy of each branch of the code. Even if the remote repository is destroyed, we can create another with one of the developer's local copies. | 0.001 | 20 | 0.02 | Everything is just gone | 02152015 - updated the mitigation approach to reflect how we will handle the situation, should it arise.
2 | Front-end views take longer to develop due to learning curve |  | Team | None of the team members have professed a strength in front-end development. As a result, extra time will need to be dedicated to learning | Research and practice front-end development prior to development of the product. Acknowledge the fact that it will take longer to do the front-end development by building into the schedule. | 1 | 2 | 2 | N/A | 02162015 - Everyone is up and running with developing views in our application at this point. No action necessary
3 | Architecture does not correctly address extensibility. |  | Architecture / Design | Team discovers that it is difficult for developers to customize and extend the solution in some area (Adding functionality to the engine, more views, more vendors) | Focus on modularity, extensibility, and creating a separation of concerns while designing the architecture. | 0.2 | 5 | 1 | It becomes hard to extend functionality while developing a feature.
4 | Requirement change late into an iteration | Safe | Process / Project | The customer changes a requirement late into an iteration, after it has already been designed and implemented for | Communicate with the sponsor at set intervals during the iteration. Make sure to evaluate whether a changed/additional requirement can be handled in the current iteration before committing to it. | 0.2 | 2 | 0.4 | N/A | 02162015 - Iterations are two weeks now. Plenty of time to react in the next iteration if requirements change near the end of an iteration. No further action necessary unless we move from 2 week sprints to longer ones.
5 | Team member gets burned out from assuming an unfair workload multiple sprints in a row |  | Team | When a member is the only expert in an area that requires more work than expected, there is a potential for the member to be assigned an unfair load multiple sprints in a row. | Engage in pair programming regularly to make multiple people experts in a given area. In this way, we can split the work load more evenly. |  |  | 0 |  | 02162015 - Tasks are assigned by the amount of effort put into the last sprint. People who finish their assigned tasks for the sprint early are expected to help others who have larger work loads (unless that person had a rather large work load and just happened to front-load their efforts).
6 | Two team members haven't taken Requirements and Architecture yet. | No longer a risk | Team | Two of the team members are currently taking Requirements and Architecture; therefore, the requirements gathering and architecture phases may be more difficult. | Consult with the team members who have already taken requirements and architecture. Do additional research on the subjects. | 1 | 0.5 | 0.5 | N/A
7 | Integration issues |  | Implementation | Code/ subsystem won't link up smoothly | Integrate small peices of the software constantly instead of trying to intergate large parts late in the process | 0.6 | 1.5 | 0.9 |  | 02162015 - Team spends time during design integration meetings specifically to discuss how components which interact will hook up to each other. Integration testing will be done by the team the Tuesday before the customer demo. Team members also keep in constant daily contact in the event that they having trouble integrating their individual components.
8 | Estimates are inaccurate | danger | Team | Team fails to estimate how long will tasks will take | 1- Breakdown tasks into small task that are easier to estimate. ; 2- Team member shall avoid take any work they can't deliver. | 0.3 | 0 | 0 |  | 03032015 - The only loss here is report with the customer as the work will have had to be done regardless of poor estimation.
9 | Communication overhead |  | Team/Stakeholders | Spending a high percentage of our time engaging stakeholders on project issues and change requests may cause our work to fall behind. | Timeboxing our communication will help us to avoid spending too much time in any one specific area during meetings. | 0.3 | 2 | 0.6 |  | 02162015 - Two week sprints and better timeboxing has reduced the amount of time wasted in meetings.
10 | Lack of formal requirements document causes wrong product to be built |  | Process/Project | The team has decided against putting together a formal "SRS" document, this may result in us building the wrong product as we do not have a formal requirements document | Formally define high-level features as well as use-cases. Meet with the customer regularly and have demos to facilitate feedback from the custom to ensure that the correct product is being built. | 0.4 | 2 | 0.8 |  | 02162015 - User stories and two week sprints allow us to adapt quickly if the product is not developed according to what is expected by the customer after each sprint.
11 | Lack of formal testing documention leading to late discovery of serious bug |  | Process/Project | The team has decided against putting together a formal testing document, this may result in discovering a bug quite some time after its creation, resulting in an expensive fix\ | Our team has elected to abide by some of the processes described by "Extreme Programming" including the writing of test cases before writing functions. This test-driven approach to development will aid us in discovering bugs before they are able to manifest themselves as something more serious. | 0.5 | 1 | 0.5
12 | NHibernate is much more difficult to setup than anticipated |  | Implementation | We are unsure of how difficult it will be to implement NHibernate. It may take a lot more effort than expected, causing us to fall behind. | Dedicating time to investigate tool in order to ensure setup costs are not too large | 0.5 | 2 | 1
13 | Dapper is much more difficult to use than anticipated |  | Implementation | We are unsure of how difficult it will be to implement Dapper. It may take a lot more effort than expected, causing us to fall behind. | Dedicating time to investigate tool in order to insure that usage/learning costs are not too large | 0.5 | 2 | 1
14 | Lack of data promised by customer begins blocking development tasks |  | Stakeholders | Our stakeholders have promised to provide us a database which has data we will use for the project. However, the customer seems uncertain about how exactly they will provide this data and what data they need to provide. This may begin blocking tasks that need the data if the customer does not deliver within a reasonable amount of time | During our Thursday meetings, we will ask the customer for status updates in order to hold them accountable. In the worst case, we will dedicate more time to mocking the data | 0.25 | 2 | 0.5
15 | Lack of hard-drive space on VM blocks development |  | Implementation | Our VM is short on space. If we wait too much longer to contact Kurt to get more space, then it may begin blocking development tasks, | Determine how much space we need and email Kurt before the end of iteration 1 | 0.75 | 1 | 0.75 |  | 02162015 - The team now has plenty of space on the VM since it was moved.
16 | Customer's responsibilities to us fall through cracks |  | Process/Project | The customer has several responsibilities to us and we currently do not log these responsibilities. So there is potential for these responsibilities to fall through the cracks | Take time to add work items for customer to TFS. Be more diligent about emailing customer (add work item to TFS) | 0.75 | 2 | 1.5
17 | Work gets backloaded until end of iteration |  | Implementation | Currently, our team has loose accountability mechanisms and no real way to say how much work should get done from one week to the next. This has the potential to create a situation where everyone procrastinates, or no one knows how much work to get done from one week to the next until it's the last week before delivery and hardly anything is done. | Implement a process to decide on how much work needs to get done from one meeting to the next. Hold team members accountable | 0.5 | 3 | 1.5 |  | 02162015 - Daily check-ins hold team members accountable and prevent work from being back-loaded until the end of the iteration.
18 | Slow progress leaves customer with unsatisfactory product |  | Implementation | In order to combat the common mistake of "overpromising" for an iteration, our team has promised less work than what we think we're capable of delivering with the promise of pulling in more stories/tasks when we finish early. If we are not diligent in completing our work as soon as possible and then pulling in extra work, we will end up delivering less than what we should. | Implement a process to decide on how much work needs to get done from one meeting to the next. Hold team members accountable | 0.5 | 4 | 2 |  | 02162015 - Assigning each team member to an individual user story allows us to divide and conquer, resulting in much faster product development. Pair programming is still done when a team member needs help or particularly complex areas of the system are encountered.
19 | Duplicated work under divide and conquer |  | Implementation | When tasks are created and split up, there is potential for team members to overlap on their work, resulting in wasted time and effort | To reduce the risk of doing duplicate work, the team should always make both the work required for tasks and the ownership of tasks explicit as the tasks are created. Members should also practice synchronizing their code with the repo before doing any work. | 0.25 | 0.5 | 0.125 | Conflicts upon pulling/checking in code; meeting reveals two members overlapped on work | 02162015 - Each person is assigned an individual user story. User stories do not overlap since they are broken down into individual elements prior to being pulled into a sprint (if necessary). If a team member needs help, they are able to assign specific work to another team member so that work is not duplicated.
20 | Massive unmanageable merge conflicts arise |  | Implementation | When we check in or merge a branch, there is a potential for a large amount of merge conflicts which may not be easy to resolve | There are two parts to mitigating this risk. The first is to make sure work is divided appropriately so that as few people as possible are working in the same files at the same time. The latter is to have all team members work on the same branch so that merge conflicts are resolved right away, rather than having a mass amount of merge conflicts occur when branches are merged together (if the team members were to each have an individual branch). | 0.4 | 0.143 | 0.0572 | Many conflicts arise when committing or merging
21 | Race conditions between jobs operating on same item |  | Implementation | If two jobs are operating on the same item at the same time, there may be a possibility of a race condition. | Queue jobs that manipulate the same data instead of having them work on it at the same time. | 0.3 | 0.5 | 0.15 |  | 02242015 - marked as a danger (yellow)
22 | Race conditions involving user interface when job is running |  | Implementation | Two people may kick off a job to run the same algorithm for an item at the same time. | Notify the user that there is already a job running the algorithm requested on the same data if this occurs. Ignore the job request or queue the job to run again. | 0.2 | 0.5 | 0.1
23 | Final product does not perform very well due to architectural/design decisions |  | Implementation | Designing the architecture and classes incorrectly may result in an application with poor performance. | When doing class level designs, emphasize performance. Perform regular design reviews prior to implemention. Perform code reviews with an eye for performance. | 0.1 | 1.5 | 0.15
24 | Dapper can't do complex mappings | Encountered, but safe now. | Implementation | Dapper is unable to do complex object mapping. This means we have to do this data to object mapping on the C# side. This is somewhat complex | We have already had to write the code to handle this scenario, and one of our members is now fairly strong with the concept and can replicate it where necessary. The solution has been well documented and other members should be able to reproduce the results now. | 1 | 0.5 | 0.5 |  | 02162015 - several team members have had to do complex mappings in Dapper at this point. As stated, it was encountered before, and now we are comfortable with doing complex mapping in Dapper.
25 | User story scope is not well-defined | Encountered | Requirements | Currently, the scope of our stories are not well-defined. This can result in us taking on more work than we can actually promise | During a planning session, we will examine user stories with a finer toothed comb to ensure that we aren't committing to anything too large. |  |  | 0
26 | Stored Procedures become extremely complex and difficult to modify |  | Implementation | We are currently writing raw SQL stored procedures, rather than using Dynamic SQL. This will result in complex, difficult to read, SQL | Ensure stored procedures are always well documented and reviewed in code reviews. | 1 | 0.5 | 0.5
27 | Short Sprints don't allow for enough communication with customer |  | Requirements | With two week sprints, it can be hard to get all that we need out of the customer in our one and only meeting with them before the end of sprint demo. This could lead to implementing a feature incorrectly or only partially. | Partially mitigated by the fact that sprints are so short that we can adapt in the next sprint. The other thing we will do as a team is schedule an online meeting with the customer early in the sprint if needed. | 0.6 | 1 | 0.6 |  | 02242015 - discussed communicating questions via email as soon as they come up with customer.
28 | Database design causes inefficient code or need to refactor | Encountered | Design | Database design is inefficient or is impossible to utilize in the manner expected resulting in a need for refactoring. | Take the hit and refactor when needed. We can't anticipate every single corner case that may come up. | 0.4 | 0.2 | 0.08 |  | 02242015 - added
29 | Poor User Experience |  | Design | We don’t have a guaranteed coherent user experience. More on the dev to create a good user experience. Lose uniformity | Have demo at end of sprint to see if end user is currently satisfied with overall user experience. Refactor during next iteration if they are unsatisfied | 0.33 | 0.25 | 0.0825 |  | 03032015 - added
30 | Lack customer data necessary to complete stories |  | Data | We currently lack season-to-date and week-to-date data that is necessary to complete certain user stories. If customer does not communicate with us effeciently, we will not be able to complete it before end of iteration | Begin communicating with customer now (3/3). Be prepared to have online meeting by conference call or in person this Thursday (3/5). |  |  | 0
31 | Testing schedule is tight |  | Implementation | Testing happen to start late most of the times due to delay in design, implementation and requirement change | Start testing at early stages of the iteration | 0.2 | 0.15 | 0.03
32 | Deployment happens too late | Encountered | Implementation | Tasks are not implemented and integrated until too late in the iteration, leading to a frenzied and possibly unstable deploy. | Complete implementation by the end of the day on the Sunday before the customer meeting. Deploy Monday morning and begin testing and fixing bugs from there. | 0.7 | 0.4 | 0.28 |  | 03122015 - added
33 | SSRS may be difficult to integrate | Encountered | Implementation | SSRS is the charting tool that the Wegmans team wants to use; however, there are a lot of unknowns around SSRS for us, which may result in wasted effort if it won't integrate well. | Seek out alternative charting tool options and then implement one of those as a backup. | 0.4 | 1 | 0.4 |  | 04012015 - added
34 | [7 empty] | 0
35 | [7 empty] | 0
36 | [7 empty] | 0
37 | [7 empty] | 0
38 | [7 empty] | 0
39 | [7 empty] | 0
40 | [7 empty] | 0
41 | [7 empty] | 0
42 | [7 empty] | 0
43 | [7 empty] | 0
44 | [7 empty] | 0
45 | [7 empty] | 0
46 | [7 empty] | 0
47 | [7 empty] | 0
48 | [7 empty] | 0
49 | [7 empty] | 0
50 | [7 empty] | 0
51 | [7 empty] | 0
52 | [7 empty] | 0
53 | [7 empty] | 0
54 | [7 empty] | 0
56 | [7 empty] | 0
57 | [7 empty] | 0
58 | [7 empty] | 0
59 | [7 empty] | 0