## Effort Tracking
ID | Work Item Type | Title | State | Assigned To | Original Estimate | Remaining Work | Completed Work | Closed Date | Iteration Path | Tags |  | Week4Iter2(12/04-12/11) | Week3Iter2(11/29-12/04) | Week2Iter2(11/21-11/28) | Week1Iter2(11/14-11/20) | Iteration 2 | Iteration 1 | Iteration 0 | All Time |  | Week4Iter2 | Week3Iter2 | Week2Iter2 | Week1Iter2 | Iteration 2 | Iteration 1 | Iteration 0
262 | Task | Investigate complex data mapping for Dapper | Closed | Curtis Burtner | 1 | 0 | 3 | 2014-12-16 18:22 | Simpply | Project Setup | Project: | 34.68330 | 27.88000 | 26.25000 | 48.5 | 137.3133 | 85.8003 | 169.87 | 420.6506 | Start: | >12/04/2014 | >11/28/2014 | >11/21/2014 | >11/14/2014 | >11/14/2014 | >10/14/2014
297 | Task | Finish Hooking Up To The Database | Closed | Curtis Burtner | 2 | 0 | 2 | 2014-12-16 18:22 | Simpply | Implementation | Product: | 64.00933 | 10.25000 | 24.91100 | 0.00000 | 99.17033333 | 32.5 |  | 100.1703333 | End: | <12/12/2014 | <12/04/2014 | <11/28/2014 | <11/21/2014 | <12/12/2014 | <11/14/2014 | <10/14/2014
292 | Task | Team Self-Assessment | Closed | Michael Yeaple | 2 | 0 | 3 | 2014-12-15 21:05 | Simpply | Academic Work Meeting | Total: | 99.94263333 | 38.13 | 51.161 | 48.5 | 237.7336333 | 121.3003 | 169.87 | 556.5709333
295 | Task | Team Self-Assessment | Closed | Mustafa Al-Salihi | 2 | 0 | 3 | 2014-12-15 21:05 | Simpply | Academic Work Meeting | Estimated Hours: | 104.05 | 24.15 | 43.5 | 41 | 212.7 | 108.497 | 158.62 | 498.317
294 | Task | Team Self-Assessment | Closed | Jeremy Shulman | 2 | 0 | 3 | 2014-12-15 21:04 | Simpply | Academic Work Meeting
293 | Task | Team Self-Assessment | Closed | Curtis Burtner | 2 | 0 | 3 | 2014-12-15 21:04 | Simpply | Academic Work Meeting | Curtis Burtner | 29.41 | 13.87 | 19.317 | 16 | 78.597 | 33.75 | 40.83 | 166.177
291 | Task | Implement Complex Mapping for ItemDetails Page | Closed | Curtis Burtner | 1 | 0 | 3 | 2014-12-13 14:20 | Simpply | Implementation | Michael Yeaple | 36.54263333 | 7.52 | 12.037 | 10 | 66.09963333 | 57.5503 | 55.83 | 188.1469333
288 | Task | Code Review With Wegmans | Closed | Curtis Burtner | 1.5 | 0 | 1.5 | 2014-12-13 14:19 | Simpply | Code/Design Review | Jeremy Shulman | 19.74 | 7.37 | 13.537 | 9.5 | 50.147 | 23.25 | 38.08 | 114.477
290 | Task | Refactor based on code review | Closed | Michael Yeaple | 0.75 | 0 | 1 | 2014-12-12 18:55 | Simpply | Refactoring | Mustafa Al-Salihi | 14.25 | 9.37 | 6.27 | 13 | 42.89 | 6.75 | 35.13 | 87.77
289 | Task | Code Review With Wegmans | Closed | Michael Yeaple | 1.5 | 0 | 1.5 | 2014-12-12 12:04 | Simpply | Code/Design Review
287 | Task | Mocked Data For Database Tables | Closed | Curtis Burtner | 0.5 | 0 | 0.5 | 2014-12-12 01:54 | Simpply | Implementation | TFS Source Query: http://simpply.se.rit.edu:8080/tfs/DefaultCollection/Simpply/_workitems#path=Shared+Queries%2FIndividual+Report+(WiP)&_a=query
286 | Task | Code Merge from Unstable to Stable | Closed | Michael Yeaple | 0.25 | 0 | 0.25 | 2014-12-12 00:23 | Simpply | Implementation
279 | Task | Pair Programming | Closed | Michael Yeaple | 2 | 1 | 2.917 | 2014-12-12 00:17 | Simpply | Implementation
130 | Task | Implement Web Role Design | Closed | Jeremy Shulman | 1.5 | 0 | 1 | 2014-12-11 23:16 | Simpply\Iteration 2 | Implementation
181 | Task | Implement Feature | Closed | Michael Yeaple | 1.5 | 0 | 17.536 | 2014-12-11 23:06 | Simpply\Iteration 2 | Implementation | Tags | Total | Curtis Butner | Jeremy Shulman | Michael Yeaple | Mustafa Al-Salihi
285 | Task | Code Review | Closed | Jeremy Shulman | 0.5 | 0 | 0.5 | 2014-12-11 21:11 | Simpply | Code/Design Review | Academic Work Effort | 16.4 | 5 | 4 | 5.9 | 1.5
284 | Task | Code Review | Closed | Michael Yeaple | 0.5 | 0 | 0.5 | 2014-12-11 21:11 | Simpply | Code/Design Review | Academic Work Meeting | 43.48 | 10.87 | 10.87 | 10.87 | 10.87
192 | Task | Feature Implementation | Closed | Mustafa Al-Salihi | 8 | 0 | 8 | 2014-12-11 19:53 | Simpply\Iteration 2 | Implementation | Bugs | 0 | 0 | 0 | 0 | 0
163 | Task | Design Distribution Algorithms | Closed | Jeremy Shulman | 5 | 0 | 1.5 | 2014-12-11 18:30 | Simpply\Iteration 2 | Design Effort | Code/Design Review | 11.75 | 4 | 2.5 | 5.25 | 0
133 | Task | Implement Engine Class Design | Closed | Jeremy Shulman | 8 | 0 | 5 | 2014-12-11 18:30 | Simpply\Iteration 2 | Implementation | Design Effort | 26 | 5 | 6 | 8 | 7
281 | Task | Customer Emails | Closed | Curtis Burtner | 0.5 | 0 | 0.5 | 2014-12-11 16:18 | Simpply | Process/Project Management Effort | Design Meeting | 75.301 | 19.977 | 20.277 | 20.277 | 14.77
207 | Task | Review Distribution Algorithms | Closed | Mustafa Al-Salihi | 1.5 | 0 |  | 2014-12-11 16:05 | Simpply\Iteration 2 | Design Meeting | Implementation | 95.76993333 | 28.25 | 15.25 | 41.26993333 | 11
206 | Task | Review Distribution Algorithms | Closed | Jeremy Shulman | 1.5 | 0 | 0.66 | 2014-12-11 16:05 | Simpply\Iteration 2 | Design Meeting | Planning Meeting | 40.75 | 11.25 | 12.25 | 11.5 | 5.75
205 | Task | Review Distribution Algorithms | Closed | Curtis Burtner | 1.5 | 0 | 0.33 | 2014-12-11 16:05 | Simpply\Iteration 2 | Design Meeting | Process/Project Management Effort | 80.25 | 42 | 13.75 | 13.25 | 11.25
280 | Task | Added Dapper Examples Using Stored Procedures. Also Added New Connection String | Closed | Curtis Burtner | 2 | 0 | 6 | 2014-12-11 16:04 | Simpply | Implementation | Process/Project Management Meeting | 18.57 | 6.08 | 3.58 | 6.08 | 2.83
164 | Task | Design Distribution Algorithms | Closed | Mustafa Al-Salihi | 5 | 0 | 3 | 2014-12-11 16:04 | Simpply\Iteration 2 | Design Effort | Project Setup | 44 | 8.5 | 2 | 32.5 | 1
143 | Task | Review Distribution Algorithms | Closed | Michael Yeaple | 1.5 | 0 | 0.66 | 2014-12-11 16:04 | Simpply\Iteration 2 | Design Meeting | Progress Meeting | 17.75 | 4.75 | 4.75 | 4.75 | 3.5
162 | Task | Design Distribution Algorithms | Closed | Curtis Burtner | 5 | 0 |  | 2014-12-11 15:11 | Simpply\Iteration 2 | Design Effort | Refactoring | 8.75 | 2.5 | 1.25 | 5 | 0
248 | Task | Implement connection string so that it changes with mode project is run in | Closed | Curtis Burtner | 0.75 | 0 | 0.75 | 2014-12-11 14:55 | Simpply\Iteration 2 | Implementation | Requirements Effort | 11.55 | 1.25 | 1.25 | 7.75 | 1.3
85 | Task | Use Autofac in code | Closed | Curtis Burtner | 1 | 1 | 0 | 2014-12-11 14:53 | Simpply\Iteration 1 | Implementation | Requirements Meeting | 60.75 | 16.25 | 16.75 | 15.75 | 12
106 | Task | NUnit Mock | Closed | Mustafa Al-Salihi |  |  |  | 2014-12-11 14:53 | Simpply\Iteration 1 | Project Setup | Testing Effort | 4 | 0 | 0 | 0 | 4
278 | Task | Make updates to SQL Creation | Closed | Michael Yeaple | 0.25 | 0 | 0.5 | 2014-12-11 14:39 | Simpply | Implementation
142 | Task | Design Distribution Algorithms | Closed | Michael Yeaple | 5 | 0 | 1 | 2014-12-11 11:04 | Simpply\Iteration 2 | Design Effort | Total: | 551.0709333 | 165.677 | 114.477 | 188.1469333 | 82.77
204 | Task | Implement Feature | Closed | Curtis Burtner | 2 | 0 | 8 | 2014-12-10 05:38 | Simpply\Iteration 2 | Implementation | All Tasks: | 556.5709333
277 | Task | Fix target framework of engine | Closed | Jeremy Shulman | 1 | 0 | 1 | 2014-12-10 04:44 | Simpply | Implementation
276 | Task | Fix AccountController SaveColumnPreferences Unit Test | Closed | Michael Yeaple | 0.25 | 0 | 0.25 | 2014-12-10 00:48 | Simpply | Implementation | Meeting Hours: | 256.601
275 | Task | Email Team | Closed | Michael Yeaple | 0.3 | 0 | 0.3 | 2014-12-10 00:35 | Simpply | Implementation
137 | Task | Implement Database | Closed | Michael Yeaple | 1.5 | 0 | 1.5833 | 2014-12-10 00:24 | Simpply\Iteration 2 | Implementation
274 | Task | 12/09 Customer Email | Closed | Curtis Burtner | 1 | 0 | 1 | 2014-12-09 22:21 | Simpply\Iteration 2 | Process/Project Management Effort
155 | Task | Comprehend Data | Closed | Mustafa Al-Salihi | 2 | 0 | 0 | 2014-12-09 21:31 | Simpply\Iteration 2 | Design Effort
273 | Task | 12/09 Meeting | Closed | Michael Yeaple | 2 | 0 | 0.5 | 2014-12-09 19:04 | Simpply | Design Meeting
272 | Task | 12/09 Meeting | Closed | Jeremy Shulman | 2 | 0 | 0.5 | 2014-12-09 19:04 | Simpply | Design Meeting
260 | Task | 12/09 Meeting | Closed | Curtis Burtner | 2 | 0 | 0.5 | 2014-12-09 19:02 | Simpply | Design Meeting
261 | Task | 12/09 Meeting | Closed | Mustafa Al-Salihi | 2 | 0 | 0 | 2014-12-09 19:02 | Simpply | Design Meeting
271 | Task | Code Review Jeremy's Engine and Michael's Providers | Closed | Michael Yeaple | 1 | 0 | 1 | 2014-12-09 18:56 | Simpply | Code/Design Review
270 | Task | Code Review Jeremy's Engine and Michael's Providers | Closed | Jeremy Shulman | 1 | 0 | 1 | 2014-12-09 18:55 | Simpply | Code/Design Review
269 | Task | Code Review Jeremy's Engine and Michael's Providers | Closed | Curtis Burtner | 1 | 0 | 1 | 2014-12-09 18:55 | Simpply | Code/Design Review
129 | Task | Design Web Role Class Interaction | Closed | Curtis Burtner | 1.25 | 0 | 1.5 | 2014-12-09 17:51 | Simpply\Iteration 2 | Design Effort
135 | Task | Review Web Role Design | Closed | Michael Yeaple | 0.75 | 0 | 1.08 | 2014-12-09 17:50 | Simpply\Iteration 2 | Design Meeting
158 | Task | Review Web Role Design | Closed | Mustafa Al-Salihi | 0.75 | 0 | 0.75 | 2014-12-09 17:50 | Simpply\Iteration 2 | Design Meeting
156 | Task | Review Web Role Design | Closed | Curtis Burtner | 0.75 | 0 | 1.08 | 2014-12-09 17:49 | Simpply\Iteration 2 | Design Meeting
157 | Task | Review Web Role Design | Closed | Jeremy Shulman | 0.75 | 0 | 1.08 | 2014-12-09 17:48 | Simpply\Iteration 2 | Design Meeting
187 | Task | Class Design | Closed | Mustafa Al-Salihi | 0.5 | 0 | 0.5 | 2014-12-09 17:32 | Simpply\Iteration 2 | Design Effort
191 | Task | Class Design Review | Closed | Mustafa Al-Salihi | 0.5 |  | 0.5 | 2014-12-09 17:31 | Simpply\Iteration 2 | Design Meeting
134 | Task | Design Database | Closed | Michael Yeaple | 2 | 0 | 2.5 | 2014-12-09 17:25 | Simpply\Iteration 2 | Design Meeting
151 | Task | Design Database | Closed | Mustafa Al-Salihi | 2 | 0 | 0 | 2014-12-09 17:25 | Simpply\Iteration 2 | Design Meeting
149 | Task | Design Database | Closed | Curtis Burtner | 2 | 0 | 2.5 | 2014-12-09 17:24 | Simpply\Iteration 2 | Design Meeting
150 | Task | Design Database | Closed | Jeremy Shulman | 2 | 0 | 2.5 | 2014-12-09 17:24 | Simpply\Iteration 2 | Design Meeting
118 | Task | 11/13 End of Iteration Customer Meeting | Closed | Curtis Burtner | 1.25 | 0 | 1.25 | 2014-12-09 16:58 | Simpply\Iteration 1 | Progress Meeting
250 | Task | Make Calendar to Track Due Dates | Closed | Michael Yeaple | 1.5 | 0 | 0.9 | 2014-12-09 10:24 | Simpply | Academic Work Effort
246 | Task | Implement Dependency Injection using AutoFac | Closed | Michael Yeaple | 3 | 2.766 | 4.2333 | 2014-12-07 17:18 | Simpply | Implementation
259 | Task | 12/05 Online Meeting With Mike | Closed | Jeremy Shulman | 1 | 0 | 1 | 2014-12-05 11:54 | Simpply | Requirements Meeting
258 | Task | 12/05 Online Meeting With Mike | Closed | Curtis Burtner | 1 | 0 | 1 | 2014-12-05 11:54 | Simpply | Requirements Meeting
257 | Task | Attend 12/02 Presentations (And Give Presentation | Closed | Mustafa Al-Salihi | 1.5 | 0 | 1.5 | 2014-12-04 20:15 | Simpply | Academic Work Effort
256 | Task | Attend 12/02 Presentations (And Give Presentation | Closed | Jeremy Shulman | 1.5 | 0 | 1.5 | 2014-12-04 20:15 | Simpply | Academic Work Effort
255 | Task | Attend 12/02 Presentations (And Give Presentation | Closed | Michael Yeaple | 1.5 | 0 | 1.5 | 2014-12-04 20:15 | Simpply | Academic Work Effort
254 | Task | Attend 12/02 Presentations (And Give Presentation | Closed | Curtis Burtner | 1.5 | 0 | 1.5 | 2014-12-04 20:15 | Simpply | Academic Work Effort
27 | Task | Quality requirements | Closed | Curtis Burtner |  |  |  | 2014-12-04 20:14 | Simpply\Iteration 1 | Requirements Effort
253 | Task | Attend 12/04 Presentations | Closed | Jeremy Shulman | 2.5 | 0 | 2.5 | 2014-12-04 20:11 | Simpply | Academic Work Effort
252 | Task | Attend 12/04 Presentations | Closed | Michael Yeaple | 2.5 | 0 | 2.5 | 2014-12-04 20:11 | Simpply | Academic Work Effort
251 | Task | Attend Presentations | Closed | Curtis Burtner | 2.5 | 0 | 2.5 | 2014-12-04 20:10 | Simpply | Academic Work Effort
140 | Task | Practice Presentation with Team | Closed | Jeremy Shulman | 2.5 | 0 | 5.37 | 2014-12-02 20:57 | Simpply | Academic Work Meeting
141 | Task | Practice Presentation with Team | Closed | Mustafa Al-Salihi | 2.5 | 0 | 5.37 | 2014-12-02 15:50 | Simpply | Academic Work Meeting
138 | Task | Practice Presentation with Team | Closed | Michael Yeaple | 2.5 | 0 | 5.37 | 2014-12-02 15:49 | Simpply | Academic Work Meeting
139 | Task | Practice Presentation with Team | Closed | Curtis Burtner | 2.5 | 0 | 5.37 | 2014-12-02 15:49 | Simpply | Academic Work Meeting
249 | Task | Added Week by Week Tag Hour Break Out | Closed | Curtis Burtner | 1.25 | 0 | 1.25 | 2014-12-01 19:10 | Simpply\Iteration 2 | Process/Project Management Effort
247 | Task | Generated Charts | Closed | Curtis Burtner | 0.5 | 0 | 1 | 2014-11-30 18:38 | Simpply | Academic Work Effort
235 | Task | Add Simpply.Global | Closed | Michael Yeaple | 0.15 | 0 | 0.15 | 2014-11-30 17:48 | Simpply | Implementation
245 | Task | Tagged Historical Data, Setup Historical Data Spreadsheet | Closed | Curtis Burtner | 1 | 0 | 2.5 | 2014-11-29 17:48 | Simpply | Process/Project Management Effort
244 | Task | Adjusted Effort Task Tracking Spreadsheet | Closed | Curtis Burtner | 0.25 | 0 | 1 | 2014-11-29 12:35 | Simpply | Process/Project Management Effort
243 | Task | Went through backlog and repathed old tasks to Simpply | Closed | Curtis Burtner | 0.5 | 0 | 0.75 | 2014-11-29 11:42 | Simpply | Process/Project Management Effort
241 | Task | Planning Meeting 11/28 | Closed | Curtis Burtner | 0.25 | 0 | 0.25 | 2014-11-28 13:00 | Simpply | Planning Meeting
242 | Task | Planning Meeting 11/28 | Closed | Mustafa Al-Salihi | 0.25 | 0 | 0.25 | 2014-11-28 13:00 | Simpply | Planning Meeting
240 | Task | Planning Meeting 11/28 | Closed | Jeremy Shulman | 0.25 | 0 | 0.25 | 2014-11-28 13:00 | Simpply | Planning Meeting
239 | Task | Planning Meeting 11/28 | Closed | Michael Yeaple | 0.25 | 0 | 0.25 | 2014-11-28 13:00 | Simpply | Planning Meeting
180 | Task | Review Class Design | Closed | Mustafa Al-Salihi | 0.5 | 0 | 0.5 | 2014-11-28 12:45 | Simpply\Iteration 2 | Design Meeting
179 | Task | Review Class Design | Closed | Jeremy Shulman | 0.5 | 0 | 0.5 | 2014-11-28 12:45 | Simpply\Iteration 2 | Design Meeting
178 | Task | Review Class Design | Closed | Curtis Burtner | 0.5 | 0 | 0.5 | 2014-11-28 12:44 | Simpply\Iteration 2 | Design Meeting
177 | Task | Review Class Design | Closed | Michael Yeaple | 0.5 | 0 | 0.5 | 2014-11-28 12:44 | Simpply\Iteration 2 | Design Meeting
136 | Task | Review Engine Class Design | Closed | Michael Yeaple | 1 | 0 | 0.75 | 2014-11-28 12:16 | Simpply\Iteration 2 | Design Meeting
160 | Task | Review Engine Class Design | Closed | Jeremy Shulman | 1 | 0 | 0.75 | 2014-11-28 12:16 | Simpply\Iteration 2 | Design Meeting
161 | Task | Review Engine Class Design | Closed | Mustafa Al-Salihi | 1 | 0 | 0.75 | 2014-11-28 12:15 | Simpply\Iteration 2 | Design Meeting
159 | Task | Review Engine Class Design | Closed | Curtis Burtner | 1 | 0 | 0.75 | 2014-11-28 12:15 | Simpply\Iteration 2 | Design Meeting | Tags |  |  | Wk3Iteration 2 | Wk2Iteration 2 | Wk1Iteration 2 | Iteration 2 | Iteration 1 | Iteration 0
186 | Task | Review User Experience | Closed | Mustafa Al-Salihi | 0.5 | 0 | 0.5 | 2014-11-28 11:30 | Simpply\Iteration 2 | Design Meeting | Academic Work Effort |  |  | 1 | 0 | 1 | 16.4 | 0 | 0
185 | Task | Review User Experience | Closed | Jeremy Shulman | 0.5 | 0 | 0.5 | 2014-11-28 11:30 | Simpply\Iteration 2 | Design Meeting | Academic Work Meeting |  |  | 21.48 | 0 | 10 | 31.48 | 0 | 0
184 | Task | Review User Experience | Closed | Curtis Burtner | 0.5 | 0 | 0.5 | 2014-11-28 11:29 | Simpply\Iteration 2 | Design Meeting | Bugs |  |  | 0 | 0 | 0 | 0 | 0 | 0
183 | Task | Review User Experience | Closed | Michael Yeaple | 0.5 | 0 | 0.5 | 2014-11-28 11:29 | Simpply\Iteration 2 | Design Meeting | Code/Design Review |  |  | 0 | 0 | 0 | 4 | 4.75 | 0
182 | Task | Design User Experience | Closed | Mustafa Al-Salihi | 1.5 | 0 | 2 | 2014-11-28 11:17 | Simpply\Iteration 2 | Design Effort | Design Effort |  |  | 2 | 11.75 | 0 | 21.25 | 4.75 | 0
238 | Task | Update Effort Task Tracking Spreadsheet | Closed | Curtis Burtner | 1 | 0 | 1 | 2014-11-27 01:00 | Simpply | Process/Project Management Effort | Design Meeting |  |  | 7 | 13.161 | 0 | 35.301 | 4 | 0
237 | Task | Reformatted Historical Task Data | Closed | Curtis Burtner | 1 | 0 | 1 | 2014-11-26 01:02 | Simpply | Process/Project Management Effort | Implementation |  |  | 0.15 | 0 | 0 | 54.30263333 | 32.8003 | 0
236 | Task | Email to customer | Closed | Curtis Burtner | 0.5 | 0 | 0.75 | 2014-11-26 00:20 | Simpply | Process/Project Management Effort | Planning Meeting |  |  | 1 | 9 | 13.25 | 23.25 | 17.5 | 0
232 | Task | Task Assignment Meeting | Closed | Jeremy Shulman | 0.5 | 0 | 0.75 | 2014-11-25 19:01 | Simpply | Planning Meeting | Process/Project Management Effort |  |  | 5.5 | 7 | 17.75 | 31.75 | 16 | 0
233 | Task | Task Assignment Meeting | Closed | Curtis Burtner | 0.5 | 0 | 0.75 | 2014-11-25 19:01 | Simpply | Planning Meeting | Process/Project Management Meeting |  |  | 0 | 0 | 0 | 0 | 4 | 0
234 | Task | Task Assignment Meeting | Closed | Mustafa Al-Salihi | 0.5 | 0 | 0.75 | 2014-11-25 19:01 | Simpply | Planning Meeting | Project Setup |  |  | 0 | 0 | 0 | 0 | 24.5 | 0
231 | Task | Task Assignment Meeting | Closed | Michael Yeaple | 0.5 | 0.25 | 0.75 | 2014-11-25 19:00 | Simpply | Planning Meeting | Progress Meeting |  |  | 0 | 1.25 | 2.5 | 5 | 3.75 | 0
153 | Task | Comprehend Data | Closed | Curtis Burtner | 2 | 0 | 1 | 2014-11-25 18:24 | Simpply\Iteration 2 | Design Effort | Refactoring |  |  | 0 | 0 | 0 | 0 | 7.75 | 0
190 | Task | Class Design Review | Closed | Jeremy Shulman | 0.5 | 0 | 0.75 | 2014-11-25 18:23 | Simpply\Iteration 2 | Design Meeting | Requirements Effort |  |  | 0 | 0 | 0 | 0 | 0 | 0
188 | Task | Class Design Review | Closed | Michael Yeaple | 0.5 | 0 | 0.75 | 2014-11-25 18:22 | Simpply\Iteration 2 | Design Meeting | Requirements Meeting |  |  | 0 | 9 | 0 | 11 | 0 | 0
189 | Task | Class Design Review | Closed | Curtis Burtner | 0.5 | 0 | 0.75 | 2014-11-25 18:22 | Simpply\Iteration 2 | Design Meeting | Testing Effort |  |  | 0 | 0 | 4 | 4 | 0 | 0
202 | Task | Class Design Review | Closed | Jeremy Shulman | 0.5 | 0 | 0.967 | 2014-11-25 17:16 | Simpply\Iteration 2 | Design Meeting
201 | Task | Class Design Review | Closed | Curtis Burtner | 0.5 | 0 | 0.967 | 2014-11-25 17:16 | Simpply\Iteration 2 | Design Meeting | Total: |  |  | 38.13 | 51.161 | 44.5 | 233.7336333 | 119.8003 | 0
200 | Task | Class Design Review | Closed | Michael Yeaple | 0.5 | 0 | 0.967 | 2014-11-25 17:15 | Simpply\Iteration 2 | Design Meeting
154 | Task | Comprehend Data | Closed | Jeremy Shulman | 2 | 0 | 1 | 2014-11-25 16:56 | Simpply\Iteration 2 | Design Effort
152 | Task | Comprehend Data | Closed | Michael Yeaple | 2 | 0 | 1 | 2014-11-25 16:55 | Simpply\Iteration 2 | Design Effort
87 | Task | Investigate Providing a "Real" Burndown | Closed | Curtis Burtner | 2 | 0.5 | 1.5 | 2014-11-25 09:38 | Simpply | Process/Project Management Effort
230 | Task | Email to Martinez | Closed | Curtis Burtner | 0.5 | 0 | 0.5 | 2014-11-25 00:36 | Simpply | Process/Project Management Effort
224 | Task | Email to Martinez about backdating in TFS | Closed | Curtis Burtner | 1 | 0 | 1 | 2014-11-24 23:12 | Simpply | Process/Project Management Effort
203 | Task | Class Design Review | Closed | Mustafa Al-Salihi | 0.5 | 0 | 0.55 | 2014-11-24 21:04 | Simpply\Iteration 2 | Design Meeting
194 | Task | User Experience Design | Closed | Jeremy Shulman | 1 | 0 | 0.5 | 2014-11-24 20:31 | Simpply\Iteration 2 | Design Effort
199 | Task | Class Design | Closed | Mustafa Al-Salihi | 0.5 | 0 | 1.5 | 2014-11-24 20:31 | Simpply\Iteration 2 | Design Effort
198 | Task | User Experience Design Review | Closed | Mustafa Al-Salihi | 0.5 | 0 | 0.67 | 2014-11-24 20:31 | Simpply\Iteration 2 | Design Meeting
175 | Task | Review User Experience Design | Closed | Mustafa Al-Salihi | 0.5 | 0 | 0.55 | 2014-11-24 20:30 | Simpply\Iteration 2 | Design Meeting
196 | Task | User Experience Design Review | Closed | Curtis Burtner | 0.5 | 0 | 0.7 | 2014-11-24 20:29 | Simpply\Iteration 2 | Design Meeting
195 | Task | User Experience Design Review | Closed | Michael Yeaple | 0.5 | 0 | 0.67 | 2014-11-24 20:29 | Simpply\Iteration 2 | Design Meeting
197 | Task | User Experience Design Review | Closed | Jeremy Shulman | 0.5 | 0 | 0.67 | 2014-11-24 20:29 | Simpply\Iteration 2 | Design Meeting
172 | Task | Review User Experience Design | Closed | Michael Yeaple | 0.5 | 0 | 0.55 | 2014-11-24 19:59 | Simpply\Iteration 2 | Design Meeting
174 | Task | Review User Experience Design | Closed | Jeremy Shulman | 0.5 | 0 | 0.55 | 2014-11-24 19:58 | Simpply\Iteration 2 | Design Meeting
173 | Task | Review User Experience Design | Closed | Curtis Burtner | 0.5 | 0 | 0.55 | 2014-11-24 19:58 | Simpply\Iteration 2 | Design Meeting
132 | Task | Engine Class Design | Closed | Jeremy Shulman | 2 | 0 | 2 | 2014-11-24 19:03 | Simpply\Iteration 2 | Design Effort
176 | Task | Class Design for Customize Item Explorer | Closed | Michael Yeaple | 2 | 0 | 2.25 | 2014-11-24 14:47 | Simpply\Iteration 2 | Design Effort
229 | Task | Reviewed and Updated risks | Closed | Curtis Burtner | 0.5 | 0 | 0.5 | 2014-11-24 10:31 | Simpply | Process/Project Management Effort
171 | Task | Design User Experience | Closed | Curtis Burtner | 1 | 0 | 2.5 | 2014-11-23 16:43 | Simpply\Iteration 2 | Design Effort
223 | Task | Planning Meeting 11/21 | Closed | Jeremy Shulman | 1 | 0 | 2 | 2014-11-21 20:31 | Simpply | Planning Meeting
222 | Task | Planning Meeting 11/21 | Closed | Curtis Burtner | 1 | 0 | 2 | 2014-11-21 20:31 | Simpply | Planning Meeting
221 | Task | Planning Meeting 11/21 | Closed | Michael Yeaple | 1 | 0 | 2 | 2014-11-21 20:31 | Simpply | Planning Meeting
146 | Task | Design Engine Architecture | Closed | Curtis Burtner | 0.75 | 0 | 0.85 | 2014-11-21 17:09 | Simpply\Iteration 2 | Design Meeting
131 | Task | Design Engine Architecture | Closed | Michael Yeaple | 0.75 | 0 | 0.85 | 2014-11-21 17:08 | Simpply\Iteration 2 | Design Meeting
147 | Task | Design Engine Architecture | Closed | Jeremy Shulman | 0.75 | 0 | 0.85 | 2014-11-21 17:08 | Simpply\Iteration 2 | Design Meeting
119 | Task | 11/13 End of Iteration Customer Meeting | Closed | Jeremy Shulman | 1.25 | 0 | 1.25 | 2014-11-21 16:22 | Simpply | Progress Meeting
228 | Task | On-site Wegmans Algorithms Meeting | Closed | Mustafa Al-Salihi | 2 | 0 | 2.25 | 2014-11-21 16:22 | Simpply | Requirements Meeting
227 | Task | On-site Wegmans Algorithms Meeting | Closed | Jeremy Shulman | 2 | 0 | 2.25 | 2014-11-21 16:21 | Simpply | Requirements Meeting
226 | Task | On-site Wegmans Algorithms Meeting | Closed | Curtis Burtner | 2 | 0 | 2.25 | 2014-11-21 16:21 | Simpply | Requirements Meeting
225 | Task | On-site Wegmans Algorithms Meeting | Closed | Michael Yeaple | 2 | 0 | 2.25 | 2014-11-21 16:21 | Simpply | Requirements Meeting
220 | Task | Email to Martinez | Closed | Curtis Burtner | 0.5 | 0 | 0.75 | 2014-11-21 00:08 | Simpply | Process/Project Management Effort
219 | Task | Design Document | Closed | Jeremy Shulman | 3 | 0 | 3 | 2014-11-20 23:47 | Simpply | Process/Project Management Effort
218 | Task | Investigate task back-dating | Closed | Curtis Burtner | 1 | 0 | 1 | 2014-11-20 23:18 | Simpply | Process/Project Management Effort
212 | Task | Presentation Meeting | Closed | Michael Yeaple | 1.75 | 0 | 2.5 | 2014-11-20 19:03 | Simpply | Academic Work Meeting
214 | Task | Presentation Meeting | Closed | Jeremy Shulman | 1.75 | 0 | 2.5 | 2014-11-20 19:03 | Simpply | Academic Work Meeting
215 | Task | Presentation Meeting | Closed | Mustafa Al-Salihi | 1.75 | 0 | 2.5 | 2014-11-20 19:03 | Simpply | Academic Work Meeting
213 | Task | Presentation Meeting | Closed | Curtis Burtner | 1.75 | 0 | 2.5 | 2014-11-20 19:03 | Simpply | Academic Work Meeting
104 | Task | 11/11 Meeting | Closed | Mustafa Al-Salihi | 1.25 | 0 | 1.25 | 2014-11-20 19:00 | Simpply | Process/Project Management Effort
170 | Task | 11/19 Meeting - Finish Story/Task Planning | Closed | Mustafa Al-Salihi | 1.5 | 0 | 1.5 | 2014-11-19 17:17 | Simpply | Planning Meeting
169 | Task | 11/19 Meeting - Finish Story/Task Planning | Closed | Curtis Burtner | 1.5 | 0 | 1.5 | 2014-11-19 17:17 | Simpply | Planning Meeting
168 | Task | 11/19 Meeting - Finish Story/Task Planning | Closed | Jeremy Shulman | 1.5 | 0 | 2 | 2014-11-19 17:17 | Simpply | Planning Meeting
167 | Task | 11/19 Meeting - Finish Story/Task Planning | Closed | Michael Yeaple | 1.5 | 0 | 1.5 | 2014-11-19 17:17 | Simpply | Planning Meeting
126 | Task | Planning Meeting 11/18 | Closed | Curtis Burtner | 1.25 | 0 | 1.5 | 2014-11-19 17:15 | Simpply | Planning Meeting
193 | Task | Rename tasks for consistency and Update Remaining field. | Closed | Michael Yeaple | 0.5 | 0 | 1 | 2014-11-19 17:09 | Simpply | Process/Project Management Effort
166 | Task | Adjusted task queries | Closed | Curtis Burtner | 0.5 | 0 | 0.5 | 2014-11-19 13:30 | Simpply | Process/Project Management Effort
144 | Task | Take care of task tagging/linking/duplication From 11/18 Meeting | Closed | Michael Yeaple | 0.5 | 0 | 1 | 2014-11-19 10:47 | Simpply | Process/Project Management Effort
17 | Task | Change Schedule | Closed | Mustafa Al-Salihi | 1 | 0 | 1 | 2014-11-19 10:27 | Simpply | Process/Project Management Effort
83 | Task | Create a test plan using TFS | Closed | Mustafa Al-Salihi | 4 | 0 | 4 | 2014-11-19 10:27 | Simpply | Testing Effort
120 | Task | 11/13 End of Iteration Customer Meeting | Closed | Mustafa Al-Salihi | 1.25 | 0 | 1.25 | 2014-11-19 10:26 | Simpply | Progress Meeting
145 | Task | Email to customer | Closed | Curtis Burtner | 0.5 | 0 | 0.75 | 2014-11-18 19:39 | Simpply | Process/Project Management Effort
127 | Task | Planning Meeting 11/18 | Closed | Jeremy Shulman | 1.25 | 0 | 2 | 2014-11-18 18:41 | Simpply | Planning Meeting
128 | Task | Planning Meeting 11/18 | Closed | Mustafa Al-Salihi | 1.25 | 0 | 1.5 | 2014-11-18 18:41 | Simpply | Planning Meeting
125 | Task | Planning Meeting 11/18 | Closed | Michael Yeaple | 1.25 | 0 | 1.75 | 2014-11-18 18:38 | Simpply | Planning Meeting
124 | Task | Investigate Interim Presentation | Closed | Michael Yeaple | 0.75 | 0 | 1 | 2014-11-17 18:41 | Simpply | Academic Work Effort
121 | Task | 11/13 End of Iteration Customer Meeting | Closed | Michael Yeaple | 1.25 | 0 | 1.25 | 2014-11-17 17:56 | Simpply | Progress Meeting
73 | Task | Set Up Individual Effort Reports | Closed | Curtis Burtner | 1.5 | 0 | 2 | 2014-11-16 17:28 | Simpply | Process/Project Management Effort
41 | Task | Manage Risks | Closed | Curtis Burtner | 6 | 0 | 6.25 | 2014-11-14 15:03 | Simpply | Process/Project Management Effort
117 | Task | Page Styling/Refactoring Meeting | Closed | Curtis Burtner | 2.5 | 0 | 2.5 | 2014-11-13 15:13 | Simpply | Refactoring
122 | Task | CSS Touch up with Michael | Closed | Jeremy Shulman | 1.25 | 0 | 1.25 | 2014-11-13 15:10 | Simpply | Refactoring
116 | Task | Page Styling/Refactoring Meeting | Closed | Michael Yeaple | 2.5 | 0 | 3.25 | 2014-11-13 15:04 | Simpply | Refactoring
101 | Task | 11/11 Meeting | Closed | Curtis Burtner | 1.25 | 0 | 1.25 | 2014-11-13 13:10 | Simpply | Process/Project Management Effort
35 | User Story | Sort Summary of All Items | Closed | Michael Yeaple |  |  |  | 2014-11-13 10:56 | Simpply\Iteration 1
114 | Task | Style Column Headers based on Sort | Closed | Michael Yeaple | 1 | 0 | 0.5 | 2014-11-12 13:30 | Simpply\Iteration 1 | Implementation
67 | Task | Implementation | Closed | Michael Yeaple | 1.5 | 0 | 1.75 | 2014-11-12 12:59 | Simpply\Iteration 1 | Implementation
66 | Task | Design Classes | Closed | Michael Yeaple | 0.75 | 0 | 0.75 | 2014-11-12 11:15 | Simpply\Iteration 1 | Design Effort
1 | User Story | View Basic Item Information | Closed | Jeremy Shulman |  |  |  | 2014-11-13 10:56 | Simpply\Iteration 1 | Implementation
115 | Task | Sales Information Logic | Closed | Jeremy Shulman | 3.5 | 0 | 3.5 | 2014-11-12 22:57 | Simpply\Iteration 1 | Implementation
33 | User Story | View Summary of All Items | Closed | Curtis Burtner |  |  |  | 2014-11-13 10:55 | Simpply\Iteration 1
105 | Task | Style Page | Closed | Curtis Burtner | 2 | 0 | 4.5 | 2014-11-13 03:13 | Simpply\Iteration 1 | Implementation
61 | Task | Style Page | Closed | Michael Yeaple | 2 | 0 | 0.25 | 2014-11-11 17:21 | Simpply\Iteration 1 | Implementation
58 | Task | Implement Design | Closed | Michael Yeaple | 4 | 0 | 6 | 2014-11-03 17:46 | Simpply\Iteration 1 | Implementation
57 | Task | Design Classes | Closed | Michael Yeaple | 1 | 0 | 1.25 | 2014-11-03 12:55 | Simpply\Iteration 1 | Design Effort
37 | User Story | Create Detailed Item Data View | Closed | Jeremy Shulman |  |  |  | 2014-11-13 10:55 | Simpply\Iteration 1 | Implementation
60 | Bug | ItemDetail Null Reference Error | Resolved | Jeremy Shulman |  |  |  |  | Simpply\Iteration 1 | Bugs
88 | Task | Fix Null Reference Error (60) | Closed | Jeremy Shulman | 1 | 0 | 0.75 | 2014-11-06 16:54 | Simpply\Iteration 1 | Implementation
80 | Task | Implementation w/mock data | Closed | Mustafa Al-Salihi | 5 |  | 3 | 2014-11-12 22:53 | Simpply\Iteration 1 | Implementation
50 | Task | Implementation w/mock data | Closed | Jeremy Shulman | 5 |  | 4 | 2014-11-12 22:50 | Simpply\Iteration 1 | Implementation
49 | Task | Wireframes/Mockups | Closed | Mustafa Al-Salihi | 1 | 1.3 | 1 | 2014-11-04 17:09 | Simpply\Iteration 1 | Design Effort;Requirements Effort
48 | Task | Class Diagram | Closed | Jeremy Shulman | 1 |  | 1 | 2014-11-04 17:09 | Simpply\Iteration 1 | Design Effort
38 | User Story | Create Item Summary View | Closed | Michael Yeaple |  |  |  | 2014-11-13 10:55 | Simpply\Iteration 1
62 | Task | Add Missing Placeholders | Closed | Michael Yeaple | 0.5 |  |  | 2014-11-03 23:42 | Simpply\Iteration 1 | Implementation
45 | Task | Implement View with Dummy Data (Item Summary View) | Closed | Michael Yeaple | 4 | 0 | 0.5 | 2014-11-03 16:46 | Simpply\Iteration 1 | Implementation
43 | Task | Design Classes (Item Summary View) | Closed | Michael Yeaple | 1 |  | 1.25 | 2014-10-28 14:07 | Simpply\Iteration 1 | Design Effort
44 | Task | Create Mockups (Item Summary View) | Closed | Michael Yeaple | 1 |  | 0.5 | 2014-10-28 14:07 | Simpply\Iteration 1 | Design Effort
47 | Task | Task Breakdown (Item Summary View) | Closed | Michael Yeaple | 1 | 0 | 1 | 2014-10-21 12:16 | Simpply\Iteration 1 | Process/Project Management Effort
102 | Task | 11/11 Meeting | Closed | Jeremy Shulman | 1.25 | 0 | 1.25 | 2014-11-12 22:50 | Simpply | Process/Project Management Effort
75 | Task | Fix ItemController Code for Failed Unit Tests | Closed | Michael Yeaple | 0.167 | 0.5 | 1.5503 | 2014-11-12 14:54 | Simpply | Implementation
113 | Task | Quick Review with Michael | Closed | Curtis Burtner | 1 | 0 | 1 | 2014-11-12 12:00 | Simpply | Code/Design Review
103 | Task | 11/11 Meeting | Closed | Michael Yeaple | 1.25 | 0 | 1.25 | 2014-11-11 18:06 | Simpply | Process/Project Management Effort
99 | Task | Email to Team | Closed | Curtis Burtner | 1 | 0 | 0.75 | 2014-11-11 15:18 | Simpply | Process/Project Management Effort
92 | Task | Setup FTP Server | Closed | Michael Yeaple | 0.5 | 0 | 1.5 | 2014-11-10 13:01 | Simpply | Project Setup
100 | Task | Setup FTP Server | Closed | Jeremy Shulman | 0.5 | 0 | 0.5 | 2014-11-10 13:01 | Simpply | Project Setup
91 | Task | Customer Progress Meeting | Closed | Jeremy Shulman | 1.25 | 0 | 1.25 | 2014-11-10 12:57 | Simpply | Progress Meeting
72 | Task | Team Meeting | Closed | Curtis Burtner | 1.25 | 0 | 2 | 2014-11-08 21:07 | Simpply | Process/Project Management Effort
98 | Task | Refactor Code Based on Code Review | Closed | Michael Yeaple | 0.33 | 0 | 0.75 | 2014-11-08 15:20 | Simpply | Refactoring
89 | Task | Customer Progress Meeting | Closed | Michael Yeaple | 1.25 | 0 | 1.25 | 2014-11-08 14:46 | Simpply | Progress Meeting
97 | Task | Post Code Review Notes | Closed | Michael Yeaple | 0.25 | 0 | 0.25 | 2014-11-08 14:44 | Simpply | Code/Design Review
95 | Task | Code Review | Closed | Michael Yeaple | 1 | 0 | 1 | 2014-11-08 14:43 | Simpply | Code/Design Review
96 | Task | Code Review | Closed | Jeremy Shulman | 1 | 0 | 1 | 2014-11-08 14:22 | Simpply | Code/Design Review
90 | Task | Customer Progress Meeting | Closed | Curtis Burtner | 1.25 | 0 | 1.25 | 2014-11-07 18:34 | Simpply | Progress Meeting
94 | Task | Create calendar notification for interim presentation | Closed | Curtis Burtner | 0.5 | 0 | 0.5 | 2014-11-07 18:33 | Simpply | Process/Project Management Effort
86 | Task | Use Dapper in code | Closed | Curtis Burtner | 1 | 0 | 3.5 | 2014-11-07 17:16 | Simpply | Implementation
54 | Task | Set Up Autofac | Closed | Curtis Burtner | 3 | 0 | 3 | 2014-11-07 10:21 | Simpply | Project Setup
78 | Task | Tag All Previous Work Items | Closed | Curtis Burtner | 1 | 0 | 1 | 2014-11-06 21:56 | Simpply | Process/Project Management Effort
93 | Task | Add All Tags | Closed | Curtis Burtner | 0.5 | 0 | 0.5 | 2014-11-06 21:05 | Simpply | Academic Work Effort;Academic Work Meeting;Design Effort;Design Meeting;Implementation;Process/Project Management Effort;Process/Project Management Meeting;Project Setup;Refactoring;Requirements Effort;Requirements Meeting;Testing Effort;Testing Meeting
81 | Task | Research Standards for CSS File Organization | Closed | Jeremy Shulman | 0.5 | 0 | 0.5 | 2014-11-06 01:22 | Simpply | Project Setup
71 | Task | Team Meeting | Closed | Jeremy Shulman | 1.25 |  | 2 | 2014-11-04 23:55 | Simpply | Process/Project Management Effort
55 | Task | Set Up Dapper | Closed | Curtis Burtner | 1.5 | 0 | 1.5 | 2014-11-04 23:15 | Simpply | Project Setup
82 | Task | Email Customer | Closed | Curtis Burtner | 0.75 | 0 | 0.75 | 2014-11-04 22:39 | Simpply | Process/Project Management Effort
70 | Task | Team Meeting | Closed | Michael Yeaple | 1.25 | 0 | 2 | 2014-11-04 18:53 | Simpply | Process/Project Management Effort
79 | Task | Clarify Action URL Generation in Code | Closed | Michael Yeaple | 0.5 | 0 | 0.5 | 2014-11-04 18:37 | Simpply | Implementation
77 | Task | Code Review With Michael | Closed | Curtis Burtner | 0.5 | 0 | 0.5 | 2014-11-04 15:27 | Simpply | Code/Design Review
68 | Task | Fix TFS Installation | Closed | Michael Yeaple | 3 |  | 3.5 | 2014-11-04 15:26 | Simpply | Project Setup
59 | Task | Review Code Changes with Team | Closed | Michael Yeaple | 1.5 | 0 | 1 | 2014-11-04 15:26 | Simpply | Code/Design Review
76 | Task | Work on AutoFac/Dapper | Closed | Michael Yeaple | 0.5 | 0 | 0.5 | 2014-11-04 15:25 | Simpply | Implementation
63 | Task | Determine How to Track Time More Efficiently | Closed | Michael Yeaple | 0.5 |  | 0.5 | 2014-11-03 23:44 | Simpply | Process/Project Management Effort
65 | Task | Add Risks | Closed | Michael Yeaple | 0.25 |  | 0.25 | 2014-11-03 22:12 | Simpply | Process/Project Management Effort
64 | Task | Set Up Branches | Closed | Michael Yeaple | 1 |  | 1 | 2014-11-03 21:18 | Simpply | Project Setup
53 | Task | Set Up Project Skeleton | Closed | Michael Yeaple | 3 |  | 3 | 2014-10-28 14:14 | Simpply | Project Setup
42 | Task | Research and Implement Template Layout | Closed | Michael Yeaple | 3 |  | 1 | 2014-10-28 08:13 | Simpply | Implementation
19 | Task | Request more hard-drive space | Closed | Curtis Burtner |  |  |  | 2014-10-27 10:25 | Simpply | Project Setup
46 | Task | Write Blurb About Why We Chose Data Layer Technology | Closed | Curtis Burtner | 0.5 | 0 | 1 | 2014-10-22 10:32 | Simpply | Process/Project Management Effort
23 | Task | Set Up VM | Closed | Michael Yeaple | 3 | 0 | 10 | 2014-10-21 12:12 | Simpply | Project Setup
40 | Task | Make sure we can commit code from TFS | Closed | Michael Yeaple | 1 | 0 | 0.5 | 2014-10-21 11:40 | Simpply | Process/Project Management Effort
18 | Task | Risk chart status column needs to be meaningful | Closed | Curtis Burtner |  |  |  | 2014-10-20 15:10 | Simpply | Process/Project Management Effort
|  | Kick-Off Meeting | Closed | Curtis Burtner | 1.25 |  | 1.25 | 2014-08-28 | Simpply | Requirements Meeting
|  | Kick-Off Meeting | Closed | Michael Yeaple | 1.25 |  | 1.25 | 2014-08-28 | Simpply | Requirements Meeting
|  | Kick-Off Meeting | Closed | Mustafa Al-Salihi | 1.25 |  | 1.25 | 2014-08-28 | Simpply | Requirements Meeting
|  | Kick-Off Meeting | Closed | Jeremy Shulman | 1.25 |  | 1.25 | 2014-08-28 | Simpply | Requirements Meeting
|  | Set Up JIRA | Closed | Michael Yeaple | 3 |  | 3 | 2014-09-05 | Simpply | Project Setup
|  | Emails to customer | Closed | Curtis Burtner | 1 |  | 1 | 2014-09-04 | Simpply | Process/Project Management Effort
|  | Searched how to build enterprise software | Closed | Mustafa Al-Salihi | 2 |  | 2 | 2014-09-04 | Simpply | Process/Project Management Effort
|  | Meeting | Closed | Curtis Burtner | 1.5 |  | 1.5 | 2014-09-04 | Simpply | Requirements Meeting
|  | Meeting | Closed | Michael Yeaple | 1.5 |  | 1.5 | 2014-09-04 | Simpply | Requirements Meeting
|  | Meeting | Closed | Jeremy Shulman | 1.5 |  | 1.5 | 2014-09-04 | Simpply | Requirements Meeting
|  | Meeting | Closed | Mustafa Al-Salihi | 1.5 |  | 1.5 | 2014-09-04 | Simpply | Requirements Meeting
|  | Meeting | Closed | Michael Yeaple | 2 |  | 2 | 2014-09-03 | Simpply | Requirements Meeting
|  | Meeting | Closed | Curtis Burtner | 2 |  | 2 | 2014-09-03 | Simpply | Requirements Meeting
|  | Meeting | Closed | Mustafa Al-Salihi | 2 |  | 2 | 2014-09-03 | Simpply | Requirements Meeting
|  | Meeting | Closed | Jeremy Shulman | 2 |  | 2 | 2014-09-03 | Simpply | Requirements Meeting
|  | Meeting | Closed | Michael Yeaple | 1.25 |  | 1.25 | 2014-09-02 | Simpply | Requirements Meeting
|  | Meeting | Closed | Curtis Burtner | 1.25 |  | 1.25 | 2014-09-02 | Simpply | Requirements Meeting
|  | Meeting | Closed | Mustafa Al-Salihi | 1.25 |  | 1.25 | 2014-09-02 | Simpply | Requirements Meeting
|  | Meeting | Closed | Jeremy Shulman | 1.25 |  | 1.25 | 2014-09-02 | Simpply | Requirements Meeting
|  | Project schedule | Closed | Mustafa Al-Salihi | 2 |  | 2 | 2014-09-13 | Simpply | Process/Project Management Effort
|  | Work on team website and time tracking sheet | Closed | Jeremy Shulman | 1.5 |  | 1.5 | 2014-09-13 | Simpply | Process/Project Management Effort
|  | Set Up & Fill Out Time Tracking | Closed | Michael Yeaple | 0.25 |  | 0.25 | 2014-09-13 | Simpply | Process/Project Management Effort
|  | Emails to customer | Closed | Curtis Burtner | 1 |  | 1 | 2014-09-11 | Simpply | Process/Project Management Effort
|  | Meeting | Closed | Curtis Burtner | 1.25 |  | 1.25 | 2014-09-11 | Simpply | Requirements Meeting
|  | Meeting | Closed | Michael Yeaple | 1.25 |  | 1.25 | 2014-09-11 | Simpply | Requirements Meeting
|  | Meeting | Closed | Jeremy Shulman | 1.25 |  | 1.25 | 2014-09-11 | Simpply | Requirements Meeting
|  | Meeting | Closed | Mustafa Al-Salihi | 1.25 |  | 1.25 | 2014-09-11 | Simpply | Requirements Meeting
|  | Setup project plan template | Closed | Mustafa Al-Salihi | 0.5 |  | 0.5 | 2014-09-10 | Simpply | Process/Project Management Effort
|  | Project Plan Sections | Closed | Jeremy Shulman | 2 |  | 2 | 2014-09-10 | Simpply | Process/Project Management Effort
|  | Project Plan Meeting | Closed | Jeremy Shulman | 1.5 |  | 1.5 | 2014-09-08 | Simpply | Process/Project Management Meeting
|  | Project Plan Meeting | Closed | Mustafa Al-Salihi | 1.5 |  | 1.5 | 2014-09-08 | Simpply | Process/Project Management Meeting
|  | Project Plan Meeting | Closed | Michael Yeaple | 1.5 |  | 1.5 | 2014-09-08 | Simpply | Process/Project Management Meeting
|  | Project Plan Meeting | Closed | Curtis Burtner | 1.5 |  | 1.5 | 2014-09-08 | Simpply | Process/Project Management Meeting
|  | User Stories & Use Cases | Closed | Michael Yeaple | 3.5 |  | 3.5 | 2014-09-08 | Simpply | Requirements Effort
|  | Project Plan Meeting | Closed | Jeremy Shulman | 1.33 |  | 1.33 | 2014-09-09 | Simpply | Process/Project Management Meeting
|  | Project Plan Meeting | Closed | Mustafa Al-Salihi | 1.33 |  | 1.33 | 2014-09-09 | Simpply | Process/Project Management Meeting
|  | Project Plan Meeting | Closed | Michael Yeaple | 1.33 |  | 1.33 | 2014-09-09 | Simpply | Process/Project Management Meeting
|  | Project Plan Meeting | Closed | Curtis Burtner | 1.33 |  | 1.33 | 2014-09-09 | Simpply | Process/Project Management Meeting
|  | Project Plan | Closed | Jeremy Shulman | 2 |  | 2 | 2014-09-09 | Simpply | Process/Project Management Effort
|  | Project Plan | Closed | Mustafa Al-Salihi | 2 |  | 2 | 2014-09-09 | Simpply | Process/Project Management Effort
|  | Project Plan | Closed | Michael Yeaple | 2 |  | 2 | 2014-09-09 | Simpply | Process/Project Management Effort
|  | Project Plan | Closed | Curtis Burtner | 2 |  | 2 | 2014-09-09 | Simpply | Process/Project Management Effort
|  | Project Plan Meeting | Closed | Jeremy Shulman | 1.5 |  | 1.5 | 2014-09-10 | Simpply | Process/Project Management Effort
|  | Project Plan Meeting | Closed | Mustafa Al-Salihi | 1.5 |  | 1.5 | 2014-09-10 | Simpply | Process/Project Management Effort
|  | Project Plan Meeting | Closed | Michael Yeaple | 1.5 |  | 1.5 | 2014-09-10 | Simpply | Process/Project Management Effort
|  | Project Plan Meeting | Closed | Curtis Burtner | 1.5 |  | 1.5 | 2014-09-10 | Simpply | Process/Project Management Effort
|  | Planning Next Meeting | Closed | Michael Yeaple | 0.5 |  | 0.5 | 2014-09-10 | Simpply | Process/Project Management Meeting
|  | Planning Next Meeting | Closed | Curtis Burtner | 0.5 |  | 0.5 | 2014-09-10 | Simpply | Process/Project Management Meeting
|  | Development Methodology Artifact (for website) | Closed | Curtis Burtner | 0.5 |  | 0.75 | 2014-09-21 | Simpply | Process/Project Management Meeting
|  | Development Methodology Artifact (for website) | Closed | Jeremy Shulman | 0.5 |  | 0.75 | 2014-09-21 | Simpply | Process/Project Management Meeting
|  | Development Methodology Artifact (for website) | Closed | Michael Yeaple | 0.5 |  | 0.75 | 2014-09-21 | Simpply | Process/Project Management Meeting
|  | Set Up TFS | Closed | Michael Yeaple | 0.5 |  | 1 | 2014-09-19 | Simpply | Project Setup
|  | Updating website | Closed | Jeremy Shulman |  |  | 0.5 | 2014-09-18 | Simpply | Process/Project Management Effort
|  | Email to Wegmans Team | Closed | Curtis Burtner | 0.5 |  | 0.75 | 2014-09-18 | Simpply | Process/Project Management Effort
|  | Created initial document to enter metrics | Closed | Curtis Burtner | 0.5 |  | 1 | 2014-09-17 | Simpply | Process/Project Management Effort
|  | Completed Initial Wireframes | Closed | Michael Yeaple | 1 |  | 1.25 | 2014-09-17 | Simpply | Requirements Effort
|  | Wireframe Meeting | Closed | Curtis Burtner | 0.5 |  | 0.5 | 2014-09-17 | Simpply | Requirements Meeting
|  | Wireframe Meeting | Closed | Jeremy Shulman | 1 |  | 1 | 2014-09-17 | Simpply | Requirements Meeting
|  | Wireframe Meeting | Closed | Michael Yeaple | 1 |  | 1 | 2014-09-17 | Simpply | Requirements Meeting
|  | Initial Wireframes | Closed | Michael Yeaple | 2 |  | 3 | 2014-09-17 | Simpply | Requirements Effort
|  | Import user stroies into the software | Closed | Mustafa Al-Salihi |  |  | 1 | 2014-09-17 | Simpply | Process/Project Management Effort
|  | User Stories Meeting | Closed | Jeremy Shulman | 1.25 |  | 1.25 | 2014-09-16 | Simpply | Requirements Meeting
|  | User Stories Meeting | Closed | Mustafa Al-Salihi | 1.25 |  | 1.25 | 2014-09-16 | Simpply | Requirements Meeting
|  | User Stories Meeting | Closed | Michael Yeaple | 1.25 |  | 1.25 | 2014-09-16 | Simpply | Requirements Meeting
|  | User Stories Meeting | Closed | Curtis Burtner | 1.25 |  | 1.25 | 2014-09-16 | Simpply | Requirements Meeting
|  | Initial Wireframes | Closed | Jeremy Shulman | 1.25 |  | 1.25 | 2014-09-15 | Simpply | Requirements Effort
|  | Initial Wireframes | Closed | Curtis Burtner | 1.25 |  | 1.25 | 2014-09-15 | Simpply | Requirements Effort
|  | Wireframes | Closed | Mustafa Al-Salihi | 1.3 |  | 1.3 | 2014-09-15 | Simpply | Requirements Effort
|  | VM Set Up | Closed | Michael Yeaple | 3 |  | 5 | 2014-09-27 | Simpply | Project Setup
|  | Customer Meeting | Closed | Curtis Burtner | 1.25 |  | 1.75 | 2014-09-25 | Simpply | Requirements Meeting
|  | Customer Meeting | Closed | Jeremy Shulman | 1.25 |  | 1.75 | 2014-09-25 | Simpply | Requirements Meeting
|  | Customer Meeting | Closed | Michael Yeaple | 1.25 |  | 1.75 | 2014-09-25 | Simpply | Requirements Meeting
|  | ORM Presentation Slides | Closed | Curtis Burtner | 1 |  | 1 | 2014-09-25 | Simpply | Process/Project Management Effort
|  | ORM Presentation Slides | Closed | Michael Yeaple | 1 |  | 1 | 2014-09-25 | Simpply | Process/Project Management Effort
|  | Emails to Customer | Closed | Curtis Burtner | 1 |  | 1 | 2014-09-25 | Simpply | Process/Project Management Effort
|  | Wireframe Revision/Planning for Customer Meeting | Closed | Curtis Burtner | 1 |  | 1 | 2014-09-24 | Simpply | Requirements Meeting
|  | Wireframe Revision/Planning for Customer Meeting | Closed | Jeremy Shulman | 1 |  | 1 | 2014-09-24 | Simpply | Requirements Meeting
|  | Wireframe Revision/Planning for Customer Meeting | Closed | Michael Yeaple | 1 |  | 1 | 2014-09-24 | Simpply | Requirements Meeting
|  | Environment Set Up Meeting | Closed | Jeremy Shulman | 1 |  | 1 | 2014-09-23 | Simpply | Project Setup
|  | Environment Set Up Meeting | Closed | Mustafa Al-Salihi | 1 |  | 1 | 2014-09-23 | Simpply | Project Setup
|  | Environment Set Up Meeting | Closed | Michael Yeaple | 1 |  | 1 | 2014-09-23 | Simpply | Project Setup
|  | Environment Set Up Meeting | Closed | Curtis Burtner | 1 |  | 1 | 2014-09-23 | Simpply | Project Setup
|  | Software Design Document Set Up/Update Project Plan | Closed | Michael Yeaple | 1 |  | 1 | 2014-09-22 | Simpply | Process/Project Management Effort
|  | Emails to Kurt | Closed | Curtis Burtner | 1 |  | 1 | 2014-09-22 | Simpply | Process/Project Management Effort
|  | Onsite meeting with customer. | Closed | Jeremy Shulman | 2 |  | 2 | 2014-10-03 | Simpply | Design Meeting
|  | Onsite meeting with customer. | Closed | Mustafa Al-Salihi | 2 |  | 2 | 2014-10-03 | Simpply | Design Meeting
|  | Onsite meeting with customer. | Closed | Michael Yeaple | 2 |  | 2 | 2014-10-03 | Simpply | Design Meeting
|  | Onsite meeting with customer. | Closed | Curtis Burtner | 2 |  | 2 | 2014-10-03 | Simpply | Design Meeting
|  | Team Meeting - User Stories in TFS; Architecture | Closed | Jeremy Shulman | 3 |  | 3 | 2014-10-02 | Simpply | Design Meeting
|  | Team Meeting - User Stories in TFS; Architecture | Closed | Mustafa Al-Salihi | 3 |  | 3 | 2014-10-02 | Simpply | Design Meeting
|  | Team Meeting - User Stories in TFS; Architecture | Closed | Michael Yeaple | 3 |  | 3 | 2014-10-02 | Simpply | Design Meeting
|  | Team Meeting - User Stories in TFS; Architecture | Closed | Curtis Burtner | 3 |  | 3 | 2014-10-02 | Simpply | Design Meeting
|  | TFS Setup - Project and Users | Closed | Michael Yeaple | 1 |  | 3 | 2014-09-30 | Simpply | Project Setup
|  | Team Meeting - Mind Map | Closed | Jeremy Shulman | 1.25 |  | 1.25 | 2014-09-30 | Simpply | Requirements Meeting
|  | Team Meeting - Mind Map | Closed | Mustafa Al-Salihi | 1.25 |  | 1.25 | 2014-09-30 | Simpply | Requirements Meeting
|  | Team Meeting - Mind Map | Closed | Michael Yeaple | 1.25 |  | 1.25 | 2014-09-30 | Simpply | Requirements Meeting
|  | Team Meeting - Mind Map | Closed | Curtis Burtner | 1.25 |  | 1.25 | 2014-09-30 | Simpply | Requirements Meeting
|  | EA Review of Architecture | Closed | Jeremy Shulman | 2 |  | 2 | 2014-10-10 | Simpply | Design Meeting
|  | EA Review of Architecture | Closed | Mustafa Al-Salihi | 2 |  | 2 | 2014-10-10 | Simpply | Design Meeting
|  | EA Review of Architecture | Closed | Michael Yeaple | 2 |  | 2 | 2014-10-10 | Simpply | Design Meeting
|  | EA Review of Architecture | Closed | Curtis Burtner | 2 |  | 2 | 2014-10-10 | Simpply | Design Meeting
|  | Customer Meeting; Update and Practice Presentation | Closed | Jeremy Shulman | 2 |  | 2.25 | 2014-10-09 | Simpply | Progress Meeting
|  | Customer Meeting; Update and Practice Presentation | Closed | Mustafa Al-Salihi | 2 |  | 2.25 | 2014-10-09 | Simpply | Progress Meeting
|  | Customer Meeting; Update and Practice Presentation | Closed | Michael Yeaple | 2 |  | 2.25 | 2014-10-09 | Simpply | Progress Meeting
|  | Customer Meeting; Update and Practice Presentation | Closed | Curtis Burtner | 2 |  | 2.25 | 2014-10-09 | Simpply | Progress Meeting
|  | Regular Tuesday meeting | Closed | Jeremy Shulman | 2 |  | 2 | 2014-10-07 | Simpply | Design Meeting
|  | Regular Tuesday meeting | Closed | Mustafa Al-Salihi | 2 |  | 2 | 2014-10-07 | Simpply | Design Meeting
|  | Regular Tuesday meeting | Closed | Michael Yeaple | 2 |  | 2 | 2014-10-07 | Simpply | Design Meeting
|  | Regular Tuesday meeting | Closed | Curtis Burtner | 2 |  | 2 | 2014-10-07 | Simpply | Design Meeting
|  | Customer Meeting - Sprint Planning | Closed | Jeremy Shulman | 1.25 |  | 1.75 | 2014-10-16 | Simpply | Planning Meeting
|  | Customer Meeting - Sprint Planning | Closed | Mustafa Al-Salihi | 1.25 |  | 1.75 | 2014-10-16 | Simpply | Planning Meeting
|  | Customer Meeting - Sprint Planning | Closed | Michael Yeaple | 1.25 |  | 1.75 | 2014-10-16 | Simpply | Planning Meeting
|  | Customer Meeting - Sprint Planning | Closed | Curtis Burtner | 1.25 |  | 1.75 | 2014-10-16 | Simpply | Planning Meeting
|  | User Story Meeting (Break down, Pointing) | Closed | Curtis Burtner | 2 |  | 3.5 | 2014-10-15 | Simpply | Planning Meeting
|  | User Story Meeting (Break down, Pointing) | Closed | Jeremy Shulman | 2 |  | 3.5 | 2014-10-15 | Simpply | Planning Meeting
|  | User Story Meeting (Break down, Pointing) | Closed | Michael Yeaple | 2 |  | 3.5 | 2014-10-15 | Simpply | Planning Meeting
|  | TFS Permissions Issues | Closed | Michael Yeaple | 0.5 |  | 0.5 | 2014-10-13 | Simpply | Project Setup
|  | Team Meeting - Finish Design for Sprint 1 | Closed | Jeremy Shulman | 1 |  | 1 | 2014-10-21 | Simpply\Iteration 1 | Design Meeting
|  | Team Meeting - Finish Design for Sprint 1 | Closed | Mustafa Al-Salihi | 1 |  | 1 | 2014-10-21 | Simpply\Iteration 2 | Design Meeting
|  | Team Meeting - Finish Design for Sprint 1 | Closed | Michael Yeaple | 1 |  | 1 | 2014-10-21 | Simpply\Iteration 3 | Design Meeting
|  | Team Meeting - Finish Design for Sprint 1 | Closed | Curtis Burtner | 1 |  | 1 | 2014-10-21 | Simpply\Iteration 4 | Design Meeting
|  | Meeting with Michael - User Story Breakdown/Tasks | Closed | Curtis Burtner | 2 |  | 2 | 2014-10-20 | Simpply | Process/Project Management Meeting
|  | Meeting with Curtis - User Story Breakdown/Tasks | Closed | Michael Yeaple | 2 |  | 2 | 2014-10-20 | Simpply | Process/Project Management Meeting
|  | Template layout implementation | Closed | Michael Yeaple | 3 |  | 1 | 2014-10-28 | Simpply | Implementation

## Historical Effort Tracking
ID | Work Item Type | Title | State | Assigned To | Original Estimate | Remaining Work | Completed Work | Closed Date | Iteration Path | Tags |  | Week3Iter2(11/21-11/25) | Week2Iter2(11/14-11/20) |  | Iteration 1 | All Time |  |  | Week3Iter2 | Week2Iter2 | Iteration 1
|  | Kick-Off Meeting | Closed | Curtis Burtner | 1.25 |  | 1.25 | 2014-08-28 | Simpply | Requirements Meeting | Process: | 0.00000 | 0 |  | 22.5 | 192.37 |  | Start: | >11/21/2014 | >11/14/2014 | >10/14/2014
|  | Kick-Off Meeting | Closed | Michael Yeaple | 1.25 |  | 1.25 | 2014-08-28 | Simpply | Requirements Meeting | Product: | 0.00000 | 0.00000 |  | 1 | 4 |  | End: | <11/28/2014 | <11/21/2014 | <11/14/2014
|  | Kick-Off Meeting | Closed | Mustafa Al-Salihi | 1.25 |  | 1.25 | 2014-08-28 | Simpply | Requirements Meeting | Total: | 0 | 0 |  | 26.5 | 196.37
|  | Kick-Off Meeting | Closed | Jeremy Shulman | 1.25 |  | 1.25 | 2014-08-28 | Simpply | Requirements Meeting | Estimated Hours: | 0 | 0 |  | 22
|  | Set Up JIRA | Closed | Michael Yeaple | 3 |  | 3 | 2014-09-05 | Simpply | Project Setup
|  | Emails to customer | Closed | Curtis Burtner | 1 |  | 1 | 2014-09-04 | Simpply | Process/Project Management Effort | Curtis Burtner | 0 | 0 |  | 8.25 | 49.08
|  | Searched how to build enterprise software | Closed | Mustafa Al-Salihi | 2 |  | 2 | 2014-09-04 | Simpply | Process/Project Management Effort | Michael Yeaple | 0 | 0 |  | 9.25 | 65.08
|  | Meeting | Closed | Curtis Burtner | 1.5 |  | 1.5 | 2014-09-04 | Simpply | Requirements Meeting | Jeremy Shulman | 0 | 0 |  | 6.25 | 44.33
|  | Meeting | Closed | Michael Yeaple | 1.5 |  | 1.5 | 2014-09-04 | Simpply | Requirements Meeting | Mustafa Al-Salihi | 0 | 0 |  | 2.75 | 37.88
|  | Meeting | Closed | Jeremy Shulman | 1.5 |  | 1.5 | 2014-09-04 | Simpply | Requirements Meeting
|  | Meeting | Closed | Mustafa Al-Salihi | 1.5 |  | 1.5 | 2014-09-04 | Simpply | Requirements Meeting
|  | Meeting | Closed | Michael Yeaple | 2 |  | 2 | 2014-09-03 | Simpply | Requirements Meeting
|  | Meeting | Closed | Curtis Burtner | 2 |  | 2 | 2014-09-03 | Simpply | Requirements Meeting
|  | Meeting | Closed | Mustafa Al-Salihi | 2 |  | 2 | 2014-09-03 | Simpply | Requirements Meeting
|  | Meeting | Closed | Jeremy Shulman | 2 |  | 2 | 2014-09-03 | Simpply | Requirements Meeting
|  | Meeting | Closed | Michael Yeaple | 1.25 |  | 1.25 | 2014-09-02 | Simpply | Requirements Meeting
|  | Meeting | Closed | Curtis Burtner | 1.25 |  | 1.25 | 2014-09-02 | Simpply | Requirements Meeting | Tags |  | Total | Curtis Butner | Jeremy Shulman | Michael Yeaple | Mustafa Al-Salihi
|  | Meeting | Closed | Mustafa Al-Salihi | 1.25 |  | 1.25 | 2014-09-02 | Simpply | Requirements Meeting | Academic Work Effort |  | 0
|  | Meeting | Closed | Jeremy Shulman | 1.25 |  | 1.25 | 2014-09-02 | Simpply | Requirements Meeting | Academic Work Meeting |  | 0
|  | Project schedule | Closed | Mustafa Al-Salihi | 2 |  | 2 | 2014-09-13 | Simpply | Process/Project Management Effort | Bugs |  | 0
|  | Work on team website and time tracking sheet | Closed | Jeremy Shulman | 1.5 |  | 1.5 | 2014-09-13 | Simpply | Process/Project Management Effort | Code/Design Review |  | 0
|  | Set Up & Fill Out Time Tracking | Closed | Michael Yeaple | 0.25 |  | 0.25 | 2014-09-13 | Simpply | Process/Project Management Effort | Design Effort |  | 0
|  | Emails to customer | Closed | Curtis Burtner | 1 |  | 1 | 2014-09-11 | Simpply | Process/Project Management Effort | Design Meeting |  | 40 | 10 | 10 | 10 | 10
|  | Meeting | Closed | Curtis Burtner | 1.25 |  | 1.25 | 2014-09-11 | Simpply | Requirements Meeting | Implementation |  | 1 | 0 | 1 | 0 | 0
|  | Meeting | Closed | Michael Yeaple | 1.25 |  | 1.25 | 2014-09-11 | Simpply | Requirements Meeting | Planning Meeting |  | 17.5 | 5.25 | 5.25 | 5.25 | 1.75
|  | Meeting | Closed | Jeremy Shulman | 1.25 |  | 1.25 | 2014-09-11 | Simpply | Requirements Meeting | Process/Project Management Effort |  | 32.5 | 10.25 | 7.5 | 5.75 | 9
|  | Meeting | Closed | Mustafa Al-Salihi | 1.25 |  | 1.25 | 2014-09-11 | Simpply | Requirements Meeting | Process/Project Management Meeting |  | 18.57 | 6.08 | 3.58 | 6.08 | 2.83
|  | Setup project plan template | Closed | Mustafa Al-Salihi | 0.5 |  | 0.5 | 2014-09-10 | Simpply | Process/Project Management Effort | Project Setup |  | 16.5 | 1 | 1 | 13.5 | 1
|  | Project Plan Sections | Closed | Jeremy Shulman | 2 |  | 2 | 2014-09-10 | Simpply | Process/Project Management Effort | Progress Meeting |  | 9
|  | Project Plan Meeting | Closed | Jeremy Shulman | 1.5 |  | 1.5 | 2014-09-08 | Simpply | Process/Project Management Meeting | Refactoring |  | 0
|  | Project Plan Meeting | Closed | Mustafa Al-Salihi | 1.5 |  | 1.5 | 2014-09-08 | Simpply | Process/Project Management Meeting | Requirements Effort |  | 11.55 | 11.55 | 11.55 | 11.55 | 11.55
|  | Project Plan Meeting | Closed | Michael Yeaple | 1.5 |  | 1.5 | 2014-09-08 | Simpply | Process/Project Management Meeting | Requirements Meeting |  | 49.75 | 49.75 | 49.75 | 49.75 | 49.75
|  | Project Plan Meeting | Closed | Curtis Burtner | 1.5 |  | 1.5 | 2014-09-08 | Simpply | Process/Project Management Meeting | Testing Effort |  | 0
|  | User Stories & Use Cases | Closed | Michael Yeaple | 3.5 |  | 3.5 | 2014-09-08 | Simpply | Requirements Effort
|  | Project Plan Meeting | Closed | Jeremy Shulman | 1.33 |  | 1.33 | 2014-09-09 | Simpply | Process/Project Management Meeting | Total= |  | 196.37
|  | Project Plan Meeting | Closed | Mustafa Al-Salihi | 1.33 |  | 1.33 | 2014-09-09 | Simpply | Process/Project Management Meeting | All Tasks= |  | 196.37
|  | Project Plan Meeting | Closed | Michael Yeaple | 1.33 |  | 1.33 | 2014-09-09 | Simpply | Process/Project Management Meeting
|  | Project Plan Meeting | Closed | Curtis Burtner | 1.33 |  | 1.33 | 2014-09-09 | Simpply | Process/Project Management Meeting | Meeting Hours: |  | 125.82
|  | Project Plan | Closed | Jeremy Shulman | 2 |  | 2 | 2014-09-09 | Simpply | Process/Project Management Effort
|  | Project Plan | Closed | Mustafa Al-Salihi | 2 |  | 2 | 2014-09-09 | Simpply | Process/Project Management Effort
|  | Project Plan | Closed | Michael Yeaple | 2 |  | 2 | 2014-09-09 | Simpply | Process/Project Management Effort
|  | Project Plan | Closed | Curtis Burtner | 2 |  | 2 | 2014-09-09 | Simpply | Process/Project Management Effort
|  | Project Plan Meeting | Closed | Jeremy Shulman | 1.5 |  | 1.5 | 2014-09-10 | Simpply | Process/Project Management Effort
|  | Project Plan Meeting | Closed | Mustafa Al-Salihi | 1.5 |  | 1.5 | 2014-09-10 | Simpply | Process/Project Management Effort
|  | Project Plan Meeting | Closed | Michael Yeaple | 1.5 |  | 1.5 | 2014-09-10 | Simpply | Process/Project Management Effort
|  | Project Plan Meeting | Closed | Curtis Burtner | 1.5 |  | 1.5 | 2014-09-10 | Simpply | Process/Project Management Effort
|  | Planning Next Meeting | Closed | Michael Yeaple | 0.5 |  | 0.5 | 2014-09-10 | Simpply | Process/Project Management Meeting
|  | Planning Next Meeting | Closed | Curtis Burtner | 0.5 |  | 0.5 | 2014-09-10 | Simpply | Process/Project Management Meeting
|  | Development Methodology Artifact (for website) | Closed | Curtis Burtner | 0.5 |  | 0.75 | 2014-09-21 | Simpply | Process/Project Management Meeting
|  | Development Methodology Artifact (for website) | Closed | Jeremy Shulman | 0.5 |  | 0.75 | 2014-09-21 | Simpply | Process/Project Management Meeting
|  | Development Methodology Artifact (for website) | Closed | Michael Yeaple | 0.5 |  | 0.75 | 2014-09-21 | Simpply | Process/Project Management Meeting
|  | Set Up TFS | Closed | Michael Yeaple | 0.5 |  | 1 | 2014-09-19 | Simpply | Project Setup
|  | Updating website | Closed | Jeremy Shulman |  |  | 0.5 | 2014-09-18 | Simpply | Process/Project Management Effort
|  | Email to Wegmans Team | Closed | Curtis Burtner | 0.5 |  | 0.75 | 2014-09-18 | Simpply | Process/Project Management Effort
|  | Created initial document to enter metrics | Closed | Curtis Burtner | 0.5 |  | 1 | 2014-09-17 | Simpply | Process/Project Management Effort
|  | Completed Initial Wireframes | Closed | Michael Yeaple | 1 |  | 1.25 | 2014-09-17 | Simpply | Requirements Effort
|  | Wireframe Meeting | Closed | Curtis Burtner | 0.5 |  | 0.5 | 2014-09-17 | Simpply | Requirements Meeting
|  | Wireframe Meeting | Closed | Jeremy Shulman | 1 |  | 1 | 2014-09-17 | Simpply | Requirements Meeting
|  | Wireframe Meeting | Closed | Michael Yeaple | 1 |  | 1 | 2014-09-17 | Simpply | Requirements Meeting
|  | Initial Wireframes | Closed | Michael Yeaple | 2 |  | 3 | 2014-09-17 | Simpply | Requirements Effort
|  | Import user stroies into the software | Closed | Mustafa Al-Salihi |  |  | 1 | 2014-09-17 | Simpply | Process/Project Management Effort
|  | User Stories Meeting | Closed | Jeremy Shulman | 1.25 |  | 1.25 | 2014-09-16 | Simpply | Requirements Meeting
|  | User Stories Meeting | Closed | Mustafa Al-Salihi | 1.25 |  | 1.25 | 2014-09-16 | Simpply | Requirements Meeting
|  | User Stories Meeting | Closed | Michael Yeaple | 1.25 |  | 1.25 | 2014-09-16 | Simpply | Requirements Meeting
|  | User Stories Meeting | Closed | Curtis Burtner | 1.25 |  | 1.25 | 2014-09-16 | Simpply | Requirements Meeting
|  | Initial Wireframes | Closed | Jeremy Shulman | 1.25 |  | 1.25 | 2014-09-15 | Simpply | Requirements Effort
|  | Initial Wireframes | Closed | Curtis Burtner | 1.25 |  | 1.25 | 2014-09-15 | Simpply | Requirements Effort
|  | Wireframes | Closed | Mustafa Al-Salihi | 1.3 |  | 1.3 | 2014-09-15 | Simpply | Requirements Effort
|  | VM Set Up | Closed | Michael Yeaple | 3 |  | 5 | 2014-09-27 | Simpply | Project Setup
|  | Customer Meeting | Closed | Curtis Burtner | 1.25 |  | 1.75 | 2014-09-25 | Simpply | Requirements Meeting
|  | Customer Meeting | Closed | Jeremy Shulman | 1.25 |  | 1.75 | 2014-09-25 | Simpply | Requirements Meeting
|  | Customer Meeting | Closed | Michael Yeaple | 1.25 |  | 1.75 | 2014-09-25 | Simpply | Requirements Meeting
|  | ORM Presentation Slides | Closed | Curtis Burtner | 1 |  | 1 | 2014-09-25 | Simpply | Process/Project Management Effort
|  | ORM Presentation Slides | Closed | Michael Yeaple | 1 |  | 1 | 2014-09-25 | Simpply | Process/Project Management Effort
|  | Emails to Customer | Closed | Curtis Burtner | 1 |  | 1 | 2014-09-25 | Simpply | Process/Project Management Effort
|  | Wireframe Revision/Planning for Customer Meeting | Closed | Curtis Burtner | 1 |  | 1 | 2014-09-24 | Simpply | Requirements Meeting
|  | Wireframe Revision/Planning for Customer Meeting | Closed | Jeremy Shulman | 1 |  | 1 | 2014-09-24 | Simpply | Requirements Meeting
|  | Wireframe Revision/Planning for Customer Meeting | Closed | Michael Yeaple | 1 |  | 1 | 2014-09-24 | Simpply | Requirements Meeting
|  | Environment Set Up Meeting | Closed | Jeremy Shulman | 1 |  | 1 | 2014-09-23 | Simpply | Project Setup
|  | Environment Set Up Meeting | Closed | Mustafa Al-Salihi | 1 |  | 1 | 2014-09-23 | Simpply | Project Setup
|  | Environment Set Up Meeting | Closed | Michael Yeaple | 1 |  | 1 | 2014-09-23 | Simpply | Project Setup
|  | Environment Set Up Meeting | Closed | Curtis Burtner | 1 |  | 1 | 2014-09-23 | Simpply | Project Setup
|  | Software Design Document Set Up/Update Project Plan | Closed | Michael Yeaple | 1 |  | 1 | 2014-09-22 | Simpply | Process/Project Management Effort
|  | Emails to Kurt | Closed | Curtis Burtner | 1 |  | 1 | 2014-09-22 | Simpply | Process/Project Management Effort
|  | Onsite meeting with customer. | Closed | Jeremy Shulman | 2 |  | 2 | 2014-10-03 | Simpply | Design Meeting
|  | Onsite meeting with customer. | Closed | Mustafa Al-Salihi | 2 |  | 2 | 2014-10-03 | Simpply | Design Meeting
|  | Onsite meeting with customer. | Closed | Michael Yeaple | 2 |  | 2 | 2014-10-03 | Simpply | Design Meeting
|  | Onsite meeting with customer. | Closed | Curtis Burtner | 2 |  | 2 | 2014-10-03 | Simpply | Design Meeting
|  | Team Meeting - User Stories in TFS; Architecture | Closed | Jeremy Shulman | 3 |  | 3 | 2014-10-02 | Simpply | Design Meeting
|  | Team Meeting - User Stories in TFS; Architecture | Closed | Mustafa Al-Salihi | 3 |  | 3 | 2014-10-02 | Simpply | Design Meeting
|  | Team Meeting - User Stories in TFS; Architecture | Closed | Michael Yeaple | 3 |  | 3 | 2014-10-02 | Simpply | Design Meeting
|  | Team Meeting - User Stories in TFS; Architecture | Closed | Curtis Burtner | 3 |  | 3 | 2014-10-02 | Simpply | Design Meeting
|  | TFS Setup - Project and Users | Closed | Michael Yeaple | 1 |  | 3 | 2014-09-30 | Simpply | Project Setup
|  | Team Meeting - Mind Map | Closed | Jeremy Shulman | 1.25 |  | 1.25 | 2014-09-30 | Simpply | Requirements Meeting
|  | Team Meeting - Mind Map | Closed | Mustafa Al-Salihi | 1.25 |  | 1.25 | 2014-09-30 | Simpply | Requirements Meeting
|  | Team Meeting - Mind Map | Closed | Michael Yeaple | 1.25 |  | 1.25 | 2014-09-30 | Simpply | Requirements Meeting
|  | Team Meeting - Mind Map | Closed | Curtis Burtner | 1.25 |  | 1.25 | 2014-09-30 | Simpply | Requirements Meeting
|  | EA Review of Architecture | Closed | Jeremy Shulman | 2 |  | 2 | 2014-10-10 | Simpply | Design Meeting
|  | EA Review of Architecture | Closed | Mustafa Al-Salihi | 2 |  | 2 | 2014-10-10 | Simpply | Design Meeting
|  | EA Review of Architecture | Closed | Michael Yeaple | 2 |  | 2 | 2014-10-10 | Simpply | Design Meeting
|  | EA Review of Architecture | Closed | Curtis Burtner | 2 |  | 2 | 2014-10-10 | Simpply | Design Meeting
|  | Customer Meeting; Update and Practice Presentation | Closed | Jeremy Shulman | 2 |  | 2.25 | 2014-10-09 | Simpply | Progress Meeting
|  | Customer Meeting; Update and Practice Presentation | Closed | Mustafa Al-Salihi | 2 |  | 2.25 | 2014-10-09 | Simpply | Progress Meeting
|  | Customer Meeting; Update and Practice Presentation | Closed | Michael Yeaple | 2 |  | 2.25 | 2014-10-09 | Simpply | Progress Meeting
|  | Customer Meeting; Update and Practice Presentation | Closed | Curtis Burtner | 2 |  | 2.25 | 2014-10-09 | Simpply | Progress Meeting
|  | Regular Tuesday meeting | Closed | Jeremy Shulman | 2 |  | 2 | 2014-10-07 | Simpply | Design Meeting
|  | Regular Tuesday meeting | Closed | Mustafa Al-Salihi | 2 |  | 2 | 2014-10-07 | Simpply | Design Meeting
|  | Regular Tuesday meeting | Closed | Michael Yeaple | 2 |  | 2 | 2014-10-07 | Simpply | Design Meeting
|  | Regular Tuesday meeting | Closed | Curtis Burtner | 2 |  | 2 | 2014-10-07 | Simpply | Design Meeting
|  | Customer Meeting - Sprint Planning | Closed | Jeremy Shulman | 1.25 |  | 1.75 | 2014-10-16 | Simpply | Planning Meeting
|  | Customer Meeting - Sprint Planning | Closed | Mustafa Al-Salihi | 1.25 |  | 1.75 | 2014-10-16 | Simpply | Planning Meeting
|  | Customer Meeting - Sprint Planning | Closed | Michael Yeaple | 1.25 |  | 1.75 | 2014-10-16 | Simpply | Planning Meeting
|  | Customer Meeting - Sprint Planning | Closed | Curtis Burtner | 1.25 |  | 1.75 | 2014-10-16 | Simpply | Planning Meeting
|  | User Story Meeting (Break down, Pointing) | Closed | Curtis Burtner | 2 |  | 3.5 | 2014-10-15 | Simpply | Planning Meeting
|  | User Story Meeting (Break down, Pointing) | Closed | Jeremy Shulman | 2 |  | 3.5 | 2014-10-15 | Simpply | Planning Meeting
|  | User Story Meeting (Break down, Pointing) | Closed | Michael Yeaple | 2 |  | 3.5 | 2014-10-15 | Simpply | Planning Meeting
|  | TFS Permissions Issues | Closed | Michael Yeaple | 0.5 |  | 0.5 | 2014-10-13 | Simpply | Project Setup
|  | Team Meeting - Finish Design for Sprint 1 | Closed | Jeremy Shulman | 1 |  | 1 | 2014-10-21 | Simpply\Iteration 1 | Design Meeting
|  | Team Meeting - Finish Design for Sprint 1 | Closed | Mustafa Al-Salihi | 1 |  | 1 | 2014-10-21 | Simpply\Iteration 2 | Design Meeting
|  | Team Meeting - Finish Design for Sprint 1 | Closed | Michael Yeaple | 1 |  | 1 | 2014-10-21 | Simpply\Iteration 3 | Design Meeting
|  | Team Meeting - Finish Design for Sprint 1 | Closed | Curtis Burtner | 1 |  | 1 | 2014-10-21 | Simpply\Iteration 4 | Design Meeting
|  | Meeting with Michael - User Story Breakdown/Tasks | Closed | Curtis Burtner | 2 |  | 2 | 2014-10-20 | Simpply | Process/Project Management Meeting
|  | Meeting with Curtis - User Story Breakdown/Tasks | Closed | Michael Yeaple | 2 |  | 2 | 2014-10-20 | Simpply | Process/Project Management Meeting
|  | Template layout implementation | Closed | Michael Yeaple | 3 |  | 1 | 2014-10-28 | Simpply | Implementation

## Process Metrics
Iteration # | Date Start/End | Hours Estimated | Hours Actual | Hours Slipped | Percent Slippage\ | # of Story Tasks Left | Complexity Evaluation[Web Role] | Lines of Code[Web Role] | Velocity | Hours in Product | Hours Per Point
1 | October 16 - November 13 | 108 | 121.3 | 13 | 10% | 0 | 71 | 155 | 18 Story Points | 32 | 1.78
2 | November 14 - December 12 | 212.7 | 237.7336 | 25 | 11% | 0 | 161 | 412 | 14 Story Points | 99.1703 | 7.1

## Code Metrics Iteration 2
Scope | Project | Namespace | Type | Member | Maintainability Index | Cyclomatic Complexity | Depth of Inheritance | Class Coupling | Lines of Code
Member | Simpply (Debug) | Simpply | AuthConfig | RegisterAuth() : void | 100 | 1 |  | 0 | 0
Member | Simpply (Debug) | Simpply | BundleConfig | BundleConfig() | 100 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply | BundleConfig | RegisterBundles(BundleCollection) : void | 64 | 1 |  | 4 | 6
Member | Simpply (Debug) | Simpply | FilterConfig | FilterConfig() | 100 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply | FilterConfig | RegisterGlobalFilters(GlobalFilterCollection) : void | 94 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply | MvcApplication | Application_Start() : void | 69 | 1 |  | 11 | 7
Member | Simpply (Debug) | Simpply | MvcApplication | MvcApplication() | 100 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply | RouteConfig | RegisterRoutes(RouteCollection) : void | 82 | 1 |  | 3 | 2
Member | Simpply (Debug) | Simpply | RouteConfig | RouteConfig() | 100 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply | WebApiConfig | Register(HttpConfiguration) : void | 89 | 1 |  | 4 | 1
Member | Simpply (Debug) | Simpply.App_Start | AutofacConfig | RegisterComponents() : void | 70 | 1 |  | 10 | 5
Member | Simpply (Debug) | Simpply.Controllers | AccountController | AccountController(IColumnPreferenceProvider) | 87 | 1 |  | 2 | 2
Member | Simpply (Debug) | Simpply.Controllers | AccountController | SaveColumnPreferences(ColumnPreferenceModel) : ActionResult | 55 | 4 |  | 9 | 12
Member | Simpply (Debug) | Simpply.Controllers | BaseController | BaseController() | 100 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Controllers | BaseController | JsonActionResult(JsonReturnType, string, string, string, object) : ActionResult | 68 | 1 |  | 5 | 6
Member | Simpply (Debug) | Simpply.Controllers | ItemController | ItemController(IItemProvider, IStoreProvider, ISalesInformationProvider, IDistributionProvider, IColumnPreferenceProvider) | 71 | 1 |  | 6 | 6
Member | Simpply (Debug) | Simpply.Controllers | ItemController | ItemDetail(long) : ActionResult | 56 | 7 |  | 19 | 12
Member | Simpply (Debug) | Simpply.Controllers | ItemController | ItemExplorer(string, bool) : ActionResult | 63 | 3 |  | 18 | 7
Member | Simpply (Debug) | Simpply.Controllers | ItemController | Search(string) : ActionResult | 66 | 2 |  | 7 | 7
Member | Simpply (Debug) | Simpply.Controllers | StoreController | CompareToMultiplestores() : ActionResult | 89 | 1 |  | 2 | 2
Member | Simpply (Debug) | Simpply.Controllers | StoreController | CompareTostore() : ActionResult | 89 | 1 |  | 2 | 2
Member | Simpply (Debug) | Simpply.Controllers | StoreController | StoreController() | 100 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Helpers | WebHelper | GenerateActionUrl(string, string, Dictionary<string, string>) : string | 63 | 5 |  | 4 | 8
Member | Simpply (Debug) | Simpply.Helpers | WebHelper | GenerateActionUrl(string, string, string) : string | 73 | 2 |  | 1 | 4
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ColumnPreferenceModel() | 73 | 1 |  | 2 | 5
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ColumnPreferenceModel(string, string, string, List<string>, List<ColumnPreference>) | 38 | 16 |  | 14 | 51
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ControllerAction.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ControllerAction.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ControllerName.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ControllerName.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | GetColumnId(string) : long? | 67 | 3 |  | 1 | 7
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | GetColumnName(string) : string | 69 | 2 |  | 0 | 6
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | HiddenColumns.get() : List<string> | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | HiddenColumns.set(List<string>) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | HiddenColumnsList.get() : List<SelectListItem> | 98 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | HiddenColumnsList.set(List<SelectListItem>) : void | 95 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ShownColumns.get() : List<string> | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ShownColumns.set(List<string>) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ShownColumnsList.get() : List<SelectListItem> | 98 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | ShownColumnsList.set(List<SelectListItem>) : void | 95 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | Table.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ColumnPreferenceModel | Table.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | ActionUrl.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | ActionUrl.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | CssClasses.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | CssClasses.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | GridCellModel() | 100 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | Value.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridCellModel | Value.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | GridModel() | 78 | 1 |  | 2 | 3
Member | Simpply (Debug) | Simpply.Models | GridModel | Header.get() : GridRowModel | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | Header.set(GridRowModel) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | Rows.get() : List<GridRowModel> | 98 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | GridModel | Rows.set(List<GridRowModel>) : void | 95 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | GridRowModel | Aggregate_Cells.get() : List<GridCellModel> | 98 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | GridRowModel | Aggregate_Cells.set(List<GridCellModel>) : void | 95 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | GridRowModel | Cells.get() : List<GridCellModel> | 98 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | GridRowModel | Cells.set(List<GridCellModel>) : void | 95 | 1 |  | 2 | 1
Member | Simpply (Debug) | Simpply.Models | GridRowModel | CssClasses.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridRowModel | CssClasses.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridRowModel | GridRowModel() | 87 | 1 |  | 2 | 2
Member | Simpply (Debug) | Simpply.Models | GridRowModel | IsHeader.get() : bool | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | GridRowModel | IsHeader.set(bool) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | Aggregate.get() : GridModel | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | Aggregate.set(GridModel) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | Grid.get() : GridModel | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | Grid.set(GridModel) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | ItemDetailModel(Item, List<Store>, List<SalesInformation>, List<Distribution>) | 22 | 29 |  | 23 | 154
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | Name.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel | Name.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel.AggregateModel | AggregateModel() | 100 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel.AggregateModel | CalculatedInventory.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel.AggregateModel | CalculatedInventory.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel.AggregateModel | LastYearSales.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel.AggregateModel | LastYearSales.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel.AggregateModel | PercentageTotal.get() : double | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel.AggregateModel | PercentageTotal.set(double) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel.AggregateModel | Sellthrough.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel.AggregateModel | Sellthrough.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel.AggregateModel | UnitsReceived.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel.AggregateModel | UnitsReceived.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel.AggregateModel | UnitsSold.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemDetailModel.AggregateModel | UnitsSold.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply (Debug) | Simpply.Models | ItemExplorerModel | ColumnPreferences.get() : ColumnPreferenceModel | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ItemExplorerModel | ColumnPreferences.set(ColumnPreferenceModel) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ItemExplorerModel | CreateHeaderCell(string, string, string, bool) : GridCellModel | 77 | 5 |  | 2 | 2
Member | Simpply (Debug) | Simpply.Models | ItemExplorerModel | Grid.get() : GridModel | 98 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ItemExplorerModel | Grid.set(GridModel) : void | 95 | 1 |  | 1 | 1
Member | Simpply (Debug) | Simpply.Models | ItemExplorerModel | ItemExplorerModel(List<Item>, string, bool, List<ColumnPreference>) | 43 | 10 |  | 10 | 32
Member | Simpply.Data (Debug) | Simpply.Data | Distribution | Distribution() | 100 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Distribution | Id.get() : long | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Distribution | Id.set(long) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Distribution | ItemAmount.get() : long | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Distribution | ItemAmount.set(long) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Distribution | ItemId.get() : long | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Distribution | ItemId.set(long) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Distribution | StoreId.get() : long | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Distribution | StoreId.set(long) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Distribution | Type.get() : AlgorithmType | 98 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Distribution | Type.set(AlgorithmType) : void | 95 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Example | Example() | 100 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Example | Id.get() : long | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Example | Id.set(long) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Item | Description.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Item | Description.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Item | Id.get() : long | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Item | Id.set(long) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Item | Item() | 100 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Item | Name.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Item | Name.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Item | stores.get() : List<Store> | 98 | 1 |  | 2 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Item | stores.set(List<Store>) : void | 95 | 1 |  | 2 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | CalculatedInventory.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | CalculatedInventory.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | Id.get() : long | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | Id.set(long) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | ItemId.get() : long | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | ItemId.set(long) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | LastYearsSales.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | LastYearsSales.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | PercentageOfTotal.get() : double | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | PercentageOfTotal.set(double) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | SalesInformation() | 100 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | Sellthrough.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | Sellthrough.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | StoreId.get() : long | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | StoreId.set(long) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | UnitsReceived.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | UnitsReceived.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | UnitsSold.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | SalesInformation | UnitsSold.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Store | Distribution.get() : Distribution | 98 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Store | Distribution.set(Distribution) : void | 95 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Store | Id.get() : long | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Store | Id.set(long) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Store | Name.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Store | Name.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Store | Sales.get() : SalesInformation | 98 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Store | Sales.set(SalesInformation) : void | 95 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Store | Segmentation.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Store | Segmentation.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data | Store | Store() | 100 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Account | ColumnPreference | Column.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Account | ColumnPreference | Column.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Account | ColumnPreference | ColumnPreference() | 100 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Account | ColumnPreference | Controller.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Account | ColumnPreference | Controller.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Account | ColumnPreference | ControllerAction.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Account | ColumnPreference | ControllerAction.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Account | ColumnPreference | Id.get() : long? | 98 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Account | ColumnPreference | Id.set(long?) : void | 95 | 1 |  | 1 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Account | ColumnPreference | Order.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Account | ColumnPreference | Order.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Account | ColumnPreference | ShowColumn.get() : bool | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Account | ColumnPreference | ShowColumn.set(bool) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Account | ColumnPreference | Table.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Data (Debug) | Simpply.Data.Account | ColumnPreference | Table.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access | AccessModule | AccessModule() | 100 | 1 |  | 1 | 1
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access | AccessModule | Load(ContainerBuilder) : void | 65 | 1 |  | 16 | 6
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IColumnPreferenceProvider | Get(string, string, string) : List<ColumnPreference> | 100 | 1 |  | 2 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IColumnPreferenceProvider | Save(List<ColumnPreference>) : void | 100 | 1 |  | 2 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IDistributionProvider | Get(long) : List<Distribution> | 100 | 1 |  | 2 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IItemProvider | Get(long) : Item | 100 | 1 |  | 1 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IItemProvider | Get(string, bool) : List<Item> | 100 | 1 |  | 2 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IItemProvider | GetDapper(long?, string, string, bool?) : List<Item> | 100 | 1 |  | 3 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IItemProvider | GetDetailsDapper(long) : Item | 100 | 1 |  | 1 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IItemProvider | Save(Item) : void | 100 | 1 |  | 1 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IItemProvider | Save(List<Item>) : void | 100 | 1 |  | 2 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | ISalesInformationProvider | Get() : List<SalesInformation> | 100 | 1 |  | 2 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | ISalesInformationProvider | Get(long, long) : SalesInformation | 100 | 1 |  | 1 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IStoreProvider | Get() : List<Store> | 100 | 1 |  | 2 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Contracts | IStoreProvider | Get(long) : Store | 100 | 1 |  | 1 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | BaseProvider | BaseProvider() | 83 | 1 |  | 3 | 2
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | BaseProvider | connectionString.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | BaseProvider | connectionString.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ColumnPreferenceProvider | ColumnPreferenceProvider() | 100 | 1 |  | 1 | 1
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ColumnPreferenceProvider | Get(string, string, string) : List<ColumnPreference> | 66 | 2 |  | 10 | 7
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ColumnPreferenceProvider | Save(List<ColumnPreference>) : void | 52 | 4 |  | 15 | 15
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | DistributionProvider | DistributionProvider() | 100 | 1 |  | 1 | 1
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | DistributionProvider | Get(long) : List<Distribution> | 69 | 2 |  | 10 | 5
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ExampleProvider | ExampleProvider() | 100 | 1 |  | 1 | 1
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ExampleProvider | SelectExample(int) : Example | 70 | 2 |  | 9 | 5
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ItemProvider | Get(long) : Item | 73 | 2 |  | 5 | 4
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ItemProvider | Get(string, bool) : List<Item> | 46 | 20 |  | 4 | 26
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ItemProvider | GetDapper(long?, string, string, bool?) : List<Item> | 69 | 2 |  | 10 | 5
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ItemProvider | GetDetailsDapper(long) : Item | 55 | 5 |  | 15 | 13
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ItemProvider | ItemProvider() | 74 | 1 |  | 3 | 2
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ItemProvider | Save(Item) : void | 100 | 1 |  | 1 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | ItemProvider | Save(List<Item>) : void | 100 | 1 |  | 2 | 0
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | SalesInformationProvider | Get() : List<SalesInformation> | 91 | 1 |  | 2 | 2
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | SalesInformationProvider | Get(long, long) : SalesInformation | 70 | 3 |  | 5 | 5
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | SalesInformationProvider | SalesInformationProvider() | 68 | 1 |  | 3 | 2
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | StoreProvider | Get() : List<Store> | 91 | 1 |  | 2 | 2
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | StoreProvider | Get(long) : Store | 71 | 2 |  | 5 | 5
Member | Simpply.Data.Access (Debug) | Simpply.Data.Access.Implementation | StoreProvider | StoreProvider() | 76 | 1 |  | 3 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine | BundleConfig | BundleConfig() | 100 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine | BundleConfig | RegisterBundles(BundleCollection) : void | 100 | 1 |  | 1 | 0
Member | Simpply.Engine (Debug) | Simpply.Engine | FilterConfig | FilterConfig() | 100 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine | FilterConfig | RegisterGlobalFilters(GlobalFilterCollection) : void | 94 | 1 |  | 2 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine | RouteConfig | RegisterRoutes(RouteCollection) : void | 82 | 1 |  | 4 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine | RouteConfig | RouteConfig() | 100 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine | WebApiApplication | Application_Start() : void | 73 | 1 |  | 9 | 5
Member | Simpply.Engine (Debug) | Simpply.Engine | WebApiApplication | WebApiApplication() | 100 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine | WebApiConfig | Register(HttpConfiguration) : void | 82 | 1 |  | 5 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Controllers | HomeController | HomeController() | 100 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Controllers | HomeController | Index() : ActionResult | 89 | 1 |  | 2 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Controllers | JobsController | Get() : string | 91 | 1 |  | 1 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Controllers | JobsController | JobsController() | 100 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Controllers | JobsController | Post(JobRequest) : object | 55 | 4 |  | 9 | 15
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | BaseJob | BaseJob() | 87 | 1 |  | 0 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | BaseJob | BaseJob(string) | 87 | 1 |  | 0 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | BaseJob | Execute() : bool | 100 | 1 |  | 0 | 0
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | JobInvoker | JobInvoker() | 100 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | JobInvoker | ScheduleJob(BaseJob) : bool | 87 | 1 |  | 1 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | ParseWegmansData | Execute() : bool | 86 | 1 |  | 1 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | ParseWegmansData | ParseWegmansData(string) | 84 | 1 |  | 3 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | ParseWegmansData | ReadWegmansData() : void | 100 | 1 |  | 0 | 0
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunAlgorithm | Execute() : bool | 91 | 1 |  | 0 | 2
Member | Simpply.Engine (Debug) | Simpply.Engine.Jobs | RunAlgorithm | RunAlgorithm(string) | 98 | 1 |  | 1 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobRequest | Data.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobRequest | Data.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobRequest | Job.get() : string | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobRequest | Job.set(string) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | JobRequest | JobRequest() | 100 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | ParseWegmansDataModel | ParseWegmansDataModel() | 100 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | ParseWegmansDataModel | Test.get() : int | 98 | 1 |  | 0 | 1
Member | Simpply.Engine (Debug) | Simpply.Engine.Models | ParseWegmansDataModel | Test.set(int) : void | 95 | 1 |  | 0 | 1
Member | Simpply.Global (Debug) | Simpply.Global | Constants | Constants() | 100 | 1 |  | 0 | 1
Member | Simpply.Global (Debug) | Simpply.Global | Constants.Controller | Controller() | 100 | 1 |  | 0 | 1
Member | Simpply.Global (Debug) | Simpply.Global | Constants.ControllerAction | ControllerAction() | 100 | 1 |  | 0 | 1
Member | Simpply.Global (Debug) | Simpply.Global | Constants.ControllerAction.Account | Account() | 100 | 1 |  | 0 | 1
Member | Simpply.Global (Debug) | Simpply.Global | Constants.ControllerAction.Item | Item() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | AccountControllerTest | AccountControllerTest() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | AccountControllerTest | SaveColumnPreferences() : void | 55 | 5 |  | 22 | 12
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | AccountControllerTest | TestInit() : void | 92 | 1 |  | 3 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | ItemControllerTest | ItemControllerTest() | 73 | 1 |  | 1 | 3
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | ItemControllerTest | ItemDetail() : void | 62 | 3 |  | 21 | 7
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | ItemControllerTest | ItemExplorer() : void | 60 | 3 |  | 19 | 8
Member | Simpply.Tests (Debug) | Simpply.Tests.Controllers | ItemControllerTest | TestInit() : void | 67 | 1 |  | 8 | 6
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | BaseProviderTest | BaseProviderTest() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | BaseProviderTest | TestInit() : void | 94 | 1 |  | 3 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ColumnPreferenceProviderTest | ColumnPreferenceProviderTest() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ColumnPreferenceProviderTest | Get() : void | 82 | 1 |  | 6 | 2
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ColumnPreferenceProviderTest | Save() : void | 75 | 1 |  | 4 | 2
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ColumnPreferenceProviderTest | TestInit() : void | 94 | 1 |  | 3 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ItemProviderTest | GetItem() : void | 100 | 1 |  | 1 | 0
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ItemProviderTest | GetItems() : void | 72 | 1 |  | 6 | 5
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ItemProviderTest | ItemProviderTest() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ItemProviderTest | SaveItem() : void | 100 | 1 |  | 1 | 0
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ItemProviderTest | SaveItems() : void | 100 | 1 |  | 1 | 0
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | ItemProviderTest | TestInit() : void | 94 | 1 |  | 3 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | SalesInformationProviderTest | GetSale() : void | 100 | 1 |  | 1 | 0
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | SalesInformationProviderTest | GetSales() : void | 100 | 1 |  | 1 | 0
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | SalesInformationProviderTest | SalesInformationProviderTest() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | SalesInformationProviderTest | TestInit() : void | 94 | 1 |  | 3 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | StoreProviderTest | GetStore() : void | 100 | 1 |  | 1 | 0
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | StoreProviderTest | GetStores() : void | 100 | 1 |  | 1 | 0
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | StoreProviderTest | StoreProviderTest() | 100 | 1 |  | 0 | 1
Member | Simpply.Tests (Debug) | Simpply.Tests.Providers | StoreProviderTest | TestInit() : void | 94 | 1 |  | 3 | 1
Member | Simpply.Util (Debug) | Simpply.Util.Extensions | CollectionExtensions | IsEmpty<T>(this ICollection<T>) : bool | 84 | 2 |  | 2 | 2
Member | Simpply.Util (Debug) | Simpply.Util.Extensions | StringExtensions | IsNullOrWhiteSpace(this string) : bool | 87 | 1 |  | 1 | 2