## Sheet1
Task | Actual | Schedule Slip | First Estimate | Revised Estimate 1 | Note: All effort times are in hours.
Mid-Project Presentation | 15 |  | 6 | 8
Final Presentation |  |  | 9 | 15
Project Poster |  |  | 6 | 7
Technical Report |  |  | 3 | 8
Post-Mortem Reflection |  |  | 4 | 5
BRS | 95 | 5 days | 10 | 46
SRS | 13 |  | 10 | 40
Risk Management Document | 3 |  |  | 10
Project Plan | 37 |  | 6
Architecture Document | 14 |  | 15 | 20
Design Document | 7 |  | 15 | 20
Test Plan | 4 |  | 12 | 20
Review Requirements and Risks (Stage 1) |  |  | 2 | 2
Design modifications |  |  |  | 6
UI Prototyping | 26 |  | 6 | 10
Design UI and web architecture |  |  | 13 | 20
Examine PAETEC examples | 2 |  | 8 | 20
Research and decide on definition method | 1 |  | 4 | 5
Design master definition | 13 |  | 15 | 30
Implementation (Stage 1) | 3 |  | 40 | 100
Testing (Stage 1) |  |  | 5 | 10
Bug fixes (Stage 1) |  |  | 10 | 20
Release (Stage 1) |  |  | 3 | 12
Research UI tools |  |  | 10 | 20
Review Previous release (Stage 2) |  |  | 4 | 4
Modify Requirements and schedule (Stage 2) |  |  | 2 | 2
Review Design |  |  |  | 6
Implementation (Stage 2) |  |  | 50 | 150
Usability |  |  | 2 | 10
Testing (Stage 2) |  |  | 5 | 10
Bug fixes (Stage 2) |  |  | 10 | 10
Release (Stage 2) |  |  | 5 | 12
Review Previous release (Stage 3) |  |  | 4 | 4
Modify Requirements and schedule (Stage 3) |  |  | 2 | 2
Design exporting modules |  |  | 3 | 30
Implementation (Stage 3) |  |  | 25 | 150
Test and verify output |  |  | 10 | 30
Bug fixes (Stage 3) |  |  | 15 | 20
Prepare final release |  |  | 10 | 12