## Info
Version: | 1.14
Last Updated On: | 2009-04-03
Results in Deliverable

## Schedule
Category | Task | Completion | Projected Time (hrs) | Projected Start Date | Projected End Date | Actual Time(hrs) | Actual Start Date | Actual End Date | Non Negotable End Date? | Predecessors | Rescource | Estimation Accuracy
Agenda | Agenda Week 1 | 100% | 1 | 2008-12-02 | 2008-12-02 | 1 | 2008-12-02 | 2008-12-02 | Yes |  | Phil
Agenda | Agenda Week 2 | 100% | 1 | 2008-12-09 | 2008-12-09 | 1 | 2008-12-09 | 2008-12-09 | Yes |  | Phil
Agenda | Agenda Week 3 | 100% | 1 | 2008-12-16 10:00 | 2008-12-16 10:00 | 1 | 2008-12-16 10:00 | 2008-12-16 10:00 | Yes |  | Phil
Agenda | Agenda Week 4 | 100% | 1 | 2009-01-05 10:00 | 2009-01-05 10:00 | 1 | 2009-01-05 10:00 | 2009-01-05 10:00 | Yes |  | Phil
Agenda | Agenda Week 5 | 100% | 1 | 2009-01-12 10:00 | 2009-01-12 10:00 | 1 | 2009-01-12 10:00 | 2009-01-12 10:00 | Yes |  | Phil
Agenda | Agenda Week 6 | 100% | 1 | 2009-01-19 09:00 | 2009-01-19 09:00 | 1 | 2009-01-19 09:00 | 2009-01-19 09:00 | Yes |  | Phil
Agenda | Agenda Week 7 | 100% | 1 | 2009-01-26 09:00 | 2009-01-26 09:00 | 1 | 2009-01-26 09:00 | 2009-01-26 09:00 | Yes |  | Phil
Agenda | Agenda Week 8 | 100% | 1 | 2009-02-02 09:00 | 2009-02-02 09:00 | 1 | 2009-02-02 09:00 | 2009-02-02 09:00 | Yes |  | Phil
Agenda | Agenda Week 9 | 100% | 1 | 2009-02-09 09:00 | 2009-02-09 09:00 | 1 | 2009-02-09 09:00 | 2009-02-09 09:00 | Yes |  | Phil
Agenda | Agenda Week 12 | 100% | 1 | 2009-03-09 09:00 | 2009-03-09 09:00 | 1 | 2009-03-09 09:00 | 2009-03-09 09:00 | Yes |  | Phil
Agenda | Agenda Week 13 | 100% | 1 | 2009-03-16 09:00 | 2009-03-16 09:00 | 1 | 2009-03-16 09:00 | 2009-03-16 09:00 | Yes |  | Phil
Agenda | Agenda Week 14 | 100% | 1 | 2009-03-23 09:00 | 2009-03-23 09:00 | 1 | 2009-03-23 09:00 | 2009-03-23 09:00 | Yes |  | Phil
Agenda | Agenda Week 15 | 100% | 1 | 2009-03-30 09:00 | 2009-03-30 09:00 | 1 | 2009-03-30 | 2009-03-30 | Yes |  | Phil
Agenda | Agenda Week 16 | 100% | 1 | 2009-04-06 09:00 | 2009-04-06 09:00 |  |  |  | Yes |  | Phil
Agenda | Agenda Week 17 | 100% | 1 | 2009-04-13 09:00 | 2009-04-13 09:00 |  |  |  | Yes |  | Phil
Agenda | Agenda Week 18 | 100% | 1 | 2009-04-20 09:00 | 2009-04-20 09:00 |  |  |  | Yes |  | Phil
Agenda | Agenda Week 19 | 100% | 1 | 2009-04-27 09:00 | 2009-04-27 09:00 |  |  |  | Yes |  | Phil
Agenda | Agenda Week 20 | 0% | 1 | 2009-05-04 09:00 | 2009-05-04 09:00 |  |  |  | Yes |  | Phil
Sponsor Meetings | Meeting With Sponsor Week 1 | 100% | 1.5 | 2008-12-02 | 2008-12-02 | 1.5 | 2008-12-02 | 2008-12-02 |  |  | Team
Sponsor Meetings | Meeting With Sponsor Week 2 | 100% | 1.5 | 2008-12-09 | 2008-12-09 | 1.5 | 2008-12-09 | 2008-12-09 |  |  | Team
Sponsor Meetings | Meeting With Sponsor Week 3 | 100% | 1.5 | 2008-12-16 10:00 | 2008-12-16 10:00 | 1.5 | 2008-12-16 10:00 | 2008-12-16 10:00 |  |  | Team
Sponsor Meetings | Meeting With Sponsor Week 4 | 100% | 1.5 | 2009-01-06 10:00 | 2009-01-06 10:00 | 1.5 | 2009-01-06 10:00 | 2009-01-06 10:00 |  |  | Team
Sponsor Meetings | Meeting With Sponsor Week 5 | 100% | 1.5 | 2009-01-13 10:00 | 2009-01-13 10:00 | 1.5 | 2009-01-13 10:00 | 2009-01-13 10:00 |  |  | Team
Sponsor Meetings | Meeting With Sponsor Week 6 | 100% | 1.5 | 2009-01-20 | 2009-01-20 | 1.5 | 2009-01-20 | 2009-01-20 |  |  | Team
Sponsor Meetings | Meeting With Sponsor Week 7 | 100% | 1.5 | 2009-01-27 | 2009-01-27 | 1.5 | 2009-01-27 | 2009-01-27 |  |  | Team
Sponsor Meetings | Meeting With Sponsor Week 8 | 100% | 1.5 | 2009-02-03 | 2009-02-03 | 1.5 | 2009-02-03 | 2009-02-03 |  |  | Team
Sponsor Meetings | Meeting With Sponsor Week 9 | 100% | 1.5 | 2009-02-10 | 2009-02-10 | 1.5 | 2009-02-10 | 2009-02-10 |  |  | Team
Sponsor Meetings | Meeting With Sponsor Week 12 | 100% | 1.5 | 2009-03-10 09:00 | 2009-03-10 09:00 | 0 | 2009-03-10 09:00 | 2009-03-10 09:00 |  |  | Team
Sponsor Meetings | Meeting With Sponsor Week 13 | 100% | 1.5 | 2009-03-17 09:00 | 2009-03-17 09:00 | 1.5 | 2009-03-17 09:00 | 2009-03-17 09:00 |  |  | Team
Sponsor Meetings | Meeting With Sponsor Week 14 | 100% | 1.5 | 2009-03-24 | 2009-03-24 | 1 | 2009-03-24 | 2009-03-24 |  |  | Team
Sponsor Meetings | Meeting With Sponsor Week 15 | 100% | 1.5 | 2009-03-31 | 2009-03-31 | 0.5 | 2009-03-31 | 2009-03-31 |  |  | Team
Sponsor Meetings | Meeting With Sponsor Week 16 | 100% | 1.5 | 2009-04-07 | 2009-04-07 | 1 | 2009-04-07 | 2009-04-07 |  |  | Team
Sponsor Meetings | Meeting With Sponsor Week 17 | 100% | 1.5 | 2009-04-14 | 2009-04-14 | 1 | 2009-04-14 | 2009-04-14 |  |  | Team
Sponsor Meetings | Meeting With Sponsor Week 18 | 100% | 1.5 | 2009-04-21 | 2009-04-21 | 1 | 2009-04-21 | 2009-04-21 |  |  | Team
Sponsor Meetings | Meeting With Sponsor Week 19 | 100% | 1.5 | 2009-04-28 | 2009-04-28 | 0 | 2009-04-28 | 2009-04-28 |  |  | Team
Sponsor Meetings | Meeting With Sponsor Week 20 | 100% | 1.5 | 2009-05-05 | 2009-05-05 | 1 | 2009-05-05 | 2009-05-05 |  |  | Team
Meeting Minutes | Meeting Minutes Week 1 | 100% | 2 | 2008-12-03 | 2008-12-03 | 2 | 2008-12-03 | 2008-12-03 | Yes |  | Rob
Meeting Minutes | Meeting Minutes Week 2 | 100% | 2 | 2008-12-10 | 2008-12-10 | 2 | 2008-12-10 | 2008-12-10 | Yes |  | Rob
Meeting Minutes | Meeting Minutes Week 3 | 100% | 2 | 2008-12-17 10:00 | 2008-12-17 10:00 | 2 | 2008-12-17 10:00 | 2008-12-17 10:00 | Yes |  | Rob
Meeting Minutes | Meeting Minutes Week 4 | 100% | 2 | 2009-01-07 10:00 | 2009-01-07 10:00 | 2 | 2009-01-07 10:00 | 2009-01-07 10:00 | Yes |  | Rob
Meeting Minutes | Meeting Minutes Week 5 | 100% | 2 | 2009-01-14 10:00 | 2009-01-14 10:00 | 2 | 2009-01-14 10:00 | 2009-01-14 10:00 | Yes |  | Rob
Meeting Minutes | Meeting Minutes Week 6 | 100% | 2 | 2009-01-21 | 2009-01-21 | 2 | 2009-01-21 | 2009-01-21 | Yes |  | Rob
Meeting Minutes | Meeting Minutes Week 7 | 100% | 2 | 2009-01-28 | 2009-01-28 | 2 | 2009-01-28 | 2009-01-28 | Yes |  | Rob
Meeting Minutes | Meeting Minutes Week 8 | 100% | 2 | 2009-02-04 | 2009-02-04 | 2 | 2009-02-04 | 2009-02-04 | Yes |  | Rob
Meeting Minutes | Meeting Minutes Week 9 | 100% | 2 | 2009-02-11 | 2009-02-11 | 2 | 2009-02-11 | 2009-02-11 | Yes |  | Rob
Meeting Minutes | Meeting Minutes Week 12 | 100% | 2 | 2009-03-11 09:00 | 2009-03-11 09:00 | 0 | 2009-03-11 09:00 | 2009-03-11 09:00 | Yes |  | Rob
Meeting Minutes | Meeting Minutes Week 13 | 100% | 2 | 2009-03-18 09:00 | 2009-03-18 09:00 | 1 | 2009-03-18 09:00 | 2009-03-18 09:00 | Yes |  | Rob
Meeting Minutes | Meeting Minutes Week 14 | 100% | 2 | 2009-03-25 | 2009-03-25 | 1 | 2009-03-25 | 2009-03-25 | Yes |  | Rob
Meeting Minutes | Meeting Minutes Week 15 | 100% | 2 | 2009-04-01 | 2009-04-01 | 2 | 2009-04-01 | 2009-04-01 | Yes |  | Rob
Meeting Minutes | Meeting Minutes Week 16 | 100% | 2 | 2009-04-08 | 2009-04-08 | 1 | 2009-04-08 | 2009-04-08 | Yes |  | Rob
Meeting Minutes | Meeting Minutes Week 17 | 100% | 2 | 2009-04-15 | 2009-04-15 | 1 | 2009-04-15 | 2009-04-15 | Yes |  | Rob
Meeting Minutes | Meeting Minutes Week 18 | 100% | 2 | 2009-04-22 | 2009-04-22 | 1 | 2009-04-22 | 2009-04-22 | Yes |  | Rob
Meeting Minutes | Meeting Minutes Week 19 | 100% | 2 | 2009-04-29 | 2009-04-29 | 1 | 2009-04-29 | 2009-04-29 | Yes |  | Rob
Meeting Minutes | Meeting Minutes Week 20 | 100% | 2 | 2009-05-06 | 2009-05-06 | 1 | 2009-05-06 | 2009-05-06 | Yes |  | Rob
Website Upkeep | Website Upkeep Week 1 | 100% | 2 | 2008-12-05 | 2008-12-05 | 2 | 2008-12-05 | 2008-12-05 |  |  | Tom
Website Upkeep | Website Upkeep Week 2 | 100% | 2 | 2008-12-12 | 2008-12-12 | 2 | 2008-12-12 | 2008-12-12 |  |  | Tom
Website Upkeep | Website Upkeep Week 3 | 100% | 2 | 2008-12-19 | 2008-12-19 | 2 | 2008-12-19 | 2008-12-19 |  |  | Tom
Website Upkeep | Website Upkeep Week 4 | 100% | 2 | 2009-01-09 10:00 | 2009-01-09 10:00 | 2 | 2009-01-09 10:00 | 2009-01-09 10:00 |  |  | Tom
Website Upkeep | Website Upkeep Week 5 | 100% | 2 | 2009-01-16 10:00 | 2009-01-16 10:00 | 2 | 2009-01-16 10:00 | 2009-01-16 10:00 |  |  | Tom
Website Upkeep | Website Upkeep Week 6 | 100% | 2 | 2009-01-23 | 2009-01-23 | 2 | 2009-01-23 | 2009-01-23 |  |  | Tom
Website Upkeep | Website Upkeep Week 7 | 100% | 2 | 2009-01-30 | 2009-01-30 | 2 | 2009-01-30 | 2009-01-30 |  |  | Tom
Website Upkeep | Website Upkeep Week 8 | 100% | 2 | 2009-02-06 | 2009-02-06 | 2 | 2009-02-06 | 2009-02-06 |  |  | Tom
Website Upkeep | Website Upkeep Week 9 | 100% | 3 | 2009-02-13 | 2009-02-13 | 2 | 2009-02-13 | 2009-02-13 |  |  | Tom
Website Upkeep | Website Upkeep Week 10 | 100% | 2 | 2009-02-20 | 2009-02-20 | 2 | 2009-02-20 | 2009-02-20 |  |  | Tom
Website Upkeep | Website Upkeep Week 11 | 100% | 2 | 2009-02-27 | 2009-02-27 | 2 | 2009-02-27 | 2009-02-27 |  |  | Tom
Website Upkeep | Website Upkeep Week 12 | 100% | 2 | 2009-03-13 | 2009-03-13 | 2 | 2009-03-13 | 2009-03-13 |  |  | Tom
Website Upkeep | Website Upkeep Week 13 | 100% | 2 | 2009-03-20 | 2009-03-20 | 2 | 2009-03-20 | 2009-03-20 |  |  | Tom
Website Upkeep | Website Upkeep Week 14 | 100% | 2 | 2009-03-27 | 2009-03-27 | 2 | 2009-03-27 | 2009-03-27 |  |  | Tom
Website Upkeep | Website Upkeep Week 15 | 100% | 2 | 2009-04-03 | 2009-04-03 | 2 | 2009-04-03 | 2009-04-03 |  |  | Tom
Website Upkeep | Website Upkeep Week 16 | 100% | 2 | 2009-04-10 | 2009-04-10 | 2 | 2009-04-10 | 2009-04-10 |  |  | Tom
Website Upkeep | Website Upkeep Week 17 | 100% | 2 | 2009-04-17 | 2009-04-17 | 2 | 2009-04-17 | 2009-04-17 |  |  | Tom
Website Upkeep | Website Upkeep Week 18 | 100% | 2 | 2009-04-24 | 2009-04-24 | 2 | 2009-04-24 | 2009-04-24 |  |  | Tom
Website Upkeep | Website Upkeep Week 19 | 100% | 2 | 2009-05-01 | 2009-05-01 | 2 | 2009-05-01 | 2009-05-01 |  |  | Tom
Website Upkeep | Website Upkeep Week 20 | 100% | 2 | 2009-05-08 | 2009-05-08 | 2 | 2009-05-08 | 2009-05-08 |  |  | Tom
Effort Tracking | Effort Tracking Week 1 | 100% | 1 | 2008-12-05 | 2008-12-05 | 1 | 2008-12-05 | 2008-12-05 | Yes |  | Team
Effort Tracking | Effort Tracking Week 2 | 100% | 1 | 2008-12-12 | 2008-12-12 | 1 | 2008-12-12 | 2008-12-12 | Yes |  | Team
Effort Tracking | Effort Tracking Week 3 | 100% | 1 | 2008-12-19 | 2008-12-19 | 1 | 2008-12-19 | 2008-12-19 | Yes |  | Team
Effort Tracking | Effort Tracking Week 4 | 100% | 1 | 2009-01-09 10:00 | 2009-01-09 10:00 | 1 | 2009-01-09 10:00 | 2009-01-09 10:00 | Yes |  | Team
Effort Tracking | Effort Tracking Week 5 | 100% | 1 | 2009-01-16 10:00 | 2009-01-16 10:00 | 1 | 2009-01-16 10:00 | 2009-01-16 10:00 | Yes |  | Team
Effort Tracking | Effort Tracking Week 6 | 100% | 1 | 2009-01-23 | 2009-01-23 | 1 | 2009-01-23 | 2009-01-23 | Yes |  | Team
Effort Tracking | Effort Tracking Week 7 | 100% | 1 | 2009-01-30 | 2009-01-30 | 1 | 2009-01-30 | 2009-01-30 | Yes |  | Team
Effort Tracking | Effort Tracking Week 8 | 100% | 1 | 2009-02-06 | 2009-02-06 | 1 | 2009-02-06 | 2009-02-06 | Yes |  | Team
Effort Tracking | Effort Tracking Week 9 | 100% | 1 | 2009-02-13 | 2009-02-13 | 1 | 2009-02-13 | 2009-02-13 | Yes |  | Team
Effort Tracking | Effort Tracking Week 10 | 100% | 1 | 2009-02-20 | 2009-02-20 | 1 | 2009-02-20 | 2009-02-20 | Yes |  | Team
Effort Tracking | Effort Tracking Week 11 | 100% | 1 | 2009-02-27 | 2009-02-27 | 1 | 2009-02-27 | 2009-02-27 | Yes |  | Team
Effort Tracking | Effort Tracking Week 12 | 100% | 1 | 2009-03-13 | 2009-03-13 | 1 | 2009-03-13 | 2009-03-13 | Yes |  | Team
Effort Tracking | Effort Tracking Week 13 | 100% | 1 | 2009-03-20 | 2009-03-20 | 1 | 2009-03-20 | 2009-03-20 | Yes |  | Team
Effort Tracking | Effort Tracking Week 14 | 100% | 1 | 2009-03-27 | 2009-03-27 | 1 | 2009-03-27 | 2009-03-27 | Yes |  | Team
Effort Tracking | Effort Tracking Week 15 | 100% | 1 | 2009-04-03 | 2009-04-03 |  |  |  | Yes |  | Team
Effort Tracking | Effort Tracking Week 16 | 100% | 1 | 2009-04-10 | 2009-04-10 |  |  |  | Yes |  | Team
Effort Tracking | Effort Tracking Week 17 | 100% | 1 | 2009-04-17 | 2009-04-17 |  |  |  | Yes |  | Team
Effort Tracking | Effort Tracking Week 18 | 100% | 1 | 2009-04-24 | 2009-04-24 |  |  |  | Yes |  | Team
Effort Tracking | Effort Tracking Week 19 | 0% | 1 | 2009-05-01 | 2009-05-01 |  |  |  | Yes |  | Team
Effort Tracking | Effort Tracking Week 20 | 0% | 1 | 2009-05-08 | 2009-05-08 |  |  |  | Yes |  | Team
| Project Plan Document | 100% | 6 | 2008-12-11 | 2008-12-17 | 37 | 2008-12-11 | 2009-01-22 |  |  | Team | 616.7%
Requirements | BRS Document | 100% | 46 | 2009-01-05 11:00 | 2009-01-09 18:00 | 68 | 2009-01-05 11:00 | 2009-01-15 18:00 |  |  | Team | 147.8%
Requirements | Risk Management Document | 100% | 10 | 2009-01-12 11:00 | 2009-01-13 11:00 |  | 2009-01-12 11:00 | 2009-01-13 11:00 |  |  | Team | 0%
Requirements | Risk Management Document Upkeep | 65% | 6 | 2009-01-13 | 2009-05-20 |  | 2009-01-13 |  |  | Risk Management Document | Team | 0%
Requirements | Examine PAETEC Examples | 100% | 20 | 2009-01-09 18:00 | 2009-01-12 11:00 | 4 | 2009-01-09 18:00 | 2009-01-12 11:00 |  |  | Team | 20%
Requirements | SRS Document | 100% | 58 | 2009-01-25 09:00 | 2009-01-31 12:00 | 44 | 2009-01-25 09:00 | 2009-01-31 12:00 |  | Revise BRS | Team | 75.86%
Requirements | UI Prototyping | 100% | 20 | 2009-02-05 09:00 | 2009-02-06 19:00 | 4 | 2009-02-05 09:00 | 2009-02-06 19:00 |  | Revise SRS | Team | 20%
Requirements | Decide on Definition Method | 100% | 3 | 2009-01-29 09:00 | 2009-01-29 12:00 |  | 2009-01-29 09:00 | 2009-01-29 12:00 |  |  | Team | 0%
| Mid Project Presentation: Coordinate With Sponsor | 100% | 1 | 2009-04-16 10:00 | 2009-04-16 11:00 | 2 | 2009-04-16 10:00 | 2009-04-16 11:00 |  |  | Team | 200%
Design | Design Master Definition | 100% | 30 | 2009-02-07 18:00 | 2009-03-06 17:00 | 14 | 2009-02-07 18:00 | 2009-03-13 |  | Requirements | Team | 46.67%
Design | Design UI and Web Architecture | 100% | 20 | 2009-02-07 18:00 | 2009-03-06 17:00 | 12 | 2009-02-07 18:00 | 2009-03-06 17:00 |  | Requirements | Team | 60%
Design | Design Document | 100% | 55 | 2009-02-09 18:00 | 2009-03-06 17:00 | 53 | 2009-02-09 18:00 |  |  | Requirements | Team | 96.36%
Design | Architecture Document | 100% | 20 | 2009-02-10 09:00 | 2009-02-18 10:00 | 10 | 2009-02-10 09:00 | 2009-02-25 |  | Requirements | Team | 50%
Design | Test Plan | 100% | 28 | 2009-03-04 09:00 | 2009-03-06 17:00 | 14 | 2009-03-04 09:00 | 2009-03-15 |  | Requirements | Team | 50%
| Mid Project Presentation: Draft | 100% | 6 | 2009-02-08 09:00 | 2009-02-08 15:00 | 24 | 2009-02-08 09:00 | 2009-02-08 15:00 |  |  | Team | 400%
| Week 10 Deliverables | 100% | 3 | 2009-02-16 09:00 | 2009-02-16 12:00 | 0 | 2009-02-16 09:00 | 2009-02-16 12:00 | Yes |  | Team | 0%
| Mid Project Presentation | 100% | 1 | 2009-02-17 09:00 | 2009-02-17 10:00 | 2 | 2009-02-17 09:00 | 2009-02-17 10:00 | Yes |  | Team | 200%
| Spring Week 1 State of Project | 100% | 3 | 2009-03-14 16:00 | 2009-03-14 19:00 | 2 | 2009-03-14 16:00 | 2009-03-14 19:00 | Yes |  | Team | 66.67%
| Week 11 Reflections | 100% | 4 | 2009-03-14 18:00 | 2009-03-16 13:00 | 2 | 2009-03-14 18:00 | 2009-03-16 13:00 | Yes |  | Team | 50%
Release 1 | Modify Requirements | 100% | 2 | 2009-03-07 16:00 | 2009-03-08 19:00 | 2 | 2009-03-09 | 2009-03-18 |  | Requirements | Team | 100%
Release 1 | Research UI Tools | 100% | 20 | 2009-03-07 08:00 | 2009-04-04 12:59 | 0 |  |  |  |  | Team | 0%
Release 1 | Design modifications | 100% | 6 | 2009-03-16 11:00 | 2009-03-16 17:00 | 8 | 2009-03-17 17:00 |  |  | Design Document | Team | 133.3%
Release 1 | Implementation | 100% | 173 | 2009-03-18 09:00 | 2009-04-03 17:00 | 102 | 2009-03-14 17:00 | 2009-04-04 |  |  | Team | 58.96%
Release 1 | Testing | 100% | 20 | 2009-04-04 09:00 | 2009-04-09 19:00 | 37 | 2009-04-04 |  |  | Implementation | Team | 185%
Release 1 | Bug Fixes | 100% | 20 | 2009-04-06 09:00 | 2009-04-10 19:00 | 10 |  |  |  | Implementation | Team | 50%
Release 1 | Create Source Package | 100% | 2 | 2009-04-11 09:00 | 2009-04-11 13:00 | 3 |  |  |  | Bug Fixes | Team | 150%
Release 1 | Release Notes | 100% | 4 | 2009-04-11 09:00 | 2009-04-11 13:00 | 3 |  |  |  |  | Team | 75%
Release 1 | Deployment Instructions | 100% | 6 | 2009-04-12 13:00 | 2009-04-13 13:00 | 2 |  |  |  | Bug Fixes | Team | 33.33%
Release 2 | Review Previous Release | 100% | 4 | 2009-04-11 12:00 | 2009-04-11 12:10 | 4 |  |  |  |  | Team | 100%
Release 2 | Review Design | 100% | 6 | 2009-04-11 14:10 | 2009-04-11 10:10 | 3 |  |  |  | Design Document | Team | 50%
Release 2 | Modify Requirements/Schedule | 100% | 2 | 2009-04-11 12:10 | 2009-04-11 14:10 | 2 |  |  |  | Requirements | Team | 100%
Release 2 | Implementation | 100% | 70 | 2009-04-12 10:10 | 2009-04-22 15:10 | 59 |  |  |  |  | Team | 84.29%
Release 2 | Testing | 100% | 20 | 2009-04-22 15:10 | 2009-04-25 15:10 | 38 |  |  |  | Implementation | Team | 190%
Release 2 | Bug Fixes | 100% | 10 | 2009-04-25 15:10 | 2009-04-27 15:10 | 45 |  |  |  | Implementation | Team | 450%
Release 2 | Deployment Instructions | 100% | 6 | 2009-04-26 15:10 | 2009-04-27 11:10 | 3 |  |  |  | Bug Fixes | Team | 50%
Release 2 | Create Source Package | 100% | 2 | 2009-04-28 15:10 | 2009-04-30 17:10 | 2 |  |  |  |  | Team | 100%
Release 2 | Release Notes | 100% | 4 | 2009-04-28 11:10 | 2009-04-28 15:10 | 5 |  |  |  | Bug Fixes | Team | 125%
| Project Poster Concept | 100% | 5 | 2009-03-31 16:10 | 2009-04-05 11:10 | 8 | 2009-03-31 | 2009-04-03 |  |  | Rob | 160%
| Preliminary Project Poster | 100% | 15 | 2009-04-05 17:00 | 2009-04-10 10:00 | 15 | 2009-04-05 17:00 | 2009-04-10 10:00 |  |  | Rob | 100%
| Final Poster Design | 100% | 5 | 2009-04-11 17:00 | 2009-04-21 10:00 | 3 | 2009-04-11 17:00 | 2009-04-21 10:00 | Yes |  | Rob | 60%
| Poster Session | 100% | 1 | 2009-05-01 09:10 | 2009-05-01 09:10 | 4 | 2009-05-01 09:10 | 2009-05-01 09:10 | Yes |  | Team | 400%
| Final Presentation: Coordinate With Sponser | 100% | 1 | 2009-04-16 10:00 | 2009-04-16 11:00 | 2 |  |  |  |  | Team | 200%
| Final Presentation Planning | 80% | 12 | 2009-05-01 18:00 | 2009-05-12 18:00 | 8 |  |  |  |  | Team | 66.67%
| Final Presentation | 0% | 2 | 2009-05-12 | 2009-05-12 18:00 | 1 |  |  |  |  | Team | 50%
| Spring Week 10 Post Mortem | 0% | 2 | 2009-05-14 18:00 | 2009-05-15 16:00 | 0 |  |  | Yes |  | Team | 0%
| Technical Report | 90% | 6 | 2009-05-01 18:00 | 2009-05-14 16:00 | 16 |  |  | Yes |  |  | 266.7%
| Spring Week 11 Final Deliverables | 0% | 5 | 2009-05-20 13:00 | 2009-05-20 18:00 | 0 |  |  | Yes |  | Team | 0%
Process Metric Tracking | Process Metrics Tracking 1 | 100% | 1 | 2008-12-05 | 2008-12-05 | 1 | 2008-12-05 | 2008-12-05 |  |  | Team
Process Metric Tracking | Process Metrics Tracking 2 | 100% | 1 | 2008-12-12 | 2008-12-12 | 1 | 2008-12-12 | 2008-12-12 |  |  | Team
Process Metric Tracking | Process Metrics Tracking 3 | 100% | 1 | 2008-12-19 | 2008-12-19 | 1 | 2008-12-19 | 2008-12-19 |  |  | Team
Process Metric Tracking | Process Metrics Tracking 4 | 100% | 1 | 2009-01-09 10:00 | 2009-01-09 10:00 | 1 | 2009-01-09 10:00 | 2009-01-09 10:00 |  |  | Team
Process Metric Tracking | Process Metrics Tracking 5 | 100% | 1 | 2009-01-16 10:00 | 2009-01-16 10:00 | 1 | 2009-01-16 10:00 | 2009-01-16 10:00 |  |  | Team
Process Metric Tracking | Process Metrics Tracking 6 | 100% | 1 | 2009-01-23 | 2009-01-23 | 1 | 2009-01-23 | 2009-01-23 |  |  | Team
Process Metric Tracking | Process Metrics Tracking 7 | 100% | 1 | 2009-01-30 | 2009-01-30 | 1 | 2009-01-30 | 2009-01-30 |  |  | Team
Process Metric Tracking | Process Metrics Tracking 8 | 100% | 1 | 2009-02-06 | 2009-02-06 | 1 | 2009-02-06 | 2009-02-06 |  |  | Team
Process Metric Tracking | Process Metrics Tracking 9 | 100% | 1 | 2009-02-13 | 2009-02-13 | 1 | 2009-02-13 | 2009-02-13 |  |  | Team
Process Metric Tracking | Process Metrics Tracking 10 | 100% | 1 | 2009-02-20 | 2009-02-20 | 1 | 2009-02-20 | 2009-02-20 |  |  | Team
Process Metric Tracking | Process Metrics Tracking 11 | 100% | 1 | 2009-02-27 | 2009-02-27 | 1 | 2009-02-27 | 2009-02-27 |  |  | Team
Process Metric Tracking | Process Metrics Tracking 12 | 100% | 1 | 2009-03-13 | 2009-03-13 | 1 | 2009-03-13 | 2009-03-13 |  |  | Team
Process Metric Tracking | Process Metrics Tracking 13 | 100% | 1 | 2009-03-20 | 2009-03-20 | 1 | 2009-03-20 | 2009-03-20 |  |  | Team
Process Metric Tracking | Process Metrics Tracking 14 | 100% | 1 | 2009-03-27 | 2009-03-27 | 1 | 2009-03-27 | 2009-03-27 |  |  | Team
Process Metric Tracking | Process Metrics Tracking 15 | 100% | 1 | 2009-04-03 | 2009-04-03 | 1 | 2009-04-03 | 2009-04-03 |  |  | Team
Process Metric Tracking | Process Metrics Tracking 16 | 100% | 1 | 2009-04-10 | 2009-04-10 | 1 | 2009-04-10 | 2009-04-10 |  |  | Team
Process Metric Tracking | Process Metrics Tracking 17 | 100% | 1 | 2009-04-17 | 2009-04-17 | 1 | 2009-04-17 | 2009-04-17 |  |  | Team
Process Metric Tracking | Process Metrics Tracking 18 | 100% | 1 | 2009-04-24 | 2009-04-24 | 1 | 2009-04-24 | 2009-04-24 |  |  | Team
Process Metric Tracking | Process Metrics Tracking 19 | 100% | 1 | 2009-05-01 | 2009-05-01 | 1 | 2009-05-01 | 2009-05-01 |  |  | Team
Process Metric Tracking | Process Metrics Tracking 19 | 100% | 1 | 2009-05-08 | 2009-05-08 | 1 | 2009-05-08 | 2009-05-08 |  |  | Team