## Instructions
Your Name: | Joseph Plourde
Instructions
Enter your name above.
At the end of each week:
Under "Accomplished this week"
Make sure planned tasks from last week copied correctly with estimated times
Fill in the actual amount of time spent on each task and indicate whether it is done.
Add any other tasks you worked on this week
Teams seem to relate better to times in hours down to the 1/4 hour, but feel free to use minutes if that has more meaning to you.
Under "Planned for next week"
Enter unfinished tasks from this week that you will continue next week
Enter other planned tasks for next week
Estimate the time you will spend on each task. Estimate your time in minutes or hours down to the 1/4 hour.
Tasks and estimates will copy to next week's accomplished section
Under "Issues"
Enter any unexpected problems you encountered
Enter any issues that require discussion with your team

## Example
First Term - Week 1
Accomplished this week
Done? | ACT | EST | Task
Y | 0.5 |  | Attended expectations talk
Y | 1 |  | Prepared for first meeting with sponsor
Y | 1.75 |  | Met with sponsor
Y | 5.25 |  | Researched webservices
Y | 2 |  | Team meeting to assign initial roles and responsibilities
| 10.5 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Regular team meeting
|  | 2 | Meeting with project sponsor
|  | 1 | Write draft synopsis with Kate
|  | 4 | Look for webservices tutorials and work through them
|  | 2.5 | Work with Adam to make list of requirements questions
|  | 11.5 | TOTAL TIME
Issues
Hard disk on my computer died, had to restore from backup
Team is having trouble finding time to meet together
May need help coding error-handling subsystem

## 1-Wk1
First Term - Week 1
Accomplished this week
Done? | ACT |  | Task
Yes | 2 |  | Meet with Sponsors
Yes | 1 |  | Work on Charter/Synopsis
Yes | 1 |  | Go over project description individually
Yes | 1 |  | Discuss project during 1st half at Group Meeting Thursday
Yes | 1 |  | Discuss project during 1st part at Group Meeting Tuesday
Yes | 2 |  | Proposal review meeting/prep for sponsor meeting before class 1
Yes | 0.5 |  | Attended senior project kickoff
| 8.5 |  | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 3 | Trip to Paetec
|  | 2 | Regular Team Meeting
|  | 1 | Discuss/adjust project synopsis
|  | 1 | Get Approval of synopsis
|  | 1 | Discuss design tasks
|  | 1 | Start Gathering requirements
|  | 2 | Brainstorming
|  | 11 | TOTAL TIME
Issues
Unsure whether it is going to be a Web Application or a Desktop Application
Risks found that not many in group have web application experience

## 1-Wk2
First Term - Week 2
Accomplished this week
Done? | ACT | EST | Task
Yes | 2 | 3 | Trip to Paetec
Yes | 3 | 2 | Regular Team Meeting
Yes | 1 | 1 | Discuss/adjust project synopsis
Yes | 0.15 | 1 | Get Approval of synopsis
Yes | 1 | 1 | Discuss design tasks
No | 0.3 | 1 | Start Gathering requirements
No | 2 | 1 | Brainstorming
Yes | 0.5 |  | Worked on Project Process Diagram (Staged/Incremental Delivery)
No | 1.5 |  | Worked on Project Plan Document
| 11.45 | 10 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1 | Prepare Agenda
|  | 2 | Sponsor meeting
|  | 4 | Gather Requirements
|  | 4 | Work and complete initial revision of SRS and BRS
|  | 1 | Advisor meeting
|  | 2 | Setup VM Server
|  | 14 | TOTAL TIME
Issues

## 1-Wk3
First Term - Week 3
Accomplished this week
Done? | ACT | EST | Task
Yes | 1 | 1 | Prepare Agenda
Yes | 2 | 2 | Sponsor meeting
Yes | 4 | 4 | Gather Requirements
No | 3 | 4 | Work and complete initial revision of SRS and BRS
Yes | 0.5 | 1 | Advisor meeting
No | 0 | 2 | Setup VM Server
Yes | 3 |  | Researched Web Applications
Yes | 2 |  | Worked on Project Plan
Yes | 0.5 |  | Installed Blueprint
No | 5 |  | Looked over GWT and IceFaces
| 21 | 14 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 5 | Continue looking over GWT
|  | 2 | Work on initial revision of SRS (Structure of document)
|  | 10 | Prototype web UI to get a feel of GWT
|  | 17 | TOTAL TIME
Issues

## 1-Wk4
First Term - Week 4
Accomplished this week
Done? | ACT | EST | Task
No | 6 | 5 | Continue looking over GWT
Yes | 2 | 2 | Work on initial revision of SRS (Structure of document)
No | 5 | 10 | Prototype web UI to get a feel of GWT
Yes | 2 | 2 | Inputed Business Requirements in Blueprint
Yes | 6 | 4 | Team Meetings
| 21 | 23 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 3 | Work on BRS initial revision
|  | 1 | Set up requirements in Blue Print
|  | 4 | Team Meeting
|  | 5 | Continue to work with GWT
|  | 13 | TOTAL TIME
Issues

## 1-Wk5
First Term - Week 5
Accomplished this week
Done? | ACT | EST | Task
Yes | 4 | 3 | Work on BRS initial revision
No | 2 | 1 | Set up requirements in Blue Print
Yes | 4 | 4 | Team Meeting
No | 3 | 5 | Continue to work with GWT
| 13 | 13 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1 | Meeting with Stakeholders
|  | 1 | Meeting with Sponsors
|  | 4 | Team meeting
|  | 2 | Setup SVN
|  | 3 | Work on SRS
|  | 5 | Clean up BRS
|  | 3 | Work with GWT
|  | 1 | Plan questions for PAETEC meeting
|  | 20 | TOTAL TIME
Issues

## 1-Wk6
First Term - Week 6
Accomplished this week
Done? | ACT | EST | Task
Yes | 1.5 | 1 | Meeting with Stakeholders
Yes | 0.5 | 1 | Meeting with Sponsors
Yes | 4 | 4 | Team meeting
No | 1.5 | 2 | Setup SVN
No | 0 | 3 | Work on SRS
Yes | 3 | 5 | Clean up BRS
No | 3 | 3 | Work with GWT
Yes | 1 | 1 | Plan questions for PAETEC meeting
| 14.5 | 20 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 8 | Start SRS
|  | 5 | Continue with GWT
|  | 1 | Start Prototyping UI
|  | 1 | Review BRS
|  | 15 | TOTAL TIME
Issues

## 1-Wk7
First Term - Week 7
Accomplished this week
Done? | ACT | EST | Task
| 5 | 8 | Start SRS
| 5 | 5 | Continue with GWT
| 2 | 1 | Start Prototyping UI
| 1 | 1 | Review BRS
| 0.5 | 0.5 | Weekly Status Report
| 2 | 2 | Meeting with Sponsor
| 15.5 | 17.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 4 | Finish Prototyping
|  | 6 | Start work on design
|  | 3 | Start work on Presentation
|  | 3 | Continue to work with GWT
|  | 16 | TOTAL TIME
Issues

## 1-Wk8
First Term - Week 8
Accomplished this week
Done? | ACT | EST | Task
Yes | 3 | 4 | Finish Prototyping
No | 8 | 6 | Start work on design
No | 1 | 3 | Start work on Presentation
No | 4 | 3 | Continue to work with GWT
Yes | 2 | 0 | Revise RS
Yes | 2 |  | Worked on Conditional Attributes
| 20 | 16 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 4 | Finish Design
|  | 2 | Complete RS
|  | 2 | Sponsor Meeting @ Paetec
|  | 3 | GWT
|  | 11 | TOTAL TIME
Issues

## 1-Wk9
First Term - Week 9
Accomplished this week
Done? | ACT | EST | Task
No | 7 | 4 | Finish Design
Yes | 2 | 2 | Complete RS
Yes | 2 | 2 | Sponsor Meeting @ Paetec
No | 2 | 3 | GWT
No | 5 |  | Presentation
| 18 | 11 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 4 | Finish Archiecture Document Revision 1
|  | 5 | Finish Initial Design Doc
|  | 0.5 | Give Presentation
|  | 2 | GWT
|  | 11.5 | TOTAL TIME
Issues

## 1-Wk10
First Term - Week 10
Accomplished this week
Done? | ACT | EST | Task
No | 4 | 4 | Finish Archiecture Document Revision 1
No | 3 | 5 | Finish Initial Design Doc
Yes | 0.5 | 0.5 | Give Presentation
No | 2 | 2 | GWT
Yes | 1 |  | Team self assessment
| 10.5 | 11.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 3 | Start Design Doc
|  | 3 | Finish Architecture Doc
|  | 4 | Start Test Doc
|  | 10 | TOTAL TIME
Issues

## 1-Finals
First Term - Finals Week
Accomplished this week
Done? | ACT | EST | Task
No | 2 | 3 | Start Design Doc
Yes | 5 | 3 | Finish Architecture Doc
No | 0 | 4 | Start Test Doc
Yes | 3 | 0 | Team Meeting/Post Mortem
| 10 | 10 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 7 | Finish Design
|  | 9 | Start Implementation
|  | 16 | TOTAL TIME
Issues

## 2-Wk1
Second Term - Week 1
Accomplished this week
Done? | ACT | EST | Task
Yes | 10 | 7 | Finish Design
No | 2 | 9 | Start Implementation
Yes | 1 | 0 | Setup configuration for implementation
Yes | 4 | 0 | Team Meeting
| 17 | 16 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 15 | Implementation
|  | 2 | Revise Design Doc
|  | 2 | Revise Test Plan
|  | 4 | Team Meeting
|  | 23 | TOTAL TIME
Issues

## 2-Wk2
Second Term - Week 2
Accomplished this week
Done? | ACT | EST | Task
No | 10 | 15 | Implementation
Yes | 2 | 2 | Revise Design Doc
No | 1 | 2 | Revise Test Plan
Yes | 4 | 4 | Team Meeting
Yes | 0.5 | 0 | Schedule
| 17.5 | 23 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 20 | Implementation
|  | 5 | Testing
|  | 25 | TOTAL TIME
Issues

## 2-Wk3
Second Term - Week 3
Accomplished this week
Done? | ACT | EST | Task
No | 23 | 20 | Implementation
NO | 2 | 5 | Testing
| 25 | 25 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 20 | Implementation of UI screens (Product Screen and so on like that. Main Screen, Connection to Server)
|  | 10 | Testing
|  | 30 | TOTAL TIME
Issues

## 2-Wk4
Second Term - Week 4
Accomplished this week
Done? | ACT | EST | Task
No | 33 | 20 | Implementation of UI screens (Product Screen and so on like that. Main Screen, Connection to Server)
No | 2 | 10 | Testing
| 35 | 30 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 5 | Testing of UI for release 1
|  | 10 | Work on Bug Fixes
|  | 15 | TOTAL TIME
Issues

## 2-Wk5
Second Term - Week 5
Accomplished this week
Done? | ACT | EST | Task
Yes | 5 | 5 | Testing of UI for release 1
Yes | 9 | 10 | Work on Bug Fixes
| 14 | 15 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 20 | Release 2 Implementation (Fixing UI functionality in all screens and cleaning up)
|  | 20 | TOTAL TIME
Issues

## 2-Wk6
Second Term - Week 6
Accomplished this week
Done? | ACT | EST | Task
No | 13 | 20 | Release 2 Implementation (Fixing UI functionality in all screens and cleaning up)
No | 2 |  | Testing
| 15 | 20 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 20 | Implementation (Remaining Screen, odds and ends)
|  | 5 | Testing
|  | 25 | TOTAL TIME
Issues

## 2-Wk7
Second Term - Week 7
Accomplished this week
Done? | ACT | EST | Task
No | 27 | 20 | Implementation (Remaining Screen, odds and ends)
No | 5 | 5 | Testing
| 32 | 25 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 5 | Clean up implementation of all screens.
|  | 15 | Fix bugs related to Adding Products to products, locking and so on
|  | 4 | Test fixes
|  | 24 | TOTAL TIME
Issues

## 2-Wk8
Second Term - Week 8
Accomplished this week
Done? | ACT | EST | Task
No | 2 | 5 | Clean up implementation of all screens.
Yes | 10 | 15 | Fix bugs related to Adding Products to products, locking and so on
No | 1 | 4 | Test fixes
Yes | 2 |  | Deployment
| 15 | 24 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 3 | Clean up UI screens (fix buttons and so on)
|  | 5 | Fix Conditional Errors
|  | 2 | Work on Tech Report
|  | 2 | Clean up UI code
|  | 8 | Implement and Test additional Fixes for bugs found
|  | 20 | TOTAL TIME
Issues

## 2-Wk9
Second Term - Week 9
Accomplished this week
Done? | ACT | EST | Task
No | 5 | 3 | Clean up UI screens (fix buttons and so on)
Yes | 4 | 5 | Fix Conditional Errors
Yes | 1 | 2 | Work on Tech Report
No | 1 | 2 | Clean up UI code
No | 5 | 8 | Implement and Test additional Fixes for bugs found
| 16 | 20 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 4 | Finish any last fixes
|  | 3 | touch up documentation
|  | 2 | prepare for presentation
|  | 2 | Final draft of release notes
|  | 1 | Final draft of tech report
|  | 1 | Post-Mortem questions
|  | 13 | TOTAL TIME
Issues

## 2-Wk10
Second Term - Week 10
Accomplished this week
Done? | ACT | EST | Task
| 20 | 4 | Finish any last fixes
| 0 | 3 | touch up documentation
| 1 | 2 | prepare for presentation
| 0.5 | 2 | Final draft of release notes
| 0 | 1 | Final draft of tech report
| 0 | 1 | Post-Mortem questions
| 21.5 | 13 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1 | Package every artifact for project onto a DVD
|  | 3 | Touch up documentation
|  | 4 | Create How to Use
|  | 2 | Post-Mortem
|  | 10 | TOTAL TIME
Issues

## 2-Finals
Second Term - Finals Week
Accomplished this week
Done? | ACT | EST | Task
|  | 1 | Package every artifact for project onto a DVD
|  | 3 | Touch up documentation
|  | 4 | Create How to Use
|  | 2 | Post-Mortem
| 0 | 10 | TOTAL TIME
Issues

## AllData
t1-1a | t1-2e | t1-2a | t1-3e | t1-3a | t1-4e | t1-4a | t1-5e | t1-5a | t1-6e | t1-6a | t1-7e | t1-7a | t1-8e | t1-8a | t1-9e | t1-9a | t1-10e | t1-10a | wt1-fe | t1-fa
8.5 | 10 | 11.45 | 14 | 21 | 23 | 21 | 13 | 13 | 20 | 14.5 | 17.5 | 15.5 | 16 | 20 | 11 | 18 | 11.5 | 10.5 | 10 | 10
t2-1e | t2-1a | t2-2e | t2-2a | t2-3e | t2-3a | t2-4e | t2-4a | t2-5e | t2-5a | t2-6e | t2-6a | t2-7e | t2-7a | t2-8e | t2-8a | t2-9e | t2-9a | t2-10e | t2-10a | t2-fe | t2-fa
16 | 17 | 23 | 17.5 | 25 | 25 | 30 | 35 | 15 | 14 | 20 | 15 | 25 | 32 | 24 | 15 | 20 | 16 | 13 | 21.5 | 10 | 0