## Instructions
Your Name: | Phillip Schmitte
Instructions
Enter your name above.
At the end of each week:
Under "Accomplished this week"
Make sure planned tasks from last week copied correctly with estimated times
Fill in the actual amount of time spent on each task and indicate whether it is done.
Add any other tasks you worked on this week
Teams seem to relate better to times in hours down to the 1/4 hour, but feel free to use minutes if that has more meaning to you.
Under "Planned for next week"
Enter unfinished tasks from this week that you will continue next week
Enter other planned tasks for next week
Estimate the time you will spend on each task. Estimate your time in minutes or hours down to the 1/4 hour.
Tasks and estimates will copy to next week's accomplished section
Under "Issues"
Enter any unexpected problems you encountered
Enter any issues that require discussion with your team

## Example
First Term - Week 1
Accomplished this week
Done? | ACT | EST | Task
Y | 0.5 |  | Attended expectations talk
Y | 1 |  | Prepared for first meeting with sponsor
Y | 1.75 |  | Met with sponsor
Y | 5.25 |  | Researched webservices
Y | 2 |  | Team meeting to assign initial roles and responsibilities
| 10.5 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Regular team meeting
|  | 2 | Meeting with project sponsor
|  | 1 | Write draft synopsis with Kate
|  | 4 | Look for webservices tutorials and work through them
|  | 2.5 | Work with Adam to make list of requirements questions
|  | 11.5 | TOTAL TIME
Issues
Hard disk on my computer died, had to restore from backup
Team is having trouble finding time to meet together
May need help coding error-handling subsystem

## 1-Wk1
First Term - Week 1
Accomplished this week
Done? | ACT |  | Task
Y | 2 |  | Preparation for sponsor meeting
Y | 0.5 |  | Orientation presentation
Y | 1 |  | Sponsor meeting
Y | 0.5 |  | Advisor meeting
Y | 2 |  | Project Charter
Y | 1 |  | Formatting meeting notes
| 7 |  | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Prepare Agenda
|  | 3 | Sponsor meeting, out to PAETEC
|  | 6 | Work requirements / project plan
|  | 2 | Advisor meeting
|  | 13 | TOTAL TIME
Issues
Decide if system will be web-based
NDA still needs to be signed

## 1-Wk2
First Term - Week 2
Accomplished this week
Done? | ACT | EST | Task
Y | 2 | 2 | Prepare Agenda
Y | 3 | 3 | Sponsor meeting, out to PAETEC
Y | 3 | 6 | Work requirements / project plan
Y | 2 | 2 | Advisor meeting
| 10 | 13 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Prepare Agenda
|  | 2 | Sponsor meeting
|  | 3 | Requirements
|  | 3 | Documentation (BRS, SRS)
|  | 2 | Advisor meeting
|  | 12 | TOTAL TIME
Issues
Still need to set up Blueprint
Decision on web vs. desktop app

## 1-Wk3
First Term - Week 3
Accomplished this week
Done? | ACT | EST | Task
Y | 2 | 2 | Prepare Agenda
Y | 2 | 2 | Sponsor meeting
Y | 2 | 3 | Requirements
N | 0 | 3 | Documentation (BRS, SRS)
Y | 0 | 2 | Advisor meeting
Y | 6 | 4 | Schedule Work
Y | 2 | 2 | Team Building Dinner
| 14 | 18 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 3 | Revise Project Plan
|  | 8 | Design Documentation
|  | 1 | Prepare Agenda
|  | 2 | Sponsor Meeting
|  | 4 | Requirements Documentation (BRS, SRS)
|  | 18 | TOTAL TIME
Issues
What definition method? XML or SQL
What web tools will we use?

## 1-Wk4
First Term - Week 4
Accomplished this week
Done? | ACT | EST | Task
Y | 8 | 3 | Revise Project Plan
N | 0 | 8 | Design Documentation
Y | 1 | 1 | Prepare Agenda
Y | 2 | 2 | Sponsor Meeting
N | 2 | 4 | Requirements Documentation (BRS, SRS)
N | 2 |  | Revise Schedule
| 15 | 18 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1 | Prepare Agenda
|  | 2 | Sponsor Meeting
|  | 6 | Work on BRS and SRS
|  | 4 | Revise Schedule
|  | 4 | Review definition examples
|  | 17 | TOTAL TIME
Issues
Will we have time for stage 3?
Who do we need to meet with for requirements?

## 1-Wk5
First Term - Week 5
Accomplished this week
Done? | ACT | EST | Task
Y | 1 | 1 | Prepare Agenda
Y | 2 | 2 | Sponsor Meeting
N | 6 | 6 | Work on BRS and SRS
Y | 1 | 4 | Revise Schedule
N | 2 | 4 | Review definition examples
Y | 2 |  | Work on Project Plan
Y | 1 |  | Stakeholder meeting agenda
| 15 | 17 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1 | Prepare Agenda
|  | 2 | Stakeholder Meeting
|  | 8 | Work on BRS and SRS
|  | 3 | Design master definition
|  | 14 | TOTAL TIME
Issues
Do attributes contain min/max info? Or are min/maxes attributes themselves?
What questions do we need to ask stakeholders?

## 1-Wk6
First Term - Week 6
Accomplished this week
Done? | ACT | EST | Task
Y | 1 | 1 | Prepare Agenda
Y | 2 | 2 | Stakeholder Meeting
N | 8 | 8 | Work on BRS and SRS
N | 2 | 3 | Design master definition
| 13 | 14 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1 | Prepare Agenda
|  | 2 | Stakeholder Meeting
|  | 2 | Work on BRS
|  | 6 | Work on SRS
|  | 2 | Design master definition
|  | 2 | UI Prototype
|  | 15 | TOTAL TIME
Issues
What other stakeholders do we need to meet with?

## 1-Wk7
First Term - Week 7
Accomplished this week
Done? | ACT | EST | Task
Y | 1 | 1 | Prepare Agenda
Y | 2 | 2 | Stakeholder Meeting
N | 2 | 2 | Work on BRS
N | 6 | 6 | Work on SRS
N | 0 | 2 | Design master definition
N | 0 | 2 | UI Prototype
N |  | 1 | Work on process metrics
| 11 | 16 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1 | Prepare Agenda
|  | 2 | Stakeholder Meeting
|  | 4 | Work on requirements
|  | 3 | Design master definition
|  | 3 | UI Prototype
|  | 2 | Process metrics
|  | 15 | TOTAL TIME
Issues
What are we going to put in our presentation?
How are conditionals going to work?
What do we need done for our next PAETEC trip?

## 1-Wk8
First Term - Week 8
Accomplished this week
Done? | ACT | EST | Task
Y | 1 | 1 | Prepare Agenda
Y | 2 | 2 | Stakeholder Meeting
N | 4 | 4 | Work on requirements
N | 3 | 3 | Design master definition
N | 1 | 3 | UI Prototype
N | 0 | 2 | Process metrics
N | 1 |  | Architecture Document
N | 1 |  | Design Document
| 13 | 15 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1 | Prepare Agenda
|  | 2 | Stakeholder Meeting
|  | 5 | Architecture Document
|  | 2 | Process Metrics
|  | 3 | Presentation work
|  | 1 | UI Prototype
|  | 14 | TOTAL TIME
Issues
Still need to set date for post mortem

## 1-Wk9
First Term - Week 9
Accomplished this week
Done? | ACT | EST | Task
Y | 1 | 1 | Prepare Agenda
Y | 2 | 2 | Stakeholder Meeting
N | 6 | 5 | Architecture Document
N | 2 | 2 | Process Metrics
N | 4 | 3 | Presentation work
N | 0 | 1 | UI Prototype
| 15 | 14 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 3.5 | Presentation week
|  | 0.5 | Midterm presentation
|  | 4 | Prepare presentation
|  | 4 | Architecture document
|  | 2 | Design document
|  | 4 | Prepare for post mortem
|  | 18 | TOTAL TIME
Issues
Still need to set a date for post mortem
Need to set up our development environment

## 1-Wk10
First Term - Week 10
Accomplished this week
Done? | ACT | EST | Task
Y | 3.5 | 3.5 | Presentation week
Y | 0.5 | 0.5 | Midterm presentation
Y | 5 | 4 | Prepare presentation
N | 0 | 4 | Architecture document
N | 0 | 2 | Design document
Y | 3 | 4 | Prepare for post mortem
| 12 | 18 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 4 | Architecture Document
|  | 4 | Design Document
|  | 4 | XML Schema
|  | 12 | TOTAL TIME
Issues
What day are we going to PAETEC?

## 1-Finals
First Term - Finals Week
Accomplished this week
Done? | ACT | EST | Task
Y | 0 | 4 | Architecture Document
N | 0 | 4 | Design Document
N | 0 | 4 | XML Schema
Y | 3 |  | Working on self assessment
Y | 2 |  | Mid-Project reflection meeting
| 5 | 12 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 10 | Design Document
|  | 4 | Test Plan
|  | 2 | Start Stage 1
|  | 1 | Prepare Agenda
|  | 2 | Sponsor Meeting
|  | 19 | TOTAL TIME
Issues
Where do we stand in our schedule?
How are we going to speed up our project?

## 2-Wk1
Second Term - Week 1
Accomplished this week
Done? | ACT | EST | Task
N | 8 | 10 | Design Document
N | 0 | 4 | Test Plan
N | 3 | 2 | Start Stage 1
Y | 1 | 1 | Prepare Agenda
N | 0 | 2 | Sponsor Meeting
N | 1 |  | Work on Schemas
| 13 | 19 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1 | Prepare Agenda
|  | 2 | Sponsor Meeting
|  | 3 | Set up development environment
|  | 5 | Implement definition subsystem
|  | 2 | Test plan
|  | 13 | TOTAL TIME
Issues
What are we going to talk about at presentation at PAETEC?
Where do we stand with our schedule?

## 2-Wk2
Second Term - Week 2
Accomplished this week
Done? | ACT | EST | Task
Y | 1 | 1 | Prepare Agenda
Y | 2 | 2 | Sponsor Meeting
N | 3 | 3 | Set up development environment
N | 7 | 5 | Implement definition subsystem
Y | 0 | 2 | Test plan
Y | 2 |  | Design document
N | 1 |  | Schedule work
| 16 | 13 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1 | Prepare Agenda
|  | 2 | Sponsor Meeting
|  | 6 | Implement definition subsystem
|  | 2 | Revise Design document
|  | 4 | Work on presentation
|  | 1 | PAETEC presentation
|  | 16 | TOTAL TIME
Issues
How are our process changes affecting our release content?

## 2-Wk3
Second Term - Week 3
Accomplished this week
Done? | ACT | EST | Task
Y | 0 | 1 | Prepare Agenda
Y | 2 | 2 | Sponsor Meeting
N | 6 | 6 | Implement definition subsystem
Y | 1 | 2 | Revise Design document
Y | 3 | 4 | Work on presentation
Y | 2 | 1 | PAETEC presentation
| 14 | 16 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1 | Prepare Agenda
|  | 1 | Sponsor Meeting
|  | 1 | Poster Session
|  | 10 | Implement definition subsystem
|  | 2 | Work on poster
|  | 15 | TOTAL TIME
Issues
What UI screens are available in release1 ?

## 2-Wk4
Second Term - Week 4
Accomplished this week
Done? | ACT | EST | Task
Y | 1 | 1 | Prepare Agenda
Y | 0.5 | 1 | Sponsor Meeting
Y | 0.5 | 1 | Poster Session
N | 15 | 10 | Implement definition subsystem
N | 0.5 | 2 | Work on poster
| 17.5 | 15 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1 | Prepare Agenda
|  | 1 | Sponsor Meeting
|  | 2 | Work on poster
|  | 5 | Integration
|  | 5 | Testing
|  | 5 | Debugging
|  | 19 | TOTAL TIME
Issues

## 2-Wk5
Second Term - Week 5
Accomplished this week
Done? | ACT | EST | Task
Y | 1 | 1 | Prepare Agenda
Y | 1 | 1 | Sponsor Meeting
N | 1 | 2 | Work on poster
Y | 6 | 5 | Integration
N | 6 | 5 | Testing
N | 3 | 5 | Debugging
| 18 | 19 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1 | Prepare Agenda
|  | 2 | Sponsor Meeting
|  | 1 | Poster work
|  | 4 | Junit
|  | 4 | Acceptence testing
|  | 4 | Debugging
|  | 5 | Prepare release
|  | 21 | TOTAL TIME
Issues

## 2-Wk6
Second Term - Week 6
Accomplished this week
Done? | ACT | EST | Task
Y | 1 | 1 | Prepare Agenda
Y | 2 | 2 | Sponsor Meeting
N | 0 | 1 | Poster work
N | 4 | 4 | Junit
N | 1 | 4 | Acceptence testing
N | 2 | 4 | Debugging
Y | 4 | 5 | Prepare release
| 14 | 21 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1 | Prepare Agenda
|  | 2 | Sponsor Meeting
|  | 6 | Implement EntityManager subsystem (R2)
|  | 3 | Junit
|  | 2 | Testing
|  | 3 | Debugging
|  | 17 | TOTAL TIME
Issues

## 2-Wk7
Second Term - Week 7
Accomplished this week
Done? | ACT | EST | Task
Y | 1 | 1 | Prepare Agenda
Y | 2 | 2 | Sponsor Meeting
N | 6 | 6 | Implement EntityManager subsystem (R2)
N | 2 | 3 | Junit
N | 2 | 2 | Testing
N | 2 | 3 | Debugging
| 15 | 17 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1 | Prepare Agenda
|  | 2 | Sponsor Meeting
|  | 1 | Junit
|  | 4 | Testing
|  | 4 | Debugging
|  | 1 | Technical Report
|  | 2 | Presentation
|  | 15 | TOTAL TIME
Issues

## 2-Wk8
Second Term - Week 8
Accomplished this week
Done? | ACT | EST | Task
Y | 1 | 1 | Prepare Agenda
Y | 1 | 2 | Sponsor Meeting
Y | 3 | 1 | Junit
N | 2 | 4 | Testing
N | 4 | 4 | Debugging
N | 0 | 1 | Technical Report
N | 1 | 2 | Presentation
Y | 2 |  | Poster Presentation
| 14 | 15 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1 | Prepare Agenda
|  | 2 | Sponsor Meeting
|  | 3 | Testing
|  | 3 | Debugging
|  | 2 | Prepare Final Release
|  | 1 | Technical Report
|  | 2 | Presentation
|  | 14 | TOTAL TIME
Issues

## 2-Wk9
Second Term - Week 9
Accomplished this week
Done? | ACT | EST | Task
Y | 1 | 1 | Prepare Agenda
Y | 2 | 2 | Sponsor Meeting
N | 2 | 3 | Testing
N | 8 | 3 | Debugging
N | 0 | 2 | Prepare Final Release
N | 0 | 1 | Technical Report
N | 0 | 2 | Presentation
| 13 | 14 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 4 | Testing
|  | 4 | Debugging
|  | 2 | Prepare Final Release
|  | 2 | Technical Report
|  | 12 | TOTAL TIME
Issues

## 2-Wk10
Second Term - Week 10
Accomplished this week
Done? | ACT | EST | Task
N | 3 | 4 | Testing
N | 3 | 4 | Debugging
N | 0 | 2 | Prepare Final Release
N | 0 | 2 | Technical Report
Y | 4 |  | Presentations
| 10 | 12 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 3 | Debugging
|  | 2 | Prepare Final Release
|  | 2 | Prepare for Post Mortem
|  | 1 | Post Mortem
|  | 8 | TOTAL TIME
Issues

## 2-Finals
Second Term - Finals Week
Accomplished this week
Done? | ACT | EST | Task
|  | 3 | Debugging
|  | 2 | Prepare Final Release
|  | 2 | Prepare for Post Mortem
|  | 1 | Post Mortem
| 0 | 8 | TOTAL TIME
Issues

## AllData
t1-1a | t1-2e | t1-2a | t1-3e | t1-3a | t1-4e | t1-4a | t1-5e | t1-5a | t1-6e | t1-6a | t1-7e | t1-7a | t1-8e | t1-8a | t1-9e | t1-9a | t1-10e | t1-10a | wt1-fe | t1-fa
7 | 13 | 10 | 18 | 14 | 18 | 15 | 17 | 15 | 14 | 13 | 16 | 11 | 15 | 13 | 14 | 15 | 18 | 12 | 12 | 5
t2-1e | t2-1a | t2-2e | t2-2a | t2-3e | t2-3a | t2-4e | t2-4a | t2-5e | t2-5a | t2-6e | t2-6a | t2-7e | t2-7a | t2-8e | t2-8a | t2-9e | t2-9a | t2-10e | t2-10a | t2-fe | t2-fa
19 | 13 | 13 | 16 | 16 | 14 | 15 | 17.5 | 19 | 18 | 21 | 14 | 17 | 15 | 15 | 14 | 14 | 13 | 12 | 10 | 8 | 0