## Activities
Summer Quarter |  |  |  |  | Fall Quarter
Week 1 |  |  |  |  | Week 1
Activities |  |  | Estimated | Actual | Activities |  |  | Estimated | Actual
Tuesday Meeting |  |  | 2 | 2 | Monday Meeting |  |  | 2 | 2
Thursday Meeting |  |  | 2 | 2 | Wednesday Meeting |  |  | 2 | 2
Connect with project sponsor |  |  | 1 | 1 | Determine Current Progress and create schedule |  |  | 1 | 3
|  | Totals: | 5 | 5 |  |  | Totals: | 5 | 7
Week 2 |  |  |  |  | Week 2
Activities |  |  | Estimated | Actual | Activities |  |  | Estimated | Actual
Tuesday Meeting |  |  | 2 | 2 | Monday Meeting |  |  | 2 | 2
Assist redmine installation |  |  | 0 | 0.5 | Wednesday Meeting |  |  | 2 | 2
Thursday Meeting |  |  | 2 | 2.25 | Phasing |  |  | 3 | 4.5
Set-up eclipse with android SDK |  |  | 1 | 0.75 | Install PHP Server locally |  |  | 1 | 2
Research Metrics |  |  | 2 | 1.5
Jitters meeting |  |  | 2 | 2
|  | Totals: | 9 | 9 |  |  | Totals: | 8 | 10.5
Week 3 |  |  |  |  | Week 3
Activities |  |  | Estimated | Actual | Activities |  |  | Estimated | Actual
Tuesday Meeting |  |  | 2 | 2 | Monday Meeting |  |  | 2 | 2
Review SRS |  |  | 0.5 | 0.5 | Wednesday Meeting |  |  | 2 | 2
Thursday Meeting |  |  | 2 | 2 | Test Phasing |  |  | 2 | 3
Setup Eclipse |  |  | 0.5 | 0.25 | Fix Timezone issues on Server |  |  | 4 | 3.5
Review Risks |  |  | 0.5 | 0.5 | Fix phasing with server |  |  | 2 | 4.2
|  | Totals: | 5.5 | 5.25 |  |  | Totals: | 12 | 14.7
Week 4 |  |  |  |  | Week 4
Activities |  |  | Estimated | Actual | Activities |  |  | Estimated | Actual
Meetings |  |  | 7 | 7 | Monday Meeting |  |  | 2
Create database connection manager |  |  | 2 | 1 | Wednesday Meeting |  |  | 2
Create connection pooling for database |  |  | 1 | 1.5 | Fix Voting limit with server |  |  | 3
Create basic properties reader implementation |  |  | 2 | 1.75 | Test changes made with server |  |  | 3
Create initial FacetsServer project stub |  |  | 0.5 | 0.6
|  | Totals: | 12.5 | 11.85 |  |  | Totals: | 10 | 0
Week 5 |  |  |  |  | Week 5
Activities |  |  | Estimated | Actual | Activities |  |  | Estimated | Actual
Meetings |  |  | 6 | 6 | Group Meeting |  |  | 4 | 4
Finish properties reader and define properties list |  |  | 3 | 2 | Help test brainstorm |  |  | 3 | 4.5
Fix LDAP code |  |  | 2 | 3
Create LDAP authentication test website |  |  | 1 | 1
Unit tests for Session Manager |  |  | 2 | 3
|  | Totals: | 14 | 15 |  |  | Totals: | 7 | 8.5
Week 6 |  |  |  |  | Week 6
Activities |  |  | Estimated | Actual | Activities |  |  | Estimated | Actual
Regular Meetings |  |  | 4 | 4 | Group Meeting |  |  | 4 | 4
Session Management meetings |  |  | 4 | 4 | Prepare acceptance test material |  |  | 2 | 2
Implement Servlet front end / testing framework for idea generation |  |  | 2 | 1.5 | Review previous documents |  |  | 2.5 | 4
Implement adding new ideas to database |  |  | 3 | 2.5
Implement retrieving all previous ideas from the database |  |  | 2 | 3.3
Create facets common |  |  | 0.5 | 0.7
|  | Totals: | 15.5 | 16 |  |  | Totals: | 8.5 | 10
Week 7 |  |  |  |  | Week 7
Activities |  |  | Estimated | Actual | Activities |  |  | Estimated | Actual
Session Management meeting |  |  | 4 | 4 | Test server fixes |  |  | 2 | 1.1
Group Meetings |  |  | 4 | 6 | Create test document |  |  | 3 | 2.7
Implement back end for grouping |  |  | 5 | 6 | Create bug tracker |  |  | 3 | 1.5
Implement flagging for client / server |  |  | 2 | 3 | Group Meeting |  |  | 4 | 4
Implement encryption for user passwords |  |  | 2 | 1
Improve list gathering speed |  |  | 2 | 2
|  | Totals: | 19 | 22 |  |  | Totals: | 12 | 9.3
Week 8 |  |  |  |  | Week 8
Activities |  |  | Estimated | Actual | Activities |  |  | Estimated | Actual
Session Management meeting |  |  | 4 | 4 | Create readme for Sponsor for server install |  |  | 4 | 5
Group Meetings |  |  | 4 | 7 | Test server install |  |  | 1 | 1
Work on unflagging for moderators |  |  | 1 | 0.6 | Group Meeting |  |  | 4 | 4
Add support for more grouping queries |  |  | 2 | 2.3
Start testing |  |  | 4 | 6
|  | Totals: | 15 | 19.9 |  |  | Totals: | 9 | 10
Week 9 |  |  |  |  | Week 9
Activities |  |  | Estimated | Actual | Activities |  |  | Estimated | Actual
Session Management meeting |  |  | 4 | 4 | Bug Fixing |  |  | 2 | 2
Group Meetings |  |  | 4 | 6 | Look into memory management problem |  |  | 4 | 5
Fix results page |  |  | 2 | 2.7 | Create build script |  |  | 5 | 5
Testing |  |  | 10 | 10 | Group Meeting |  |  | 4 | 4
Get ready for presentation |  |  | 2 | 3
|  | Totals: | 22 | 25.7 |  |  | Totals: | 15 | 16
Week 10 |  |  |  |  | Week 10
Activities |  |  | Estimated | Actual | Activities |  |  | Estimated | Actual
Group Meetings |  |  | 4 |  | Presentation |  |  | 2 | 1
Presentation |  |  | 2 |  | Group Meetings |  |  | 4 | 5
|  | Totals: | 6 | 0 |  |  | Totals: | 6 | 6
| Summer Quarter Totals: |  | 123.5 | 129.7 |  | Summer Quarter Totals: |  | 92.5 | 92
[6 empty] | Two Quarter Total: |  | 216 | 221.7