## Activities
Summer Quarter |  |  |  |  | Fall Quarter
Week 1 |  |  |  |  | Week 1
Activities |  |  | Estimated | Actual | Activities |  |  | Estimated | Actual
Meet With Team |  |  | 4 | 4 | Monday Lab Time / Meeting |  |  | 3 | 3
Research FACETs and EDGE system |  |  | 1 | 1 | Wednesday Lab Time / Meeting |  |  | 3 | 3
Set up Android SDK |  |  | 1 | 1 | Refactoring Servlet Adapter |  |  | 2 | 1
|  | Totals: | 6 | 6 |  |  | Totals: | 8 | 7
Week 2 |  |  |  |  | Week 2
Activities |  |  | Estimated | Actual | Activities |  |  | Estimated | Actual
Meet With Team |  |  | 4 | 4 | Monday Lab Time / Meeting |  |  | 3 | 3
Research feasibility of "new items" in ListActivity |  |  | 0.5 | 1.5 | Wednesday Lab Time / Meeting |  |  | 3 | 3
Team Meeting @ Jitters |  |  | 2 | 2 | Sunday Meeting |  |  | 1.5 | 1
[5 empty] | Finished refactoring Servlet Adapter |  |  | 3 | 1
|  | Totals: | 6.5 | 7.5 |  |  | Totals: | 10.5 | 8
Week 3 |  |  |  |  | Week 3
Activities |  |  | Estimated | Actual | Activities |  |  | Estimated | Actual
Meet With Team |  |  | 4 | 4 | Monday Lab Time / Meeting |  |  | 3 | 3
Package and Submit Usability Project to Redmine |  |  | 0.5 | 0.25 | Wednesday Lab Time / Meeting |  |  | 3 | 3
Work on Project Plan Document |  |  | 5 | 5.5
Work on Story Points for Brainstorm Tool |  |  | 2 | 2
|  | Totals: | 11.5 | 11.75 |  |  | Totals: | 6 | 6
Week 4 |  |  |  |  | Week 4
Activities |  |  | Estimated | Actual | Activities |  |  | Estimated | Actual
Meet With Team |  |  | 8.5 | 7.75 | Monday Lab Time / Meeting |  |  | 3 | 3
Set up Android Project in Eclipse |  |  | 1 | 2 | Wednesday Lab Time / Meeting |  |  | 3 | 3
[5 empty] | Sunday Meeting |  |  | 1.5 | 1
[5 empty] | Preparing for acceptance testing |  |  | 1 | 1
|  | Totals: | 9.5 | 9.75 |  |  | Totals: | 8.5 | 8
Week 5 |  |  |  |  | Week 5
Activities |  |  | Estimated | Actual | Activities |  |  | Estimated | Actual
Meet With Team |  |  | 6 | 6 | Monday Lab Time / Meeting |  |  | 3 | 3
Create Input Dialog for add ideas |  |  | 1 | 2 | Wednesday Lab Time / Meeting |  |  | 3 | 3
Work on IdeaGeneration |  |  | 2 | 2 | Sunday Meeting |  |  | 1.5 | 0
[5 empty] | Persistant Storage |  |  | 3 | 1
ListCreateActivity for adding stakeholder groups
|  | Totals: | 9 | 10 |  |  | Totals: | 10.5 | 7
Week 6 |  |  |  |  | Week 6
Activities |  |  | Estimated | Actual | Activities |  |  | Estimated | Actual
Meet With Team |  |  | 6 | 11 | Monday Lab Time / Meeting |  |  | 3 | 3
Move Input Dialog code to DialogBuilder |  |  | 2 | 3 | Wednesday Lab Time / Meeting |  |  | 3 | 3
|  | Totals: | 8 | 14 |  |  | Totals: | 6 | 6
Week 7 |  |  |  |  | Week 7
Activities |  |  | Estimated | Actual | Activities |  |  | Estimated | Actual
Meet With Team |  |  | 8 | 8 | Monday Lab Time / Meeting |  |  | 3 | 3
Move networking code to Servlet Adapter |  |  | 2 | 2 | Wednesday Lab Time / Meeting |  |  | 3 | 3
UI improvements to Idea Generation |  |  | 1 | 1 | Wednesday Demo |  |  | 2 | 2.5
[5 empty] | Sunday Meeting (Missed) |  |  | 2 | 0
|  | Totals: | 11 | 11 |  |  | Totals: | 10 | 8.5
Week 8 |  |  |  |  | Week 8
Activities |  |  | Estimated | Actual | Activities |  |  | Estimated | Actual
Meet With Team |  |  | 6 | 8 | Monday Lab Time / Meeting |  |  | 3 | 3
Work on Voting |  |  | 4 | 3 | Wednesday Lab Time / Meeting |  |  | 3 | 3
IdeaGen Bug Fixes |  |  | 1 | 2 | Sunday Meeting |  |  | 1.5 | 0.5
|  | Totals: | 11 | 13 |  |  | Totals: | 7.5 | 6.5
Week 9 |  |  |  |  | Week 9
Activities |  |  | Estimated | Actual | Activities |  |  | Estimated | Actual
Meet With Team |  |  | 12 | 13 | Monday Lab Time / Meeting |  |  | 3 | 3
IdeaGen and Voting Bug Fixes |  |  | 2 | 2 | Wednesday Lab Time / Meeting |  |  | 3 | 3
[5 empty] | Friday Presentation |  |  | 2 | 2
[5 empty] | Sunday Meeting |  |  | 2 | 2
[5 empty] | Preparing for final presentation |  |  | 4 | 2
|  | Totals: | 14 | 15 |  |  | Totals: | 14 | 12
Week 10 |  |  |  |  | Week 10
Activities |  |  | Estimated | Actual | Activities |  |  | Estimated | Actual
Meet With Team |  |  | 4 | 4 | Monday Lab Time / Meeting / Presentation |  |  | 4 | 4
Presentation |  |  | 2 | 2 | Wednesday Lab Time / Meeting |  |  | 3 | 3
Team Review |  |  | 1 | 1 | Documentation |  |  | 1 | 2
Post Mortem |  |  |  |  | Wrapup work |  |  | 1 | 1
[5 empty] | Tech Report Work |  |  | 3 | 2
|  | Totals: | 7 | 7 |  |  | Totals: | 12 | 12
| Summer Quarter Totals: |  | 93.5 | 105 |  | Fall Quarter Totals: |  | 93 | 81
[6 empty] | Two Quarter Total: |  | 186.5 | 186