## Instructions
Your Name: | Derek Leung
Instructions
Enter your name above.
At the end of each week:
Under "Accomplished this week"
Make sure planned tasks from last week copied correctly with estimated times
Fill in the actual amount of time spent on each task and indicate whether it is done.
Add any other tasks you worked on this week
Teams seem to relate better to times in hours down to the 1/4 hour, but feel free to use minutes if that has more meaning to you.
Under "Planned for next week"
Enter unfinished tasks from this week that you will continue next week
Enter other planned tasks for next week
Estimate the time you will spend on each task. Estimate your time in minutes or hours down to the 1/4 hour.
Tasks and estimates will copy to next week's accomplished section
Under "Issues"
Enter any unexpected problems you encountered
Enter any issues that require discussion with your team

## Example
First Term - Week 1
Accomplished this week
Done? | ACT | EST | Task
Y | 0.5 |  | Attended expectations talk
Y | 1 |  | Prepared for first meeting with sponsor
Y | 1.75 |  | Met with sponsor
Y | 5.25 |  | Researched webservices
Y | 2 |  | Team meeting to assign initial roles and responsibilities
| 10.5 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Regular team meeting
|  | 2 | Meeting with project sponsor
|  | 1 | Write draft synopsis with Kate
|  | 4 | Look for webservices tutorials and work through them
|  | 2.5 | Work with Adam to make list of requirements questions
|  | 11.5 | TOTAL TIME
Issues
Hard disk on my computer died, had to restore from backup
Team is having trouble finding time to meet together
May need help coding error-handling subsystem

## 1-Wk1
First Term - Week 1
Accomplished this week
Done? | ACT |  | Task
Y | 0.15 |  | Submit team account request to system administrator
Y | 0.5 |  | Run project and explore the UI
Y | 0.5 |  | Review documentation from previous team
Y | 1 |  | 1st meeting in Auditorium (Vallino presentation) + slack channel created
Y | 1.15 |  | 1st meeting with coach
| 3.3 |  | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1.25 | Kickoff meeting with sponsor
|  | 1 | Install play framework and run project from source code
|  | 1.25 | Meeting with team to complete action items from the kickoff meeting
|  | 0.5 | Determine what module have actually been completed in the project proposal
|  | 4 | Dig through the source code to determine what can be used
|  | 8 | TOTAL TIME
Issues

## 1-Wk2
First Term - Week 2
Accomplished this week
Done? | ACT | EST | Task
Y | 1.25 | 1.25 | Kickoff with sponsor
Y | 1.25 | 1 | Install play framework and run project from source code
Y | 0 | 1.25 | Meeting with team to complete action items from the kickoff meeting
N | 0.15 | 0.5 | Determine what module have actually been completed in the project proposal
N | 1.25 | 4 | Dig through the source code to determine what can be used
Y | 0.5 | 0.5 | Review test plan that teammates wrote, make edits/add to it
N | 0.15 |  | Agenda for week 3 sponsor meeting
| 4.55 | 8.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1.25 | Meeting with sponsor
|  | 1.25 | Meeting with team to discuss/complete action items from meeting with sponsor
|  | 2.5 | TOTAL TIME
Issues

## 1-Wk3
First Term - Week 3
Accomplished this week
Done? | ACT | EST | Task
Y | 1.25 | 1.25 | Meeting with sponsor
Y | 1.25 | 1.25 | Meeting with team to discuss/complete action items from meeting with sponsor
N | 4 |  | Rebuild the tax engine back-end using java
Y | 1 |  | Meeting with team to prepare for sponsor meeting (agenda, rebuild discussion)
| 7.5 | 2.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1.25 | Meeting with sponsor
|  | 1.25 | Meeting with team to discuss/complete action items from meeting with sponsor
|  | 1 | Update Project Plan with info from sponsor meeting
|  | 0.5 | Create Domain Model
|  | 4 | TOTAL TIME
Issues

## 1-Wk4
First Term - Week 4
Accomplished this week
Done? | ACT | EST | Task
y | 1.25 | 1.25 | Meeting with sponsor
y | 1.25 | 1.25 | Meeting with team to discuss/complete action items from meeting with sponsor
y | 0.75 | 1 | Update Project Plan with info from sponsor meeting
y | 0 | 0.5 | Create Domain Model
| 3.25 | 4 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 3 | Learn React and Redux
|  | 1.25 | Meeting with team Tuesday
|  | 1.25 | Meeting with team Thursday
|  | 4.5 | Begin working on user stories if sprint begins
|  | 10 | TOTAL TIME
Issues

## 1-Wk5
First Term - Week 5
Accomplished this week
Done? | ACT | EST | Task
n | 7.5 | 3 | Learn React and Redux
y | 1.25 | 1.25 | Meeting with team Tuesday
y | 0.5 | 1.25 | Meeting with team Thursday
|  | 4.5 | Begin working on user stories if sprint begins
| 9.25 | 10 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1.25 | Meeting with team Tuesday
|  | 1.25 | Meetings with team Thursday
|  | 5 | Continue working on user stories
|  | 7.5 | TOTAL TIME
Issues

## 1-Wk6
First Term - Week 6
Accomplished this week
Done? | ACT | EST | Task
| 1.25 | 1.25 | Meeting with team Tuesday
| 1.25 | 1.25 | Meetings with team Thursday
| 4 | 5 | Continue working on user stories
| 4.5 |  | Learn React and Redux
| 11 | 7.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 8 | work on front end user stories
|  | 1.25 | Meeting with team Tuesday
|  | 1.25 | Meeting with team Thursday
|  | 10.5 | TOTAL TIME
Issues

## 1-Wk7
First Term - Week 7
Accomplished this week
Done? | ACT | EST | Task
n | 0 | 8 | work on front end user stories
y | 1.25 | 1.25 | Meeting with team Tuesday
y | 1.25 | 1.25 | Meeting with team Thursday
| 2.5 | 10.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1.25 | meeting with team thursday
|  | 8 | work on front end user stories
|  | 9.25 | TOTAL TIME
Issues

## 1-Wk8
First Term - Week 8
Accomplished this week
Done? | ACT | EST | Task
y | 1.25 | 1.25 | meeting with team thursday
n | 8 | 8 | work on front end user stories
| 9.25 | 9.25 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1.25 | meeting with sponsor tuesday
|  | 1.25 | meeting with team thursday
|  | 8 | front end user stories for sprint 2
|  | 10.5 | TOTAL TIME
Issues

## 1-Wk9
First Term - Week 9
Accomplished this week
Done? | ACT | EST | Task
y | 1.25 | 1.25 | meeting with sponsor tuesday
y | 2 | 1.25 | meeting with team thursday
y | 7.5 | 8 | front end user stories for sprint 2
| 10.75 | 10.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 8 | Front end user stories for sprint 3
|  | 1.25 | meeting with team tuesday
|  | 1.25 | meeting with team thursday
|  | 10.5 | TOTAL TIME
Issues

## 1-Wk10
First Term - Week 10
Accomplished this week
Done? | ACT | EST | Task
n | 8 | 8 | Front end user stories for sprint 3
y | 1.25 | 1.25 | meeting with team tuesday
y | 1.25 | 1.25 | meeting with team thursday
| 10.5 | 10.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1.25 | meeting with team tuesday
|  | 1.25 | meeting with team thursday
|  | 2.5 | TOTAL TIME
Issues

## 1-Wk11
First Term - Week 11
Accomplished this week
Done? | ACT | EST | Task
n | 8 | 8 | Front end user stories for sprint 3
y | 1.25 | 1.25 | meeting with team tuesday
y | 1.25 | 1.25 | meeting with team thursday
| 10.5 | 10.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1.25 | meeting with team tuesday
|  | 1.25 | meeting with team thursday
|  | 8 | Front end user stories for sprint 4
|  | 10.5 | TOTAL TIME
Issues

## 1-Wk12
First Term - Week 12
Accomplished this week
Done? | ACT | EST | Task
n | 8 | 8 | Front end user stories for sprint 4
n | 0 | 1.25 | meeting with team tuesday
y | 1.25 | 1.25 | meeting with team thursday
| 9.25 | 10.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1.25 | meeting with team tuesday
|  | 1.25 | meeting with team thursday
|  | 8 | Front end user stories for sprint 5
|  | 10.5 | TOTAL TIME
Issues

## 1-Wk13
First Term - Week 13
Accomplished this week
Done? | ACT | EST | Task
n | 5 | 0 | Front end user stories for sprint 4
y | 1.25 | 1.25 | meeting with team tuesday
y | 1.25 | 1.25 | meeting with team thursday
n | 3 | 8 | Front end user stories for sprint 5
| 10.5 | 10.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1.25 | meeting with team tuesday
|  | 1.25 | meeting with team thursday
|  | 8 | Front end user stories for sprint 5
|  | 10.5 | TOTAL TIME
Issues

## 1-Wk14
First Term - Week 14
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1.25 | meeting with team tuesday
|  | 1.25 | meeting with team thursday
|  | 8 | Front end user stories for sprint 5
|  | 10.5 | TOTAL TIME
Issues

## 1-Wk15
First Term - Week 15
Accomplished this week
Done? | ACT | EST | Task
y | 1.25 | 1.25 | meeting with sponsor tuesday
|  | 1.25 | meeting with team thursday
y | 6 | 8 | Front end user stories for sprint 5
| 7.25 | 10.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1.25 | meeting with team tuesday
|  | 1.25 | meeting with team thursday
|  | 2.5 | TOTAL TIME
Issues

## 1-Finals
First Term - Finals Week
Accomplished this week
Done? | ACT | EST | Task
|  | 1.25 | meeting with team tuesday
|  | 1.25 | meeting with team thursday
| 0 | 2.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-Wk1
Second Term - Week 1
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-Wk2
Second Term - Week 2
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-Wk3
Second Term - Week 3
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-Wk4
Second Term - Week 4
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-Wk5
Second Term - Week 5
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-Wk6
Second Term - Week 6
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-Wk7
Second Term - Week 7
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-Wk8
Second Term - Week 8
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-Wk9
Second Term - Week 9
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-Wk10
Second Term - Week 10
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-Finals
Second Term - Finals Week
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Issues

## AllData
t1-1a | t1-2e | t1-2a | t1-3e | t1-3a | t1-4e | t1-4a | t1-5e | t1-5a | t1-6e | t1-6a | t1-7e | t1-7a | t1-8e | t1-8a | t1-9e | t1-9a | t1-10e | t1-10a | wt1-fe | t1-fa
3.3 | 8.5 | 4.55 | 2.5 | 7.5 | 4 | 3.25 | 10 | 9.25 | 7.5 | 11 | 10.5 | 2.5 | 9.25 | 9.25 | 10.5 | 10.75 | 10.5 | 10.5 | 2.5 | 0
t2-1e | t2-1a | t2-2e | t2-2a | t2-3e | t2-3a | t2-4e | t2-4a | t2-5e | t2-5a | t2-6e | t2-6a | t2-7e | t2-7a | t2-8e | t2-8a | t2-9e | t2-9a | t2-10e | t2-10a | t2-fe | t2-fa
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0