## Instructions
Your Name: | Jordan Tice
Instructions
Enter your name above.
At the end of each week:
Under "Accomplished this week"
Make sure planned tasks from last week copied correctly with estimated times
Fill in the actual amount of time spent on each task and indicate whether it is done.
Add any other tasks you worked on this week
Teams seem to relate better to times in hours down to the 1/4 hour, but feel free to use minutes if that has more meaning to you.
Under "Planned for next week"
Enter unfinished tasks from this week that you will continue next week
Enter other planned tasks for next week
Estimate the time you will spend on each task. Estimate your time in minutes or hours down to the 1/4 hour.
Tasks and estimates will copy to next week's accomplished section
Under "Issues"
Enter any unexpected problems you encountered
Enter any issues that require discussion with your team

## Example
First Term - Week 1
Accomplished this week
Done? | ACT | EST | Task
Y | 0.5 |  | Attended expectations talk
Y | 1 |  | Prepared for first meeting with sponsor
Y | 1.75 |  | Met with sponsor
Y | 5.25 |  | Researched webservices
Y | 2 |  | Team meeting to assign initial roles and responsibilities
| 10.5 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Regular team meeting
|  | 2 | Meeting with project sponsor
|  | 1 | Write draft synopsis with Kate
|  | 4 | Look for webservices tutorials and work through them
|  | 2.5 | Work with Adam to make list of requirements questions
|  | 11.5 | TOTAL TIME
Issues
Hard disk on my computer died, had to restore from backup
Team is having trouble finding time to meet together
May need help coding error-handling subsystem

## 1-Wk1
First Term - Week 1
Accomplished this week
Done? | ACT |  | Task
Y | 1.5 |  | Initial project presentation and meeting with coach
Y | 1.5 |  | Project meeting
| 3 |  | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 1-Wk2
First Term - Week 2
Accomplished this week
Done? | ACT | EST | Task
Y | 1.25 | 1.25 | Sponsor meeting
Y | 2 | 3 | Review previous project source code
Y | 1.25 | 1.25 | Team meeting
| 4.5 | 5.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 1-Wk3
First Term - Week 3
Accomplished this week
Done? | ACT | EST | Task
Y | 2 | 1 | Set up development environment
Y | 1.25 | 1.25 | Sponsor meeting
Y | 2 | 1.25 | Project planning meeting
Y | 2 | 2 | Domain research
| 7.25 | 5.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1.25 | Meet with sponsor to discuss test plans and future development
|  | 1.25 | TOTAL TIME
Issues

## 1-Wk4
First Term - Week 4
Accomplished this week
Done? | ACT | EST | Task
Y | 1.25 | 1.25 | Meet with sponsor to discuss test plans and future development
Y | 1.25 | 1.25 | Work on completing project plan
Y | 1.25 | 1 | Research accounts module for development planning
Y | 2 | 1.5 | Create accounts module architecture
Y | 3.5 | 3.5 | Begin developing accounts module
| 9.25 | 8.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 4 | Continue accounts module development of basic architecture
|  | 4 | TOTAL TIME
Issues

## 1-Wk5
First Term - Week 5
Accomplished this week
Done? | ACT | EST | Task
Y | 5 | 4 | Continue accounts module development of basic architecture
Y | 1.5 | 1.5 | Team Meeting
Y | 1.5 | 1.5 | Meet with sponsor
Y | 1.5 | 2 | Research database options
| 9.5 | 9 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 4 | Set up database connections
|  | 4 | TOTAL TIME
Issues

## 1-Wk6
First Term - Week 6
Accomplished this week
Done? | ACT | EST | Task
Y | 5 | 4 | Set up database connections
Y | 1 | 1 | Sponsor meeting
| 6 | 5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 1-Wk7
First Term - Week 7
Accomplished this week
Done? | ACT | EST | Task
| 1.25 | 1.25 | Tuesday Meeting
| 1.25 | 1.25 | Thursday Meeting
| 1 | 1 | Added accounts to database
| 3.5 | 3.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 1-Wk8
First Term - Week 8
Accomplished this week
Done? | ACT | EST | Task
| 1.25 | 1.25 | Thursday Meeting
| 3 | 3 | Convert database from MySQL to ormlite
| 1 | 1 | Simplify initial set up of database
| 5.25 | 5.25 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 1-Wk9
First Term - Week 9
Accomplished this week
Done? | ACT | EST | Task
Y | 2 | 1 | Get front end running with back end
Y | 2 | 1 | Switch account type to enum
Y | 1.25 | 1.25 | Tuesday meeting
Y | 1.25 | 1.25 | Thursday meeting
| 6.5 | 4.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 3 | Implement account rules
|  | 4 | Savings Projection
|  | 3 | Group Meetings
|  | 10 | TOTAL TIME
Issues

## 1-Wk10
First Term - Week 10
Accomplished this week
Done? | ACT | EST | Task
Y | 4 | 3 | Implement account rules
Y | 4 | 4 | Savings Projection
Y | 2.75 | 3 | Group Meetings
| 10.75 | 10 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 1-Wk11
First Term - Week 11
Accomplished this week
Done? | ACT | EST | Task
Y | 3 | 1 | Implemented withdraw and deposit methods for accounts
Y | 3 | 3 | Group Meetings
Y | 1 | 0 | Savings Projections
| 7 | 4 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 1-Wk12
First Term - Week 12
Accomplished this week
Done? | ACT | EST | Task
Y | 8 | 5 | Savings Projections
Y | 4 | 3 | Meetings
Y | 2 | 1 | Output projections to front end
| 14 | 9 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues
There is a dependency issue with the front-end excel library that was used.

## 1-Wk13
First Term - Week 13
Accomplished this week
Done? | ACT | EST | Task
Y | 2 | 2 | Inflation
Y | 3 | 3 | Meetings
Y | 5 | 5 | Bug fixing
| 10 | 10 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 1-Wk14
First Term - Week 14
Accomplished this week
Done? | ACT | EST | Task
| 0 | 2 | Add Client fields
| 0 |  | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 1-Wk15
First Term - Week 15
Accomplished this week
Done? | ACT | EST | Task
Y | 5 | 3 | Group Meetings
Y | 3 | 0 | Snapshots
Y | 5 | 4 | Convert projections to use Snapshot
| 13 | 7 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 1-Finals
First Term - Finals Week
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-Wk1
Second Term - Week 1
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-Wk2
Second Term - Week 2
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-Wk3
Second Term - Week 3
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-Wk4
Second Term - Week 4
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-Wk5
Second Term - Week 5
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-Wk6
Second Term - Week 6
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-Wk7
Second Term - Week 7
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-Wk8
Second Term - Week 8
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-Wk9
Second Term - Week 9
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-Wk10
Second Term - Week 10
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-Finals
Second Term - Finals Week
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Issues

## AllData
t1-1a | t1-2e | t1-2a | t1-3e | t1-3a | t1-4e | t1-4a | t1-5e | t1-5a | t1-6e | t1-6a | t1-7e | t1-7a | t1-8e | t1-8a | t1-9e | t1-9a | t1-10e | t1-10a | wt1-fe | t1-fa
3 | 5.5 | 4.5 | 5.5 | 7.25 | 8.5 | 9.25 | 9 | 9.5 | 5 | 6 | 3.5 | 3.5 | 5.25 | 5.25 | 4.5 | 6.5 | 10 | 10.75 | 0 | 0
t2-1e | t2-1a | t2-2e | t2-2a | t2-3e | t2-3a | t2-4e | t2-4a | t2-5e | t2-5a | t2-6e | t2-6a | t2-7e | t2-7a | t2-8e | t2-8a | t2-9e | t2-9a | t2-10e | t2-10a | t2-fe | t2-fa
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0