## Instructions
Your Name: | Ryan Wilson
Instructions
Enter your name above.
At the end of each week:
Under "Accomplished this week"
Make sure planned tasks from last week copied correctly with estimated times
Fill in the actual amount of time spent on each task and indicate whether it is done.
Add any other tasks you worked on this week
Teams seem to relate better to times in hours down to the 1/4 hour, but feel free to use minutes if that has more meaning to you.
Under "Planned for next week"
Enter unfinished tasks from this week that you will continue next week
Enter other planned tasks for next week
Estimate the time you will spend on each task. Estimate your time in minutes or hours down to the 1/4 hour.
Tasks and estimates will copy to next week's accomplished section
Under "Issues"
Enter any unexpected problems you encountered
Enter any issues that require discussion with your team

## Example
First Term - Week 1
Accomplished this week
Done? | ACT | EST | Task
Y | 0.5 |  | Attended expectations talk
Y | 1 |  | Prepared for first meeting with sponsor
Y | 1.75 |  | Met with sponsor
Y | 5.25 |  | Researched webservices
Y | 2 |  | Team meeting to assign initial roles and responsibilities
| 10.5 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Regular team meeting
|  | 2 | Meeting with project sponsor
|  | 1 | Write draft synopsis with Kate
|  | 4 | Look for webservices tutorials and work through them
|  | 2.5 | Work with Adam to make list of requirements questions
|  | 11.5 | TOTAL TIME
Issues
Hard disk on my computer died, had to restore from backup
Team is having trouble finding time to meet together
May need help coding error-handling subsystem

## 1-Wk1
First Term - Week 1
Accomplished this week
Done? | ACT |  | Task
Y | 0.5 |  | Attended expectations talk
Y | 1 |  | Prepared for first meeting with sponsor
Y | 0.25 |  | Got access to last year's team's code
Y | 1 |  | Built old code and got it running
| 2.75 |  | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1.25 | Meet with sponsor
|  | 2 | Set up website on SE machine
|  | 2 | Create a test plan for ensuring tax accuracy
|  | 1 | Begin testing old code and seeing where they left off
|  | 5 | Research project technologies/frameworks
|  | 11.25 | TOTAL TIME
Issues
Needed to get access to old team's repository

## 1-Wk2
First Term - Week 2
Accomplished this week
Done? | ACT | EST | Task
Y | 1.25 | 1.25 | Meet with sponsor
Y | 2.25 | 2 | Set up website on SE machine
Y | 1.5 | 2 | Create a test plan for ensuring tax accuracy
Y | 2 | 1 | Begin testing old code and seeing where they left off
Y | 4 | 5 | Research project technologies/frameworks
| 11 | 11.25 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1 | Present test and development plans to sponsor
|  | 2 | Create project plan
|  | 1.5 | Set up VM with continuous Integration
|  | 3 | Begin new front-end project decoupled from backend
|  | 2 | Set up automated test framework
|  | 9.5 | TOTAL TIME
Issues
The last team left the project in not the most usable state
Needed to update code so that tests would compile

## 1-Wk3
First Term - Week 3
Accomplished this week
Done? | ACT | EST | Task
Y | 1 | 1 | Present test and development plans to sponsor
Y | 1.5 | 2 | Create project plan
Y | 0.25 | 1.5 | Set up VM with continuous Integration
Y | 1.5 | 3 | Begin new front-end project decoupled from backend
Y | 0.5 | 2 | Set up automated test framework
N | 5 |  | Reimplement tax engine
| 9.75 | 9.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 3 | Write Tests for Tax Engine
|  | 1.5 | Create Domain Model
|  | 1 | Clean up project plan
|  | 1.5 | Set up Jira and start first sprint
|  | 7 | TOTAL TIME
Issues
The 1040 returns do a lot of complicated math. Need to go through each one to find discrepancies in the code.

## 1-Wk4
First Term - Week 4
Accomplished this week
Done? | ACT | EST | Task
Y | 3.5 | 3 | Write Tests for Tax Engine
Y | 2 | 1.5 | Create Domain Model
Y | 1.5 | 1 | Clean up project plan
Y | 2 | 1.5 | Set up Jira and start first sprint
| 9 | 7 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 5 | Finish Implementing Tax Engine
|  | 2 | Start Building UI elements
|  | 7 | TOTAL TIME
Issues
None.

## 1-Wk5
First Term - Week 5
Accomplished this week
Done? | ACT | EST | Task
N | 4 | 5 | Finish Implementing Tax Engine
Y | 2.5 | 2 | Start Building UI elements
| 6.5 | 7 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 3 | Finish Implementing Tax Engine
|  | 3 | Fully test Tax Engine
|  | 1.5 | Meeting with Sponsor
|  | 7.5 | TOTAL TIME
Issues
Discrepancies between names in tax returns and test tax data excel sheet.

## 1-Wk6
First Term - Week 6
Accomplished this week
Done? | ACT | EST | Task
N | 2 | 3 | Finish Implementing Tax Engine
N | 1.5 | 3 | Fully test Tax Engine
Y | 1.25 | 1.5 | Meeting with Sponsor
| 4.75 | 7.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Implement tax calculation worksheet
|  | 4 | Test individual tax calculations
|  | 2 | Connect UI elements to backend APIs
|  | 8 | TOTAL TIME
Issues
None

## 1-Wk7
First Term - Week 7
Accomplished this week
Done? | ACT | EST | Task
Y | 1.5 | 2 | Implement tax calculation worksheet
N | 0 | 4 | Test individual tax calculations
Y | 2.5 | 2 | Connect UI elements to backend APIs
| 4 | 8 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Implement Login page
|  | 2 | Implement Navigation bar
|  | 1 | Style the home page
|  | 4 | Test individual tax calculations
|  | 9 | TOTAL TIME
Issues
None

## 1-Wk8
First Term - Week 8
Accomplished this week
Done? | ACT | EST | Task
Y | 2.5 | 2 | Implement Login page
Y | 1.5 | 2 | Implement Navigation bar
Y | 2 | 1 | Style the home page
N | 0 | 4 | Test individual tax calculations
| 6 | 9 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Implement Client List
|  | 2 | Implement Single Client Page
|  | 4 | Test individual tax calculations
|  | 8 | TOTAL TIME
Issues
Jira trial license expired. Need to apply valid license and bring it back up.

## 1-Wk9
First Term - Week 9
Accomplished this week
Done? | ACT | EST | Task
Y | 1.5 | 2 | Implement Client List
Y | 1 | 2 | Implement Single Client Page
Y | 3 | 4 | Test individual tax calculations
Y | 3 |  | Connect account creation to backend
Y | 2 |  | Apply finishing touches to UI
| 10.5 | 8 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Create script to download and install program
|  | 4 | Dig in the backend and start the optimizer skeleton
|  | 6 | TOTAL TIME
Issues

## 1-Wk10
First Term - Week 10
Accomplished this week
Done? | ACT | EST | Task
Y | 4 | 2 | Create script to download and install program
N | 1 | 4 | Dig in the backend and start the optimizer skeleton
Y | 2 |  | Build the savings projection view
| 7 | 6 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 4 | Finish correcting tax calculations
|  | 3 | Design and Build the optimizer skeleton
|  | 3 | Move tax config files to database
|  | 10 | TOTAL TIME
Issues

## 1-Wk11
First Term - Week 11
Accomplished this week
Done? | ACT | EST | Task
N | 1 | 4 | Finish correcting tax calculations
Y | 5 | 3 | Design and Build the optimizer skeleton
N | 0 | 3 | Move tax config files to database
N | 3 |  | Started the projection table in the UI
| 9 | 10 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 4 | Complete projection table
|  | 4 | Export table to excel
|  | 8 | TOTAL TIME
Issues

## 1-Wk12
First Term - Week 12
Accomplished this week
Done? | ACT | EST | Task
Y | 3.5 | 4 | Complete projection table
Y | 8.5 | 4 | Export table to excel
| 12 | 8 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 5 | Create Line graph to show projection data
|  | 3 | Convert exporting to excel file to the backend
|  | 2 | Add more client fields
|  | 10 | TOTAL TIME
Issues
There is a dependency issue with the front-end excel library that was used.

## 1-Wk13
First Term - Week 13
Accomplished this week
Done? | ACT | EST | Task
Y | 6 | 5 | Create Line graph to show projection data
N | 1.5 | 3 | Convert exporting to excel file to the backend
Y | 5 | 2 | Add more client fields
| 12.5 | 10 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | Thanksgiving
|  | 0 | TOTAL TIME
Issues

## 1-Wk14
First Term - Week 14
Accomplished this week
Done? | ACT | EST | Task
Y | 0 | 0 | Thanksgiving
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 10 | Refactor Front-end and update to new client objects
|  | 5 | Final Tweaks
|  | 3 | Prep for presentation
|  | 18 | TOTAL TIME
Issues

## 1-Wk15
First Term - Week 15
Accomplished this week
Done? | ACT | EST | Task
Y | 12 | 10 | Refactor Front-end and update to new client objects
Y | 4 | 5 | Final Tweaks
Y | 2.5 | 3 | Prep for presentation
| 18.5 | 18 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 1-Finals
First Term - Finals Week
Accomplished this week
Done? | ACT | EST | Task
|  | 4 | Finish correcting tax calculations
|  | 3 | Design and Build the optimizer skeleton
|  | 3 | Move tax config files to database
| 0 | 10 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-Wk1
Second Term - Week 1
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-Wk2
Second Term - Week 2
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-Wk3
Second Term - Week 3
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-Wk4
Second Term - Week 4
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-Wk5
Second Term - Week 5
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-Wk6
Second Term - Week 6
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-Wk7
Second Term - Week 7
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-Wk8
Second Term - Week 8
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-Wk9
Second Term - Week 9
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-Wk10
Second Term - Week 10
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-Finals
Second Term - Finals Week
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Issues

## AllData
t1-1a | t1-2e | t1-2a | t1-3e | t1-3a | t1-4e | t1-4a | t1-5e | t1-5a | t1-6e | t1-6a | t1-7e | t1-7a | t1-8e | t1-8a | t1-9e | t1-9a | t1-10e | t1-10a | wt1-fe | t1-fa
2.75 | 11.25 | 11 | 9.5 | 9.75 | 7 | 9 | 7 | 6.5 | 7.5 | 4.75 | 8 | 4 | 9 | 6 | 8 | 10.5 | 6 | 7 | 10 | 0
t2-1e | t2-1a | t2-2e | t2-2a | t2-3e | t2-3a | t2-4e | t2-4a | t2-5e | t2-5a | t2-6e | t2-6a | t2-7e | t2-7a | t2-8e | t2-8a | t2-9e | t2-9a | t2-10e | t2-10a | t2-fe | t2-fa
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0