## Instructions
Task Form Instructions
This form has various purposes. First, individual team members will use it to estimate the number of hours that they will spend in each of the activities, when applicable. Second, it will be used by the Planning Leader to generate a consolidated project plan. Third, after the planning stage, individuals will use this form to record the actual hours spent in the activities assigned to them and, when the case arrives, will enter the actual week number (from 1 to 10) when each specific activity was completed. On a weekly basis, the Planning Leader will use this form to consolidate the team's data as the project progresses.
Warning! This form has been designed so that all areas shaded in yellow can be edited; while blue and green areas are protected and cannot be edited mannually. These areas are automatically updated by Excel.
In general, individual team members will use a copy of this form to enter their project data. The planning leader will then get copies of the forms from each team member and will proceeed with the consolidation process. The consolidation process assumes that individual workbooks that contain the forms are each named as a) planningL.xls (Planning Leader), developmentL.xls (Development Leader), qualityL.xls (Quallity Assurance Leader), supportL.xls (Support Leader), teamL.xls (Team Leader), and testingL.xls(Testing Leader). These names match the various roles played by team members throughout the project. The names of the workbooks must be exactly as stated above, otherwise the consolidation process will not work. If for any reason the team is lacking an individual role, a fake workbook must be created that corresponds to that role with all yellow entries filled with "0" (zero).
During the planning stage, the Planning Leader will place the team's Planning workbook together with those workbooks from each and all team members in the same directory. To consolidate all plans, follow the following steps:
a) Select the Planning workbook.
b) Locate and press the button labeled "Consolidate Planned Hours".
When the consolidation process ends, all blue cells under the section labeled "Planned Value" will be updated.
While project development is in progress, the Planning Leader will get weekly copies of this form from each member and will proceed to consolidate the "Actual Hours" by first placing a copy of each of the teammates' workbooks plus the team's workbook in the same directory. Then he/she will proceed as before but this time, will press the "Consolidate Actual Hours" button.
Although individuals will enter data in workbooks that are functionally equivalent to the Team's workbook. Pressing any of the "Consolidate" buttons in an individual's worksheet will not do anything. The macro is designed to consolidate information from individual workbooks into the Planning workbook.
A word of advise: Always keep at least one copy of the team's workbook in a safe place. In Fact, you may want to keep the history of all Planning workbooks as updates are effected onto it. This will allow the team to recover from a possible loss of data. This can be easily accomplished by storing all of your project's stuff under CVS.

## Task
Task Planning Template: TASK Form
Planning Manager | Jason Gilman |  | Date | 2026-07-28 18:49
Team | A-Team
Project | JVMS
| Task | [5 empty] | Planned Hours |  |  |  | Planned Value |  |  |  | Actual
Phase | Task Name | Team Leader | Development Leader | Planning Manager | Support Manager | Testing Manager |  | Total Team Hours | Cumulative Total Hours | Week # | Planned Value | Cumulative Planned Value | Hours | Cumulative Hours | Earned Value | Cumulative Earned Value | Week #
Planning | Project Plan | 0.5 | 0.5 | 10 | 0.5 | 0.5 |  | 12 | 12 | 5 | 1.031% | 1.031% | 10 | 10 | 1.031% | 1.031% | 5 | 0.010309
Requirements | Elicitation | 30 | 30 | 30 | 30 | 30 |  | 150 | 162 | 5 | 12.89% | 13.92% | 133 | 143 | 12.89% | 13.92% | 5 | 0.13918
Requirements | Document | 15 | 15 | 15 | 15 | 15 |  | 75 | 237 | 5 | 6.443% | 20.36% | 35 | 178 | 6.443% | 20.36% | 5 | 0.20361
Requirements | Review | 10 | 10 | 10 | 10 | 10 |  | 50 | 287 | 5 | 4.296% | 24.66% | 24 | 202 | 4.296% | 24.66% | 5 | 0.24656
Misc | Miscelaneous and Tracking | 3 | 3 | 3 | 3 | 2.5 |  | 14.5 | 301.5 | 5 | 1.246% | 25.9% | 19.5 | 221.5 | 1.246% | 25.9% | 5 | 0.25902
High Level Design | Design (phase 1) | 8 | 8 | 8 | 8 | 8 |  | 40 | 341.5 | 6 | 3.436% | 29.34% | 24 | 245.5 | 3.436% | 29.34% | 6 | 0.29338
High Level Design | Review (phase 1) | 2 | 2 | 2 | 2 | 2 |  | 10 | 351.5 | 6 | 0.8591% | 30.2% | 6.5 | 252 | 0.8591% | 30.2% | 6 | 0.30198
Prototype |  | 5 | 2 | 2 | 0 | 0 |  | 9 | 360.5 | 6 | 0.7732% | 30.97% | 8 | 260 | 0.7732% | 30.97% | 6 | 0.30971
Misc | Miscelaneous and Tracking | 3 | 3 | 3 | 2.5 | 2.5 |  | 14 | 374.5 | 6 | 1.203% | 32.17% | 7 | 267 | 1.203% | 32.17% | 6 | 0.32174
Testing | Test Plan Document | 0.5 | 0.5 | 0.5 | 0.5 | 10 |  | 12 | 386.5 | 7 | 1.031% | 33.2% | 5 | 272 | 1.031% | 33.2% | 6 | 0.33204
Testing | Review Test Plan | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  | 2.5 | 389 | 7 | 0.2148% | 33.42% | 3 | 275 | 0.2148% | 33.42% | 6 | 0.33419
Prototype |  | 5 | 2 | 2 | 0 | 0 |  | 9 | 398 | 7 | 0.7732% | 34.19% | 13.5 | 288.5 | 0.7732% | 34.19% | 7 | 0.34192
Misc | Miscelaneous and Tracking | 3 | 3 | 3 | 2.5 | 2.5 |  | 14 | 412 | 7 | 1.203% | 35.4% | 6 | 294.5 | 1.203% | 35.4% | 7 | 0.35395
Prototype |  | 5 | 2 | 2 | 0 | 0 |  | 9 | 421 | 8 | 0.7732% | 36.17% | 7 | 301.5 | 0.7732% | 36.17% | 9 | 0.36168
Detailed Design | Design (phase 1) | 5 | 7 | 5 | 5 | 5 |  | 27 | 448 | 8 | 2.32% | 38.49% | 67.5 | 369 | 2.32% | 38.49% | 9 | 0.38488
Detailed Design | Review (phase 1) | 2 | 2 | 2 | 2 | 2 |  | 10 | 458 | 8 | 0.8591% | 39.35% | 24 | 393 | 0.8591% | 39.35% | 9 | 0.39347
Testing | Test Cases Document | 5 | 5 | 5 | 5 | 15 |  | 35 | 493 | 9 | 3.007% | 42.35% | 8 | 401 | 3.007% | 42.35% | 10 | 0.42354
Implementation | Coding (phase 1) | 5 | 5 | 5 | 5 | 5 |  | 25 | 518 | 9 | 2.148% | 44.5% | 18 | 419 | 2.148% | 44.5% | 9 | 0.44502
Misc | Miscelaneous and Tracking | 3 | 3 | 3 | 2.5 | 2.5 |  | 14 | 532 | 9 | 1.203% | 45.7% | 10 | 429 | 1.203% | 45.7% | 9 | 0.45704
Testing | Review Test Cases | 1 | 1 | 1 | 1 | 1 |  | 5 | 537 | 10 | 0.4296% | 46.13% | 0 | 429 | 0.4296% | 46.13% | 10 | 0.46134
Implementation | Coding (phase 1) | 10 | 10 | 10 | 10 | 10 |  | 50 | 587 | 10 | 4.296% | 50.43% | 30 | 459 | 4.296% | 50.43% | 10 | 0.5043
Misc | Miscelaneous and Tracking | 3 | 3 | 3 | 2.5 | 2.5 |  | 14 | 601 | 10 | 1.203% | 51.63% | 17 | 476 | 1.203% | 51.63% | 10 | 0.51632
Implementation | Coding (phase 1) | 5 | 5 | 5 | 5 | 5 |  | 25 | 626 | 11 | 2.148% | 53.78% | 59 | 535 | 2.148% | 53.78% | 11 | 0.5378
Testing | Testing (phase 1) | 5 | 5 | 5 | 5 | 7 |  | 27 | 653 | 11 | 2.32% | 56.1% | 8 | 543 | 2.32% | 56.1% | 12 | 0.561
Requirements | Update (phase 2) | 2 | 2 | 2 | 2 | 2 |  | 10 | 663 | 11 | 0.8591% | 56.96% | 2.5 | 545.5 | 0.8591% | 56.96% | 12 | 0.56959
Misc | Miscelaneous and Tracking | 3 | 3 | 3 | 2.5 | 2.5 |  | 14 | 677 | 11 | 1.203% | 58.16% | 3 | 548.5 | 1.203% | 58.16% | 11 | 0.58162
High Level Design | Update (phase 2) | 1 | 1 | 1 | 1 | 1 |  | 5 | 682 | 12 | 0.4296% | 58.59% | 3 | 551.5 | 0.4296% | 58.59% | 12 | 0.58591
Detailed Design | Design (phase 2) | 4 | 6 | 4 | 4 | 4 |  | 22 | 704 | 12 | 1.89% | 60.48% | 7 | 558.5 | 1.89% | 60.48% | 13 | 0.60481
Detailed Design | Review (phase 2) | 2 | 2 | 2 | 2 | 2 |  | 10 | 714 | 12 | 0.8591% | 61.34% | 5 | 563.5 | 0.8591% | 61.34% | 13 | 0.6134
Misc | Miscelaneous and Tracking | 3 | 3 | 3 | 2.5 | 2.5 |  | 14 | 728 | 12 | 1.203% | 62.54% | 5.5 | 569 | 1.203% | 62.54% | 12 | 0.62543
Testing | Update Test Cases (phase 2) | 0.5 | 0.5 | 0.5 | 0.5 | 2 |  | 4 | 732 | 13 | 0.3436% | 62.89% | 3 | 572 | 0.3436% | 62.89% | 13 | 0.62887
Implementation | Coding (phase 2) | 5 | 5 | 5 | 5 | 5 |  | 25 | 757 | 13 | 2.148% | 65.03% | 71.5 | 643.5 | 2.148% | 65.03% | 13 | 0.65034
Misc | Miscelaneous and Tracking | 3 | 3 | 3 | 2.5 | 2.5 |  | 14 | 771 | 13 | 1.203% | 66.24% | 1 | 644.5 | 1.203% | 66.24% | 13 | 0.66237
Implementation | Coding (phase 2) | 10 | 10 | 10 | 10 | 10 |  | 50 | 821 | 14 | 4.296% | 70.53% | 51 | 695.5 | 4.296% | 70.53% | 14 | 0.70533
Misc | Miscelaneous and Tracking | 3 | 3 | 3 | 2.5 | 2.5 |  | 14 | 835 | 14 | 1.203% | 71.74% | 5 | 700.5 | 1.203% | 71.74% | 14 | 0.71735
Implementation | Coding (phase 2) | 5 | 5 | 5 | 5 | 5 |  | 25 | 860 | 15 | 2.148% | 73.88% | 68 | 768.5 | 2.148% | 73.88% | 15 | 0.73883
Testing | Testing (phase 2) | 5 | 5 | 5 | 5 | 7 |  | 27 | 887 | 15 | 2.32% | 76.2% | 6 | 774.5 | 2.32% | 76.2% | 16 | 0.76203
Misc | Miscelaneous and Tracking | 3 | 3 | 3 | 2.5 | 2.5 |  | 14 | 901 | 15 | 1.203% | 77.41% | 2.5 | 777 | 1.203% | 77.41% | 15 | 0.77405
Requirements | Update (phase 3) | 2 | 2 | 2 | 2 | 2 |  | 10 | 911 | 16 | 0.8591% | 78.26% | 0 | 777 | 0.8591% | 78.26% | 16 | 0.78265
High Level Design | Update (phase 3) | 1 | 1 | 1 | 1 | 1 |  | 5 | 916 | 16 | 0.4296% | 78.69% | 0 | 777 | 0.4296% | 78.69% | 16 | 0.78694
Detailed Design | Design (phase 3) | 4 | 6 | 4 | 4 | 4 |  | 22 | 938 | 16 | 1.89% | 80.58% | 0 | 777 | 1.89% | 80.58% | 16 | 0.80584
Detailed Design | Review (phase 3) | 2 | 2 | 2 | 2 | 2 |  | 10 | 948 | 16 | 0.8591% | 81.44% | 0 | 777 | 0.8591% | 81.44% | 16 | 0.81443
Misc | Miscelaneous and Tracking | 3 | 3 | 3 | 2.5 | 2.5 |  | 14 | 962 | 16 | 1.203% | 82.65% | 14 | 791 | 1.203% | 82.65% | 16 | 0.82646
Testing | Update Test Cases (phase 3) | 0.5 | 0.5 | 0.5 | 0.5 | 2 |  | 4 | 966 | 17 | 0.3436% | 82.99% | 2 | 793 | 0.3436% | 82.99% | 17 | 0.8299
Implementation | Coding (phase 3) | 5 | 5 | 5 | 5 | 5 |  | 25 | 991 | 17 | 2.148% | 85.14% | 59 | 852 | 2.148% | 85.14% | 17 | 0.85137
Misc | Miscelaneous and Tracking | 3 | 3 | 3 | 2.5 | 2.5 |  | 14 | 1005 | 17 | 1.203% | 86.34% | 2 | 854 | 1.203% | 86.34% | 17 | 0.8634
Implementation | Coding (phase 3) | 5 | 5 | 5 | 5 | 5 |  | 25 | 1030 | 18 | 2.148% | 88.49% | 37 | 891 | 2.148% | 88.49% | 19 | 0.88488
Misc | Miscelaneous and Tracking | 3 | 3 | 3 | 2.5 | 2.5 |  | 14 | 1044 | 18 | 1.203% | 89.69% | 11.5 | 902.5 | 1.203% | 89.69% | 18 | 0.89691
Testing | Testing (phase 3) | 5 | 5 | 5 | 5 | 7 |  | 27 | 1071 | 19 | 2.32% | 92.01% | 1 | 903.5 | 2.32% | 92.01% | 19 | 0.9201
Final | User Document | 5 | 5 | 5 | 15 | 5 |  | 35 | 1106 | 19 | 3.007% | 95.02% | 12 | 915.5 | 3.007% | 95.02% | 19 | 0.95017
Misc | Miscelaneous and Tracking | 3 | 3 | 3 | 2.5 | 2.5 |  | 14 | 1120 | 19 | 1.203% | 96.22% | 9 | 924.5 | 1.203% | 96.22% | 19 | 0.9622
Final | Delivery | 10 | 0 | 0 | 0 | 0 |  | 10 | 1130 | 20 | 0.8591% | 97.08% | 0 | 924.5 | 0% | 0% | 0 | 0.9622
Final | Training | 5 | 0 | 0 | 0 | 0 |  | 5 | 1135 | 20 | 0.4296% | 97.51% | 0 | 924.5 | 0% | 0% | 0 | 0.9622
Final | Post Mortem | 1 | 1 | 1 | 1 | 1 |  | 5 | 1140 | 20 | 0.4296% | 97.94% | 0 | 924.5 | 0% | 0% | 0 | 0.9622
Final | Presentation Preparation | 2 | 2 | 2 | 2 | 2 |  | 10 | 1150 | 20 | 0.8591% | 98.8% | 2 | 926.5 | 0% | 0% | 0 | 0.9622
Misc | Miscelaneous and Tracking | 3 | 3 | 3 | 2.5 | 2.5 |  | 14 | 1164 | 20 | 1.203% | 100% | 0 | 926.5 | 0% | 0% | 0 | 0.9622
|  | 0 | 0 | 0 | 0 | 0 |  | 0 | 1164 | 20 | 0% | 100% | 0 | 926.5 | 0% | 0% | 0 | 0.9622
Final |  | 246.5 | 228.5 | 232 | 219.5 | 237.5 | 0 | 0 | 1164 | 20 | 0% | 100% | 0 | 926.5 | 0% | 0% | 0 | 0.9622
Consolidate Planned Hours
Consolidate Actual Hours

## Schedule
Schedule Planning Template: Form SCHEDULE
Student | [5 empty] | Total Task Plan Hours | 714
Team | [5 empty] | Total Schedule Plan Hours | 0
Part/Level | [5 empty] | Difference | 714
Date | 2000-11-30
|  |  |  | Planned | Actual
| Week #. | Date | Planned Hours | Cummulative Planned Hours | Actual Value | Cummulative Actual Value
| 1 | 2001-03-26 | 0 | 0 | 0 | 0
| 2 | 2001-04-02 | 0 | 0 |  | 0
| 3 | 2001-04-09 | 0 | 0 |  | 0
| 4 | 2001-04-16 | 0 | 0 |  | 0
| 5 | 2001-04-23 | 0 | 0 |  | 0
| 6 | 2001-04-30 | 0 | 0 |  | 0
| 7 | 2001-05-07 | 0 | 0 |  | 0
| 8 | 2001-05-14 | 0 | 0 |  | 0
| 9 | 2001-05-21 | 0 | 0 |  | 0
| 10 | 2001-05-28 | 0 | 0 |  | 0
Formulas:
Date = [Date, row above]+7