## Sheet1
|  | New Features |  |  | Requirements Changes
Monday | Week | Major | Moderate | Minor | Major | Moderate | Minor
2004-11-28 | 1 | 0 | 0 | 0 | 0 | 0 | 0
2004-12-05 | 2 | 7 | 1 | 0 | 0 | 0 | 0
2004-12-12 | 3 | 2 | 2 | 1 | 0 | 2 | 1
2005-01-03 | 4 | 1 | 2 | 0 | 0 | 1 | 0
2005-01-10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | Didn't meet
2005-01-17 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | Didn't meet
2005-01-23 | 7 | 0 | 1 | 0 | 0 | 0 | 0
2005-01-30 | 8 | 6 | 1 | 0 | 0 | 0 | 0
2005-02-06 | 9 | 2 | 1 | 0 | 0 | 0 | 3
2005-02-13 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | Didn't meet
2005-02-20 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | Didn't meet
2005-03-06 | 12 | 1 | 1 | 0 | 6 | 2 | 1
2005-03-13 | 13 | 1 | 1 | 0 | 3 | 5 | 0
2005-03-20 | 14 | 0 | 0 | 0 | 0 | 0 | 0
2005-03-27 | 15 | 2 | 1 | 0 | 1 | 1 | 1
2005-04-03 | 16 | 0 | 0 | 0 | 0 | 0 | 0
2005-04-10 | 17 | 1 | 0 | 0 | 1 | 2 | 0
2005-04-17 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | Done
2005-04-24 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | Done
| 20 | 0 | 0 | 0 | 0 | 0 | 0 | Done
New Features That We Didn't Previously Know About
* New question types (likart,essay) - 12/7/04 - MAJOR
* Questions should be viewable by both student and group scores - 12/7/04 - MAJOR
* Ability to export report data to other formats - 12/7/04 - MAJOR
* Search results view by things thing graduation year, quarter, # co-op - 12/7/04 - MAJOR
* View submitted results by associated employer and student - 12/7/04 - MAJOR
* Email notifications telling students that they have something to do - 12/7/04 - MAJOR
* Ability to fill out forms in multiple stages - 12/7/04 - MAJOR
* ANT build scripts are needed - 12/10/04 - MODERATE
* Need access to old co-op information (on Jim's hard drive) - 12/14/04 - MODERATE
* Our system should pull information from co-op DB and LDAP - 12/14/04 - MODERATE
* System should not use javascript or cookies - 12/14/2004 - MINOR
* Use existing DCE login for system - 12/14/04 - MAJOR
* Once a form is submitted, it should give confirmation email - 12/14/04 - MAJOR
* Emails that are sent out should be staggered - 1/6/05 - MODERATE
* Questions can have categories - attitude, ability, etc - 1/6/05 - MAJOR
* We need to import the list of students on co-op this quarter - 1/6/05 - MODERATE
* We now have the option to not use folium - 1/25/05 - MODERATE
* system should send mail to student RIT mail and preferred mailbox - 2/1/05 - MODERATE
* Students should be able to change their information on forms - 2/1/05 - MAJOR
* Both departments adn administrators can add forms to system - 2/1/05 - MAJOR
* The form will be broken up into 2 parts, generic & department - 2/1/05 - MAJOR
* Administrators should have a page to see all dept email templates - 2/8/05 - MAJOR
* System should log dates of all emails sent - 2/8/05 - MODERATE
* All the student information should be shown on one page - 2/8/05 - MAJOR
* Rejected forms should send student a confirmation email - 3/7/05 - MODERATE
* Reporting needs to group data same as employer reporting - 3/7/05 - MAJOR
* System needs to support waived coop - 3/14/05 - MAJOR
* All search results should be sortable by column - 3/14/05 - MODERATE
* Pending/saved work reports should be highlighted - 3/28/05 - MODERATE
* Need to add third column to double likart - 3/28/05 - MAJOR
* Need to add Co-op Block/Start/End/Wage/Hours at top of form - 3/28/05 - MAJOR
* Hardcode validation for top questions into jsp - 4/11/05 - MAJOR
Changes in Requirements to Existing Features
* Incomplete saved forms must now use status codes in DB - 12/14/04 - MODERATE
* Unanswered questions must be highlighted when student comes back to saved form - 12/14/04 - MINOR
* System should be able to export CSV and excel files - 12/14/04 - MODERATE
* Session cookies are OK (contradicts no cookies earlier) - 1/6/05 - MODERATE
* Highlighted questions should be colored AND askterik'd - 2/8/05 - MINOR
* Reverse likart numbering (1->5 5->1 on forms) - 2/8/05 - MINOR
* Submitted forms should show dates - 2/8/05 - MINOR
* All tables should show date information - 3/7/05 - MINOR
* Searches should also be done by company name - 3/7/05 - MODERATE
* Searches should work for partial search criteria - 3/7/05 - MAJOR
* Quarter search boxes format clarification (20041 vs 041) - 3/7/05 - MODERATE
* Searches should allow you to specify a range - 3/7/05 - MAJOR
* searches should allow search by student id - 3/7/05 - MAJOR
* Only administrators can edit department email templates - 3/7/05 - MAJOR
* Department users cannot edit forms anymore - 3/7/05 - MAJOR
* Forms should only be one part now - 3/7/05 - MAJOR
* Search should be able to select multiple majors - 3/14/05 - MAJOR
* Change data importer for new columns - 3/14/05 - MODERATE
* Change data shown on student view page - 3/14/05 - MODERATE
* Add how many co-ops remaining the student has - 3/14/05 - MODERATE
* Results should display if evaluation is saved,submitted,pending - 3/14/05 - MODERATE
* Change N/A to None on double likart - 3/21/05 - MINOR
* Add notes to search page - 3/21/05 - MINOR
* Change wording in approved column to Yes/no - 3/21/05 - MINOR
* Change time format in results - 3/21/05 - MINOR
* Add "All" option to dept. search criteria - 3/21/05 - MODERATE
* Pressing ENTER on student form should not do anything - 3/28/05 - MINOR
* Reporting should include wage and location - 3/28/05 - MODERATE
* Reporting should show second set of likart data in separate table - 3/28/05 - MAJOR
* Remove boxes on printed forms - 4/11/05 - MINOR
* Search by evaluation status - 4/11/05 - MAJOR
---------
Changes from bugzilla:
1/17/05 - email students when they have a form to fill out - MAJOR
2/1/05 - department users can edit their email templates - MAJOR
** update 3/9/05 - department users can't edit templates anymore - MAJOR
2/1/05 - students should see their submitted forms - MAJOR
2/2/05 - dept users can accept or reject a form - MAJOR
3/18/05 - approved status changed to red/green dot - MINOR
3/18/05 - reporting should generate an excel file with company-focused info - MAJOR
3/18/05 - if user checks no opportunity on double likart, second one should be disabled - MAJOR
4/14/05 - add wage, gender, year, co-op num to excel file & include location - MODERATE