## SE361 Risks
Risk ID | Description of Risk | Probability (0 - 1) | Impact (low, med, high) | Classification | Mitigation Strategy
1 | Changing requirements | 0.75 | med | Schedule | Build the system with flexibility in mind and stay on top of changing requirements
11 | Introducing new bugs into existing system | 0.75 | med | Technical | Regression testing is necessary after each iteration. Work with ITS to develop tests.
12 | Configuration of existing system | 0.75 | med | Technical | Examine documentation and work with ITS to determine current configuration
10 | Difficulty understanding existing system design | 0.5 | med | Technical | Plan plenty of time to deal with understanding existing system and architecture, share information between developers.
14 | Integration problems with existing system | 0.5 | med | Technical | Plan enough time in each iteration for integration testing
2 | Keeping the system secure | 0.3 | med | Technical | Work with ITS to help configure a secure system
3 | Testing/Debugging | 0.3 | med | Schedule | Involve testing at all levels, for both functionality and usability
4 | Tight Schedule | 0.25 | med | Schedule | Plan an aggressive schedule and stick with it
13 | ITS unavailable or too busy to respond to important requests | 0.2 | med | Technical | Work with ITS ahead of time to establish a good relationship. Maintain contact information for key people.
7 | Design complexity | 0.3 | low | Technical | Document all design decisions and keep an up to date reference of the database schema
8 | Installing tools locally | 0.3 | low | Technical | Check for free academic versions of most tools to allow us to set up local development environments
6 | Unfamiliarity with tools | 0.25 | low | Technical | Research tools beforehand and experiment with them
5 | CVS Problems | 0.2 | low | Technical | Work backed up on local machines regularly
9 | Meeting Times | 0.15 | low | Schedule | Possibility of online meetings if we need more meeting time than 4 hours a week
Note on A1: The risk ID is the sequential order of risk entry.
Note on B1: Identify the Risk.
Note on C1: Likelihood that the risk will occur. 1 means the risk will definitely occur.
Note on D1: What will be the impact on the program if the risk occurs. Relative ranking: low = 1 med = 5 high = 10
Note on E1: Where will the biggest impact of the risk occur? Examples: Technical Schedule Reliability Cost/UMC
Note on F1: Plan or strategy to minimize the impact and/or reduce the probability that the risk occurs.