## Instructions
Your Name: | Colton Dennis
Instructions
Enter your name above.
At the end of each week:
Under "Accomplished this week"
Make sure planned tasks from last week copied correctly with estimated times
Fill in the actual amount of time spent on each task and indicate whether it is done.
Add any other tasks you worked on this week
Teams seem to relate better to times in hours down to the 1/4 hour, but feel free to use minutes if that has more meaning to you.
Under "Planned for next week"
Enter unfinished tasks from this week that you will continue next week
Enter other planned tasks for next week
Estimate the time you will spend on each task. Estimate your time in minutes or hours down to the 1/4 hour.
Tasks and estimates will copy to next week's accomplished section
Under "Issues"
Enter any unexpected problems you encountered
Enter any issues that require discussion with your team

## Example
First Term - Week 1
Accomplished this week
Done? | ACT | EST | Task
Y | 0.5 |  | Attended expectations talk
Y | 1 |  | Prepared for first meeting with sponsor
Y | 1.75 |  | Met with sponsor
Y | 5.25 |  | Researched webservices
Y | 2 |  | Team meeting to assign initial roles and responsibilities
| 10.5 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Regular team meeting
|  | 2 | Meeting with project sponsor
|  | 1 | Write draft synopsis with Kate
|  | 4 | Look for webservices tutorials and work through them
|  | 2.5 | Work with Adam to make list of requirements questions
|  | 11.5 | TOTAL TIME
Issues
Hard disk on my computer died, had to restore from backup
Team is having trouble finding time to meet together
May need help coding error-handling subsystem

## 1-Wk1
First Term - Week 1
Accomplished this week
Done? | ACT |  | Task
Yes | 1 |  | Prepared for first sponsor meeting with group outside of scheduled meeting time
Yes | 1.25 |  | Initial meeting with customer and project coach outlining project details
Yes | 0.75 |  | Go through original source code on repository to learn more about its architecture
Yes | 1.5 |  | Began research on Swift and Sails.js
YEs | 0.25 |  | Generated questions for customer
| 4.75 |  | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1.25 | Scheduled Dev Meeting
|  | 1.25 | Scheduled Sponsor Meeting
|  | 2 | Learn more about web component's purpose
|  | 4.5 | TOTAL TIME
Issues

## 1-Wk2
First Term - Week 2
Accomplished this week
Done? | ACT | EST | Task
Yes | 1.25 | 1.25 | Scheduled Dev Meeting
Yes | 1 | 1.25 | Scheduled Sponsor Meeting
Yes | 1.5 | 2 | Learn more about web component's purpose
No | 1 | 1 | Extra weekend Dev Meeting
Yes | 0.5 |  | Setup new Apple equipment
| 5.25 | 5.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 3 | Search for functionality to migrate from web to app
|  | 0.5 | Discuss with Cailan possible new website design/layouts
|  | 3 | Work on new design/layouts
|  | 6.5 | TOTAL TIME
Issues

## 1-Wk3
First Term - Week 3
Accomplished this week
Done? | ACT | EST | Task
y | 2 | 3 | Search for functionality to migrate from web to app
y | 0.5 | 0.5 | Discuss with Cailan possible new website design/layouts
n | 3 | 3 | Work on new design/layouts
y | 1.5 |  | Updated Mac
y | 1 |  | Planned dev meeting
y | 0.5 |  | Planned customer meeting
y | 0.5 |  | Impromptu weekend dev meeting
| 9 | 6.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1 | Finish layout for new site
|  | 1 | Planned dev meeting
|  | 1 | Planned customer meeting
|  | 6 | Work on assigned tasks for sprint (unplanned currently)
|  | 9 | TOTAL TIME
Issues

## 1-Wk4
First Term - Week 4
Accomplished this week
Done? | ACT | EST | Task
Y | 2 | 1 | Finish layout for new site
Y | 1 | 1 | Planned dev meeting
Y | 1 | 1 | Planned customer meeting
N | 4 | 6 | Began looking at Bluetooh issues in app
| 8 | 9 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 10 | Figure out how to detect bluetooth beacons
|  | 1 | Planned dev meeting
|  | 1 | Planned customer meeting
|  | 12 | TOTAL TIME
Issues
Learning about bluetooth since it's new to me
There's a lot of code assosciated with bluetooth beacons to look through
Project deliverables for outside courses due this week

## 1-Wk5
First Term - Week 5
Accomplished this week
Done? | ACT | EST | Task
Yes | 4 | 10 | Figure out how to detect bluetooth beacons
Yes | 1 | 1 | Planned dev meeting
Yes | 1 | 1 | Planned customer meeting
Yes | 2 |  | Set up admin accounts for everyone
Yes/No | 1 |  | Set racechipper.com to point to AWS instance
Yes | 2 |  | Research DNS/SSL certificate registration for AWS instance
Yes | 0.75 |  | Revert back to xcode 7.3.1 to set up for demo (pre-swift 3 conversion)
| 11.75 | 12 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1 | Prepare iOS app for iPad for demo
|  | 2 | Finish SSL certificate signing
|  | 1 | Dev Meeting
|  | 1 | Customer Meeting/Demo
|  | 7.5 | Work on next sprint (need to plan out bluetooth stories more)
|  | 12.5 | TOTAL TIME
Issues
Unsure of how the certificate is going to be signed, dependent on things outside my control
Ran into personal issues that hindered/may continue to hinder progress for the next few days

## 1-Wk6
First Term - Week 6
Accomplished this week
Done? | ACT | EST | Task
yes | 2 | 1 | Prepare iOS app for iPad for demo
no | 13 | 2 | Finish SSL certificate signing
no | 0 | 1 | Dev Meeting
yes | 1 | 1 | Customer Meeting/Demo
no | 0 | 7.5 | Work on next sprint (need to plan out bluetooth stories more)
| 16 | 12.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Submit existing SSL Certificate to a third-party authority
|  | 1 | Dev Meeting
|  | 1 | Customer Meeting
|  | 10 | Work on detecting bluetooth beacons for registration
|  | 14 | TOTAL TIME
Issues
Getting the certificate signed will cost time and money

## 1-Wk7
First Term - Week 7
Accomplished this week
Done? | ACT | EST | Task
Yes | 5 | 2 | Submit existing SSL Certificate to a third-party authority
Yes | 1 | 1 | Dev Meeting
Yes | 1 | 1 | Customer Meeting
In Prog | 7 | 10 | Work on detecting bluetooth beacons for registration
| 14 | 14 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1 | Dev Meeting
|  | 1 | Customer Meeting/Sprint Planning
|  | 10 | Continue bluetooth work
|  | 3 | Upgrade Mac/iOS software
|  | 15 | TOTAL TIME
Issues

## 1-Wk8
First Term - Week 8
Accomplished this week
Done? | ACT | EST | Task
yes | 0 | 1 | Dev Meeting
yes | 1 | 1 | Customer Meeting/Sprint Planning
In Prog. | 7 | 10 | Continue bluetooth work
Yes | 4 | 3 | Upgrade Mac/iOS software
| 12 | 15 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 4 | Finish work on detecting beacons (assigning beacons)
|  | 5 | Debug beacon detection for map view
|  | 1 | Dev Meeting
|  | 1 | Customer meeting
|  | 11 | TOTAL TIME
Issues

## 1-Wk9
First Term - Week 9
Accomplished this week
Done? | ACT | EST | Task
No | 2 | 4 | Finish work on detecting beacons (assigning beacons)
no | 0 | 5 | Debug beacon detection for map view
Yes | 2 | 1 | Dev meeting (peer programming refactor)
Yes | 1 | 1 | Customer meeting
Yes | 1 |  | Dev meeting (refactor planning)
No | 3 |  | Began refactoring my section (group 1)
| 9 | 11 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1 | Customer Meeting/Sprint Planning
|  | 1 | Dev Meeting
|  | 2.5 | Continue refactoring my section
|  | 3 | Redo bluetooth functionality in refactored code
|  | 7.5 | TOTAL TIME
Issues
Refactoring this mess is awful

## 1-Wk10
First Term - Week 10
Accomplished this week
Done? | ACT | EST | Task
|  | 1 | Customer Meeting/Sprint Planning
|  | 1 | Dev Meeting
|  | 2.5 | Continue refactoring my section
|  | 3 | Redo bluetooth functionality in refactored code
| 0 | 7.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 1-Finals
First Term - Finals Week
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-Wk1
Second Term - Week 1
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-Wk2
Second Term - Week 2
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-Wk3
Second Term - Week 3
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-Wk4
Second Term - Week 4
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-Wk5
Second Term - Week 5
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-Wk6
Second Term - Week 6
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-Wk7
Second Term - Week 7
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-Wk8
Second Term - Week 8
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-Wk9
Second Term - Week 9
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-Wk10
Second Term - Week 10
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-Finals
Second Term - Finals Week
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Issues

## AllData
t1-1a | t1-2e | t1-2a | t1-3e | t1-3a | t1-4e | t1-4a | t1-5e | t1-5a | t1-6e | t1-6a | t1-7e | t1-7a | t1-8e | t1-8a | t1-9e | t1-9a | t1-10e | t1-10a | wt1-fe | t1-fa
4.75 | 5.5 | 5.25 | 6.5 | 9 | 9 | 8 | 12 | 11.75 | 12.5 | 16 | 14 | 14 | 15 | 12 | 11 | 9 | 7.5 | 0 | 0 | 0
t2-1e | t2-1a | t2-2e | t2-2a | t2-3e | t2-3a | t2-4e | t2-4a | t2-5e | t2-5a | t2-6e | t2-6a | t2-7e | t2-7a | t2-8e | t2-8a | t2-9e | t2-9a | t2-10e | t2-10a | t2-fe | t2-fa
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0