## Process Metrics - Fall Semester
Task Slippage
Week # | # of Tasks Estimated | # of Tasks Completed
1 | N/A | 8
2 | 17 | 15
3 | 25 | 19
4 | 21 | 17
5 | 21 | 18
6 | 21 | 16
7 | 19 | 14
8 | 21 | 15
9 | 22 | 18
10 | 20 | 17
11 | 21 | 16
12 | 17 | 13
13 | 22 | 19
14 | 12 | 5
15 | 20 | 17
16 | 14 | 8
Finals Week | 0 | 0
Estimation Accuracy (Hours Worked)
Week # | Total Estimation | Total Actual Time
1 | N/A | 16
2 | 24 | 27.5
3 | 33.5 | 27.1
4 | 33 | 33
5 | 33 | 38.75
6 | 39 | 33.25
7 | 26.5 | 31.5
8 | 27 | 25.5
9 | 27.25 | 43.55
10 | 34.25 | 38.75
11 | 35.5 | 32.45
12 | 38 | 45.1
13 | 43.75 | 50.75
14 | 41.5 | 22.5
15 | 59.25 | 49.2
16 | 21 | 24.05
Finals Week | 0 | 0

## Technical Metrics - Fall Semest
Requirements Volatility
Week # | # of Requirements Changed | Total # of Requirements | Percent Change
1 | N/A | N/A | N/A
2 | N/A | N/A | N/A
3 | N/A | N/A | N/A
4 | N/A | N/A | N/A
5 | N/A | N/A | N/A
6 | N/A | N/A | N/A
7 | N/A | N/A | N/A
8 | 1 | 48 | 0.02
9 | 0 | 48 | 0
10 | 0 | 48 | 0
11 | 0 | 48 | 0
12 | 0 | 48 | 0
13
14
15
16
Finals Week
Functional Testing Coverage
Week # | Number of Functions | % Covered
1 | N/A | N/A
2 | N/A | N/A
3 | N/A | N/A
4 | N/A | N/A
5 | N/A | N/A
6 | N/A | N/A
7 | N/A | N/A
8 | N/A | N/A
9 | N/A | N/A
10 | N/A | N/A
11 | N/A | N/A
12 | N/A | N/A
13
14
15
16
Finals Week
Class Testing Coverage
Week # | Number of Classes | % Covered
1 | N/A | N/A
2 | N/A | N/A
3 | N/A | N/A
4 | N/A | N/A
5 | N/A | N/A
6 | N/A | N/A
7 | N/A | N/A
8 | N/A | N/A
9 | N/A | N/A
10 | N/A | N/A
11 | N/A | N/A
12 | N/A | N/A
13
14
15
16
Finals Week

## Personal Metrics - Fall Semeste
Dan's Metrics |  |  | Jared's Metrics |  |  | Warren's Metrics |  |  | Tim's Metrics
Estimation Accuracy |  |  | Estimation Accuracy |  |  | Estimation Accuracy |  |  | Estimation Accuracy
Week # | Estimated Time | Actual Time | Week # | Estimated Time | Actual Time | Week # | Estimated Time | Actual Time | Week # | Estimated Time | Actual Time
1 | N/A | 5.5 | 1 | N/A | 4.5 | 1 | N/A | 3.5 | 1 | N/A | 4
2 |  | 3.5 | 2 | 14.5 | 12.5 | 2 | 5.5 | 6.5 | 2 | 4 | 5
3 | 5.5 | 8 | 3 | 14.5 | 10 | 3 | 15 | 4.1 | 3 | 4 | 4
4 | 4.5 | 7.5 | 4 | 14 | 10 | 4 | 8 | 8.5 | 4 | 6.5 | 7
5 | 9 | 11 | 5 | 12.5 | 9.5 | 5 | 5.5 | 8 | 5 | 8 | 10.5
6 | 12.5 | 9.5 | 6 | 15 | 12 | 6 | 4 | 5.5 | 6 | 7.5 | 6.25
7 | 6 | 6 | 7 | 12.5 | 10 | 7 | 5 | 7 | 7 | 9 | 8.5
8 | 6 | 6.5 | 8 | 12 | 8.25 | 8 | 7 | 10 | 8 | 8 | 0.75
9 | 5.5 | 10.5 | 9 | 9.75 | 11.25 | 9 | 6 | 13.5 | 9 | 6 | 8.3
10 | 8.5 | 13.5 | 10 | 11.5 | 9 | 10 | 4 | 6 | 10 | 10.25 | 10.25
11 | 10.5 | 12.5 | 11 | 11.5 | 5 | 11 | 4 | 10 | 11 | 9.5 | 4.95
12 | 10.5 | 10.5 | 12 | 11 | 11.5 | 12 | 9 | 10.5 | 12 | 7.5 | 12.6
13 | 11.5 |  | 13 | 11.25 | 13 | 13 | 12 | 20 | 13 | 10.5 | 9.25
14 |  |  | 14 | 9.75 | 7.25 | 14 |  |  | 14 | 8.25 | 4.25
15 |  |  | 15 | 16.5 | 9.5 | 15 |  |  | 15 | 10.25
16 |  |  | 16 |  |  | 16 |  |  | 16
Finals Week |  |  | Finals Week |  |  | Finals Week |  |  | Finals Week
Tasks Committed / Tasks Delivered |  |  | Task Slippage |  |  | Task Slippage |  |  | Task Slippage
Week # | # of Tasks | # Completed | Week # | # of Tasks | # Completed | Week # | # of Tasks | # Completed | Week # | # of Tasks | # Completed
1 |  |  | 1 | 2 | 2 | 1 | 2 | 2 | 1 | 1 | 1
2 |  |  | 2 | 9 | 7 | 2 | 5 | 5 | 2 | 1 | 1
3 |  |  | 3 | 9 | 8 | 3 | 5 | 5 | 3 | 1 | 1
4 |  |  | 4 | 9 | 7 | 4 | 7 | 7 | 4 | 2 | 2
5 |  |  | 5 | 7 | 5 | 5 | 5 | 5 | 5 | 4 | 4
6 |  |  | 6 | 8 | 5 | 6 | 4 | 4 | 6 | 4 | 4
7 |  |  | 7 | 5 | 4 | 7 | 7 | 7 | 7 | 4 | 4
8 |  |  | 8 | 3 | 2 | 8 | 10 | 8 | 8 | 4 | 2
9 |  |  | 9 | 5 | 4 | 9 | 7 | 7 | 9 | 4 | 3
10 |  |  | 10 | 5 | 4 | 10 | 4 | 4 | 10 | 5 | 4
11 |  |  | 11 | 5 | 3 | 11 | 7 | 7 | 11 | 4 | 4
12 |  |  | 12 | 4 | 3 | 12 | 4 | 5 | 12 | 3 | 3
13 |  |  | 13 | 5 | 3 | 13 | 4 | 3 | 13 | 3 | 3
14 |  |  | 14 | 3 | 2 | 14 |  |  | 14 | 2 | 2
15 |  |  | 15 | 5 | 3 | 15 |  |  | 15 | 3
16 |  |  | 16 |  |  | 16 |  |  | 16
Finals Week |  |  | Finals Week |  |  | Finals Week |  |  | Finals Week
|  |  | Number of Unstarted Tasks |  |  | Average Time Spent Resolving Issues
|  |  | Week # | # Unstarted Tasks |  | Week # | # of Issues | Avg Time to completion(hrs)
|  |  | 1 | 0 |  | 1 | 0 | 0
|  |  | 2 | 2 |  | 2 | 0 | 0
|  |  | 3 | 1 |  | 3 | 0 | 0
|  |  | 4 | 1 |  | 4 | 0 | 0
|  |  | 5 | 2 |  | 5 | 0 | 0
|  |  | 6 | 1 |  | 6 | 0 | 0
|  |  | 7 | 0 |  | 7 | 1 | 1
|  |  | 8 | 0 |  | 8 | 3 | 3hrs(ongoing)
|  |  | 9 | 0 |  | 9 | 2 | 1 hour(finished) / 3 hours
|  |  | 10 | 0 |  | 10 | 1 | 30 mins
|  |  | 11 | 0 |  | 11 | 1 | (TFS authentication error, 30 mins)
|  |  | 12 | 0 |  | 12 | 2 | Printer paper was in wrong way/printer wasn't printing anything(30 mins). Resolving Binaries dependencies(30 mins)
|  |  | 13 | 0 |  | 13 | 3 | 7 hrs(win32 not working on surface/cant print around windows print charm/ USB printer also doesnt work)
|  |  | 14 | 0 |  | 14
|  |  | 15 | 0 |  | 15
|  |  | 16 |  |  | 16
|  |  | Finals Week |  |  | Finals Week

## Process Metrics - Spring Semest
Task Slippage
Week # | # of Tasks Estimated | # of Tasks Completed
1 | 19 | 18
2 | 23 | 18
3 | 20 | 14
4 | 19 | 13
5 | 19 | 12
6 | 19 | 16
7 | 23 | 20
8 | 16 | 11
9 | 22 | 19
10 | 21 | 14
11 | 18 | 13
12
13
14
15
Finals Week
Estimation Accuracy
Week # | Total Estimation | Total Actual Time
1 | 33 | 43.5
2 | 43 | 46.5
3 | 42.25 | 30.15
4 | 35 | 42.25
5 | 38.75 | 31.5
6 | 22.5 | 43.75
7 | 33.75 | 49.25
8 | 28.5 | 29.75
9 | 51 | 57.75
10 | 55 | 60.5
11 | 38 | 40.75
12
13
14
15
Finals Week

## Technical Metrics - Spring Sems
Requirements Volatility
Week # | # of Requirements Changed | Total # of Requirements | Percent Change
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
Finals Week
Functional Testing Coverage
Week # | Number of Functions | % Covered
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
Finals Week
Class Testing Coverage
Week # | Number of Classes | % Covered
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
Finals Week

## Personal Metrics - Spring Semes
Dan's Metrics |  |  | Jared's Metrics |  |  | Warren's Metrics |  |  | Tim's Metrics
Estimation Accuracy |  |  | Estimation Accuracy |  |  | Estimation Accuracy |  |  | Estimation Accuracy
Week # | Estimated Time | Actual Time | Week # | Estimated Time | Actual Time | Week # | Estimated Time | Actual Time | Week # | Estimated Time | Actual Time
1 |  |  | 1 | 13.5 | 13.5 | 1 |  |  | 1
2 |  |  | 2 | 15 | 13.5 | 2 |  |  | 2
3 |  |  | 3 | 15 | 11 | 3 |  |  | 3
4 |  |  | 4 | 14 | 10.5 | 4 |  |  | 4
5 |  |  | 5 | 16 | 9 | 5 |  |  | 5
6 |  |  | 6 | 7.75 | 5.75 | 6 |  |  | 6
7 |  |  | 7 | 9.75 | 8.25 | 7 |  |  | 7
8 |  |  | 8 | 19.5 | 9 | 8 |  |  | 8
9 |  |  | 9 | 20.5 | 26.5 | 9 |  |  | 9
10 |  |  | 10 | 14.5 | 16 | 10 |  |  | 10
11 |  |  | 11 | 13.5 | 12.25 | 11 |  |  | 11
12 |  |  | 12 | 10.5 | 14.75 | 12 |  |  | 12
13 |  |  | 13 | 16 | 21.5 | 13 |  |  | 13
14 |  |  | 14 |  |  | 14 |  |  | 14
15 |  |  | 15 |  |  | 15 |  |  | 15
16 |  |  | 16 |  |  | 16 |  |  | 16
Finals Week |  |  | Finals Week |  |  | Finals Week |  |  | Finals Week
Task Slippage |  |  | Task Slippage |  |  | Task Slippage |  |  | Task Slippage
Week # | # of Tasks | # Completed | Week # | # of Tasks | # Completed | Week # | # of Tasks | # Completed | Week # | # of Tasks | # Completed
1 |  |  | 1 | 5 | 5 | 1 |  |  | 1
2 |  |  | 2 | 8 | 5 | 2 |  |  | 2
3 |  |  | 3 | 8 | 7 | 3 |  |  | 3
4 |  |  | 4 | 6 | 4 | 4 |  |  | 4
5 |  |  | 5 | 8 | 6 | 5 |  |  | 5
6 |  |  | 6 | 5 | 3 | 6 |  |  | 6
7 |  |  | 7 | 8 | 7 | 7 |  |  | 7
8 |  |  | 8 | 9 | 5 | 8 |  |  | 8
9 |  |  | 9 | 10 | 10 | 9 |  |  | 9
10 |  |  | 10 | 8 | 4 | 10 |  |  | 10
11 |  |  | 11 | 5 | 3 | 11 |  |  | 11
12 |  |  | 12 | 6 | 6 | 12 |  |  | 12
13 |  |  | 13 | 7 | 6 | 13 |  |  | 13
14 |  |  | 14 |  |  | 14 |  |  | 14
15 |  |  | 15 |  |  | 15 |  |  | 15
16 |  |  | 16 |  |  | 16 |  |  | 16
Finals Week |  |  | Finals Week |  |  | Finals Week |  |  | Finals Week
Number of Unstarted Tasks
|  |  | Week # | # Unstarted Tasks
|  |  | 1 | 0
|  |  | 2 | 0
|  |  | 3 | 1
|  |  | 4 | 1
|  |  | 5 | 1
|  |  | 6 | 2
|  |  | 7 | 1
|  |  | 8 | 4
|  |  | 9 | 0
|  |  | 10 | 2
|  |  | 11 | 0
|  |  | 12 | 0
|  |  | 13 | 1
14
15
16
Finals Week