## Instructions
Your Name: | Alex Maniates
Instructions
Enter your name above.
At the end of each week:
Under "Accomplished this week"
Make sure planned tasks from last week copied correctly with estimated times
Fill in the actual amount of time spent on each task and indicate whether it is done.
Add any other tasks you worked on this week
Teams seem to relate better to times in hours down to the 1/4 hour, but feel free to use minutes if that has more meaning to you.
Under "Planned for next week"
Enter unfinished tasks from this week that you will continue next week
Enter other planned tasks for next week
Estimate the time you will spend on each task. Estimate your time in minutes or hours down to the 1/4 hour.
Tasks and estimates will copy to next week's accomplished section
Under "Issues"
Enter any unexpected problems you encountered
Enter any issues that require discussion with your team

## Example
First Term - Week 1
Accomplished this week
Done? | ACT | EST | Task
Y | 0.5 |  | Attended expectations talk
Y | 1 |  | Prepared for first meeting with sponsor
Y | 1.75 |  | Met with sponsor
Y | 5.25 |  | Researched webservices
Y | 2 |  | Team meeting to assign initial roles and responsibilities
| 10.5 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Regular team meeting
|  | 2 | Meeting with project sponsor
|  | 1 | Write draft synopsis with Kate
|  | 4 | Look for webservices tutorials and work through them
|  | 2.5 | Work with Adam to make list of requirements questions
|  | 11.5 | TOTAL TIME
Issues
Hard disk on my computer died, had to restore from backup
Team is having trouble finding time to meet together
May need help coding error-handling subsystem

## 2-Wk1
First Term - Week 1
Accomplished this week
Done? | ACT |  | Task
Y | 1 |  | Sponsor Meeting
Y | 1 |  | Thursday Meeting
Y | 4 |  | Framework Creation Tool
Y | 1 |  | Set up cumulative flow diagram
| 7 |  | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1 | Sponsor Meeting
|  | 5 | Framework Creation Tool
|  | 0.5 | Update metrics
|  | 6.5 | TOTAL TIME
Issues

## 2-Wk2
First Term - Week 2
Accomplished this week
Done? | ACT | EST | Task
Y | 1 | 1 | Sponsor Meeting
Y | 5 | 5 | Framework Creation Tool
Y | 1 | 0.5 | Update metrics
| 7 | 6.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1 | Sponsor Meeting
|  | 5 | Library Creation tool
|  | 1 | Thursday Meeting
|  | 7 | TOTAL TIME
Issues

## 2-Wk3
First Term - Week 3
Accomplished this week
Done? | ACT | EST | Task
Y | 1 | 1 | Sponsor Meeting
Y | 6 | 5 | Library Creation tool
Y | 1 | 1 | Thursday Meeting
| 8 | 7 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1 | Sponsor Meeting
|  | 4 | Library Tool writing out to file
|  | 1 | Thursday Meeting
|  | 6 | TOTAL TIME
Issues

## 2-Wk4
First Term - Week 4
Accomplished this week
Done? | ACT | EST | Task
Y | 1 | 1 | Sponsor Meeting
Y | 6 | 4 | Library Tool writing out to file
Y | 1 | 1 | Thursday Meeting
Y | 1 |  | Code Reviews
| 9 | 6 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1 | Sponsor Meeting
|  | 1 | Code Reviews
|  | 2 | TOTAL TIME
Issues

## 2-Wk5
First Term - Week 5
Accomplished this week
Done? | ACT | EST | Task
Y | 1 | 1 | Sponsor Meeting
Y | 1 | 1 | Code Reviews
Y | 3 |  | Migrate old stdlib.sizeit file to new file from creation tool
Y | 1 |  | Thursday meeting
Y | 2 |  | Start looking into UI for sizeit files
| 8 | 2 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1 | Sponsor meeting
|  | 1 | Thursday meeting
|  | 1 | Code reviews
|  | 5 | UI for sizeit files
|  | 8 | TOTAL TIME
Issues

## 2-Wk6
First Term - Week 6
Accomplished this week
Done? | ACT | EST | Task
Y | 1 | 1 | Sponsor meeting
Y | 1 | 1 | Thursday meeting
Y | 1 | 1 | Code reviews
N | 0 | 5 | UI for sizeit files
Y | 5 |  | Write out public states for sizeit files
Y | 0.5 |  | Make AST pictures for Gobble and Pollster
| 8.5 | 8 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1 | Sponsor meeting
|  | 1 | Thursday Meeting
|  | 1 | Code reviews
|  | 3 | TOTAL TIME
Issues

## 2-Wk7
First Term - Week 7
Accomplished this week
Done? | ACT | EST | Task
Y | 1 | 1 | Sponsor meeting
Y | 1 | 1 | Thursday Meeting
Y | 1 | 1 | Code reviews
Y | 6 |  | Add packages to sizeit file parameters
| 9 | 3 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1 | Senior project poster meeting
|  | 1 | Sponsor meeting
|  | 1 | Thursday Meeting
|  | 1 | Code reviews
|  | 4 | TOTAL TIME
Issues

## 2-Wk8
First Term - Week 8
Accomplished this week
Done? | ACT | EST | Task
|  | 1 | Senior project poster meeting
|  | 1 | Sponsor meeting
|  | 1 | Thursday Meeting
|  | 1 | Code reviews
| 0 | 4 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-Wk9
First Term - Week 9
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-Wk10
First Term - Week 10
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-Wk11
First Term - Week 11
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-Wk12
First Term - Week 12
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-Wk13
First Term - Week 13
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-Wk14
First Term - Week 14
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-Wk15
First Term - Week 15
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-Wk16
First Term - Week 16
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-FinalsWeek
First Term - Week 16
Accomplished this week
Done? | ACT | EST | Task
Y | 2
| 2 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues