## Instructions
Your Name: | Eric Mammoser
Instructions
Enter your name above.
At the end of each week:
Under "Accomplished this week"
Make sure planned tasks from last week copied correctly with estimated times
Fill in the actual amount of time spent on each task and indicate whether it is done.
Add any other tasks you worked on this week
Teams seem to relate better to times in hours down to the 1/4 hour, but feel free to use minutes if that has more meaning to you.
Under "Planned for next week"
Enter unfinished tasks from this week that you will continue next week
Enter other planned tasks for next week
Estimate the time you will spend on each task. Estimate your time in minutes or hours down to the 1/4 hour.
Tasks and estimates will copy to next week's accomplished section
Under "Issues"
Enter any unexpected problems you encountered
Enter any issues that require discussion with your team

## Example
First Term - Week 1
Accomplished this week
Done? | ACT | EST | Task
Y | 0.5 |  | Attended expectations talk
Y | 1 |  | Prepared for first meeting with sponsor
Y | 1.75 |  | Met with sponsor
Y | 5.25 |  | Researched webservices
Y | 2 |  | Team meeting to assign initial roles and responsibilities
| 10.5 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Regular team meeting
|  | 2 | Meeting with project sponsor
|  | 1 | Write draft synopsis with Kate
|  | 4 | Look for webservices tutorials and work through them
|  | 2.5 | Work with Adam to make list of requirements questions
|  | 11.5 | TOTAL TIME
Issues
Hard disk on my computer died, had to restore from backup
Team is having trouble finding time to meet together
May need help coding error-handling subsystem

## 2-Wk1
First Term - Week 1
Accomplished this week
Done? | ACT |  | Task
Y | 1.5 |  | Met with sponsor
Y | 1 |  | Met to discuss tasks and story points
N | 3 |  | Worked on GUI R/W for stdlib file
Y | 1 |  | Worked on maintenance and documentation
N | 1 |  | Reviewed code
| 7.5 |  | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1.5 | Meet with sponsor
|  | 3 | Work on GUI R/W for stdlib
|  | 3 | Make library analyzer work for our system
|  | 1 | maintenance and documentation
|  | 1 | Review code
|  | 9.5 | TOTAL TIME
Issues

## 2-Wk2
First Term - Week 2
Accomplished this week
Done? | ACT | EST | Task
Y | 1.5 | 1.5 | Meet with sponsor
Y | 3 | 3 | Work on GUI R/W for stdlib
|  | 3 | Make library analyzer work for our system
Y | 1 | 1 | maintenance and documentation
Y | 1 | 1 | Review code
| 6.5 | 9.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1.5 | Meet with sponsor
|  | 2 | Review Code
|  | 2 | Migrate stdlib file to new format
|  | 2 | maintenance and documentation
|  | 7.5 | TOTAL TIME
Issues

## 2-Wk3
First Term - Week 3
Accomplished this week
Done? | ACT | EST | Task
Y | 1.5 | 1.5 | Meet with sponsor
| 2 | 2 | Review Code
Y | 5 | 2 | Migrate stdlib file to new format
Y | 2 | 2 | maintenance and documentation
| 10.5 | 7.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1.5 | Meet with sponsor
|  | 2 | Review Code
|  | 2 | Code for overall library mapping
|  | 2 | maintenance and documentation
|  | 7.5 | TOTAL TIME
Issues

## 2-Wk4
First Term - Week 4
Accomplished this week
Done? | ACT | EST | Task
Y | 1 | 1.5 | Meet with sponsor
Y | 1 | 2 | Review Code
Y | 3 | 2 | Code for overall library mapping
Y | 2 | 2 | maintenance and documentation
Y | 3 |  | Inital Read and Writes
| 10 | 7.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0.5 | Meet remotely for sprint planning
|  | 2 | Review Code
|  | 5 | Extend Read and Write Capability
|  | 2 | maintenance and documentation
|  | 9.5 | TOTAL TIME
Issues

## 2-Wk5
First Term - Week 5
Accomplished this week
Done? | ACT | EST | Task
Y | 0.5 | 0.5 | Meet remotely for sprint planning
Y | 1 | 2 | Review Code
Y | 5 | 5 | Extend Read and Write Capability
Y | 1 | 2 | maintenance and documentation
Y | 0.5 | N/A | meet to discuss IFPUG
| 8 | 9.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1.5 | Meet with the sponsor
|  | 3 | Work on IFPUG visitor
|  | 2 | Review Code
|  | 2 | maintenance and documentation
|  | 8.5 | TOTAL TIME
Issues

## 2-Wk6
First Term - Week 6
Accomplished this week
Done? | ACT | EST | Task
Y | 1.5 | 1.5 | Meet with the sponsor
Y | 2 | 3 | Work on IFPUG visitor
| 2 | 2 | Review Code
| 1 | 2 | maintenance and documentation
| 1 | N/A | Work on IO terminology code fix
| 7.5 | 8.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1.5 | Meet with the sponsor
|  | 2 | Review Code
|  | 2 | maintenance and documentation
|  | 2 | Add more expressions to our internal model
|  | 7.5 | TOTAL TIME
Issues

## 2-Wk7
First Term - Week 7
Accomplished this week
Done? | ACT | EST | Task
Y | 1.5 | 1.5 | Meet with the sponsor
Y | 2 | 2 | Review Code
Y | 2 | 2 | maintenance and documentation
N | 0 | 2 | Add more expressions to our internal model
Y | 3 | N/A | Add package matching
| 8.5 | 7.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1.5 | Meet with the sponsor
|  | 2 | Review Code
|  | 2 | maintenance and documentation
|  | 2 | Run on larger projects
|  | 7.5 | TOTAL TIME
Issues

## 2-Wk8
First Term - Week 8
Accomplished this week
Done? | ACT | EST | Task
Y | 1 | 1.5 | Meet with the sponsor
Y | 2 | 2 | Review Code
Y | 2 | 2 | maintenance and documentation
N | 1 | 2 | Run on larger projects
Y | 1.5 | N/A | Added ability for analyzer to recognize packages
| 7.5 | 7.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1.5 | Meet with sponsor
|  | 2 | Review Code
|  | 2 | maintenance and documentation
|  | 3 | Fix bugs when running on larger projects
|  | 8.5 | TOTAL TIME
Issues

## 2-Wk9
First Term - Week 9
Accomplished this week
Done? | ACT | EST | Task
|  | 1.5 | Meet with sponsor
|  | 2 | Review Code
|  | 2 | maintenance and documentation
|  | 3 | Fix bugs when running on larger projects
| 0 | 8.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-Wk10
First Term - Week 10
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-Wk11
First Term - Week 11
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-Wk12
First Term - Week 12
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-Wk13
First Term - Week 13
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-Wk14
First Term - Week 14
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-Wk15
First Term - Week 15
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-Wk16
First Term - Week 16
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-FinalsWeek
First Term - Week 16
Accomplished this week
Done? | ACT | EST | Task
Y | 2
| 2 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues