## Baseline
Design
Date | Names | Task | Start | End | Total Time | People | Man Hours
2006-01-26 | All | Initial Design Discussion | 16:40 | 17:25 | 0:45 | 4 | 3:00
2006-01-29 | Erik | Create Visio Design Docs | 15:00 | 15:15 | 0:15 | 1 | 0:15
2006-01-31 | All | Transfer Objects | 16:30 | 16:45 | 0:15 | 4 | 1:00
Implementation
Date | Names | Task | Start | End | Total Time | People | Man Hours
2006-01-31 | Erik | Initial Development | 13:00 | 14:00 | 1:00 | 1 | 1:00
2006-02-02 | All | Install Websphere | 16:30 | 18:30 | 2:00 | 4 | 8:00
2006-02-04 | All | Generated Code; Wrote Information | 16:30 | 20:00 | 3:30 | 3 | 10:30
2006-02-07 | Erik |  | 19:30 | 22:30 | 3:00 | 1 | 3:00
2006-02-09 | Erik |  | 18:00 | 20:00 | 2:00 | 1 | 2:00
2006-03-08 | Erik, Justin | Loading Sample Data (XML) | 19:30 | 23:30 | 4:00 | 2 | 8:00
2006-03-14 | Jaden, Erik | getProduct | 12:00 | 14:00 | 2:00 | 2 | 4:00
2006-03-15 | Justin | XML Reader | 14:00 | 15:00 | 1:00 | 1 | 1:00
2006-03-16 | Jason | XML Generator | 19:00 | 21:00 | 2:00 | 1 | 2:00
2006-03-22 | Erik |  | 20:00 | 22:00 | 2:00 | 1 | 2:00
2006-03-25 | Jason, Jaden | Code Cleanup/Commenting | 19:30 | 23:30 | 4:00 | 2 | 8:00
Testing
Date | Names | Task | Start | End | Total Time | People | Man Hours
2006-03-08 | All | Installed/Learned IBM Agent Controller | 17:30 | 18:30 | 1:00 | 4 | 4:00
2006-03-08 | Jaden, Jason | Planning Test Analysis | 19:30 | 23:30 | 4:00 | 2 | 8:00
2006-03-09 | Erik | Aspects (Spring) | 0:00 | 1:00 | 1:00 | 1 | 1:00
2006-03-13 | Erik | Aspects (Spring) | 11:00 | 13:00 | 2:00 | 1 | 2:00
2006-03-13 | Erik, Jaden | Aspects (Spring) | 13:30 | 15:30 | 2:00 | 2 | 4:00
2006-03-14 | Justin | Test Result Parser | 12:00 | 14:00 | 2:00 | 1 | 2:00
2006-03-15 | All | Various testing and data generation. | 18:00 | 23:30 | 5:30 | 4 | 22:00
2006-03-22 | Justin | Situating testing environment | 20:00 | 22:00 | 2:00 | 1 | 2:00
2006-03-22 | Jaden | Function Points | 20:00 | 22:00 | 2:00 | 1 | 2:00
2006-03-25 | Justin | Resource Metrics | 19:30 | 23:30 | 4:00 | 1 | 4:00
2006-03-25 | Jaden, Justin | Resource Metrics | 23:29 | 23:59 | 0:30 | 2 | 1:00

## Iteration 1 - Caching
Design
Date | Names | Task | Start | End | Total Time | People | Man Hours
2006-03-20 | All | Design Discussion | 16:30 | 17:00 | 0:30 | 4 | 2:00
Implementation
Date | Names | Task | Start | End | Total Time | People | Man Hours
2006-03-22 | Erik | Began implementation | 20:00 | 22:00 | 2:00 | 1 | 2:00
2006-04-05 | All | Finished Implementation | 19:00 | 21:30 | 2:30 | 4 | 10:00
2006-04-05 | Jaden, Erik | Fixed caching bug | 21:30 | 22:00 | 0:30 | 2 | 1:00
2006-04-06 | Jaden | Merged changes to other branches | 17:00 | 18:30 | 1:30 | 1 | 1:30
Testing
Date | Names | Task | Start | End | Total Time | People | Man Hours

## Iteration 2 - Threading
Design
Date | Names | Task | Start | End | Total Time | People | Man Hours
2006-04-10 | All | Design Discussion | 16:30 | 17:00 | 0:30 | 4 | 2:00
Implementation
Date | Names | Task | Start | End | Total Time | People | Man Hours
Testing
Date | Names | Task | Start | End | Total Time | People | Man Hours

## Iteration 3 - Distr. Sys.
Design
Date | Names | Task | Start | End | Total Time | People | Man Hours
2006-04-12 | Jaden, Jason, Erik | Design Discussion | 18:30 | 19:30 | 1:00 | 3 | 3:00
Implementation
Date | Names | Task | Start | End | Total Time | People | Man Hours
2006-04-12 | All | Implementation | 19:30 | 23:30 | 4:00 | 4 | 16:00
Testing
Date | Names | Task | Start | End | Total Time | People | Man Hours