## SE361 Risks
Risk ID | Description of Risk | Probability (0 - 1) | Impact (low, med, high) | Exposure | Classification | Owner | Mitigation Strategy | Status
1 | Unable to obtain correct software, hardware or login information within a reasonable amount of time. | 0.2 | low | 0.2 | Technical | All | Make sure that the tools and login information that we need is provided to our group as quickly as possible. If we don't have what we need in the time we need it, use our advisor to help us get those tools.
2 | We incorrectly estimate the amount of work that is required and do not allow enough time to finish our project. | 0.75 | high | 7.5 | Schedule | Erik | Plan in advance to keep the amount of work limited by discussing what is needed with the customer and what we are capable of.
3 | Due to the evolving nature of this project, the scope or requirements of the project change halfway through the project. | 0.5 | high | 5 | Technical, Schedule | Jaden | Have the customer sign off on different aspects of the project before the next phase of the project begins.
4 | Team members do not work up to potential or slack off due to senioritis, getting sick or class overload. Procrastination and Warcraft are also problems. | 0.9 | high | 9 | People | All | Know each others schedules and what we have going on that quarter. Plan around the various schedules and make sure that we know when someone is busy. If a team member is not as busy one week, that person should make up for another person's slack.
5 | Requirements elicitation does not gather enough specific data from the customer. | 0.75 | med | 3.75 | Technical | All | Due to the nature of Excellus, requirements are run very loosely. This needs to be mitigated by the team by forcing specific and measurable requirements from the customer who can then sign off on those requirements.
6 | All the team members do not have the necessary domain/technical knowledge to easily implement the solutions. | 0.5 | low | 0.5 | Technical, People | Erik, Jaden | Some members of the group do not have expertise in EJBs and other technologies Excellus uses. This is very likely, however, these members will be able to be tutored and trained by other members of the group and will be able to catch up quickly.
7 | We lose our code and/or document repositories on the CVS server. | 0.1 | med | 0.5 | Technical | Jaden | Jaden will periodically make a checkpoint and a backup of the CVS server every other week.
8 | We temporarily lose access to the CVS server due to network failure preventing us from doing work. | 0.15 | med | 0.75 | Technical | All | Wait it out for a couple hours and then have one of the team members contact Kurt.
9 | Threading may be more difficult than expected. | 0.5 | high | 5 | Technical | All | Shift scope or remove third iteration as a last resort.
0
0
0
Note on A1: The risk ID is the sequential order of risk entry.
Note on B1: Identify the Risk.
Note on C1: Likelihood that the risk will occur. 1 means the risk will definitely occur.
Note on D1: What will be the impact on the program if the risk occurs. Relative ranking: low = 1 med = 5 high = 10
Note on E1: Exposure = Probability * risk This is the primary sort field.
Note on F1: Where will the biggest impact of the risk occur? Examples: Technical Schedule Reliability Cost/UMC
Note on G1: Responsible person working to mitigate the risk.
Note on H1: Plan or strategy to minimize the impact and/or reduce the probability that the risk occurs.
Note on I1: History of the status of the risk.