## Sheet1
Risk Categories | Risk Name | Status | Probability | Impact | Risk Factor | Prevention Strategy | Mitigation Strategy | Reason For Closure
Technologies | Touch Screen
| Hardware is not Delivered | Closed | 0 | 7 | 0% | Communication with Sponsor | Simulate Using a Mouse | Hardware Delivered
| Compatibility Issues | Closed | 0 | 7 | 0% | Tech Lead for Touch screen Integration | Consult with Sponsor | Demoed Touchscreen
| Hardware Failure/Loss |  | 2 | 5 | 10% | Left in Secure Room | Request Another Touch screen
| Unknown Usage of Interface | Closed | 0 | 7 | 0% | Tech Lead for Touch screen Integration | Consult with Sponsor | Demoed Touchscreen
| Slow Touch Screen Response Time |  | 10 | 5 | 50% | Tech Lead for Touch screen Integration | Do not display mouse icon
.NET
| Lack of Experience with .NET | IN PROGRESS | 7 | 5 | 35% | Training Meeting with Experienced Team Members | .NET Lead Available to Answer Questions
| Lack of C# Knowledge |  | 7 | 4 | 28% | Training Meeting with Experienced Team Members | .NET Lead Available to Answer Questions
| Lack of Experience with Visual Studio | IN PROGRESS | 7 | 4 | 28% | Training Meeting with Experienced Team Members | .NET Lead Available to Answer Questions
| Obtaining Proper Version of Tool/Libraries on Work Machines | Closed | 0 | 8 | 0% | Request from Sys Admin | Use Personal Systems | Tools are set up on main machine
Windows Embedded
| Obtaining Kodak's Image of Windows Embedded | Closed | 0 | 7 | 0% | Communication with Sponsor | Approximate Kodak Setup | Not using windows embedded
| Lack of Experience with Windows Embedded | Closed | 0 | 6 | 0% | Research into Windows Embedded | Request Formal Training from Outside Source | Not using windows embedded
| Obtaining Windows Embedded on a Machine | Closed | 0 | 7 | 0% | Request from Sys Admin | Consult Sponsor for an Acceptable Solution | Not using windows embedded
GUI
| Localization Issues | IN PROGRESS | 7 | 4 | 28% | Research Localization Techniques | Localization Lead Comes up with Solution
| Lack of Usability | IN PROGRESS | 8 | 6 | 48% | Early Prototypes and Storyboarding | Communication with Kodak Human Factors Group
| Compatibility with Kodak Standards | Closed | 5 | 5 | 25% | Early Prototypes, Storyboarding, and Using Kodak Usability Standards | Negotiation of Needs with Sponsor | Met with Damien
| Poor Memory Management |  | 10 | 10 | 100% | Make Use of Profiling Software and Metrics | Code Reviews
| Rendering Issues and Speed | IN PROGRESS | 8 | 6 | 48% | Research and Making Use of Profiling Software and Metrics | GDI+ Lead Works to Improve Algorithms
| Creation of Specialty Controls | IN PROGRESS | 10 | 5 | 50% | High Priority in Development | Adapt Existing Tools
GDI
| Lack of Experience | IN PROGRESS | 9 | 8 | 72% | GDI Tech Lead Research | Request Formal Training from Outside Source
| Lack of Support for Tool Algorithms | Closed | 0 | 10 | 0% | Tool Lead will Develop New Tool Algorithms | Request Compromise from Sponsor | Algorithms have been developed
| Possible Tool/Algorithm Development | IN PROGRESS | 10 | 4 | 40% | Tool Lead will Develop New Tool Algorithms | Request Compromise from Sponsor
Implementation Issues
| Image Management | IN PROGRESS | 7 | 7 | 49% | Early Development of Architecture | Research into Image Transition Techniques
| Line Completion for Free Form Drawing | IN PROGRESS | 10 | 7 | 70% | Early Prototypes | Always Straight Line Completion
| Design Complexity Could Slow Implementation | IN PROGRESS | 7 | 8 | 56% | Develop Subsystems First then Integrate | Design Reviews to Simplify Design
Data Loss
| Version Control Repository Lost |  | 1 | 6 | 6% | Request Recovery from Sys Admin | Back Up on Personal Computers
| Hard Disk Failure |  | 1 | 6 | 6% | Request Recovery from Sys Admin | Back Up on Personal Computers
| Lack of Control Over Resources |  | 6 | 2 | 12% | Request Additional Control from Sys Admin | Use Provided Hardware
Project Management | Schedule Slip
| Senioritis |  | 8 | 6 | 48% | Project Coordinator Ensures that Project is On Track | Rework Schedule
| Code Development Issues |  | 7 | 10 | 70% | Unit Testing and Small Incremental Releases | Code Reviews
| School Workload | IN PROGRESS | 10 | 7 | 70% | Attempt to Rigidly Follow Schedule in Place | Leave Extra Time in Schedule for Slippage
| Lack of Additional Resources | IN PROGRESS | 10 | 10 | 100% | Attempt to Rigidly Follow Schedule in Place | Leave Extra Time in Schedule for Slippage
| Poor Project Planning | IN PROGRESS | 8 | 10 | 80% | Project Coordinator Constantly Evaluates Schedule | Consult with Faculty Coach and Reschedule
| Limited Maintenance Time | IN PROGRESS | 9 | 4 | 36% | Attempt to Rigidly Follow Schedule in Place | Follow Good Documentation Processes
Project Completion
| Delivery of Nonfunctional Product |  | 3 | 10 | 30% | Make Use of Evolutionary Development Process | Revert to Last Working Increment
| Lack of Proper Documentation |  | 3 | 5 | 15% | Good Documentation Standards | Documentation Reviews
| Unable to Satisfy Requirements |  | 5 | 8 | 40% | Constant Feedback from Sponsor after Every Increment | Renegotiate Requirements with Sponsor
Inexperienced with Project Management
| Team Issues | IN PROGRESS | 1 | 8 | 8% | Frequent Status Meetings within the Team | Consult with Faculty Coach
| Lack of Communication | IN PROGRESS | 5 | 10 | 50% | Frequent Status Meetings/Emails within the Sponsor | Consult with Sponsor
| Poor Selection of Project Methodology |  | 3 | 8 | 24% | Frequent Status Meetings within the Team | Consult with Faculty Coach
| Poor Implementation of Project Methodology |  | 7 | 8 | 56% | Frequent Status Meetings within the Team | Consult with Faculty Coach
| In Progress |  |  | Avg Risk Factor: | 34.7%

## Sheet2
DATE | Running Risk Factor | Unaddressed | Closed | In Progress
2007-01-16 | 41% | 36 | 0 | 0
2007-01-23 | 39% | 19 | 7 | 13
2007-01-30 | 38% | 15 | 8 | 16
2007-02-06 | 35% | 14 | 9 | 17
2007-02-13
2007-02-20
2007-02-27
2007-03-06
2007-03-13
2007-03-20
2007-03-27
2007-04-03
2007-04-10
2007-04-17
2007-04-24
2007-05-01
2007-05-08
2007-05-15
2007-05-22