## Sheet1
Risk Categories | Risk Name | Status | Probability | Impact | Risk Factor | Prevention Strategy | Mitigation Strategy | Reason For Closure
Technologies | Touch Screen
| Hardware is not Delivered | Closed | 0 | 7 | 0 | Communication with Sponsor | Simulate Using a Mouse | Hardware Delivered
| Compatibility Issues | Closed | 0 | 7 | 0 | Tech Lead for Touch screen Integration | Consult with Sponsor | Demoed Touchscreen
| Hardware Failure/Loss | IN PROGRESS | 2 | 5 | 10 | Left in Secure Room | Request Another Touch screen
| Unknown Usage of Interface | Closed | 0 | 7 | 0 | Tech Lead for Touch screen Integration | Consult with Sponsor | Demoed Touchscreen
| Slow Touch Screen Response Time | IN PROGRESS | 10 | 5 | 50 | Tech Lead for Touch screen Integration | Do not display mouse icon
.NET
| Lack of Experience with .NET | Closed | 7 | 5 | 35 | Training Meeting with Experienced Team Members | .NET Lead Available to Answer Questions | We all know .NET now
| Lack of C# Knowledge | Closed | 7 | 4 | 28 | Training Meeting with Experienced Team Members | .NET Lead Available to Answer Questions | We all know .NET now
| Lack of Experience with Visual Studio | Closed | 7 | 4 | 28 | Training Meeting with Experienced Team Members | .NET Lead Available to Answer Questions | We all know .NET now
| Obtaining Proper Version of Tool/Libraries on Work Machines | Closed | 0 | 8 | 0 | Request from Sys Admin | Use Personal Systems | Tools are set up on main machine
Windows Embedded
| Obtaining Kodak's Image of Windows Embedded | Closed | 0 | 7 | 0 | Communication with Sponsor | Approximate Kodak Setup | Not using windows embedded
| Lack of Experience with Windows Embedded | Closed | 0 | 6 | 0 | Research into Windows Embedded | Request Formal Training from Outside Source | Not using windows embedded
| Obtaining Windows Embedded on a Machine | Closed | 0 | 7 | 0 | Request from Sys Admin | Consult Sponsor for an Acceptable Solution | Not using windows embedded
GUI
| Localization Issues | IN PROGRESS | 7 | 4 | 28 | Research Localization Techniques | Localization Lead Comes up with Solution
| Lack of Usability | IN PROGRESS | 4 | 6 | 24 | Early Prototypes and Storyboarding | Communication with Kodak Human Factors Group
| Compatibility with Kodak Standards | Closed | 5 | 5 | 25 | Early Prototypes, Storyboarding, and Using Kodak Usability Standards | Negotiation of Needs with Sponsor | Met with Damien
| Poor Memory Management | IN PROGRESS | 8 | 10 | 80 | Make Use of Profiling Software and Metrics | Code Reviews
| Rendering Issues and Speed | IN PROGRESS | 5 | 6 | 30 | Research and Making Use of Profiling Software and Metrics | GDI+ Lead Works to Improve Algorithms
| Creation of Specialty Controls | IN PROGRESS | 7 | 5 | 35 | High Priority in Development | Adapt Existing Tools
GDI
| Lack of Experience | Closed | 9 | 8 | 72 | GDI Tech Lead Research | Request Formal Training from Outside Source | All set with GDI
| Lack of Support for Tool Algorithms | Closed | 0 | 10 | 0 | Tool Lead will Develop New Tool Algorithms | Request Compromise from Sponsor | Algorithms have been developed
| Possible Tool/Algorithm Development | Closed | 10 | 4 | 40 | Tool Lead will Develop New Tool Algorithms | Request Compromise from Sponsor | All set with tools
Implementation Issues
| Image Management | IN PROGRESS | 4 | 7 | 28 | Early Development of Architecture | Research into Image Transition Techniques
| Line Completion for Free Form Drawing | IN PROGRESS | 7 | 7 | 49 | Early Prototypes | Always Straight Line Completion
| Design Complexity Could Slow Implementation | Closed | 7 | 8 | 56 | Develop Subsystems First then Integrate | Design Reviews to Simplify Design | Done with design. Implementation going smoothly
| Certain Image Actions May Require Re-Rendering | Closed | 8 | 10 | 80 | Early Development of Actions That Could Produce This Issue | Re-Design of the Model To Implement This Issue | Addition of transformer object into design solved this issue.
Data Loss
| Version Control Repository Lost | IN PROGRESS | 1 | 6 | 6 | Request Recovery from Sys Admin | Back Up on Personal Computers
| Hard Disk Failure | IN PROGRESS | 1 | 6 | 6 | Request Recovery from Sys Admin | Back Up on Personal Computers
| Lack of Control Over Resources | Closed | 6 | 2 | 12 | Request Additional Control from Sys Admin | Use Provided Hardware
Project Management | Schedule Slip
| Senioritis | IN PROGRESS | 10 | 6 | 60 | Project Coordinator Ensures that Project is On Track | Rework Schedule
| Code Development Issues | IN PROGRESS | 4 | 10 | 40 | Unit Testing and Small Incremental Releases | Code Reviews
| School Workload | IN PROGRESS | 10 | 7 | 70 | Attempt to Rigidly Follow Schedule in Place | Leave Extra Time in Schedule for Slippage
| Lack of Additional Resources | IN PROGRESS | 5 | 10 | 50 | Attempt to Rigidly Follow Schedule in Place | Leave Extra Time in Schedule for Slippage
| Poor Project Planning | IN PROGRESS | 10 | 10 | 100 | Project Coordinator Constantly Evaluates Schedule | Consult with Faculty Coach and Reschedule
| Limited Maintenance Time | IN PROGRESS | 10 | 5 | 50 | Attempt to Rigidly Follow Schedule in Place | Follow Good Documentation Processes
Project Completion
| Delivery of Nonfunctional Product | IN PROGRESS | 3 | 10 | 30 | Make Use of Evolutionary Development Process | Revert to Last Working Increment
| Lack of Proper Documentation | IN PROGRESS | 3 | 5 | 15 | Good Documentation Standards | Documentation Reviews
| Unable to Satisfy Requirements | IN PROGRESS | 5 | 8 | 40 | Constant Feedback from Sponsor after Every Increment | Renegotiate Requirements with Sponsor
Inexperienced with Project Management
| Team Issues | IN PROGRESS | 1 | 8 | 8 | Frequent Status Meetings within the Team | Consult with Faculty Coach
| Lack of Communication | IN PROGRESS | 5 | 10 | 50 | Frequent Status Meetings/Emails within the Sponsor | Consult with Sponsor
| Poor Selection of Project Methodology | IN PROGRESS | 3 | 8 | 24 | Frequent Status Meetings within the Team | Consult with Faculty Coach
| Poor Implementation of Project Methodology | IN PROGRESS | 7 | 8 | 56 | Frequent Status Meetings within the Team | Consult with Faculty Coach
| In Progress |  |  | Avg Risk Factor: | 1315

## Sheet2
DATE | Running Risk Factor | Unaddressed | Closed | In Progress
2007-01-16 | 1453 | 36 | 0 | 0
2007-01-23 | 1502 | 19 | 7 | 13
2007-01-30 | 1476 | 15 | 8 | 16
2007-02-06 | 1388 | 14 | 9 | 17
2007-02-13 | 1468 | 14 | 9 | 18
2007-02-20 | 1468 | 14 | 9 | 18
2007-02-27 | 1468 | 14 | 9 | 18
2007-03-06 | 1468 | 14 | 9 | 18
2007-03-13 | 1468 | 14 | 9 | 18
2007-03-20 | 1468 | 14 | 9 | 18
2007-03-27 | 1598 | 0 | 9 | 42
2007-04-03 | 1315 | 0 | 17 | 34
2007-04-10
2007-04-17
2007-04-24
2007-05-01
2007-05-08
2007-05-15
2007-05-22